Evaluation Report Title: / Final Evaluation of the Palestinian Market Development Programme (PMDP) to Strengthen the Private Sector in the Occupied Palestinian Territories

Response to Evaluation Report (overarching narrative)
DFID provided £15 million and spent £13.97 million between 2013 and 2018 to the Palestinian Market Development Programme (PMDP), which was implemented by DAI Europe. This was complemented by funding by the European Union in the value of £5.9 million, bringing the total financial commitment to £19.87 million. There was also an M&E element, implemented by GDSI, which conducted this evaluation. / The programme aimed to improve the competitiveness of the Palestinian private sector by i) providing matching grants and technical assistance to mitigate the risk associated with business development, ii) undertaking market analysis to identify and address market failures, and iii) strengthening inward investment and transfer of know how. Over five years it met or exceeded its targets, supported over 800 Palestinian enterprises improve their business operations and revenues, and contributing to the creation of around 2,800jobs. / The evaluation used a theory-based approach to: understand the impact of the design, management and delivery of the Programme; identify factors that contributed or hampered its success; and identify key lessons for future programming. The evaluation drew on case studies, key informant interviews and workshops, and the data and surveys conducted throughout the programme. / We welcome the findings of the evaluation. It concluded that ‘PMDP has been effective – broadly speaking, it met its targets under all three components’, despite operating in an extremely challenging context of the ongoing conflict and occupation across the Occupied Palestinian Territories. The main recommendations refer to how to learn the lessons from PMDP in DFID’s future programming. These have been, or will be, taken forward as part of the new Supporting Economic Empowerment and Development in the Occupied Palestinian Territories (SEED OPTs) programme approved in 2018. / The findings of this evaluation are relevant to the development community in OPTs and the Palestinian Authority, and are being shared through disseminating the report and presentations of the main findings. / Our response to key findings is summarised below.

Evaluation Report Title: Final Evaluation of the Palestinian Market Development Programme (PMDP) to Strengthen the Private Sector in the Occupied Palestinian Territories

Recommendations	Accepted or Rejected	If “Accepted”, Action plan for Implementation or if “Rejected”, Reason for Rejection
DFID develops a new programme in Palestine in support of private sector development, building on PMDP but with new approaches. / A future theory of change will need to take account of the distinctions between a market development programme; a programme aimed to contributing to resilience and a programme conceptualised as contributing to sovereignty building. / A central concern of the future market development programme should be the encouragement of new frameworks of engagement within which key contingent (political) obstacles to growth can be identified and addressed. / Consider establishing and supporting a business advisory service for micro and small enterprises. / Consider how to maximise the use of data and information generated from the project, such as writing more regular policy notes for the PA and donors with information generated. / Ensure strong coordination with other donors, including EU, US and Office of Quartet. / As part of preparatory work for the new programme, consider commissioning a study to ‘map’ the organisations currently engaged in economic confidence-building between Israelis and Palestinians. / Consider a successor programme, based on the following five components: / A new matching grant scheme: on a scale comparable to PMDP; with a goal that includes sovereignty building; with broad coverage across geographies and marginalised groups (East Jerusalem, Area C, Gaza, women, youth); providing larger grants to smaller number of beneficiaries; prioritising beneficiaries without access to other funding sources; including matching grants for pioneer proposals and micro grants for demonstration projects; including strategic support for smaller businesses; and continuing the flexibility of PMDP and the use of local partners and co-facilitators. / Continue strengthening trade and investment linkages and the Business Enabling Environment, including capacity-building within Palestinian institutions and civic society; further work on Doing Business indicators, and developing CTR in a participatory way. / An economic confidence building strategy: develop and support a medium term confidence building strategy that sets out an approach and vision for future sovereignty and sustainability, promoting a broad informal dialogue inside and outside Palestine to revive the Joint Economic Committee or its equivalent, possibly opening communication with the International Fund. / Stand-alone ICT component: including engaging with other donors on a broader ICT strategy for the OPTs. / Infrastructure in Gaza: involving larger interventions, more donor coordination and higher element of risk sharing.	Accepted / Accepted / Accepted / Partially accepted / Accepted / Accepted / Partially Accepted / Partially accepted	A new Supporting Economic Empowerment and Development in the Occupied Palestinian Territories (SEED OPTs) programme was approved in May 2018, which included support to private sector development as part of a broader programme of support to economic development. / This has been taken forward in the theory of change for the new SEED programme, which presents a broader programme of support including elements related to market development, resilience, and sovereignty building. / This will be taken forward as part of the new programme, and particularly the new Trade Facility which is due to be initiated later in 2019. The new Facility will allow for a larger range of potential interventions to improve markets. / This will be considered as part of the new Trade Facility, due to be launched later this year, along with other priority interventions. / This will be taken in to account during the implementation of the new economic development programme (SEED). / There will be strong coordination throughout the new programme, including through a Steering Committee for the Trade Facility and regular meetings with partners. / This will be considered as part of the new Trade Facility, due to be launched later this year, along with other priority interventions. / The new SEED programme incorporates many of these recommendations. The new Trade Facility is expected to include matching grants and the recommendations here will be used to inform the final design. Economic confidence building, the examples given on trade and investment and a stand-alone ICT component will be considered along with other priorities. / The SEED programme includes significant support for water and energy infrastructure in Gaza, including for the Gaza Central Desalination Plant.