Business Case

Summary Sheet

Title: Supporting agricultural transformations by tackling market failures in agricultural innovation
Project Purpose: / Increased access to and availability of appropriate agricultural technologies for small-holder farmers in targeted countries in Sub-Saharan Africa.
Programme Value: Up to £10,000,000			Country/Region: Africa
Project Code: 204988	Start Date: September 2015		End Date: August 2020
Overall programme risk rating:	Low
Quest Number:	5021349

Intervention Summary (2 Pages)

What support will the UK provide?
The UK will provide up to £10 million to the African Agricultural Technology Foundation (AATF) over the period 2015 – 2020 to support the organisation to tackle market failures in the development of appropriate agricultural technologies, including genetically modified crops. Core funding will remain at the same level as in the previous phase of funding (£1.5 million/year). In addition, a performance related component of up to £500,000/year will be structured to incentivise more rapid progress in key areas: achieving and assessing impact at scale, financial sustainability and strengthening of the product pipeline. The performance related component will take on board lessons from a similar mechanism developed for funding of international agriculture research centres.
This support builds on the UK’s previous support to AATF, an organisation with a proven track record of identifying, developing and deploying technology to increase the productivity of small-holder farmers in Sub-Saharan Africa. During the period 2010 – 2015, AATF consistently met or exceeded donor expectations. Among other notable achievements, AATF has delivered drought tolerant maize varieties to over 57,000 households and developing a pipeline of new products. UK support has been instrumental in AATF being able to attract significant new investment from other investors (USAID and Gates) to take proven products to scale.
UK support will enable AATF to continue identifying technology and developing projects, building up a pipeline to attract other investors, and in the process diversify the range of investors in the institution. This will prepare the ground for a transition from DFID support as AATF changes its business model.

What are the main programme activities?
The programme will support AATF activities in two areas. Support to organisational systems and development to enable:
- identification of, and access to, technologies and Management of Intellectual Property (IP)
- knowledge management and information dissemination
- improved monitoring, evaluation and impact assessment
- gender mainstreaming
- development of AATF’s Ten Year Strategy and Business Plan to become a financially sustainable institution.
Support to specific projects to enable scaling up of
- production of herbicide resistant maize seed to control the parasitic weed Striga reach 2,000 tons. This will open up about 80,000 ha of farmland, enough to generate some 120,000 tons of maize grain and enhance food security for about 300,000 smallholder households.
- the Cassava Mechanisation and Agro-processing Project (CAMAP) testing technologies that are new to Africa. CAMAP will target an additional 100,000 farmers, increase cassava yields by 200% and strengthen market linkages and market capacity to enhance enterprise and employment creation
- drought resistant hybrid maize, including genetically modified varieties, to an additional three countries, to produce and distribute at least 5,000 tons of seed and reach at least 800,000 households.

Why is UK support required?
There are significant market failures in the development and deployment of appropriate technology for smallholder farmers in Sub-Saharan Africa. While farmers are willing to adopt the right technology at the right price, their ability to do so is constrained by a range of factors including a lack of access to effective input and secure output markets, risk aversion and lack of appropriate technology. Conversely, the owners of technology/innovation with the potential to tackle the constraints faced by smallholders have little incentive to develop products for which the market, and hence profitability, is uncertain.
AATF has a developed an excellent reputation for tackling market failures in agricultural innovation by accessing technology and working in partnership with both public and private organisations to develop products that are appropriate for smallholder farmers and have the potential to increase their productivity.
UK support to AATF over the next five years will support the organisation to expand its portfolio of products, maintain and enhance organisational capacity and incentivise AATF to alter its business model, becoming a more sustainable organisation, less dependent on donor funds and more attractive to other investors. Four options for further funding to AATF after this funding period have been outlined in para 53) under the Management Case.

What are the expected results?
The expected impact of support to the proposed intervention is increased productivity of small-holder farmers in Sub-Saharan Africa.
This impact will be achieved through two outcomes
  1. Increased access/availability of appropriate agricultural technologies for small-holder farmers in targeted countries in Sub-Saharan Africa.
  2. A financially sustainable organisation/mechanism that is responsive to the needs of small-holder farmers in ensuring that market failures in the development and adoption of appropriate agricultural technologies continue to be addressed.

How does the project fit with the country programme or department’s strategic objectives set out in the Operational Plan?
This programme is closely aligned with current priorities of the Research and Evidence Division, which has prioritised initiatives to accelerate the pace of innovation and engagement with the private sector. The AATF model, working with private and public partnerships is also aligned with DFID’s priority of engaging more with the private sector.
DFID’s Agriculture Refresh, implemented by the Growth and Resilience Department also highlights the importance of technology and innovation to agricultural transformations and rural transitions, not least as a key driver of productivity growth and value addition and in the way technology affects land and labour productivity.

What are the key risks to the success of the programme?
There are two key risks to the success of the programme. Firstly, the regulatory environment in AATF target countries with respect to seed systems and biosafety frameworks[1]. This has the potential to prevent approval of new plant varieties developed by AATF. While this is a specific legal area over which AATF has no direct control, they engage proactively with partners in target countries to ensure appropriate regulations are promulgated.
[1] “biosafety” encompasses the practices, procedures, and use of equipment needed to ensure adequate safety conditions in all facilities that work with potentially infectious microorganisms and other biological hazards including genetically modified materials.
Secondly, there is a risk that the proposed performance related funding component does not deliver:
- the anticipated organisational and business model changes required to build a financially sustainable organisation tackling market failures in agricultural innovation;
- increased adoption of AATF technologies at scale.
DFID will work closely with AATF and other investors to manage this risk proactively and AATF has expressed commitment to organisational change.
## Strategic Case
Agricultural Productivity and Innovation
1. DFID’s long-term perspective on agriculture, as articulated in the Agriculture Refresh, approved in 2014, is based on the assumption that sustained wealth creation and a self-financed exit from poverty depend, in the long-term, on economic transformation and the majority of the rural poor finding productive and better paid employment outside of primary agricultural production. Despite the need for this transition, agricultural growth and downstream processing and productivity growth are likely to be important, if not essential, as a continued source, if not driver, of growth. Agriculture sector growth, where it can be achieved cost-effectively, is likely to have a bigger impact on poverty reduction than growth in other sectors as it offers the most direct route of raising returns to poor people’s main assets, land and labour
2. The Agriculture Refresh also highlights the importance of technology and innovation to agricultural transformations and rural transitions, not least as a key driver of productivity growth and value addition and in the way technology affects land and labour productivity. Climate change and rising oil prices also demand new technology that can raise productivity while using less fossil fuels.
3. Dramatic rises in agricultural productivity have been based on the development and application of new technologies. Over the past 50 years global food production has more than tripled. Global yields per hectare of the major staple crops grew at an annual rate of 2-3% between 1961 and 1990, exceeding population growth rates and contributing to a long-term decline in food prices. Major food security successes – such as the Asian Green Revolution, and the expansion of improved maize varieties in East and Southern Africa, have been driven by agricultural innovation. Crop genetic improvement based on research by the CGIAR[2] has made a major contribution to global yield gains[3].
  [2] The CGIAR is a worldwide research partnership addressing agricultural research for development, whose work contributes to the global effort to tackle poverty, hunger and major nutrition imbalances, and environmental degradation.
  [3] Agriculture for Development, World Development Report, 2008
4. Contrary to popular belief, agricultural production in Africa has increased steadily over the last thirty years: its value has almost tripled and it is now almost identical to that of South America, and below but comparable to growth in Asia.[4] However, there has been limited improvement in production factors and agricultural growth in Africa is generally achieved by cultivating more land and by mobilising a larger agricultural labour force, which produces very little improvement in yields. On average, cereal yields are less than half those obtained in Asia. The fact that agriculture in most countries Sub-Saharan Africa (SSA) is characterised by a dual system combining a subsistence farming sector, often using poor and inadequate inputs, and an export-oriented sector, producing crops such as cotton, groundnuts, cocoa, and coffee contributes to explaining this situation. Small-scale farming not only provides most of the food consumed in Africa, as well as employment for 60% of working people, but the linkages between small-farming development and poverty reduction have also been widely studied. By contrast, the trickledown benefits from large-scale commercial agriculture are unproven.
  [4] Fuglie, K. and Nin-Pratt, A. (2013) “Agricultural productivity: a changing global harvest”, in 2012 Global Food Policy Report, International Food Policy Research Institute (IFPRI), Washington, USA.
5. As a result of the low level of agriculture productivity at smallholder farming level, food security has worsened in many countries in SSA - while population has doubled overall and tripled in urban areas since the early 1960s, food production has been unable to keep pace since it has only increased by a factor of 1.8. In order to reverse this situation, smallholder farming must be transformed from a largely subsistence-level activity to a market-oriented production system that may contribute to improve national and household food security and, ultimately, reduce poverty. New organizational systems, a more technological focus, and innovative financing with an investment focus are some of the solutions provided to increase agriculture productivity.
6. Investment in agricultural productivity is not in itself sufficient to enable countries to develop, but there are very few examples of countries that have escaped chronic poverty without achieving rapid growth in the agricultural sector. The empirical relationship between agriculture and poverty reduction is well established[5]. For example, in Africa, agricultural growth has been found to be four times more effective in increasing the incomes of the extreme poor than growth originating in other sectors5.
  [5] Agriculture for Development, World Development Report, 2008
7. There is a comprehensive body of evidence demonstrating high rates of returns and global impact of public investment in international agricultural research over the last 4 decades. The direct impact of technology on agriculture productivity and indirect effects on increased wages and reduced food prices of agricultural research by the CGIAR generated significant benefits to the rural and urban poor. The evidence suggests that the benefits have been worth many times more than the costs[6]. For example, for every $1 invested in CGIAR at least an additional $9 worth of additional food is produced in developing countries[7]. Further analysis of the rates of return to investment in agricultural research is provided in Annex 1.
  [6] Alston, J. M. (2010), “The Benefits from Agricultural Research and Development, Innovation, and Productivity Growth”, OECD Food, Agriculture and Fisheries Papers, No. 31, OECD Publishing
  [7] Raitzer, 2003. Benefit-Cost Meta-Analysis of Investment in the International Agricultural Research Centres of the CGIAR

Small Holder Agriculture
1. Poverty is still predominantly a rural phenomenon and will remain so for at least the next two decades[8]. Over 70% percent of the poor reside in rural area but rural populations make up 58% of the developing world. More than three quarters of those living in extreme poverty are in rural areas and nearly two thirds of the extremely poor earn a living from agriculture[9]. While poor rural people’s livelihoods are typically highly diversified, agriculture continues to provide a critical source of food and income for the majority of the rural poor. IFAD estimate there are around 500 million smallholder farms in developing countries, supporting almost 2 billion people.
  [8] Ravallion, Chen and Sangraula. (2007) New Evidence on the Urbanisation of Global Poverty.
  [9] World Bank (2013) The state of the poor: Where Are The Poor, Where Is Extreme Poverty Harder to End, and What Is the Current Profile of the World’s Poor?
2. The DFID Agriculture Refresh acknowledged that in the medium to long-term agriculture cannot provide a pathway out of poverty for all those who are currently engaged in agriculture. Some households may be able to become small-scale commercial farmers, whilst others in remote areas with less potential must rely on agriculture in the short term during the transition to other livelihood opportunities. In both contexts small-holders are poor, but need access to appropriate technologies, particularly crop varieties that are adapted to local conditions.
3. The relatively slow pace of adoption of new varieties is shown by a an impact assessment on the Diffusion and Impact of Improved Varieties in Africa (DIIVA) focused on 20 crops and 30 countries in Sub-Saharan Africa, together representing over 70% of the region’s total agricultural production value, and 83% of the area in Sub-Saharan Africa harvested. Results published in 2014 showed:
- Modern Varieties were cultivated on 35% of the area in 20 primary and secondary food crops in Sub-Saharan Africa in 2010.
- Around 3,500 improved cultivars had been released nationally since 1970; and more than 1,150 improved varieties and hybrids were adopted by farmers in Sub-Saharan Africa as of 2010.
- For the ten crops with benchmark data from the earlier study, Modern Varieties adoption rose from 25% in 1998 to 44% in 2010. This increase was equivalent to an annual gain of 1.45% over the 13-year period.
Despite this clear rise in the penetration of modern varieties, up from 23% in Africa in 2000 to 35% in 2010, this is still low in comparison with the global average of 65%, and the contribution of crop genetic improvement on yield growth is consequently lower than it could be.

Investment in Innovation
1. There are two major market failures, often referred to as “valleys of death,” that impede the translation of technological opportunities, often meaning that potentially beneficial technology is not developed and/or does not reach those who can use it. The first gap is at the early stage of innovation where funds are required to go from the proof of concept to product (see Figure 1). Generally research funds (from public sources or from internal sources in the case of private firms) are sufficient to demonstrate the technical feasibility of a concept; but support for translating the proof of concept to a working prototype is relatively limited. Private firms hold back due to an excess of technical risk and the lack of a business case at this stage.
2. The second “valley of death” refers to a later stage where significant funds are needed to establishing facilities for commercial-scale manufacturing of a product. At this stage, there still remains some market risk since there is no guarantee that the product will be attractive to consumers.
Figure 1: Innovation “valleys of death” [10]
[10] Menon, J., Sagar, A. (2012) Prize-Driven Innovation for Development. X PRIZE Foundation, US and IIT Delhi, India.

1. New technologies are developed by large international private companies, such as Monsanto and Syngenta, aimed at increasing profits. These companies concentrate on large markets and the needs of the smallholder farmers in Sub-Saharan Africa are simply not central to their technological development process. This greatly limits the access by public researchers to new ideas and tools and therefore limits the development of a pipeline of products appropriate for smallholder farmers.
2. This is important because the poor have limited purchasing power, leaving firms with little incentive to develop technologies for them. Therefore, there is a distributional argument in favour of incentivising the development of technologies that address the needs of the poor. Moreover, the fact that the poor are a user group that firms are less familiar with means it is difficult to assess the potential demand for new technologies (uncertain/unknown demands and returns), exacerbating the risk involved in developing new products for them.

Background on the African Agricultural Technology Foundation (AATF)
1. In this context, DFID supported the establishment of AATF in 2004 in partnership with the Rockefeller Foundation, and USAID. AATF was created with a mandate to bridge the gap between owners of technologies willing to donate them for use by SSA smallholder farmers and those that need the technologies. In undertaking its mandate, AATF creates partnerships and assumes certain stewardship responsibilities, becoming the bridge that allows SSA scientists and development experts and seed companies access to the new tools that they need, and through them get the final product into the hands of farmers, overcoming the valleys of death highlighted in Figure 1.
2. An evaluation of the first five years of funding highlighted the innovative approach of AATF. It found that, while AATF has taken time to establish itself in Phase 1, was well placed to deliver significant impact going forward. There are no similar organisations to AATF working at the interface between public and private institutions to facilitate the effective transfer of technologies for poor farmers. A second phase of funding to AATF was approved in 2010.
3. DFID core support has been used to
- build institutional and operational capacity;
- strengthen corporate governance
- raise funding from other sources;
- initiate and implement projects;
- identify, access, develop and deliver technologies;
- strengthen intellectual property;
- reach farmers and policy makers through active and coherent communications and advocacy strategies and policies; and
- develop strong public-private partnerships.

The Proposed Intervention
DFID proposes to support a mechanism that will ensure that market failures in the development and adoption of appropriate agricultural technologies in Africa are, and continue to be, addressed.

The Strategic Fit - Why DFID’s intervention is justified
1. Tackling the slow development and adoption of technology appropriate for small-holder farmers in Sub-Saharan Africa will contribute to the UK and DFID’s commitments to delivering the emerging Sustainable Development Goals, particularly proposed Goal 2: “End hunger, achieve food security and improved nutrition and promote sustainable agriculture”.
2. Intervening in this area is also aligned with DFID’s Agriculture Refresh, which highlights the importance of agricultural research and innovation in bringing about agricultural transformations and supporting small-holder farmers.
3. The programme is aligned to DFID’s agriculture research priorities paper, particularly in terms of current priorities of working with the private sector, to accelerate agricultural innovation. AATF works with a range of partners and the principle method of delivering improved technology to end-users is through the private sector, notably African seed companies.
4. This programme is also aligned with Research and Evidence Division’s priority on testing approaches to getting research into us.

Expected Outcomes and Impact
1. The expected impact of support to proposed intervention is increased productivity of small-holder farmers in Sub-Saharan Africa.
2. This impact will be achieved through two outcomes
  1. Increased access/availability of appropriate agricultural technologies for small-holder farmers in targeted countries in Sub-Saharan Africa.
  2. A financially sustainable organisation/mechanism to ensure that market failures in the development and adoption of appropriate agricultural technologies continue to be addressed.

Compliance with the Gender Equality Act 2014
This programme will provide core support to AATF to tackle market failures in the identification and development of appropriate agricultural technologies. AATF generates technology that is appropriate to the needs of smallholder farmers in Africa and approximately 50% of smallholders are women. AATF is fully aware that a strong, continued commitment to gender mainstreaming is one of the most effective means for them to ensure that vulnerable women, youths, the under privileged as well as men can influence, participate in and benefit from agricultural development efforts. A number of AATF staff have undergone training in gender mainstreaming and AATF has developed a new strategy for gender in project implementation and adoption with emphasis on actively encouraging women’s participation. DFID funding will support AATF to strengthen their efforts in gender mainstreaming and tackling gender inequality which will ensure that the technologies developed through this programme will have the potential to benefit male and female small-holders equally.

## Appraisal Case
Options
As outlined above, efforts to address market failures in the development and uptake of technology appropriate to the needs of small-holder farmers are needed. Three options are considered:-
  1. Continue providing unrestricted core funding to AATF.
  2. Core funding, with additional, performance related funding for AATF.
  3. Work with partners to establish a new Product Development Partnership to address market failures in the development and uptake of agricultural innovation.
Background information on the African Agricultural Technology Foundation (AATF) has been provided under the Strategic Case.

Options Appraisal
Option 1: Continue providing unrestricted core funding to AATF
Under this option, DFID would continue to provide core, unrestricted funding to DFID for a further five year period. DFID would maintain its status as a donor, with observer status on the AATF Board. Funding would be in line with the funding we currently provide.
Option 2: Core funding, with additional, performance related funding.
Under this option, DFID would alter the modality in which funding given, splitting it in to two types.
1. Core, unrestricted funding.
2. Performance related funding. During the first year of a new round of funding DFID would discuss and agree performance targets/milestones would be set for each subsequent year. Potential indicators include
  1. Progress in achieving uptake of technology at scale.
  2. Commissioning of Impact Evaluations to demonstrate impact of AATF technology.
  3. Level and proportion of financing obtained from new investors.
  4. Number of new technologies identified and taken to project development stage.
  5. Development of new organisational strategy.
  6. Proportion of staff with a more commercial/private sector background.

Option 3: Establish a new Product Development Partnership
Under this option, DFID would work with partners to establish a new mechanism to support Product Development Partnerships (PDP) in the crop sector. The mechanism would identify specific areas in which new products/innovation are needed and then run an open competitive process to select projects to address identified challenges.

Options Analysis
1. The three options have been assessed against four criteria
  1. Evidence of Impact:- an assessment of the ability of each option to deliver impact.
  2. Leverage of additional investment:- an assessment of the potential for DFID funding to leverage funding to tackle market failures in technology development and uptake.
  3. Sustainability:- an assessment of the anticipated sustainability of the mechanism to continue to tackle market failures in technology development and uptake at the end of the proposed five year funding period.
  4. DFID Resource:- specifically, how much staff time would be required to deliver the option.

1. Evidence of Impact: In late 2014, DFID commissioned an independent, Institutional Review of AATF to provide an evidence based and independent opinion as to the effectiveness of AATF and the appropriateness of the institution in tackling constraints to the adoption of agricultural technology. The review highlighted that AATF “has achieved important successes in the last few years and that it is absolutely essential to keep this momentum going”.
2. The review also noted that support from AATF donors has “built up a well-managed and productive institution with a good reputation and much potential”. However, it also pointed out that AATF’s record is poorer in the area of impact delivery. This is principally due to the long, but anticipated, lead times for developing technology and the fact that the maturity process of the organisation is still ongoing. In the opinion of the reviewers, AATF has significant potential to deliver impact.
3. AATF has worked on seven priority areas: Impact of climate change on agriculture, Pest management, Soil management, Nutrient enhancement in foods, Improved breeding methods, Mechanisation, The enabling environment. These priority areas have resulted in the roll out of 10 projects which are at varying stages in the product development process.
Water Efficient Maize for Africa (WEMA) - Drought tolerant and insect-pest resistant technologies	Aflatoxin Control in Maize and Groundnuts
Striga Control in Maize	Cassava Mechanisation and Agro-processing Project (CAMAP)
Pod Borer Resistant Cowpea	Hybrid Rice
Nitrogen-Use Efficient, Water-Use Efficient and Salt Tolerant (NEWEST) Rice	Open Forum on Agricultural Biotechnology in Africa (OFAB)
Banana Bacterial Wilt resistance	Seeds2B

To date, AATF has accessed 37 technologies, of which 32 have been developed and adapted and, concurrently, AATF is managing 17 intellectual property licenses. All stakeholders consulted as part of Institutional Review agreed that acquisition of technologies is the area where AATF excels. They used phrase like “reliable partner”, “trustworthy” or “an organisations that delivers” to define AATF. Specific examples of success include:-
Using genetic material acquired from Monsanto the Water Efficient Maize for Africa (WEMA) project has released 27 maize varieties in Kenya, Uganda, Tanzania and South Africa. 37 commercial sub-licenses to seed companies have been issued to enable them to produce WEMA varieties. Some seed companies have shown interest in commercialising these technologies outside the WEMA countries, which may provide greater reach to more smallholder farmers in Africa.
AATF is currently working with 18 seed companies in the five WEMA countries. More than 229 tonnes of certified seed of the first WEMA hybrid, WE1101 DroughtTEGO, were sold in Kenya by the December 2014 season, reaching about 57,000 farm households.
The first group of released varieties have been bred using traditional breeding practices. The WEMA variety pipeline also includes a number of transgenic (Genetically Modified) varieties for future release should regulations permit.
The Cassava Mechanisation and Agro-processing Project (CAMAP) project has acquired machinery from Brazil and is working in Nigeria, Zambia and Uganda covering a total of 2,655ha. Historically, farmers in Nigeria were harvesting an average of 7 tons per ha. The CAMAP Project has demonstrated increased average yields of 28 tons per ha, with some farmers achieving 33 tons per ha. Taking a value chain approach, the project links farmers to processors. Net profit in Nigeria ranged from US$ 1,284 to US$ 1,984 per ha as a result of this intervention . In subsequent years, farmers are required to pay to use the mechanisation services provided by AATF partners.
Evidence of the effectiveness of AATF as an institution, and the value of DFID support, is also shown by the level of investment by other investors, as shown in the table below. DFID support has varied between 10% and 20% of annual expenditure over the past seven years.
Table 1: AATF Income in US Dollars
	2008	2009	2010	2011	2012	2013	2014
DFID	2,193,441	2,283,288	1,811,791	1,572,248	2,537,996	3,124,109	2,822,516
Rockefeller	584,554	877,066	62,844	0	0	1,257	0
USAID	2,003,348	2,456,609	2,358,249	3,490,076	2,458,259	3,779,042	5,634,228
Bill & Melinda Gates Foundation	7,287,908	4,882,289	6,215,496	10,005,247	10,757,782	11,664,777	15,399,470
Howard G. Buffet Foundation	1,000,000	1,000,000	1,000,000	1,000,000	1,000,822	200,000	200,000
Syngenta Foundation	0	0	0	0	0	28,745	268,667
Various	16,720	31,559	299,059	115,736	189,616	639,492	311,755
TOTAL DFID	2,193,441	2,283,288	1,811,791	1,572,248	2,537,996	3,124,109	2,822,516
TOTAL OTHERS	10,892,530	9,247,523	9,935,648	14,611,059	14,406,479	16,313,313	21,814,120
GRAND TOTAL	13,085,971	11,530,811	11,747,439	16,183,307	16,944,475	19,437,422	24,636,636
% DFID funding	17%	20%	15%	10%	15%	16%	11%

1. In a number of cases, eg Insect Resistant Cowpea and NEWEST Rice, the initial conceptualisation and implementation was funded by DFID. This leveraged significant additional funding from the United States Agency for International Development (USAID). Evaluations by other donors of individual projects by other donors have been positive.
2. The evidence of impact for Options 1 and 2 is comparable. Performance related funding under Option 2 would incentivise AATF to push for increased impact. There is limited evidence of impact for Option 3, which would require establishment of a new mechanism to support Product Development Partnerships in the crop sector.
3. Leverage of additional investment:- To date, core funding of AATF (Option 1) has attracted significant investment from other donors, as evidenced in Table 1, above. The proposed funding Option (Option 2) has potential to leverage additional investment as the performance related funding component would be structured to incentivise organisational change within AATF ensuring that it continues to evolve as a high-performing organisation that delivers results. Diversity and size of other investors could also be performance criteria.
4. Discussions with existing donors concerning support to AATF have indicated that DFID’s core contribution is stimulating them to consider core support to AATF.
5. Option 3, a new mechanism, has the potential to leverage additional investment but this is not guaranteed.
6. Sustainability:- The sustainability of any mechanism to continue addressing markets failures to technology development and uptake is crucial in ensuring on-going impact from DFID investment. Option 1 has some potential to deliver a sustainable mechanism, but there is a risk that in five years’ time AATF has not advanced sufficiently in becoming a sustainable organisation. The proposed blended funding mechanism (Option 2), if structured correctly, has significant potential to improve the sustainability of AATF as an institution and the impact they have a demonstrated ability to deliver. It is highly unlikely that Option 3 would deliver a sustainable mechanism at the end of a five year period, as it would need to be established and develop a programme of activities to be able to demonstrate sufficient impact and thus attract continued investment.
7. DFID Resource: Option 1 would require relatively limited DFID resourcing, continuing funding through a core funding mechanism. This would require no change from current resourcing with regular reporting and quarterly payments to AATF. Managing the blended funding of Option 2 would require more resources from DFID staff to agree and monitoring the performance funding mechanism. Option 3 would require substantially more DFID resources to scope, design and procure a new Product Development Partnership.
8. Option 2, blended funding to AATF, is the preferred option. While requiring more DFID resource, continuing funding to AATF through a modified mechanism has the potential to enable a well performing and successful organisation to scale up impact for small-holder farmers in Africa, develop a robust pipeline of new products and become a more sustainable organisation. The performance related component will incentivise AATF to build a strong pipeline of projects more rapidly than previously and transition to a more sustainable business model.
Theory of Change for preferred option
1. The theory of change for the preferred option of blended funding to AATF is at Figure 2. This will be refined and developed further with AATF, as recommended in the Institutional Review, to ensure that the AATF Team are fully aware of the logic underpinning DFID support to the organisation.
2. The theory of change underpinning DFID’s support to AATF can be summarised as
DFID support to AATF in the form of core funding and performance related funding will enable AATF to build a strong project pipeline of new technologies, scale up adoption of existing AATF technology and begin the transition to a financially sustainable business model that is not dependent on donor funding.
Details of assumptions underpinning the theory of change are grouped into three categories. Where appropriate they are located (with letters) at specific points on the theory of change.
Assumptions about CAUSALITY
  1. New investors exist and are attracted by the impact of AATF technology on smallholders and AATF’s pipeline of new technology.
  2. AATF continues to deliver appropriate technology for small-holder farmers during and after this phase of funding.
  3. There is strong evidence that the adoption of new technology contributes significantly to improved agricultural productivity.
  4. A performance related funding component that is mutually agreed between DFID and AATF supports more rapid development of new technology and the transition to a financially sustainable organisation.
  5. Other donors support the implementation of the performance related funding component.
  6. A sustainable business model for AATF can be identified and institutional development of AATF enables the transition to the new model.
  7. AATF technologies are able to compete with others in their target market.
Assumptions about PROGRAMME IMPLEMENTATION
  1. Private sector holders of new and promising technology/IP remain committed to a process of sharing proprietary technologies.
  2. AATF does not receive negative publicity linked to their involvement in research on genetically modified crops.
  3. AATF is able to maintain good relationships with stakeholders and partners to support project activities.
  4. The AATF Board remains proactively engaged with AATF’s agenda and supports the Leadership Team.
  5. The regional integration agenda in East Africa with respect to seed certification moves forward, reducing the burden of see registrations in multiple countries.
Assumptions about EXTERNAL FACTORS that could influence the programme
  1. The policy and regulatory environment with respect to varietal development and release and biosafety remains favourable.
  2. There is no political instability or conflict in AATF target countries that impacts the ability of AATF or partners to operate freely.
Figure 2: Theory of Change

What the preferred option will deliver
Under the preferred option, DFID funding will be split in to two types. The first will provide core support to support to AATF to fund the following activities.
Identification, access to technologies and Management of IP
This activity is central to AATF’s core mission. AATF’s success is defined by its ability to map constraints affecting agricultural productivity and through intelligence gathering/technology scouting, identifies appropriate technologies that can address those constraints.
Knowledge management and information dissemination
The key goal of the AATF communications and partnerships work is to position the organisation as a responsible partner in addressing the needs of, and managing agricultural technology transfers to, resource poor smallholder farmer in SSA. It stresses management of perceptions and strategic relationships that feed the overall and project specific goals while also providing a strong base for resource mobilisation. Communications also recognises that the success of the Foundation’s interventions will be determined by how well it manages the relationship with its various stakeholders and the wider community. AATF produces and utilises a mix of communication products that have grown in number and type over the years. These products seek to establish, maintain and promote AATF’s distinct identity in ways that foster a consistent understanding of its core values, competencies, objectives and activities.
Monitoring and Evaluation (M&E)
M&E is a critical function to enable AATF to monitoring progress and demonstrate impact. Over the next five years, AATF intends to develop a robust Theory of Change, as recommended by the Institutional Review, and finalise their M&E Strategy. The implementation of the strategy will be supported by enhancements to their in house Monitoring, Evaluation, Learning, Improvement and Alignment (AMELIA) system, the main work planning and data collection tool. AMELIA allows uniformity in planning and data collection and guarantees quality. AATF will continue with regular enhancements to keep it relevant within the changing scope of data needs and types that vary with each project and working environment.
Impact assessment
Building on DFID’s experience of strengthening impact assessment in agricultural research centres, core support will be used to strengthen AATFs capacity to commission robust impact evaluations. Robust evaluations will enable AATF to demonstrate the effectiveness of their technologies for smallholders in Africa.
Resource mobilization
AATF will continue to invest time and effort in exploring all possible approaches to mobilize resources. A professional resource mobilization consultant has been engaged to accelerate the activities of the on-going resource mobilisation campaign and reach more investors faster. Other on-going efforts include the production of project concept notes, visibility and profiling of AATF with investors through donor roadshows, and increased involvement of board members in creating linkages and networks for resource mobilisation.
Gender Mainstreaming
A strong, continued commitment to gender mainstreaming is one of the most effective means for AATF to ensure that vulnerable women, youths, the under privileged as well as men can influence, participate in and benefit from agricultural development efforts. This approach will be implemented along the entire product value chain to enhance gender equity in participation and distribution of benefits through awareness workshops, trainings and demonstrations on the importance of gender inclusiveness. Thus AATF will be working on institutionalization of gender and will complement this strategy with targeted interventions to promote gender equality and women's and youth empowerment, particularly in situations where there is persistent discrimination against women.
Corporate Management/governance
To act as trustworthy and responsible party capable of entering into contracts with both public and private sector organizations to facilitate technology access, development and deployment, AATF has to consistently ensure that its governance structures, processes, operational systems and control mechanisms meet needs while making the best use of resources. The main areas to be addressed by the core funds for the following five years will be:
Board meetings: AATF will strive to keep a highly regarded and responsible Board of Trustees and will continue to hold two face-to-face board meetings annually and to get that fair and impartial oversight necessary for checks and balances and fundamental in promoting the confidence of our investors and shareholders including donor participation in Board of Trustee meetings.
Audits: To continue to be a go-to institution for many agricultural organizations looking to address constraints facing small scale farmers through various innovative solutions, AATF needs to enhance transparency and the Board of Trustees will continue to be assisted in this exercise by annual internal and external audits conducted by credible audits firms selected from the top four international audit firms.
Development of AATF’s Ten Year Strategy and revised Business Plan
Over the years, the AATF has grown both in terms of number of projects, the level of activities and also staffing. The landscape has also changed calling for a review of the organization’s contribution towards attainment of the overall goal of ensuring food security for SSA. In 2017 AATF will develop a ten year organizational strategy to outline the actions to take to achieve long-term goals, including institutional sustainability. Based on the outcome of the 2018 – 2027 AATF strategy, AATF will develop the 2019 – 2023 Business Plan as the roadmap for implementing the strategy.
AATF has also approached DFID to support a number of existing projects. Funding existing projects would result in activities whose impact is clearly attributable to DFID funding. DFID proposes to engage further with AATF to select specific projects which mostly closely align with DFID priorities, specifically in countries with DFID offices. Examples of potential projects are.
Out-scaling of StrigAway in Eastern and Southern Africa
In the next five years, the project would intensify outreach within the East African region. In addition, the project aims to out-scale and bring the benefit of the technologies to farmers in southern Africa, particularly, Zimbabwe and Malawi. The objective is to facilitate production of at least 2,000 tons of certified StrigAway (IR) maize seed in Kenya, Uganda, Tanzania, Zimbabwe and Malawi. This will open up the productivity of about 80,000 ha of farmland, enough to generate some 120,000 tons of maize grain, to enhance the food security for about 300,000 smallholder households. The adoption of the new IR maize hybrids is expected to at least double the grain yield per harvest; from an average of 500 kg, to at least 1,500 kg/ha. This translates to extra maize grain worth of about £17 million within the next 5 year phase.
Cassava Mechanisation and Agro-processing Project (CAMAP)
Currently in its second year of implementation in Nigeria, Zambia, and Uganda, the Cassava Mechanisation and Agro-processing Project (CAMAP) has been 100% funded by DFID. It aims at transforming the cassava sector through enhancing production, processing and market linkages based on business models to engender sustainability. The approach not only emphasises on machines, but also the linkage with use of improved varieties (high quality, high yielding disease resistant planting materials), use of best management practices – agronomy (including optimum plant density, fertiliser and herbicides application, weeding, timely planting and harvesting).The project also aims to improve market linkages and encourage value addition to ensure that farmers get the maximum profit from cultivating cassava as a business. The project is testing approaches to negotiating access to cassava mechanisation equipment and work with service providers, local fabricators and smallholder farmers to increase mechanisation along the value chain.
The CAMAP has stimulated significant demand. Therefore, AATF is seeking additional funding for up scaling and testing within the current countries and outscaling to new countries (Ghana, Mozambique and Angola) to target additional 500,000 farmers, youths, service providers, processors, fabricators, and the agribusiness. The up-scaling and out-scaling of CAMAP is expected to:
    - Increase cassava yield by 200%.
    - Train and facilitate 300 entrepreneurs in to cassava business
    - Transfer additional 20 technologies for planting, harvesting and processing
    - Increase market size of cassava products by 200%.
    - Increase production and processing efficiency especially among women and youths who do the bulk of the work on cassava production and processing
    - Strengthen market linkages and market capacity to enhance enterprise and employment creation
Out-scaling drought tolerant maize hybrids outside current WEMA countries
As AATF has successfully commercialised drought tolerant maize hybrids in Kenya, with promising results for South Africa, Mozambique, Tanzania and Uganda, plans are underway to scale-up the project outside the current five countries to three countries in West Africa: Nigeria, Ghana, and Cote D’Ivoire, and two countries in Southern Africa: Zimbabwe and Zambia. The aim will be to contribute to the production and distribution of at least 5,000 tons of certified drought tolerant maize hybrid maize seed within five years of operation to reach at least 800,000 farm households in these countries. These five new countries have similar incidences of frequent drought events and stem-borer insect-pest that affect maize production. They also have low maize yielding varieties that are highly susceptible to both drought and stem-borer insect-pests. In addition, some of the countries have infant seed systems, and in-efficient markets due to poor linkage to input (e.g. seed) and output markets (quality seed and grain) that the introduction of drought tolerant maize will address.
1. AATF funds a number of projects with financing from other investors, including the Open Forum for Agricultural Biotechnology (OFAB) funded by the Bill and Melinda Gates Foundation. OFAB is a platform that brings together stakeholders in biotechnology and enables interactions between scientists, journalists, the civil society, industrialists, lawmakers and policy makers to explore new avenues of bringing the benefits of biotechnology to African agriculture. There is a risk that AATF and OFAB activities linked to biosafety and seed system regulations are perceived as advocacy for specific technology, including genetically modified crops. DFID will require AATF to provide assurances that DFID funds are not used for advocacy activities.
2. The performance related funding component will be structured to incentivise AATF to reach impact at scale, develop a robust product pipeline and begin the process of organisational change to become a more financially sustainable organisation. Following approval of the Business Case DFID will engage with AATF to agree a set of milestones against which to assess their performance and which will support them in achieving their institutional objectives. The decision on a future business model will rest with AATF and their Board of Trustees.
3. DFID’s strategic vision is that AATF transitions to a business model, possibly a social enterprise, that starts to generate its own income, becoming progressively less dependent on donor funds.
4. Unless there is substantial change in the market, the market failures that AATF addresses will remain in 2020. At this point, the potential for future DFID support would be reassessed. The need for ongoing donor funding will be dependent on whether there is potential for AATF to transition to another vehicle, such as a social enterprise, which is less reliant on donor support.
5. Four potential outcomes are envisaged.
  1. AATF has not made significant changes to its business model, has struggled to achieve impact at scale and has not been able to diversify its investor base. Under this outcome, DFID funding would cease.
  2. AATF has made considerable changes to its business model, has achieved reasonable impact at scale and has made substantial progress in diversifying its investor base and has the potential to become financially sustainable, possibly as a social enterprise, within two to three years. Under this outcome, DFID would consider options for further funding to support AATF’s ongoing transition. This could be in the form of core-funding or support to specific projects/activities.
  3. AATF has become financially sustainable having changed its business model, achieved impact at scale and attracted significant investment from diverse sources. Under this outcome, DFID funding would no longer be necessary.
  4. The market failures that AATF was set up to address are no longer present due to intervention by other actors, such as seed companies or national governments. Under this outcome DFID funding would no longer be necessary.

## Commercial Case
1. The proposed intervention will be implemented through signature of an Accountable Grant with the AATF, which is a registered charity. There are no direct procurement implications for the proposed funding.
2. The Accountable Grant, using DFID’s standard template, will clearly set out DFID expectations with respect to programme management, financial reporting and Value for Money.

Value for Money
1. AATF uses competitive tendering processes both for procurement of goods and professional services to ensure value for money (VfM).
2. AATF has also been exploring mechanisms for cost recovery. At present, they recover some development costs from seed companies licensed to produce seed of AATF varieties. This has provided AATF with additional funds to reinvest in programme activities. AATF intends to expand this more commercial approach to resourcing.
3. AATF evaluate the net positive gain to society as part of the project design process. This is achieved by conducting feasibility studies and developing a business plan to outline the cost-benefit analysis as part of the initial preparation of a project.
4. AATF have a web-based financial reporting system to facilitate entry and analysis of financial information across projects and countries of operation. With this system AATF managers can have an accurate picture of their budgets at any time thereby enhancing budget management.
5. The modified funding approach proposed in this business case will provide DFID with greater opportunities to engage with AATF to improve value for money. Measures used to assess performance as part of the performance related payment component of funding will be used to incentivise more attention to VfM both through reducing costs and increasing outputs and impact. Potential indicators include:-
1. Progress in achieving uptake of technology at scale.
2. Indirect/direct cost ratios.
3. Commissioning of Impact Evaluations to demonstrate impact of AATF technology.
4. Level of financing obtained from new investors.
5. Development of new organisational strategy.
6. Proportion of staff with a more commercial/private sector background.

## Financial Case
The UK will provide up to £10 million to AATF over a five year period 2015-2020. The funds will come from Research and Evidence Divisions programme budget and will be split into two streams.
1. Core, unrestricted funding to a value of £7.5 million (£1.5 million/year).
2. Performance related funding up to a value of £500,000/year. During the first year of a new round of funding DFID would discuss and agree performance targets/milestones would be set for each subsequent year.
1. The proposed ore funding to AATF, is at the same level as previous funding. Performance related funding is additional which will signal clearly to AATF what DFID expects from them as an institution with respect to programme delivery.
2. DFID will carry out a Due Diligence assessment of AATF prior to signing an Accountable Grant with them. We do not anticipate that any substantive issues will arise as a number of reviews of AATF have indicated that they have strong procedures in place. Payments in respect of core and project funding will be made directly to AATF on a quarterly basis in arrears and upon receipt of a detailed statement of expenditure. Each statement will set out actual expenditure to date against the approved project budget and quarterly forecast expenditure for both the calendar and DFID financial year, i.e. 1st April to 31st March. The level of project funding for the forthcoming year will be notified to AATF after their performance during the preceding year has been assessed against the agreed objectives/milestones, as part of the Annual Review process.
3. The risk of the funds not being used for their intended purposes and the expenditure not being properly accounted for are low. AATF has strong governance and financial systems in place and an excellent track record of financial reporting. They have received unqualified audits for each of the years covered by our recently completed Phase 2 funding. AATF have appropriate policy and procedural manuals in place to ensure that staff follow generally accepted accounting practices. These manuals along with the strong internal and external controls that are in place are intended to mitigate the risk of any fraudulent activities.
4. AATF have a zero tolerance policy towards fraud. All employees are expected to report concerns or complaints regarding the conduct of Board Trustees, employees, vendors, contractors, sub-contractors, consultants, partners, grantees and donors which they believe breaches, fails to implement or comply with AATF’s rules, procedures policies or established standards of practice or is illegal or unlawful. Board trustees are required to declare all conflicts of interest. Staff may not associate with or hold financial interest in any business or organisation if it is possible for them to benefit from such association or financial interest, by reason of their position in AATF. The Audit Committee will review any conflict of interest situations pertinent to the AATF’s operation and recommend any relevant changes of policy to the Board. Such policies are set out in AATF’s Board and HR Manuals.
5. AATF have provided a list of the key risks faced by the organisation and described the mitigation actions to manage these risks. AATF’s programme monitoring and evaluation system, AMELIA, is an important tool for work planning, budgeting and tracking progress towards delivering key strategic outcomes and impacts. Most project impact indicators have been integrated into the system and it is now easy to get figures as and when needed. AMELIA will provide the reports that allows DFID to regularly monitor AATF’s performance against a specific set of deliverables. We will also review AATF’s quarterly financial reports and annual audited accounts to ensure our funds are used properly. We will work with other investors in reviewing AATF’s performance. The three main investors already share privately commissioned reports with each other.
6. A Deputy Programme Manager will be responsible for ensuring:
1. due diligence in the disbursement of funds and taking any appropriate action as deemed necessary;
2. DFID’s contribution is properly recorded in AATF accounts; and
3. AATF’s annual audited accounts comply with Blue Book requirements.
## Management Case
Programme Management
1. The proposed funding of AATF will be managed by Research and Evidence Division’s Agriculture Team through a Livelihoods Adviser, who will be the Senior Responsible Owner (SRO) supported by a Deputy Programme Manager (DPM).
2. During the previous funding period, DFID has developed a good working relationship with AATF and their other core investors, i.e. USAID and BMGF. One of the three core investors attends AATF Board Meetings as an observer on a rota basis raising issues of mutual concern and reporting back to the others after each event. This arrangement, along with other collaborative meetings, has helped to strengthen our technical and governance oversight of AATF and maximise the effectiveness of our respective investments. By sharing technical reports and reviews, it also enables us to minimise administrative costs. We will continue this approach to managing our relationship under the proposed intervention. Recent discussions have recommended to AATF that they rationalise and harmonise their reporting to investors as much as possible.
3. DFID will continue to fund AATF on a quarterly basis through an Accountable Grant. The level of core funding and part of the project support will be paid at the level set out in the Accountable Grant. The balance of the project support will be paid depending upon AATF’s performance against the agreed deliverables and milestones. In undertaking this review, DFID will use individual project reports and AATF’s Annual Report. DFID will hold an annual performance meeting with AATF (using VC or audio facilities) structured around the deliverables and milestones. AATF will give a presentation against these, but they will not have to provide a separate project report. Other investors will be invited to participate in these discussions. The annual performance meeting will feed into DFID’’s Annual Review process
4. The log frame will provide the basis for monitoring during DFID Annual Reviews.
Programme Risk
1. Risk and mitigation has been considered by the team that has developed the case for funding to AATF.
2. AATF works with smallholders in practice in 10-15 different countries depending on the specific project. The level of risk will differ from country to country, and from project to project. However the majority of risk has been internalised within the Project design. AATF is aware of these risks and will manage its portfolio of projects to reflect this. Now that AATF has been successfully established and is operational the overall risk of the programme is low.
	Probability	Impact	How risks will be minimised/mitigated
Management Risks
Establishment of the performance related funding component does not result in institutional change within AATF.	L	H	The DFID Management Team will engage proactively with AATF to ensure that the performance related component is fully understood and is aligned with AATF’s own objectives. AATF has a good track record of implementing organisational change and has a good relationship with DFID making the probability of this risk occurring Low.
AATF has a strong core team, but staffing changes within AATF could impact ongoing programme management.	L	L	This risk is minimised through AATF’s robust procedures and systems.
Programme Risk
Failure to adopt appropriate biosafety regulations in AATF target countries	M	H	This is a specific area of policy and law over which AATF has little direct control, but AATF has continued to engage partners and countries in dialogue with impressive outcomes.
AATF receives negative publicity in regional or national press	L	M	This risk is largely associated with public perception in Africa and the UK of both biotechnology and bio-safety. This can be seen in the context of AATF and UK government involvement in technology development. This has been internalised through the establishment of an information and management system and the awareness that publicity and profile need to be carefully managed. DFID will also need to be aware of this and manage publicity effectively
Private sector is not committed to process of sharing proprietary technologies	L	H	The delivery of the Outputs depends not only on the owners of proprietary technologies fulfilling their commitments and honouring their obligations but also in continuing to provide support with appropriate new technologies. This is largely internalised through AATF’s negotiation process and through the sharing of information on developments and progress, but other factors will also affect their willingness to engage.
Seed companies in target countries are no longer willing to work with AATF to deliver improved seed or access technology through other sources.	L	H	AATF technologies, including improved seed, are delivering to smallholders in partnership with private seed companies. AATF proactively manages its relationship with seed companies to mitigate this risk and has built up strong relationships with them.

In addition to assessing programme risks for the proposed new phase of funding to AATF, DFID has also reviewed past performance and the status of issues that have arisen during previous phases of funding. These are presented in the table below, along with a summary of the current status/mitigating actions.
Issue	Status/Mitigating actions
Scaling up of technology	There were specific technical challenges around the adoption and scaling up of IR maize for tackling striga, principally linked to the requirement for segregation of insecticide treated seed. These are still present, but availability and adoption is increasing. / AATF have learnt from the IR maize experience developing products that will be easier to scale up including Water Efficient Maize for Africa (WEMA). They are also engaging earlier and more proactively with seed companies to ensure the route to market is clear. / We intend to incentivise continued improvement in this area by linking performance payments to scaling up of technology.
Impact Assessment	AATF has developed a strong pipeline of products, four of which are in deployment/scale up. Using DFID core funding, AATF has developed a robust monitoring system to support project implementation and monitor progress. However, AATF struggles to measure the impact of adoption of technology at scale after initial research. / This is an on-going issue which AATF is aware of as DFID has discussed it with them on a number of occasions. During this funding phase DFID will continue to push for improve impact evaluation by AATF and this will be a criteria for performance related funding.
Executive Director	In the past seven years evidence of misconduct by two previous Executive Directors of AATF was identified during the course of their tenure. With support from donors, the AATF Board took firm action in both cases and the individuals left the organisation. The current Executive Director, Denis Kyetere, has been in post since January 2012 and the Board is very active and engaged. / AATF is well managed and has good procedures in place providing assurance that should issues arise in the future they will be handled effectively.
AATF staffing	While the technical skills and capacity of AATF staff are excellent, the majority have a public sector research institution background. AATF Investors have encouraged them to recruit staff with a more commercial/private sector background to support a shift to a more market-led approach to technology development. Acknowledging this issue, AATF commissioned an Organisation Structure Review in 2013. The review recommended the appointment of a Director – Commercialisation and Deployment. While the organisational structure was changed, the new Director post has not been filled. / Appointment of the new Director and staff with a more commercial/private sector background will be a criteria for performance related funding.