 Annual Review

Title: Market Development in Northern Ghana (MADE)
Programme Value £ (full life): £15,430,000		Review Date: July 2019
Programme Code: 201857	Start Date: January 2013	End Date: March 2020

Summary of Programme Performance
Year	2013/14	2014/15	2015/16	2016/17	2017/18	2018/19
Programme Score	A	A+	A	A	A+	A
Risk Rating	Medium	Medium	Medium	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-201857/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-201857/

A. Summary and Overview

This Annual Review was carried out jointly by DFID Ghana’s Senior Responsible Owner (SRO) for MADE, and a Livelihoods and Private Sector Development Adviser from DFID’s Growth and Resilience Department in London. The team was supported by a wide range of stakeholders from MADE in Tamale, Nathan Associates in London, other DFID advisers, and the MADE Programme Officer from DFID Ghana. The review set out to validate results through farmer and partner interviews, and to assess whether MADE intervention focus and activities were still appropriate.

Description of programme

Ghana’s success in poverty reduction[1] is a story predominantly of progress in the South, with rising income inequality that has notable spatial and gender dimensions. Development in Northern Ghana lags behind the rest of the country, with the Northern regions combined accounting for more than two thirds of those living in extreme poverty (67.2%).[2] Four out of five people living below the poverty line in Ghana are located in rural areas. Over three quarters of these, mainly women, earn a living from agriculture.
[1] Ghana has experienced relative development success, with poverty levels falling from 56.5 percent in 1992 to 24.2 percent in 2013
[2] Ghana Living Standards Survey (GLSS) Round 7

The UK is providing £15.34 million over seven years (2013-2020) for MADE, a Market Development programme in Northern Ghana. MADE seeks to improve the incomes and resilience of poor farmers and small-scale rural entrepreneurs in the Northern Savannah Economic Zone by improving the way in which markets work, with a focus on agricultural value chains.[3] In addition, DFID had funded an independent evaluation which was closed in 2017.
[3] Maize, rice, soya bean, sorghum, onions, other vegetables, groundnuts.

MADE uses a Making Markets Work for the Poor (M4P) approach. M4P is an approach to poverty reduction which places emphasis on sustainability and systemic change. It does this by focusing on causes rather than symptoms, addressing constraints rather than delivering specific services, through providing support as a ‘market facilitator’ – working with key players in market systems to get them to work more effectively - rather than aiming to provide goods and services directly. More lasting and deeper change can be achieved by addressing the reasons why the market is not working effectively for such people in the first place.

In December 2017, a two-year time extension was approved using unspent funds to scale up programme results by deepening and widening the impact of MADE and mainstreaming the impacts.

Summary supporting narrative for the overall score in this review

The overall score of MADE is A and it is currently moderately exceeding targets in terms of delivery and achievements. Given the extent of thin markets in Northern Ghana, the pre-commercial nature of some of the smallholder farmers engaged by the programme, the challenging operating environment and legacy of reliance on public / development sector support, this represents a significant achievement. However, there are some delays to implementing several key activities that are deemed most critical to sustainability in the final year of the programme.

Output 1: Moderately exceeded expectations (A+), with market actors and smallholder farmers engaged and changes made to business practices;
Output 2: Met expectations (A), with smallholder access to credit and services increased and new products and services introduced to the market;
Output 3: Met expectations (A), with MADE focusing on delivering sustainable changes to the informal rules governing markets, and a high level of satisfaction reported by market actors;
Output 4: Moderately exceeded expectations (A+), offering excellent value for money for DFID’s support to economic transformation in Northern Ghana.

MADE continues to perform strongly and has built upon its previous work, demonstrating good value for money. The programme has generated approximately £29.4m additional net income for 65,868 direct beneficiaries, of which 26,740 were women, representing an average of £447 per farmer. The programme has created 1,455 new high-value jobs and leveraged £36.2m of private sector investment through MADE’s business models. MADE continues to perform strongly on gender, substantially exceeding logframe and business case targets.

As MADE’s interventions continue to mature, we are seeing the percentage of support provided by MADE to businesses representing a very small share of the total investment cost, with the MADE investment percentage having declined steeply across the life of the programme. In the past reporting year, MADE investment represented just 1.97% of the total investment costs, with partner businesses providing 98.03%. It is impressive that the programme has influenced business model changes given the small investment share provided, which fits the market systems facilitation model and suggests an increased likelihood that business model changes will thrive beyond the end of the programme.

The dynamic growth in commercial partnerships which have led to a broadening of service and input supply capacity, while opening new markets and risk sharing opportunities, has been a key factor in the increase in private sector investment. Two original partner firms, Wumpini Agrochemicals (a supplier of agrochemicals) and Zug-Faan (a farm produce aggregator) are now working together in a formal partnership to deliver commitments to smallholder farmers (SHFs) agreed under the MADE programme. This has doubled the number of smallholder farmers reached through the programme from 1,040 to 2,300 and widened the range of services provided. Zug-Faan is now able to access inputs such as improved seeds, fertilizers, agrochemicals and tractor services from Wumpini and supply them as a bundle to their SHFs. Similarly, SHFs working with Wumpini now have access to reliable markets for their produce through Zug-Faan.

It should also be noted that the MADE programme is consistent with shifts in agricultural policy set out in DFID’s 2015 Conceptual Framework in Agriculture, such as an increased focus on commercial agriculture programming, on linking farmers to produce output markets and to supporting SHFs with the potential to ‘step up’ into commercial value chains to do so. Field interviews with farmer groups demonstrated that MADE has been successful in linking previously non-commercial farmers, particularly female SHFs, to commercial markets for the first time.

The programme’s successes on gender should be particularly commended, given the context and gender-specific barriers. Sex-disaggregated data shows the programme is delivering significant benefits to female farmers, who represent nearly half the beneficiaries, a significant increase on the 15% target set in the Business Case. In interviews, several businesses reported a shift in sourcing preferences towards female farmer groups, due to their higher levels of loyalty (businesses reported that female farmers displayed a decreased likelihood to side-sell), higher credit recovery rates of female farmers and better maintenance of hired mechanised equipment. One large input supply company, Antika, advised that they have begun to negotiate with local traditional chiefs responsible for land allocation on behalf of female farmers, to increase land apportionment to female smallholder farmers. The private sector leading in such an initiative in women’s empowerment is a good example of the sustainability of models promoted by the programme

There is significant emphasis in previous annual reviews and Theory of Change discussions on how the programme can step up to deliver change which is ‘transformational’. There is a significant challenge in demonstrating whether the programme is meeting this bar: most recent available official statistics on the growth of the agriculture sector in the Upper East, Upper West and Northern regions are from 2016. In the absence of more recent data, supported businesses interviewed for this review repeatedly cited that growth and investment is discernible in the agriculture sector in northern Ghana. Interviewees cited evidence of farmer investment in homes, land, village level storage systems and their own transport, as growth proxies. Better evidence on sectoral growth would be extremely useful for any future investment that DFID Ghana may make and there may be opportunities to work in partnership with the Ghana Statistics Survey (GSS) and the Ministry of Food and Agriculture (MoFA) to update survey data required to assess agriculture sector growth in the North. Progress on provision of affordable irrigation systems for small-scale farms would be likely to shift transformation significantly, having a major positive impact on yields and productivity, but affordability of this remains a key challenge for the programme.

MADE continues to exceed targets in four out of five outcome indicators with farmers improving yields, incomes and connectivity to markets (see Section C). These results indicate progress towards achieving the programme impact of economic growth and poverty reduction in Northern Ghana. The inclusion of pre-commercial farmers to ‘step up’ into commercial value chains is an indication of agricultural transformation, as set out in DFID’s Conceptual Framework for Agriculture.

Summary of Key Recommendations for the year ahead:

R1: Access to affordable irrigation on small-scale farms could be a game-changer for agriculture in Northern Ghana, with the potential to deliver transformative yield increases and two season cultivation if the issue of affordability could be addressed. The programme should dedicate significant resource to ensure lessons from the trial linking drip irrigation providers to selected agri-businesses are fully captured, as this work could inform future investment in agriculture in northern Ghana.

R2: As it enters its final year of operations, the programme would benefit from conducting a ‘stepping up’ survey to accurately capture data on the number of pre- and semi-commercial SHFs among total farmer beneficiary numbers. Being able to show solid data – disaggregated by gender - about the number of SHFs enabled to enter commercial markets for the first time due to service and input access facilitated by the programme would be a powerful piece of impact data. Linking this to poverty status of beneficiaries would be even more compelling developmentally but could be challenging to do retro-actively.

R3: With seven months remaining on the programme, firm willingness and capacity to cover the costs of the Farmer Enterprise Adviser (FEA) and Business Development Adviser (BDA) operation is the critical factor governing sustainability of the approach credited by many interviewees as key to increased farmer integration into MADE value chains. The last Annual Review recommended that a robust financial / commercial understanding of the market viability of these functions needed to be in place by December 2018, but operational challenges have prevented this. Research to more firmly establish the business benefits and cost / benefit of the field staff model needs to be expedited as a priority activity and wide dissemination made of results by September 2019.

R4: Interviews with farmers, lead farmers and aggregating companies revealed that timely availability of ploughing services has been a key challenge, particularly for those operating a credit model where payment for the service is given at harvest time. Demand for tractors peaks at one point in the Northern agricultural calendar and those farmers only able to pay for services on a credit repayment basis would often receive ploughing services late. In response to this challenge, the programme has assumed a market intelligence function, linking providers of ploughing services in other parts of the country with a different agricultural calendar to demand in the North. Whilst this has alleviated the supply-demand problem, in its final seven months of operation, the programme needs to complete hand over of this function to relevant private sector actors.

R5: Delivery of the Enterprise Benchmarking Competitiveness Assessment is a key product to segment firm performance, enable the identification of high potential lead firms and the development of strategic growth plans, as well as the dissemination of information on high potential companies to the financial ecosystem (allowing those firm to increased access to finance). However, it is running behind schedule. The anticipated strategic plans for future growth being developed in quarter 1 of the next reporting period for MADE businesses should be expedited and shared with DFID and the wider financial ecosystem. DFID and MADE should explore options to continue to promote the benchmarking work beyond the end of the programme.

R6: At a strategic level, DFID and MADE should continue to engage with the Ghana Commodity Exchange (GCX), particularly exploring the GCX’s appetite and capacity to integrate systems within its model which would enable farmers, as well as aggregators, to benefit from price appreciation and discovery. DFID has supported other Commodity Exchanges and structured trading systems in Africa to invest in transport, warehousing, product tracing and grading technology capable of reaching down to farmer level, so enabling farmers to store product directly, rather than working only through aggregating companies. A useful research element for the final year of the programme would be to revisit these investments, ascertain success in integrating farmers directly into exchange mechanisms and the associated benefits to farmers to inform future strategic engagement and discussions with GCX.

R7: MADE will commission a study of the Farmer Enterprise Adviser (FEA) and Business Development Adviser (BDA) models to ensure that this study considers whether safeguarding risks exist in the FEA / BDA – farmer relationship. If found to constitute a safeguarding risk, MADE should present recommendations to DFID on possible mitigating actions, such as establishment of independent grievance or whistle-blowing mechanisms.

R8: MADE should make a concerted effort to engage with key institutions to share its work and to help sustain MADE approaches, including the FEA and BDA models. MADE should identify and explore different approaches to achieve this, for example with the Ghana Commodity Exchange.

## B: DETAILED OUTPUT SCORING

Output Title	Selected rural market systems work more effectively for poor farmers and small-scale rural entrepreneurs
Output number per LF		1	Output Score	A+
Impact weighting (%):		40%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
Number of market actors facilitated by MADE changing their business practices and/or forming new partnerships in markets facilitated by MADE. (Supported enterprises in brackets). (cumulative)	75 (9)	Exceeded: 77 / (11)
Number of poor farmers who use new or improved inputs as a result of facilitation by MADE (women in brackets). (cumulative)	66,000 (28,000)	Substantially exceeded: 82,670 / (33,909)
Number of poor farmers supported by MADE to cope with the effects of climate change (women in brackets) (cumulative) ICF Indicator	58,500 (26,000)	Exceeded: 63,240 / (26,145)

Supporting narrative for the score

Output 1 is the principal output measuring MADE’s added value, focusing on facilitating sustainable, systematic and scalable change in enabling poor farmers to access much needed agricultural inputs and services. Performance on the output has moderately exceeded expectations, against indicator targets which were revised upwards following the last annual review to ensure they were sufficiently challenging. MADE was able to: facilitate change of business practices of an additional 11 partners, bringing the cumulative total to 77; increase the number of farmers using new or improved inputs by 29,175 (21% higher than expected), and; increase poor farmers supported to cope with the effects of climate change by 15,456. The role of women continues to be strong, with female SHFs making up 41% of beneficiaries.

The recent visit by DFID’s Deputy Chief Economist confirmed that agricultural markets in Ghana are marked by market failure. Productivity is held back by problems co-ordinating groups of farmers and challenges such as providing credit to invest in improved varieties of seeds and production technologies, e.g. row planting and tractors. The visit highlighted that aggregators who can provide extension advice, inputs on credit and co-ordinate groups to ensure repayment have a critical role in market transformation.

The business practice changes that MADE is facilitating, directly respond to these challenges. Changes to business as usual practices include companies committing to make the whole suite of services required for agricultural production accessible to their farmers, often through a credit-based system repaid with produce at harvest. Frequently, enabling farmer access to a comprehensive service suite requires lead companies to enter into new commercial partnerships with other enterprises to deliver the programme’s ‘Advanced Model’, which includes: land preparation services (ploughing), access to improved or certified seed, plant nutrition and protection products, extension services, buy-back arrangements, harvesting services, planting and seeding services, levelling and bounding (building of ridges to conserve water), and on-farm water management. At the close of the reporting period, 20 of the 33 lead firms supported were delivering this comprehensive package to farmers, with the other 13 delivering packages with fewer elements (the ‘basic’ and ‘medium’ bundles). The bundling model has reduced the cost of service and input delivery, enhancing farmer’s access to and use of the right quantity and quality of inputs and services, increasing land area used for cultivation and improving the reliability of credit recovery.

Based on a qualitative gender assessment, the MADE bundle, particularly the buy-back scheme, has allowed women to engage in commercial farming in ways they could not previously. This has significantly benefitted them. They are able to contribute to household expenses and invest in their livelihoods, which has positively impacted both the way they perceive themselves and the way others perceive them. Male SHFs have observed that women are good farmers and can contribute to household expenses, and they not only allow them to expand their activities but are also in some cases helping on farms or in households. Nonetheless, the majority of female farmers associated with MADE are still constrained by household responsibilities that limit their economic opportunities.

The number of farmers using new or improved inputs and services increased in the reporting year by 29,175. As noted above, 41% of these farmers are female, a significant achievement given gender norms in the area. Interviews with female farmer groups illustrated that support facilitated by the programme had enabled them to engage with commercial markets for the first time. In interviews, several businesses reported a shift in sourcing preference towards female farmer groups, due to their higher levels of loyalty (businesses reported that female farmers displayed a decreased likelihood to side-sell), improved credit recovery rates of female farmers and better maintenance of hired mechanised equipment. One large input supply company, Antika, advised that they have begun to negotiate with local traditional chiefs responsible for land tenure allocation on behalf of female farmers, to increase land allocations to female smallholder farmers.

For indicator 1.3, 15,456 farmers have been supported with climate smart agricultural techniques disseminated through Farm Enterprise Advisers (FEAs) who are engaged by and work for aggregating companies as well as through Business Development Advisers (BDAs), who are engaged by and work for input supply companies. The private sector nature of the extension model is key to the anticipated sustainability of advisory services. FEAs and BDAs disperse training to farmers on two or more of the following climate-smart agricultural techniques: drought-resistant variety adoption and use of early maturing seeds; on-farm water management, mulching, cross-field ploughing to maximise water retention, use of organic inputs and bonding (building of ridge system to trap water).

Lessons identified this year, and recommendations for the year ahead linked to this output

Interviews with farmer groups, lead farmers and agricultural training establishments revealed a strong preference for moving into vegetable production due to the high prices commanded by these commodities. Increased vegetable production and supply would also clearly assist with increasing supply of nutritious foods in the programme area. The primary barrier preventing smallholder farmer diversification in the programme area is the absence of affordable irrigation which is required to meet the high-water demand of vegetable cultivation in an area highly susceptible to climatic shocks. The programme has previously attempted to resolve the irrigation provision challenge unsuccessfully, but activities are planned for the final seven-month period to link irrigation service providers to a select group of supported companies perceived to have appetite to co-invest here. Beyond MADE, DFID should look at opportunities to further engage on irrigation and how farmers and businesses can take advantage of the new infrastructure developments by the Government and other development partners.

Recommendation: Access to affordable irrigation on small-scale farms could be a game-changer for agriculture in Northern Ghana, with the potential to deliver transformative yield increases and two season cultivation if the issue of affordability could be addressed. The programme should dedicate significant resource to its final intervention on irrigation in the remaining programme period and ensure lessons from the trial linking drip irrigation providers to selected agri-businesses are fully captured, as this work could inform future investment in agriculture in northern Ghana.

Recommendation: As it enters its final year of operations, the programme would benefit from conducting a ‘stepping up’ survey to accurately capture data on the number of pre- and semi-commercial smallholder farmers among total farmer beneficiary numbers. Being able to show solid data – disaggregated by gender - about the number of smallholder farmers enabled to enter commercial markets for the first time due to service and input access facilitated by the programme would be a powerful piece of impact data. Linking this to poverty status of beneficiaries would be more compelling developmentally but could be challenging to do retro-actively.

Output Title	Supporting functions to effective markets strengthened
Output number per LF		2	Output Score	A
Impact weighting (%):		25%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
Number of smallholder farmers accessing financial, credit, and or business services through MADE support. (women in brackets) (cumulative)	46,000 (21,000)	Met: 50,618 / (22,054)
Number of new or improved services or products being provided to smallholder farmers or small-scale entrepreneurs as a direct result of MADE's facilitation (cumulative)	31	Exceeded: 34
Percentage of surveyed market actors (who do not receive facilitation through MADE) who report positive perceptions of relevant business models supported by MADE (cumulative)	85%	Met: 88%

Briefly describe the output and provide supporting narrative for the score

Overall, the output has met expectations. MADE supports provision of and access to a series of specific services for smallholder farmers, which are critical to effective functioning of agricultural markets. In the reporting period: an additional 14,809 farmers received financial or business services; three new products and services were introduced through MADE facilitation and co-investment, and; 88% of non-MADE supported businesses taking part in the qualitative questionnaire used to measure perceptions of MADE business models reported viewing these changes as positive.

Services include credit, inputs (seeds, fertiliser) and tractor ploughing. These are made available to farmers on an input credit system, with farmers repaying either to the firms who have negotiated these services with other companies on their behalf or to the service provider directly, at the time of harvest. The system adopted by MADE-supported firms removes the need for farmers to negotiate with service providers on their own behalf and enables them to benefit from the economy of scale of accessing a service / input as a member of a much larger group.

Interviews with all parts of the value chain (aggregators, input suppliers, lead farmers, farmer groups) repeatedly confirmed the critical nature played by the Farm Enterprise Advisers (FEAs) and Business Development Advisers (BDAs). The FEA model was introduced by the programme in the previous reporting year and has been expanded significantly in the year under review. The BDA / FEA model relies on the availability of trained field staff working at farm level ratios of 1 BDA or FEA to 200 smallholder farmers. FEAs / BDAs appear to play a critical role linking farmer groups and access to services and inputs, dispensing advice to farmers about appropriate input use, building trust between firms and farmers, and are reported to have had a key role in increasing product volume aggregated from farmers and decreasing the incidence of side-selling.

One of the key functions of FEAs is the identification and selection of the SHFs and the management of bundled supplies and services. The pre-season process of farmer registration and in-season monitoring and reporting of transactions is hugely problematic and time-consuming because of the sheer number of records involved. The use of farmer passbooks, introduced in year 4 of MADE, helped to formalise the process of data collection and management but the paper-based system lacked robustness. During the current reporting period, MADE has been working with a specialist service provider to design an electronic data capture and management system called M-Access with the intention of rolling it out across all partner firms in Y6. Progress in the development of a system which addresses the interests and capabilities of MADE’s partners firms, while offering a means of more effectively monitoring the impact of higher levels of investment on SHF performance, has been slow and is proving challenging. However, the potential impact of such a system in relationship building and lowering the cost of farm enterprise advisory services is huge and should be pursued vigorously.

The previous Annual Review recommended that MADE should begin to develop growth pathways for the high potential businesses that could ultimately take the supported business functions to a much greater scale and outreach by January 2019. As a first step at the beginning of the current reporting period the MADE team focused on reducing the number of lead firms they were working with and deepening relationships with stronger, more commercially viable firms that have the potential to reach transformational scale. This was achieved by MADE raising the bar in its partner selection criteria and encouraging businesses to work together to improve and expand service delivery. 31 lead businesses were selected for partnerships in Y6 with a further 31 firms receiving programme support as support enterprises.

The facilitation of commercial partnerships with the implicit sharing of investment and risk is aimed at ensuring a higher level of planned investment in input supplies and services to smallholder farmers. In the current reporting year, only 85% of projected partner investment was achieved due to the inability of some partners to access full credit financing from financial institutions.

In response to last year’s annual review recommendation, MADE has commissioned an Enterprise Benchmarking Competitiveness Assessment to competitively benchmark MADE partners by assessing business functionality to differentiate those with high growth potential. Progress on delivery of this however has not moved as quickly as anticipated due to the additional engagement required of the team in monitoring company compliance with terms and conditions of support (see risks section for more detail). Early in the next year, Business Development Advisers will be appointed to work with each of the partner firms to address identified constraints and to set out strategic plans for future growth. However, the relatively early stage of the Benchmarking work during the period under review means it has not been possible to assess the degree to which it will enable identification of firms most likely to achieve transformational scale. The impact of this exercise could be substantial, and DFID should explore opportunities to continue support beyond the end of the programme.

Lessons identified this year, and recommendations for the year ahead linked to this output

As this is the last Annual Review given programme closure in seven months’ time, all recommendations below focus on actions needed to maximise the chance of sustaining programme achievements at the point of closure.

The FEA / BDA system has clearly been paramount in catalysing changes to business models facilitated by MADE. The programme provides some support for the network, covering training and transportation costs of the agents, with firms covering agents’ remuneration costs. For the model to remain in place at programme close, additional costs borne by the programme will need to be assumed by firms and so the business case setting out the links between FEA / BDA function and enterprise growth, increased competitiveness and improved profitability, need to be firmly established. For this reason, the programme committed to conducting research to demonstrate the links between the network and for growth during the current reporting period. Unfortunately, the need to increase focus on monitoring company compliance with terms and conditions of support (covered in more detail in the Risk section) has delayed this important work and this is now scheduled to start in the next reporting year, with a return on investment study being planned for early in year 6.

Recommendation: With seven months remaining on the programme, firm willingness and capacity to cover the costs of the FEA and BDA operation is the critical factor governing sustainability of the approach credited by many interviewees as key to increased farmer integration into MADE value chains. The last Annual Review recommended that a robust financial / commercial understanding of the market viability of these functions needed to be in place by December 2018, but operational challenges have prevented this. Research to more firmly establish the business benefits and cost / benefit of the field staff model needs to be expedited as a priority activity and the results widely disseminated.

Recommendation: Interviews with farmers, lead farmers and aggregating companies revealed that timely availability of ploughing services could be a key challenge, particularly for those operating a credit model where payment for the service will be given at harvest time. Demand for tractor services peaks during key times in the Northern agricultural calendar, typically immediately prior to the seasonal rains and during harvesting, and those farmers only able to pay for services on a credit repayment basis often receive ploughing services late, In response to this challenge, the programme has assumed a market intelligence function, linked providers of ploughing services in other parts of the country with a different agricultural calendar to demand in the North. Whilst this has alleviated the supply-demand problem, in its final seven months of operation, the programme needs to urgently examine how it can hand over this function to a private sector actor.

Recommendation: The Enterprise Benchmarking Competitiveness Assessment is a key product which is running behind schedule. The anticipated strategic plans for future growth being developed in Y6 Q2 of the next reporting period for MADE businesses should be expedited and shared with DFID as well as disseminated by the supplier within the commercial financing ecosystem, given firm challenges in accessing full credit financing anticipated in the year five budgeting exercise. DFID and MADE should explore options to continue to promote the benchmarking work beyond the end of the programme.

Output Title	More effective rules and practices of market system in selected sectors
Output number per LF		3	Output Score	A
Impact weighting (%):		25%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
Number of changes in regulation, policy and informal market rules brought about as a result of the programme (cumulative)	20	Exceeded: 22
Level of satisfaction of surveyed market actors with key aspects* of commercial relationships facilitated by MADE (cumulative)	High	Met: High

Provide supporting narrative for the score

Output 3 measures changes in the ‘rules of the game’ component of the market, a key pillar for M4P programmes to succeed. MADE has actively engaged with partners to promote the market system approach, opening-up opportunities to work with actors to transformation Ghana’s agricultural markets. Programme interventions have focused on informal market rules set by actors with whom the programme engages but is starting to deliver on regulatory or policy level change. The programme reports delivery of 5 changes to regulation, policy and informal market rules as a result of the programme, exceeding the target of 3 set for the reporting period.

Rule changes include: adoption of strategic commercial partnerships between agribusinesses to deliver integrated packages of inputs and services to farmers (see output 1 reporting). Previously, agribusiness firms operated in silos, within the limits of their capacity, offering SHFs only inputs and services they could afford and regarding other companies operating the space as competitors. MADE has introduced the concept of encouraging commercial partnerships between firms to increase their capacity and service / input offer, resulting in many interviewed businesses reporting a change of mindset regarding the benefits of corporate partnership, and an increase in inputs and services supplied to farmers.

Other changes include: use of supplier credit agreements between MADE lead firms and their support enterprises (aggregators and input suppliers) which set out terms and conditions previously agreed orally; the issuance of performance-based contracts to FEAs/BDAs who were previously engaged on a monthly salary basis but who are now rewarded based on deliverables and results; and the setting up of agri-businesses as "one-stop shops" for input and service delivery to SHFs.

One particular engagement to note under this output this year has been the programme’s engagement with the nascent Ghana Commodity Exchange (GCX) which has taken two forms. Firstly, the organisation of workshops with supported businesses to familiarise them with the Commodity Exchange structure and opportunities presented. Network facilitation with apex dealers is perceived to open-up opportunities for value chain financing and by working with support enterprises, lead firms can share credit risks. MADE has signed an MoU with GCX, six MADE supported businesses have signed up to store and trade on the exchange and two MADE supported businesses have completed trades on it. MADE plans to build the capacity of partners on grading and quality control through workshops. Secondly, the programme has sourced expertise from the global commodity exchange community to develop GCX’s strategic plan, offering a significant opportunity to help improve farmer and agribusiness access to high-value markets, with warehousing, storage and other services and offering access to higher prices.

Lessons identified this year, and recommendations for the year ahead linked to this output

Ghana’s agricultural policy remains centred around the Government of Ghana’s (GoG) flagship Planting for Food and Jobs (PFJ) campaign, which has been complemented during the reporting period by two new programmes: Planting for Export and Rural Development (PERD) and Rearing for Food and Jobs (RFJ). Whilst MADE has not directly engaged on these flagship programmes, it does, through its market systems approach, offer government a framework within which the subsidised inputs to farmers, provided through the PFJ, can be securely and effectively channelled and applied.  Additionally, by helping to reduce the cost of production, the 50% subsidy on selected seeds and fertilisers has enabled MADE agribusiness partners to extend the range of services offered to SHFs and increase their client base.  The FEA service model directly supports the GoG’s ambition to increase its extension service presence at farm level.

Engagement with the GCX appears to offer significant opportunities for MADE supported firms and wider agricultural transformation. The programme should continue to engage and explore further partnership opportunities. Dissemination of the benefits of producing to different grades and quality will continue to be critical, given that different product grades are not rewarded on the open market.

Recommendation: At a strategic level, DFID should continue to engage, particularly exploring GCX’s appetite and capacity to integrate systems within its model which would enable farmers, as well as aggregators, to benefit from price appreciation and discovery. DFID has supported other Commodity Exchanges and structured trading systems in Africa to invest in transport, warehousing, product tracing and grading technology capable of reaching down to farmer level, so enabling farmers to store product directly, rather than working only through aggregating companies. A useful research element for the final year of the programme would be to revisit these investments, ascertain success in integrating farmers directly into exchange mechanisms and farmer benefit to inform future strategic engagement and discussions with GCX.

Recommendation: MADE should make a concerted effort to engage with key institutions to share its work and to help sustain MADE approaches, including the FEA and BDA models. MADE should identify and explore different approaches to achieve this, for example with the Ghana Commodity Exchange.

Output Title	Programme is being delivered at value for money
Output number per LF		4	Output Score	A+
Impact weighting (%):		10%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
Management cost per facilitation (intervention fund) £ spent	£0.15	Met: £0.17
Facilitation (intervention fund) cost per beneficiary (cumulative)	£60.81	Exceeded: £54.68
Amount of additional private sector investment leveraged (cumulative)	£26.1m	Substantially Exceeded: £36.2m

Provide supporting narrative for the score

Overall, this output moderately exceeds expectations. MADE leveraged over £20 million in private sector resources in Y5, exceeding the combined investment from Years 1-4 with a total leverage for the programme lifetime of £36.2m. This increase in private sector investment suggests a strong commitment to the business models proposed by the programme. Detailed analysis on value for money and these indicators is provided in Section D below.

A key driver for exceeding the targets on facilitation cost per beneficiary and amount of additional private sector investment being leveraged is the delivery by MADE’s partners of a higher level of input supply and service delivery. The target investment budget per beneficiary defined during work planning sessions with prospective partners and verified at end-of-year survey, has risen year-on-year as agribusinesses realise improved returns on investment associated with increased yields and improved SHF performance. This increased willingness to capitalise out-grower operations has been driven by enhanced assess to wholesale markets facilitated through improved networking and the growing confidence in the value of the FEA model.

Lessons identified this year, and recommendations for the year ahead linked to this output
See Section D below on Value for Money.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change and any major changes in the past year

For MADE, in the below diagram, the ‘poor’ are female and male smallholder farmers, small rural entrepreneurs and those indirectly benefitting from jobs and labour opportunities created on commercialising farms. The MADE Theory of Change (ToC) proposed that as a consequence of farmers having access to new services and inputs required for agricultural production through improved service, extension and input provision facilitated by aggregators and input suppliers, and improvements to the market systems governing agricultural production, farmers will improve yields, incomes and connectivity to commercial markets.

Last year’s Annual Review identified flaws in the Theory of Change (ToC), most notably that businesses were referred to in the Business Case as if a uniform, rather than a differentiated, group and that the growth of MADE partners (supported companies) was taken for granted, pointing out that programme experience to date had shown this to be an incorrect assumption. It therefore recommended that MADE start developing and / or strengthening new relationships to establish the building blocks of a much wider, scalable and transformational theory of change, and that it increases the focus on providing support to enable the firms it partners with to grow.

Figure 1: Overview of Making Markets Work for the Poor (M4P) Theory of Change

Elements of this new direction have been adopted by the supplier without a rewriting of the programme Theory of Change – there has been an increased focus on firm support and differentiation, and support has been prioritised to firms which are perceived to be better able to scale. There has also been adoption of a commercial partnership model linking lead firms to support enterprises to enable growth in the package of services, inputs and extension being made available to farmers. The extent to which the market system changes promoted by the programme to deliver change has improved significantly following the emergence in the programme area of an increasing number of medium-sized agribusinesses working together to achieve scale. 14 of MADE’s partner firms and support enterprises had annual turnovers greater than £250,000, of which 8 were greater than £500,000 and 3 exceeded £1m. Allah is Able, for example, has grown its investment in service delivery for SHFs within three years from £88,185 in 2017 to £1,116,840 in 2018 and is projected to invest upwards of £4,169,750 in 2019. This due to the business entering into commercial partnerships with two new support enterprises, Segrace Enterprise and Okyerefo Consult and adopting the bundling model across all of the partnership out-growers.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead

In the case of Outcome Indicator 1, the number of small-scale farmers and entrepreneurs in northern Ghana experiencing positive income change as a result of the new models facilitated by MADE is measured at the enterprise level, rather than the household level. The indicator looks only at direct beneficiaries, i.e. those SHFs registered with MADE partner firms and targeted for receipt of input supplies and services covered by the grant agreements. In practice, most partner firms and their support enterprises extend the MADE business models beyond the target SHF figure. There are also other agribusinesses who have observed the benefits of the programme but have not sought direct support from MADE, who are also applying the advanced model to the benefit of SHF across the region.

With the exception of the average income increase per smallholder farmer experiencing positive income change, which is slightly below the target of £481 at £447, MADE continues to exceed its outcome indicators. In so doing, interviews confirm that supported smallholders include those who were not previously commercially engaged, and sex-disaggregated data as well as business interviews show the programme is delivering significant benefits to female farmers, who represent nearly half the beneficiaries.

Indicator(s)	Milestone(s) for this review	Progress
Number of smallholder farmers and small-scale entrepreneurs in MADE target markets experiencing positive income change (women in brackets)	57,500 (25,500)	Exceeded: 65,868 / (26,740)
Number of SHFs who experience income increase over £80 (women in brackets)	40,000 (18,500)	Exceeded: 46,487 / (16,615)
Average income (£) increase per SHF experiencing positive income change (cumulative)	£481	Not met: £447
Number of poor farmers and small-scale entrepreneurs who, respectively, experience higher sales and higher turnover (volume of production) as a result of new or improved models introduced through facilitation by MADE (women in brackets) (cumulative)	59,500 (26,500)	Significantly exceeded: 72,092 / (29,404)
Number of instances of progress towards systemic change (see MADE's definition of systemic change) (cumulative)	18	Significantly exceeded: 32

Key considerations for the final annual review seven months before the closure of the programme are those around sustainability and exit strategy. There has been a delay on the delivery of some recommendations from the previous annual review and completion of these is critical to a sustainable exit. These areas need prioritisation and expedited delivery in the remaining phase:

Documenting and demonstrating the cost-benefits of the field worker extension model to businesses to enable the presentation of a solid business case which is a pre-requisite if firms are to absorb the additional costs required to sustain this model at the point of programme closure;

Delivery of the Enterprise Benchmarking Competitiveness Assessment to segment firm performance, enable identification of highest potential lead firms and the development of strategic growth plans, as well as the dissemination of information on high potential companies to the financial ecosystem (allowing those firm to increased access to finance);

In addition, the programme needs to cease providing a market intelligence function matching supply of, and demand for, ploughing services and identify a market or public sector actor which could assume this role at programme close.

R9: MADE reviews the proxy indicators and captures the indirect smallholder farmer beneficiary numbers.

Explain major changes to the logframe in the past year

The following key changes were made to the logframe following recommendations from last year’s Annual Review which was approved in March 2019:

- All baseline milestones were updated using Year 4 actual results;
- Year 5 and 6 milestones were revised upwards accordingly based on Year 4 actual results;
A detailed overview of all the changes can be found in the ‘Summary of Changes’ tab on the logframe.

Describe any planned changes to the logframe as a result of this review

There are no planned changes to the logframe for the final year of the programme.

## D: VALUE FOR MONEY

Assess VfM compared to the proposition in the Business Case, based on the past year

The MADE programme was designed to achieve VfM by functioning as a market facilitator to help market systems work more efficiently rather than providing goods and services directly. MADE continues to perform strongly on value for money. During the past year, MADE commissioned an external benchmarking assessment against other market development programmes. DFID’s VfM framework remains based on the 4 E’s measures of economy, efficiency, effectiveness and equity. The VfM for the intervention is assessed below:

Economy refers to inputs. MADE continues to perform better than the economy indicator targets. MADE measures economy against two ratios typical to M4P programmes: a management spend ratio (i.e. the ratio of management overhead to total spend); and, a management intervention ratio (i.e. the ratio of management overhead to intervention commitments). MADE has continued to decrease the first ratio from 11% last year to 10% in 2019. However, due to slower than anticipated intervention fund spending the latter has marginally increased from 15% to 16%.

The implementation structure continues to contribute to reduced costs in two key areas – the procurement costs and the costs of investment. During Year 5, the programme introduced value for money indicators that tracked cost savings. The programme continues to minimise external procurement and has concentrated on local sourcing for goods and services, increasing competition, due diligence process and allowing inputs to be bought at a competitive price. A good example is the programme’s decision to use short-term contract drivers in lieu of hiring two new full-time drivers, reducing daily expenditure from £95 to £38.

Efficiency refers to how well programme inputs are converted into outputs. The majority of MADE’s efficiency indicators continued a positive downward trend, a result of the significant increase in outreach and lower relative growth in expenditures. Two indicators illustrate this: The first is total spend per beneficiary (access/use) of £124,[4] compared to £172 in Year 4 and an expected £192 in the original Business Case. This represents a 28% decline from last year but remains slightly above other M4P programmes at a similar stage of spend, such as Northern Delta MADE (£108); and the second is overhead per beneficiary, with the project currently costing £7.72 per beneficiary compared to £9.54 last year (a 19% reduction)[5] whilst the original Business Case envisaged £30 per beneficiary.
[4] Total spend per beneficiary is calculated using the total MADE expenditure figure to date, £10,744,602, which includes management costs and fees, reimbursables and intervention fund divided by total beneficiaries reached 84,361.
[5] Based on total management spend of £651,269.75 against total beneficiaries accessing/using new or improved inputs of 84,361.
The intervention fund cost per market actor change rose slightly by 4%, most likely reflecting the change in implementation approach, which provided more concentrated support to a reduced number of partners. Despite this increase, MADE continues to be amongst the highest performers on the cost per systemic change at £541, compared to similar programmes such as Samarth (£1,299), MOST (£1,147), and MADE Nigeria (£1,785). The management cost ratio (i.e. the total cumulative management fees to the number of market actors changing business practices) has slightly fallen over the last year from £7,503 to £7,401 and remains considerably lower than what was anticipated in the Business Case.
The budget variance, the difference between the remaining budget and time remaining on the programme, remained at 18% (see Section F). As a point of comparison, the average budget variance in the 2018 external benchmarking study was 13.9% but with a range between 0.68% and -31.67% and five out of the nine programmes assessed were outside a standard 10% variance.
Effectiveness refers to how well outputs are achieving the outcome. This will largely be realised over the next 10 years, however, MADE is performing strongly across all effectiveness indicators, and is ranked among the top M4P programmes on 3 out of 4 effectiveness indicators. MADE leveraged over £20 million in private sector resources in Y5, exceeding the combined investment from Years 1-4 with a total leverage for the programme lifetime of £36.2m. This increase in private sector investment suggests a strong commitment to the business models proposed by the programme.

This significant mobilisation has led to a further lowering of the cost per additional income generated from £0.44 to £0.35, and a reduction in the private sector leverage ratio from £0.57 to £0.29. For comparison, in the 2018 benchmarking exercise, the lowest cost per additional income generated was £0.39 (KMAT programme[6]) and the best private sector leverage ratio was £0.51 (PEPE programme).
[6] Benchmark programmes reported on cost per total NAIC and not total average income as reported MADE (as required by the log frame).

We are starting to see the additional services and resources driving down costs of inputs and business services for poor producers. This indicator estimates the smallholder farmer cost savings of using the bundle model (see earlier discussion), instead of seeking out individual inputs and services on their own. Overall, the average cost for smallholder farmers and entrepreneurs to access new or improved inputs and services has fallen by 17%. Total estimated cost savings for onion and other vegetable increased in by 217% and 59% respectively and decreased slightly for groundnuts by 3%.

There are continued positive results on income uplifts, now averaging £447 per beneficiary, representing a five-fold increase compared to the expected £80 in the Business Case (see earlier discussions). The depth of impact continues to be significantly higher than comparable M4P programmes, with KMAT the next highest at £206. The cost per average annual income change has continued to decrease from £191 to £157, a 18% decrease from Year 4. This income change is broadly comparable to other market development programmes but remains amongst the lowest performers with the MOST programme the best performer (£69).
Number of poor farmers and small-scale entrepreneurs experiencing higher production through MADE models Number of small-holder farmers accessing financial credit and business services through MADE
Equity refers to ensuring that benefits are distributed fairly. MADE’s activities contribute to DFID’s Leave No One Behind agenda, making substantial progress to ensure women benefit from its investments and smallholders have access to markets, inputs and finance. Based on Y5 data, the overall trend for both sexes have been upward, and that women have made impressive strides. Despite a small decline in the percentage of female beneficiaries (access/use) and average income of beneficiaries, from 44% to 41% for both, the total outreach of women increased (see earlier discussion). The current percentage of female beneficiaries is still considerably above the target established in the 2013 Business Case of 15%.
The programme is also working actively in a severely underdeveloped geography and context, supporting farmer’s agricultural productivity and to have greater market access. Smallholder farmers in hinterlands and ‘difficult terrains’ usually have difficulty in accessing quality inputs – improved seeds, plant protection and nutrition products. MADE has worked with input dealers to increase their sales outlets and site them closer to these ‘hard to reach’ communities. This has led to a reduction in transportation cost incurred by farmers and in purchasing supplies. It has also increased the adoption and use of quality inputs by smallholder farmers and the attendant increases in yield and income.
Explain whether it makes sense to continue with the programme from a VfM perspective

Overall, MADE is at a mature stage after five years and remains very good value for money for DFID, building upon its previous work and delivering in a difficult operating environment. The programme continues to perform strongly across all indicators and against benchmarks, offering excellent value for money for DFID’s support to economic transformation in Northern Ghana.

Out of 18 benchmarked VfM indicators, MADE had a positive directional trend in 13 (72%), a neutral change in 1 (6%) and a negative directional trend in 4 (22%). The equity indicators continue to perform strongly for women and for SHFs in poor regions. The last year of the programme offers the opportunity to continue to push scale and sustainability in the business models promoted by MADE. The programme needs a continued focus on economy, with respect to spending the budgeted intervention fund.

R10: It is recommended that MADE reviews and proposes an alternative indicator[7] in advance of the next VFM assessment to better capture the full benefits of the Bundle Model.
[7] ‘How the additional services and resources are driving down costs of inputs and business services for poor producers, across selected sectors’

E: RISK

Overall risk rating: Moderate

Overview of programme risk and mitigation

MADE maintains a comprehensive risk register tracking external context, delivery, operational, safeguards, fiduciary and reputational risks. The risk register is updated and highlighted to DFID quarterly.

The external context has improved in the reporting period. Ghana’s economy continued to expand in 2018 albeit at the slower pace (5.6%) compared with 2017 (almost 8.1%). The IMF’s Extended Credit Facility programme closed in March 2019 reporting significant improvements in macroeconomic performance, with inflation and debt-growth having been contained. ‘Severe’ risks flagged in the programme’s risk register have not materialised, but should be retained, given their ability to disrupt programme progress if realised. These include: the risk of change to the Government of Ghana’s (GoG) attitude towards private sector led growth, risk of change to its capacity and willingness to support market development; the risk of conflict between traditional / local power structures and the GoG; and the adverse effects of climate change, weather and disease, particularly given the predominance of rain-fed agriculture in the programme area.

Two risks were realised during the reporting period. Both relate to programme delivery and both are ranked as ‘minor’. While these have set back timely delivery of a small number of outputs to some degree, they have not constituted a significant block on overall programme progress. They are:

“MADE has fulfilled a market function rather than a catalytic role”: in one instance - that of assuming a market intelligence function in matching supply of ploughing and harvesting services to demand – the programme runs the risk of having adopted a market function which may not be filled by private sector actors at programme completion. This issue is addressed in the recommendations for the final programme period (see Section B, Output 1 above);

“Partners do not perform and/or deliver necessary results” and “programme not delivering outputs on time and in budget”: the MADE programme began the reporting period with 35 lead companies. Of these, five companies breached the Terms and Conditions of Support agreed in annual partnership agreements. The supplier responded actively by increasing its monitoring effort, issuing warnings of possible termination of support, adjusting payments in proportion to firms’ delivery of milestones and ultimately by terminating support where breaches continued. This last sanction had to be applied to three companies, leading to the programme closing the reporting year with 32 lead firms in place. The additional monitoring effort required to survey firms’ compliance with terms and conditions led to a delay in delivering one planned activity (Benchmarking exercise, see Output Section), as well as to a delay on budget spend (see Financial Section).

Finally, there are twin risks[8] contained in the register concerning the danger of supported businesses and market systems receiving support from sources other than MADE which were raised in last year’s Annual Review. These risks stem from the significant amount of development and public sector programming in agricultural markets in the programme area. The Ministry of Food and Agriculture’s Planting for Food and Jobs (PFJ) Campaign is an example of public sector engagement in Ghana’s agriculture markets. These are risks that the supplier is keenly aware of. While the private sector nature of MADE partnerships makes it challenging for the supplier to obtain full disclosure of all donor / public sector funds or inputs received by supported businesses, the supplier is actively managing these risks by working in close coordination with other others active in business support and agricultural markets in the programme area (see monitoring section below).
[8] These are expressed in the risk register as ‘market systems in Northern Ghana being based on dependency of the private sector on the public sector’ (ranked ‘major’) and ‘the impact of the donor and GoG landscape on the markets and businesses’ (ranked ‘severe’).

Outstanding actions from risk assessment:

Safeguarding: last year’s annual review covered safeguarding from the perspective of ensuring a balance is struck between transparency and commercial sensitivity of data generated from partners. One element meriting further investigation is whether the FEA / BDA relationship with farmer groups may increase farmer vulnerability to exploitation, particularly female farmers. FEAS and BDA’s dispense inputs and services critical for farmer livelihoods and therefore enjoy a position of relative power in their relationships with supported farmers. As part of Nathan Associate’s procedures, the MADE team undertakes an annual online training for Code of Conduct and Harassment, as well as signs a “Safeguarding Self-Declaration Form”.

Recommendation: the supplier will commission a study of the FEA / BDA model in the first quarter of the next year and should ensure that this study considers whether safeguarding risks exist in the FEA / BDA – farmer relationship. If found to constitute a safeguarding risk, the supplier should present recommendations to DFID on possible mitigating actions, such as establishment of independent grievance or whistle-blowing mechanisms.

Rationalisation and shortening of risk register: The previous Annual Review identified many additional risks which were duly added to the Risk Register following that review. The current programme register is now a lengthy document containing some duplicated risks, such as the twin risks identified in the paragraph above.

R11: It is the recommendation of this review that the Risk Register is rationalised and shortened, and areas of duplication and overlap are removed.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Performance of partners and DFID, notably on commercial, and financial issues

MADE is an output-based contract, with Key Performance Indicators (KPI’s) and milestones driving payments to the suppliers. Key cost drivers for the programme have been programme management costs through the consultancy fees, direct consultant overheads, indirect overhead costs, and the profit margin. This remains consistent with the Business Case.

To date the programme has spent a total of £10,744,602, but it is off track in meeting its spending targets by the end of the programme. There remains significant underspend on the intervention fund (used for co-investment in partners, design of models, technical assistance, and so on). Under current forecasts, this will represent 23% of the extension intervention budget. There is also a marginal overspend on the reimbursable budget due to increased relocation cost for staff to Tamale to implement the programme.

Delivery against contract

MADE has continued to either meet or exceed its output targets over the lifetime of the contract. The programme has scored either an A (2014, 2016, 2017) or an A+ (2015, 2018) in Annual Reviews. MADE has built upon the strong trust, willingness and relationships with its partner businesses and is continuing to see the interventions mature. The programme has continued to meet or exceed its outcome level targets.

Over the reporting period, the programme has performed satisfactorily in achieving its KPI’s, passing three out of the four quarterly assessments. For the missed quarter, DFID withheld the KPI payment. The programme consistently performed well against the quality and delivery, client relationship and corporate social responsibilities pillars. The financial management pillar has continued to perform below expectations as the programme has struggled to meet their budgets and forecasts, leading to moderately high variances and a further underspend for the intervention fund.

Overall the quality of the outputs has been of a high standard. The programme has struggled at times to meet its deliverables during the reporting period, completing all their deliverables in only one quarter. These deliverables are then carried over into the following quarter. When deliverables were missed, DFID withheld payment of fees until these deliverables were acceptably met. MADE has developed and maintained a very robust system to control or manage spend in accordance with the contract. This has consistently been noted in spot checks and verifications.

Performance of partnership

MADE has continued to cement and build strong trust and relationships with its partners. Partners and SHFs have expressed their appreciation for the MADE approach and how it has helped improve enterprise and farm performance. The programme has made some improvements developing relationships and partnerships with other key stakeholders, but there remain some shortcomings in the extent to which MADE is plugged into the latest innovations and policy shifts (see earlier discussion on Output 3).

The last two Annual Reviews highlighted the need to develop a strategy of engagement and partnership with the public sector and other stakeholders, which although is now on a positive trajectory, remains weak at national and international levels. The programme has taken several positive steps over the last year. The first is the development of a clear strategic narrative of what and who the programme will engage with. Good examples of this are the partnerships with the Ghana Commodity Exchange (see earlier discussion) and the Extension Directorate of the Ministry of Food and Agriculture to bring the farm advisory services and the public extension services into greater alignment. The second is the inclusion of development partners and key government representatives to ‘Pause and Reflect’ meetings held each quarter to improve awareness of what MADE has achieved and to share lessons learned (see Monitoring section below). As the programme moves into its final year, it will concentrate on strengthening these existing relationships and continue to share lessons and experience of market development in Northern Ghana with key stakeholders to further embed and strengthen sustainability of MADE results.
The MADE team has a robust system in place for procuring goods and services, set out in the programme’s procurement manual. The majority of MADE’s procurement goes through a rigorous competitive process and MADE is on track to complete all planned activities. Overall, the service provider is responsive to DFID requests, proactive in its dialogue of risk, and updates its delivery chain maps when necessary.

Quality of financial management

The MADE programme continues to deliver and spend within approved limits and agreed procedures. MADE’s compliance with these management, financial and procurement systems have been recognised in the quarterly assessment against KPIs. Given the consistency in MADE’s compliance with programme standards as well as the execution of Year 4’s audit, DFID did not carry out additional spot checks or expenditure verification within this year but has closely monitored spend and process for such expenditure through financial reports and invoices.

MADE has consistently improved on its quarterly financial reporting, providing enough detail and proper representation of expenditure, resulting in fewer requests for clarifications from DFID. Forecasting accuracy for the reporting period is 77% which is an improvement from last year of 52.5%, but significant variances within individual activities were realised. Further work is needed in the final year of implementation to bring forecasting and budgeting back to within an acceptable range of 5-10%.

Asset monitoring and control

The programme maintains an asset register which is updated by MADE on a quarterly basis and reviewed by DFID Programme Officer. During the reporting period, an independent audit for the Year 4 of the programme was completed, which verified that programme assets are being effectively managed and maintained. This audit was completed in October 2018. The Year 5 independent audit is currently being implemented and a final financial audit will be conducted at the end of the programme.

Date of last narrative financial report(s)	30th April 2019
Date of last audited annual statement (s)	28th February 2019

G: MONITORING, EVIDENCE & LEARNING

Monitoring

Regular monitoring of the programme takes place through quarterly and annual progress reports produced by MADE, regular meetings between DFID and MADE as well as monitoring visits by DFID. In Y5, the programme instituted a new strategic meeting, named ‘Pause and Reflect’ (P&R), which is held once per quarter. This meeting allows for programme staff, both from HQ and the field, to share progress on planned activities, have an open discussion on next steps and make decisions on any changes needed to planned work. The results of these discussions are captured in the quarterly reports submitted to DFID. The DFID SRO participated in one P&R meeting held in February 2019, which provided a clear steer for the Y6 planning process. In Y6, the P&R meetings now include learning with external stakeholders, such as USAID’s ADVANCE programme and GIZ to share experience and identify areas of collaboration.

The P&R meetings have been invaluable at reviewing programme progress and informing decisions. A good example of this was the flat-line budgeting approach for each quarter, which was identified as an issue as it did not account for the timeline of delivering activities. Based on this, activity-based budgeting was introduced to closely budget and track expenditures based on the scope of work. This has now been adopted and improved the accuracy of forecasting significantly, as well as informed budgeting for Year 6.

The P&R meetings have also strengthened the adaptability and flexibility of the programme structure. For instance, when presenting on progress regarding irrigation activities, key issues were raised by the team around the capacity of businesses to access service providers and understand their tailored needs. Through the meeting, the team was able to quickly agree the way forward in regards to this activity, which included contracting a consulting firm to conduct an assessment of the partners with the appetite and capacity to have irrigation systems in place, as well as agreeing to co-invest in the equipment and demonstration plot costs to reduce the risk for participating firm.

Over the reporting period, MADE continued to improve its monitoring arrangements. A new organisational structure was introduced which has increased MADE’s contact and engagement with its partners, as well as mainstreaming learning across programme activities. MADE introduced a clear set of parameters for data collection and reporting, as well as a centralised data bank. Data collection was standardised, and the market development team trained to capture the required information. Data collection was also digitised, reducing the number of errors and shortening the time to complete the validation exercise.

Last Year’s Annual Review recommended reviewing the objectives, purpose and structure of the Advisory Committee to ensure alignment and relevance with the Year 5 Business Plan. Following this review, DFID and MADE agreed to discontinue the Advisory Committee. The P&R meetings have helped strengthen the strategic direction and oversight of the programme.

Annual Review Process

This Annual Review was carried out jointly by DFID Ghana’s Senior Responsible Owner (SRO) for MADE, and a Livelihoods and Private Sector Development Adviser from DFID’s Growth and Resilience Department in London. The team was supported by a wide range of stakeholders from MADE in Tamale, Nathan Associates in London, other DFID advisers, and the MADE Programme Officer from DFID Ghana. The Annual Review process consisted of review and analysis of existing literature, MADE’s value for money framework and benchmarking studies, annual and quarterly reports, performance data, business model concept notes, etc. A field visit was undertaken to the Northern, Bono East, Savannah and Upper West Regions, which included key informant interviews and focused group discussions with 8 MADE Lead and Support partners, their smallholder farmers and FEAs/BDAs. Further key informant interviews were held MoFA’s Agricultural College in Damongo and the GCX in Accra.

Evidence

As an M4P programme, MADE continues to adapt its programme plan, closing interventions that don’t gain traction, and adapting interventions to market needs. The key challenge for the programme to scale up and maintain results is its ability to develop lasting public and private sector partnerships (see detail in the risk section). This needs to be factored into activities and closely monitored.

As part of the programme’s commitment to sustainability in the extension phase, the programme designed a gender assessment in Year 5, to analyse programme performance and potential impact on households, communities and the business-enabling environment in terms of gender, and to provide information and tools to MADE staff and partners to carry out meaningful gender work for the life of the project and beyond. The main finding was that traditional patriarchal norms are transforming, thanks to efforts by the Government of Ghana and a host of development sector actors, including MADE. There are an increasing number of opportunities for women to participate in economic activities, as well as more acceptance of these changes. However, in most cases, women are still expected to prioritise household responsibilities. In Y6, the programme aims to scale up its offer on women’s empowerment by creating targeted activities, disseminating findings to other stakeholders, and ensuring that all work carried out takes women’s barriers to access into account.

Looking forward, as part of MADE’s evidence dissemination and communications strategy in Year 6, the Monitoring and Learning Specialist with the Communications and Information Advisor will identify and develop a number of learning and evidence products. These include the dissemination of codes of practice and the further development and integration of farm advisory services, the promotion of climate smart agriculture practices, and women’s economic empowerment.
Learning

Key Lessons Learnt:

Business partnerships are positive. In the first four years of operations, MADE focused on a small number of high-performing partners that were more resourceful and more willing to adopt the business models promoted by MADE. In Y5, MADE widened its partner selection process in order to accept bids from business syndicates comprising lead and support enterprises working together under formalised agreements. By supporting enterprises to work in clusters rather than as individual firms, MADE is not only seeking to ensure SHFs gain access to improved input supplies and services, but also to encourage partner firms to be more selective in their production and outreach strategies, to widen market opportunities and to make it possible for farming communities to move out of subsistence farming into the production of marketable surpluses.

Effective farm enterprise management needs an on-farm presence. Since its adoption into the advanced model in Year 3, the provision of farm enterprise advisory services has fast become recognised as a crucial component. An on-farm presence during key times in the agricultural calendar, to ensure input supplies and services are properly applied, has been shown to be essential to bring about the necessary yield and productivity improvements required to cover the costs of delivering the advance model.

Looking forward, as part of MADE’s evidence dissemination and communications strategy in Year 6, the programme will develop a number of learning and evidence products that will be presented during a final close out workshop in February 2020, such as:

Improving women’s empowerment

MADE will externally promote the findings of the gender assessment, which was designed in Y5 and undertaken in Y6, with relevant stakeholders.

To break through some of the glass ceilings that continue to exist for women – particularly with regards to work opportunities for female agricultural extension course students – MADE will also work with TEDMAG[9] to support a female apprenticeship programme designed to help students gain work experience in a farm enterprise environment. MADE partner firms that have shown an interest in working with female FEAs will be targeted and offered gender-sensitisation training and lessons in safeguarding before receiving these students. Throughout this assignment, the programme will capture key findings and results that will be widely shared.
[9] Technical Education Development for Modernized Agriculture in Ghana – funded by Global Affairs Canada.
The building of a sustainable private extension – farm advisory – service

MADE will undertake an assessment study aimed at substantiating evidence of improvements in yields and productivity experienced by SHFs, attributed to the presence of FEAs. The study will review the evidence and look at how the FEA component of the Advanced Model is being applied. This will include examining the various remuneration models being applied in the appointment of FEAs and the ways in which partner firms are applying the operational support provided by the programme. The output will look more closely at how agribusinesses could maximise the efficiency and effectiveness of the FEA service and will inform future DFID programming in this area.

Climate and environmentally smart agricultural practices

MADE will follow-up on its work to promote the use of climate smart agriculture practices by undertaking an assessment study of practices being adopted in the region. This will include the extent to which the use of drought resistant seeds, the introduction of minimum tillage, the use of inter-cropping and the adoption of water harvesting and drip irrigation systems. The assessment will also look at how MADE’s partners are enforcing the safe use of agrochemicals and protecting the health of agricultural workers. The output of the study will be identifying the opportunities and constraints faced by businesses introducing CSA and environmental protection measures. It will inform future DFID programming in this area.

Progress on recommendations from previous reviews

MADE have implemented most of the recommendations from the previous annual review (discussed during earlier sections). The previous Annual Review made several recommendations around improving data generated by partner businesses; around disseminating MADE market intelligence into the wider business investment ecosystem in order to demonstrate investment opportunity in Northern Ghana and attract investment to enable higher potential businesses to reach scale; and around establishing an innovation interface, scanning for relevant innovations and feeding intelligence into the innovation ecosystem by January 2019. This recommendation is being responded to by the supplier through the commissioning of M-Access: An Agribusiness and farmer data management tool which will aim to improve data management and record keeping of transactions between MADE partner businesses and smallholder farmers.
RECOMMENDATION	STATUS
Overall: Given the context that the programme operates in, it is vital that MADE is seen as a step on a much longer journey and should position itself during the remaining time available to ensure it supports the building blocks for long-term impact.	Met. Y5 concentrated on encouraging the development of commercial partnerships and value chain networks while building the capacity of partner firms to seize the opportunities presented as supply and demand criteria are brought into line. The programme is addressing the digital technology gaps that are being exposed as operational scale is increased and highlighting best practice opportunities through a benchmarking exercise to improve operational management practices. MADE is addressing longer-term sustainability issues by conducting assessment studies and building business cases for key private sector led developments such as Farm enterprise advisors, climate smart technology and gender inclusivity.
R1: Explore investment and finance possibilities for businesses, and to form new relationships within the investment and financing ecosystem, especially innovative new investment and financing models by November 2018	Met. Partner firms are taken through an annual planning process, which ensures businesses meet minimum requirements to access commercial loans and this is being supported through the introduction of digital data collection and management. Network facilitation is introducing opportunities for value chain financing and by working with support enterprises, lead firms are able to share credit risk.
R2: MADE should scope options for establishing an innovation interface, scanning for relevant innovations, and feeding intelligence into the innovation ecosystem by January 2019	Met. By January 2019 MADE had designed and submitted a Concept Note to DFID around the creation of M-Access, an innovative data collection tool that is market viable and business-driven.
R3: MADE to review the data generated by partner businesses, including its quality, use by the partners, and the range of their management information systems that are employed.	Met. Partner data verification and validation is a core function of the MADE programme based around milestone payment reporting criteria linked to approved workplans and budgets
R4: MADE to start developing and/or strengthening new relationships to establish the building blocks of a much wider, scalable and transformational theory of change by October 2018.	Not applicable. The partner selection criteria upgraded year-on-year and with an emphasis on increasing private sector investment in the delivery of input supplies and services to SHFs, has encouraged firms to build commercial partnerships and seek closer alignment with wholesale buyers in the south. The drive towards transformational change has its own market-led momentum that MADE will continue to facilitate albeit without direct involvement.
R5: The hard commercial, financial, markets, value chains intelligence that MADE is now deriving from its activities should be disseminated into the wider business, investment ecosystem	Met. MADE continues to facilitate links with apex enterprises to encourage this intelligence sharing.
R6: MADE needs to develop a robust financial, commercial understanding of the market viability of these functions and businesses providing them by December 2018.	Not applicable. MADE ensures that these robust financial and commercial understanding are appreciated by our partner firms, there is no direct activity to build these relationships
R7: MADE should begin to develop growth pathways for the high potential businesses that could ultimately take the supported functions to a much greater scale and outreach by January 2019.	Planned. This recommendation is the basis for the benchmarking exercise, which commenced but was not met in January 2019. The development of individual partner firm growth development road maps will be completed by October 2019.
R8: MADE should ensure that they are aware of relevant innovations in the marketplace elsewhere in Ghana and the wider world, that these are not moving ahead of or rendering obsolete the programmes strategy, and that MADE activities are enhancing and not harming the expansion of viable innovations by October 2018.	Met. Responsibility for ensuring the relevance of programme interventions rests with the Nathan Technical team. Planning sessions held each year prior to partner selection ensures that best practice is built into the work planning and budgeting exercises. Quarterly pause and reflect meetings allow for adaptations to be introduced as new opportunities arise or constraints are encountered.
R9: Business advisory services could be brought along on this journey, building their capacity in parallel.	Met. MADE has carefully avoided taking on a market function role. Growth and capacity building initiatives which are outlined as part of the partner selection process are private sector led with MADE’s role one of facilitation and support.
R10: MADE should take an active role in preparing and disseminating market intelligence and bringing potential investment and financing stakeholders or innovators along on the MADE pathway, even if this is only part of a longer-term journey for them by January 2019.	Not met but planned. MADE has continued to facilitate networking between market players and where constraints are identified, has taken an active role in helping to build capacity amongst its partner firms to address limitations. Dissemination of success stories and key programme initiatives through engagement with development partners and government agencies has not kept pace with the progress being made by the programme and this will be addressed in Y6
R11: MADE identifies formal rules that are limiting innovation expansion, and scope opportunities for engagement by November 2018.	Not met. No formal market rules were identified that that are likely to limit innovation and market development. In Y6 Workplan Narrative, the programme outlines which formal rules it will target and engage with.
R12: MADE to start to benchmark its VfM results against other market development programmes by October 2018.	Met. An external benchmarking exercise against other market development programme was undertaken and results shared with DFID by October 2018.
R13: MADE to develop a strategy of engagement and partnership with key stakeholders in Northern Ghana and the agricultural sector by September 2018.	Not met but planned. MADE conducted a Political Economy Analysis in June/July 2018, however this did not yield in higher engagement with external stakeholders. In Y6 Workplan Narrative, the programme outlines how it will target engagement with external stakeholders.
R14: MADE and DFID to review the objectives, purpose and structure of the Advisory Committee to ensure alignment and relevance with the Year 5 Business Plan by September 2018.	Met. It was agreed to disband the Advisory Committee and introduce a more formalised quarterly planning session (Pause and Reflect) bringing together key stakeholders and provide strategic steering to the programme.