Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Support to the National Fund for Climate and Environment (FONERWA) - Rwanda
Programme Value: £22.5m		Review Date: 31 March 2015
Programme Code: 203582	Start Date: April 2013	End Date: March 2017

Summary of Programme Performance

Year	2013/2014	2014/2015
Programme Score	B	A
Risk Rating	Medium	Medium

Summary of progress and lessons learnt since last review

FONERWA is Rwanda’s national Fund for Environment and Climate Change (FONERWA is the French acronym). Set up in 2012, the Fund has the objective to mobilise domestic and international climate finance, and secure sustainable financing to support projects which contribute to environmental sustainability, resilience to climate change, and green growth. The Fund carries out public Calls For Proposals (CFPs) whereby applicants submit their project concepts on environment, climate adaptation and low carbon development activities, developed according to pre-established criteria and with a strong emphasis on value for money.
This Annual Review (AR) of the ‘Support to the National Fund for Climate and Environment - FONERWA’, (henceforth ‘the Fund’) has used the logframe indicators to assess the programme performance over the period, and to consider whether the project is on track to meet the June 2015 targets. The AR also analyses the effectiveness of the indicators in capturing DFID’s objectives (the stated outcomes and impact). A separate Annual Review has been undertaken for the DFID programme ‘Creation of the National Fund for Climate and Environment’, which funds the FONERWA Fund Management Team (FMT).

The previous AR of the Support to the Fund was conducted shortly after the first grant agreements were signed (January 2014), which was 8 months later than originally planned, and thus the first AR scored the programme as a B (moderately below expectations). It recommended 19 actions, grouped below. On the basis of this review, these recommendations have all been addressed, or are in the process of being addressed:

- Strengthening M&E and reviewing the logframe. A review of the logframe indicators was conducted in October 2014 to incorporate the recommendations of the previous annual review. The revised logframes were approved by the FONERWA Managing Committee (FMC) in January 2015, and informed the Monitoring and Evaluation (M&E) plan, which has recently been finalised. Unit costs have started being collected at project level, which will enable FMT to assess the value for money of individual projects.
- Risk management. The risk matrix is now updated by FMT on a monthly basis. Environment risks are screened as part of the Environmental Impact Assessment (EIA), which is a requirement for projects that require a EIA under Rwandan law. The FMT has introduced processes to minimise the risk of conflict of interests for the FMT members reviewing project proposals, as recommended in the previous AR. Measures have been taken to mitigate the risk of holding insufficient funds to cover liabilities. Additional capital injections have been secured (see highlights below).
- Fund Management Team (FMT). The previous AR recommended a contract extension to DFID’s support to the FMT. In September 2014, DFID extended the FMT programme to allow more time for hand-over to full Government management. Recruitment and capacity building of additional staff is ongoing, with new members of staff appointed this year and more to be recruited in the next few months.
- Strategy and Value for Money (VfM). Last year, independent consultants carried out a backward- and forward-looking VfM review of the Fund, reporting favourably on its VfM performance. A review of VfM indicators, proposed by DFID, is currently with the FMT for review and will be subject to broader consultation with project developers by May 2015.
- Application process. The previous AR recommended the Fund do more to encourage ministries and districts to submit proposals. Training on PPD and PD development has been carried out targeting district applicants, supported by a CDKN-funded capacity building project. More broadly, applicants can now access ‘clinics’ to help them through the PD development process. New templates for project data collection have been introduced.

Over the reporting period (March 2014-15), there has been significant progress with the Fund.

- The Fund was officially launched by the Rwandan Prime Minister in October 2014. There has been high political buy-in for the Fund in the Government of Rwanda (GoR): it was mentioned explicitly by the President in his opening address at the World Economic Forum Meeting in Davos in January 2015.
- During the period (to end of March 2015), there were four calls for proposals (CFPs). This is a significant increase on the two proposal calls during the previous AR period. FONERWA’s current portfolio (after the first 5 CFP) includes 21 projects with commitments of RWF 21bn or £20.4m.
- The quality of PPDs has improved significantly compared to the previous AR, and improved further over the year: the number of project profile documents (PPD) meeting the required standard to move to project document (PD) stage doubled in the last two CFPs. Also, to increase private sector participation, a private sector engagement strategy is being developed and will be finalised by May 2015.
- The Fund has been successful in its objective of mobilising climate finance for Rwanda, not only by securing additional capital injections to the Fund from other development partners, including USD 9m from the German Development Bank (KfW), but also by helping leverage international climate finance for other parts of Government, helping to secure a Least Developed Countries Fund (LDCF) project managed by the African Development Bank (AfDB) (USD 9m). The Fund is also at an advanced stage of discussion – and in the process of submitting proposals – to the Green Climate Fund (GCF).
There has been international recognition of the Fund and the way it is managed: its performance compares extremely favourably to other international climate Funds, such as the Bangladesh Climate Change Resilience Fund (BCCRF), due to FONERWA’s ability to swiftly mobilise financing, introduce strong processes and good governance, and conduct frequent calls for proposals[1].
[1] For example, the BCCRF was created in 2010 with pledged contributions of USD 188m. In 2012, 52% of pledged contributions remained unpaid, and a result framework was still to be designed. In 2012 and 2013, only four projects or two each year started disbursements for a total of USD 5.7m. BCCRF Annual reports, available at http://bccrf-bd.org/AnnualReports.html

FONERWA has shown good progress against most logframe targets and output indicators, even though it has not always met the intended milestones. The latter is due to the initial delay in becoming fully operational, and the early challenges in project implementation, which resulted in delayed results and lack of project data to assess performance. Nevertheless, the Fund has improved its score and is on track to improve further. It has undertaken actions aimed at improving its operational efficiency and impact, including streamlining and reviewing the approval process (e.g. the frequency of CFPs will move from quarterly to half-yearly from March 2015), strengthening the monitoring of project status implementation (now bi-weekly), and improving data collection and lesson-sharing mechanisms.

The Fund continues to evolve, and two consultancy assignments are currently underway to help inform the future direction. The first is looking at the role of the Fund and assessing whether it should become more strategic, extending to cover a broader range of activities and instruments (in addition to the current demand-led CFPs). The second is looking at the institutional positioning of the Fund as the FMT fully transfers across to Government. A further piece on future resource mobilisation strategy is also planned. The initial findings of these various studies indicate a broader and more strategic role for the Fund is likely, which will also enhance the value added of the Fund and increase the potential for leveraging, transformation and impact. However, it is also likely to influence the way FONERWA operates, DFID’s logframe and relevant performance indicators, and could create some additional risks.

The risk score continues to be MEDIUM, as in the previous AR. This reflects the risks associated with the hand-over process of FMT activities to the GoR. Some uncertainties on this transition process remain, notably around the transfer of key staff, on which there is a current high reliance. The outcome of the institutional positioning, i.e. on the location of the Fund in GoR, could also affect the ability to access DFID, domestic or international finance. Finally, at the portfolio level, a risk is that the current low levels of disbursement continue, delaying DFID’s projected spend to the programme.

Summary of recommendations for the next year

This AR proposes the following set of recommendations:

Logframe and M&E. Current targets continue to be set at over-optimistic levels and thus are difficult to achieve, especially given the demand-led nature of the Fund which makes it challenging to know in advance what projects will be funded and therefore the type and level of results that will be delivered. We therefore recommend that further attention be given to these indicators during the next logframe review, to ensure that they are realistic. These issues could also be addressed by adopting a flexible approach to setting the logframe (revisions), without compromising its function as a monitoring and accountability mechanism, i.e. reviewing logframes on an annual basis to incorporate lessons and adjust consistently with the strategic direction of the Fund. However, it is recommended to urgently review the FONERWA Metadata Handbook to clarify indicators and methodologies that are currently unclear (see below).

Recommendation 1: Adopt a more flexible approach. Review the logframe on an annual basis and adjust indicators to ensure targets are realistic given the demand-led nature of the Fund, and align with strategic direction, while monitoring performance against DFID objective of economic development and poverty reduction. These include:

1.1 Introduce a clear methodology for measuring indicator 2.4; Review wording of 3.2; Monitor performance of indicators 3.4 and 3.5 to assess whether milestones are excessively optimistic.
1.2 Introduce an explicit target of (minimum) 20% funding to private sector.
1.3 Introduce an output indicator on poverty reduction – e.g. by asking projects to report on how beneficiaries fall under Rwandan first and second poverty categories[2] (i.e. ubudehe categories).
[2] The first category has the very poor who do not have a house or cannot to pay rent; have a poor diet; cannot get basic household tools and clothes. The second category includes those who have their own houses; can afford to rent a house; mostly get food and earn a wage from working with others. The third category includes those who have at least one person in the family working in the government or the private sector. The fourth category includes people who earn high incomes; people who own houses; people who can afford a luxurious lifestyle.
1.4 During the M&E template review (currently on-going), consider special requirements around the VfM section for more innovative projects, especially if this issue emerges as part of the options review (see recommendation 2 below). Ensure calculation methods are clearly explained in guidelines.

Strategy and Mainstreaming. There is currently a review of the future role of the Fund, and a number of options will be presented to the Board early in the next reporting period. However, early findings indicate a strong interest for the Fund to become more strategic, whilst also maintaining some element of the current demand-driven (bottom-up) funding. This strategic role would help to advance ‘mainstreaming’ across Government, i.e. to help pilot promising areas for scale-up (including more innovative projects), to support the integration of climate into sector development and investment planning, and to help fund or leverage projects at scale and deliver greater (transformational) impact. This may initially involve more targeted calls for proposals and/or earmarking of funds, but then transition to more strategic activities, including the development of the enabling environment (technical support and co-ordination) across Government. This evolution will require some strategic development, as well as enhanced capacity among FMT staff. It will also require changes to the current demand-led nature of fund and will influence the suitability of the current indicators.

Recommendation 2: To ensure sufficient opportunity for FMC members to debate the future role of FONERWA, and support decision-making through the development of a strategy paper presenting a set of clear options going forward. Following the agreement on the preferred strategy for the Fund, it is recommended to develop a roadmap for transitioning to the new strategic role which include:

2.1 Undertaking a future resource mobilisation strategy (currently planned) with a view to ensuring the Fund is sufficiently capitalised (consistent with the strategic direction agreed for the Fund). Attention should be given to both short-term and long-term, domestic and international capitalisation sources.
2.2 Considering legal status and institutional home of the Fund including implications on its effectiveness, and resource mobilisation strategy.
2.3 Clarifying roles and responsibility for the Fund vs. other GoR institutions, aligned to the resource mobilisation plan. It would also be useful to consider development of a FONERWA strategic (prioritised) action plan to help define and deliver this new role.
2.4 Undertake a capacity needs assessments to match the new role, to identify FMT staff and capacity gaps and training needs/staff recruitment/internal organisational structure.
2.5 Pilot the new strategic role, e.g. with one or two targeted calls for a specific area, and/or one or two targeted larger mainstreaming projects or initiatives with Ministries.
2.6 Review and revise the indicators in the logframe to match the new strategic direction, including changes that would encourage more innovative projects (e.g. criteria for screening PPDs and PDs to ensure innovative proposals are not excluded).
2.7 As the Fund becomes more strategic, follow-up the recommendation from the previous AR to include greater discussion of future climate change.

Portfolio management and fund disbursement. While disbursement rates have increased significantly over the past year, disbursements to projects are still slower than expected and the FMT’s quarterly forecasts of anticipated expenditure have been very optimistic compared to actual outturns. It is recommended that disbursement rates continue to be monitored closely on a monthly basis, and additional support is provided to reduce bottlenecks.

Recommendation 3: Focus on increasing fund disbursement, tackling bottlenecks and improving financial analysis and reporting, including:

3.1 Increase FMT staff numbers and resources in order to speed-up fund disbursements. Consider creating a dedicated team for providing the support/training to project applicants on PD development towards project approval and supervision of project implementation.
3.2 Consider different approval processes for small and large projects, with small projects (total cost of project < USD 1m) following a fast-track approval process, freeing up more resources for the bigger/larger capital projects.
3.3 Adopt a more conservative forecasting approach, which accounts for some risk of not disbursing (i.e. reduce forecasts by 20%). FMT to report on the difference between forecasts and actual disbursements on a monthly basis.
3.4 Improve the financial analysis and monitoring provided in the quarterly reports. This should present a better overview of the financial performance of the Fund, and include e.g. a breakdown of funds committed during the reporting quarters, funds disbursed and to be disbursed to projects over the next two quarters and comparison with previous forecasts, and also revenues from credit lines (actual and projected).
3.5 Improve monitoring of implementing partners. Consider requesting project implementers to report regularly (quarterly) on their procurement processes to ensure they comply with the rules set in the Fund’s Operational Manual. It is recommended that during the on-going M&E template review, the FMT in consultation with DFID finalise the VfM requirements, and update VfM guidance and methodology for applicants accordingly. Continue monitoring timely reporting of project implementers (on a quarterly basis).
3.6 Strengthen the M&E system by increasing staff capacity on M&E. Review and simplify the template for applicants to report against logframe, and consider organising workshops regularly (quarterly) and the need for guidelines in Kinyarwanda language.

FONERWA Managing Committee (FMC) / FONERWA Technical Committee (FTC). The FMC is the last body in the approval chain. It should have a more of an over-sight role, but often it introduces additional comments that further delay approval before a grant/loan agreement can be signed. Some of these arise from earlier pending comments or delays in EIAs, etc.

Recommendation 4: Ensuring the FMC functions strategically, including:

4.1 Consider a clearer division of labour (i.e. roles) between FMT, FMC and FTC to ensure that the review process is not repeated at each stage of the approval process, but focus on specific aspects at each stage. Ensure that ‘substantial’ comments on PDs are submitted to applicants and addressed before proposals are submitted to FMC for final approval, so that FMC resources are freed-up and can play a more strategic role.

There is also a recommendation on the FMC composition, see next point.

Addressing barriers, financial instruments and encouraging the private sector. The private sector has a key role in economic development and innovation. By supporting good private sector projects, the Fund will help the create jobs, increase trade, provide goods and services efficiently, and generate tax revenue for the GoR. While the number of private sector applications and approvals is increasing, there are further opportunities for the Fund in this area. This includes the potential to increase the enabling environment and reduce the barriers for investment, as well as to consider a wider range of instruments to increase access to finance. At the time of this review, FONERWA has started considering introducing more sophisticated instruments (e.g. guarantees), but there are other options.

Recommendation 5: Encouraging the private sector, including:

5.1 Ensure that at least one member of each governance level (FMT, FTC, FMC) has the right skills to understand and represent the interests of private sector investors. Consider having people with strong financial sector background (e.g. who have worked in private equity funds) on both Committees.
5.2 Approach financial institutions other than BRD (the Development Bank of Rwanda - Banque Rwandaise de Développement) for broadening the array of financial instruments on a competitive basis.
5.3 Refine and consider increasing the range of instruments particularly to address the shortage of financial instruments available to the private sector in the financial market.
5.4 Investigate a broader analysis of options for removing barriers, including introducing regulatory reforms (e.g. tax regime), supporting complementary approaches such as the Second Economic Development and Poverty Reduction Strategy (EDPRS2) proposal for a Climate Innovation Centre to support ‘green’ SMEs develop innovative business ideas, and even strengthening Public-Private Partnership (PPP) capacity within Government.

Knowledge management. The Fund is building up a very rich evidence base on fund management and operations, as well as expertise on climate change responses in Rwanda. This provides an unique opportunity for learning (in Rwanda and internationally), as well as positioning the fund as a central resource. However, steps are needed to ensure this learning and information sharing is maximised. Learning and sharing should be done at different levels – programme, regional, international level and within the Fund and DFID.

Recommendation 6: Improving learning and sharing at different levels, including:

6.1 FMT could submit a periodic (6 monthly) summary of lessons learned at project and portfolio level (summary of lessons learning templates submitted by projects, and from FMT overall) and consider publishing online.
6.2 FMT could also consider providing examples (e.g. six monthly) of projects where communities and gender issues have been addressed.
6.3 A series of information and dissemination notes could be developed. These would include higher level policy briefs as well as more technical orientated areas (e.g. building on the technical data sheets on specific projects such as terracing or rain water harvesting, or information on climate projections for Rwanda).
6.4 Develop this material into an on-line resource, centred around the Fund web-site.
6.5 To consider learning events, e.g. country workshops to bring development partners in Rwanda together, or regional / African workshops to share learning with other countries looking to develop funds.
6.6 To feed the knowledge and lessons from the points above back to the International Climate Fund (ICF) – which funds this programme - to provide lessons on what works (and does not) and experience of learning by doing.

Additional recommendations to improve the FMT’s performance are presented separately in the Annual Review of the ‘Creation of the National Fund for Climate and Environment’.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-203582/documents/
DevTracker Link to Log frame:

Outline of the programme
Rwanda is highly vulnerable to current climate variability, due its strong reliance on agriculture. Rain-fed agriculture is important for rural livelihoods, and the sector is key source of exports as well as future economic development. The country is also affected by major weather extremes, with high levels of soil erosion from heavy rainfall, and major impacts on livelihoods and the economy from the periodic major flood and drought events that occur. It therefore has a high existing adaptation deficit. Climate change is expected to increase these impacts and lead to new challenges, notably from higher temperatures, changes in rainfall and potential changes in the intensity and frequency of extreme events[3]. In 2009, it was estimated that the cost of adaptation to build capacity and to specifically address future climate change (enhancing resilience) by 2030 would be in the range of USD 50-300 million per year (lower bound estimate)[4]. Rwanda also imports all of its oil-based products, so oil price volatility has the potential to negatively impact Gross Domestic Product (GDP) and economic growth[5]. However, the country has large, untapped clean energy resources, in the form of geothermal, hydro and solar, which have the potential to meet Rwanda’s electricity needs and replace diesel-fuelled power plants.
[3] Republic of Rwanda: Green Growth and Climate Resilience, National Strategy for Climate Change and Low Carbon Development, October 2011
[4] Stockholm Environment Institute (2009), Economics of Climate Change in Rwanda.
[5] Econometric modelling conducted as part of the Baseline Report to inform the National Strategy, (unpublished) suggests that a 10% increase in the price of oil will lead to a reduction in GDP by 1.5%
In 2011, the Government of Rwanda (GoR), with UK support, developed the National Green Growth and Climate Resilience Strategy. As part of its support to the GoR to implement this Strategy, the UK is contributing up to £22.5m to FONERWA – the national environment and climate change fund - over the period from July 2013 to March 2017. The Fund was set up to mobilise domestic and international climate and environmental finance, and to secure sustainable financing for public and private investment that would contribute to environmental sustainability, resilience to climate change, and green growth. FONERWA is supporting a wide range of climate adaptation, low carbon development and environmental projects in Rwanda. Proposals are selected on the basis of agreed criteria with a strong emphasis on value for money. The UK contribution goes directly to FONERWA which is managed by a team of experts recruited by DFID under a separate project, under the oversight of the Rwanda Ministry for Natural Resources (MINIRENA). The intended impact of the programme is that Rwanda’s economic growth is environmentally sustainable, low carbon and climate resilient. The expected outcome is that sustainable and equitable finance supports national programmes and private sector initiatives to address climate and environment priorities. The outputs will flow through two channels: primarily, the delivery of high quality climate and environment projects and programmes; but also through improved institutional capacity for mainstreaming climate change into existing and future programmes. This latter channel helps ensure the impact of UK support is sustained over time.
The programme is expected to result in at least 20 low carbon, climate resilient or environmentally sustainable projects implemented successfully and delivering, by June 2018[6] and to deliver:
[6] The Fund is demand-led i.e. the nature and quality of the project proposals received determines the specific allocation of resources and results achieved. Since it is difficult to know in advance what proposals will be submitted, and of these, which will receive funding, the results listed here are those indicated in the original business case, hence illustrative of the size and scope of results expected from the Fund. A rigorous screening process ensures that only proposals with high value for money receive support. Results are attributed to DFID in proportion to the share of the total Fund – which over the reporting period subject to this review was 87%.
- 0.57 MW of new installed capacity and 1000 households with improved access to off-grid clean energy;
- 3,699 hectares more land protected against soil erosion;
- At least USD 8m finance mobilised from the GoR to capitalise the Fund and USD 100m from MDBs;
- 355,310 people supported to cope with effects of climate change;
- 4,416 tonnes of carbon emissions equivalent avoided.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment
The outcome of the project is “sustainable and equitable finance supports national programmes and private sector initiatives to address climate and environment priorities”, with three indicators:

Outcome Indicator 1 Cumulative volume of finance [US$ millions] mobilized for climate and environment purposes as A) Contributions to Fund; B) leveraging (including co-financing for Fund supported projects) disaggregated by private sector/GoR/MDBs/other development partners (including DFID)/other sources.
Outcome Indicator 2 Number of Project Profile Documents: a) received by the FMT, b) meeting the standard required to proceed to Project Document stage, c) approved by the FMC.
Outcome Indicator 3 % of projects successfully implemented.

A combination of time delays – mainly in the capitalisation of the Fund and early project implementation - delayed the start of FONERWA, which is why several indicators are running behind target. Nevertheless, the Outcome indicators show that the Fund is on the right track to meet the June 2015 milestones[7], with most indicators showing significant improvements over the two last reporting periods (quarterly, covering Jul-Sept and Oct-Dec).
[7] The reviewers used the data reported in the FONERWA Meta Handbook, Annex A, updated in March 2015; and last quarterly report (Oct-Dec 2014).

With regards indicator 1, as of March 2015:
- Contributions to the Fund from bilateral, multilateral donors (MDBs) and other sources reached a total of USD 59.5 m, achieving the June 2015 milestone target of USD 59.5m, though this includes funds from a LDCF/AfdB project[8] (USD 9m).
  [8] These funds will not capitalise the Fund but will finance a specific project. Arguably this contribution should therefore be assigned to the indicator ‘funds leveraged by MDBs’(Bc in the logframe). If this approach is applied, the level of Ac would be reduced by USD 9m and thus below the target of USD 59.5m. However, the FONERWA fund – and FMT staff - were critical in winning the LDCF funds and the allocation to Ac reflects this contribution and the broader role of the Fund in increasing climate finance mobilisation in Rwanda.
- Cumulatively, the GoR contributed to the Fund with USD 4.2m, achieving this target.
- Leveraged funds amounted to USD 20.4m (to end March), against a June 2015 target of USD 24.4m. While two areas in this target achieved their objectives (funds leveraged by the GoR at USD 6.2m and other Development Partners (DPs) USD 11m), one indicator was slightly underperforming (leveraging by private sector, USD 4m below target).

With regards indicator 2, as of March 2015:
- Good performance has been achieved with respect to the number of PPDs received by the FMT (1028 against a target of 1088).
- PPDs meeting the standards required increased to 64, exceeding the target of 43: PPDs approved by the FMC were 20 or 1 below milestone (and will achieve the milestone by June 2015).

With regards indicator 3, as of March 2015:
As per logframe, the % of projects successfully implemented remains low at 28% against a target of 80%, due to slower than anticipated implementation by the project recipients. However, this number will increase by June 2015.

Overall, the performance during the past year has been very positive and showed major signs of improvement with respect to the Fund’s operational efficiency, quality of proposal submitted, and learning. Several actions have been undertaken by the Fund during the period to address remaining areas, as explained below.

Overall output score and description

The overall output score is A, i.e. when averaged, the project outputs met expectations. In many areas there has been over-performance, though these have been balanced against under-performance in some other areas. However, even in those areas where the Fund is currently underperforming, compared to last year there is evidence of progress.

The score also captures the quality and speed at which improvements have been adopted and implemented within the Fund over the last year, and the highly positive trend and direction of travel. Based on the improved performance over the past year, and provided this continues, the Fund will most likely meet the Outcome by the end of the Programme. However, several recommendations have been made to address the remaining areas of under-performance and ensure the programme delivers against all the output indicators.

Key lessons
- Disbursement rates forecasts need to be more realistic, and some further actions are needed to accelerate disbursement further.
- A target of 20% of funds to the private sector is set in the Operational Manual, but not in the logframe. Private sector participation was initially lower than expected. In the first CFPs, private sector PPDs were of lower quality than Government and NGOs. After workshops tailored to the private sector, the quality of these proposals have improved. Currently, seven private sector projects are in the portfolio (of which two have signed loan agreements), and three of these are currently facing severe delays at implementation stage. Total Fund’s commitments to private sector projects are of RWF 2.1bn (£2m).
- Resource mobilisation is still critical to the Fund, and DFID continues to be the largest contributor (74%), though positively there is now a large contribution from KfW (19%) and GoR (7%), and UNDP will support the Secretariat with USD 5m (up to 2018)[9]. These will increase the sustainability of the Fund. There are prospects for further capitalisation from other DPs in Rwanda. There is also growing interest in FONERWA, particularly at the international level including from the GCF. The FMT has also helped identify and support proposals in other parts of government (e.g. Adaptation Fund (AF) and Pilot Program for Climate Resilience (PPCR) proposals), providing a technical support role; and have leveraged funds from MDBs (LDCF/AfDB for USD 9m). These are important achievements for FONERWA, and showed the Fund’s ability to mobilise both domestic and international finance to help strengthen Rwanda’s resilience to climate change.
  [9] UNDP funds are managed through the Government budget system, and cover consultancy fees (PD reviewers), local staff salaries, facilities and hiring services e.g. hotel services for workshops and PD orientations, communication and publications costs, and office supplies.

Key actions
Over the reporting period, the Fund has carried out a number of actions as reported in the summary sheet above. Additional actions include:
- Improving quality and scrutiny. A new EXCEL template was developed for PD applicants which included guidance notes, basic project information, a logframe, workplan, budget, CBA and unit cost calculations all in one EXCEL spreadsheet. This improved the quality of the submissions (particularly the budgets), reducing the need for intensive support from the FMT in PD preparation. In addition, a modified, more rigorous process was used to review the PPDs with a new checklist for reviewers and blind reviews of a random sample of reds and ambers in addition to the greens and high ambers.
- Boosting private sector investment. Targeting and support is underway for private sector project developers for PPD submissions. A workshop was held in November 2014 to gather the views of the private sector. At the time of this review, a private sector investment plan is being developed and new dedicated instruments will be investigated following the review of the current instruments.
- Knowledge management and reporting. The FONERWA log-frame and metadata revisions was approved by FMC in early 2015, and informed the M&E plan. An online tool to collect and aggregate project data for monitoring fund level indicators is currently being designed. To help applicants in the approval process, and standardise FMT support, a step by step guide has been developed.
- Financial Instruments. The Innovation Grant and the Credit Line facility (developed with BRD) are currently under review, following workshops with relevant stakeholders. Once the Innovation Grant and Credit Line review are complete and presented to FMC, and orientation is provided to FTC/FMT, work will commence on developing a methodology for identifying potential additional instruments.
- The previous AR recommended DFID review VfM indicators and contribute to discussions around revisions to the VfM requirements at PPD and PD stages and monitoring VfM at project level. The indicators have been developed by DFID and are currently under review by FMT/FMC, though this action needs to be completed.

Has the logframe been updated since the last review?

Following a recommendation from the 2014 Annual Review, a two-day workshop was held in October 2014, to review the FONERWA and FMT logframe indicators and targets. The workshop involved representatives from the FMT, FTC, FMC, other Government Departments with an interest, and contributing development partners. The logframes were revised following the workshop and were approved by the FMC in January 2015.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Management of Natural Resources strengthened and sustained as a result of fund support
Output number per LF		1	Output Score	B
Risk:		Medium	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones (June 2015)	Progress (March 2015)
1.1 Area (ha) of land secured against erosion	1599	720
1.2 Area (ha) forest and agro-forest covered (disaggregated by afforestation/restored forest/agroforestry)	2206	0
1.3 Area (ha) of watershed and waterbodies protected	975	236.5
1.4 Pilot model mine	PD for model mine	0 [PD expected to be submitted before June 2015]

Key Points
In the previous AR, this output was scored C: i.e. output substantially did not meet expectations. Following the logframe review (October 2014), output indicator 1.4 was added to the list and is therefore subject to this AR. The performance during the year – as assessed in this AR - does show an improved performance with two of the four indicators showing a positive trend towards the logframe targets (both scored as B), and one indicator expected to meet the target by June 2015 (scored as A). Only one indicator showed no progress from the previous AR (scored as C), giving an overall score of B. The reviewers also note that the first three targets appear to be over-ambitious, which partly explains under-performance.

Output Indicator 1.1: There has been progress against this milestone indicator, although this is slower than anticipated (scored B).

Output Indicator 1.2: There has not been any progress against this indicator. It is reported that this is because most of the trees will be planted around November (scored C).

Output Indicator 1.3: Performance against this milestone indicator has increased significantly over the last two reporting quarters - from 90ha to 236.5ha of watershed and water bodies protected, all from one project. However, it is below the target (scored B).

Output indicator 1.4: FONERWA reported that a PPD submitted by the Rwanda Natural Resources Authority (RNRA) was revised following FMT comments and will be resubmitted in the next call. Thus, Project Document for a model mine is expected to be submitted in the sixth round of submissions (scored A).

Summary of responses to issues raised in previous annual reviews (where relevant)
There is been positive progress towards meeting the output indicators milestones. In the previous AR, a point was made around the ‘challenge fund’ nature of the Fund, which makes it difficult to predict in advance if any natural resources management project would be submitted and approved. Hence, the AR made the recommendation to review these indicators on the basis of the experience gained and calls for proposals. The review in October 2014 has resulted in some changes in the June 2015 milestones, upwards (for indicator 1.1 and 1.3) and downwards (for 1.2) on the basis of projects that have already been approved; with 1.4 added.

Recommendations: The previous AR’s recommendation on adopting a flexible approach to the logframe design is still made for this AR (recommendation 1 above). The reviewers recognise the positive trend of Output 1 indicators in meeting the milestones, but note that targets continue to be over optimistic and difficult to achieve, given the current pipeline of projects and the demand-led nature of the Fund. We therefore recommend that further attention be given to these indicators during the next logframe review, to ensure that they are realistic, and in line with the future strategic direction of the Fund.

Output Title	Renewable energy and other environmentally sustainable, low carbon and climate resilient technologies adopted, developed and/or improved for use in Rwanda as a result of the Fund
Output number per LF		2	Output Score	B
Risk:		Medium	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones (June 2015)	Progress (March 2015)
2.1 Research and feasibility studies for adoption of clean and climate resilient technologies	PD for bio-diversity, renewable energy and green building, e-waste	2 PDs [note this is reported in the quarterly report, not in the Metadata handbook, which hence needs to be updated]
2.2a Installed capacity (MW)	0.57	0
2.2b Number of households with improved access to off-grid clean energy	400	1170 people [or approx. 272 households. Note this is not reported in the Metadata handbook]
2.3 Tonnes of CO2 equivalent avoided	2,136.48	0
2.4 Number of people supported to cope with effects of climate change	225,310	93,110

Key points
There are positive but mixed results for these Output indicators. The Fund has over-performed against one milestone (2.1), but is currently under-performing against others, though a number of projects have recently started which will address these under-performing areas. Positive progress is therefore expected against indicators 2.2a, 2.2b, 2.3 and 2.4 between now and June, although given the ambitious targets for these indicators, they are still likely to be missed. Since most indicators are unlikely to be met in full, we have scored this output as a B overall, though note that there has been progress over the year and further improvements are expected in the coming months. However, positive progress, and the fact that some of these targets are technically unachievable, suggests a higher score could be warranted, and as a minimum, targets should be revised so that they are more realistic.

Output Indicator 2.1: Positive over-performance with 2 projects approved, or double the number set in the June milestone (scored A+).

Output Indicator 2.2a: The Fund achieved progress towards this indicator with loan agreements signed and disbursement started for two projects (one biomass, one hydro project), though as there is an expected delay before operation (commissioning), the installed capacity is still zero (scored B).

Output Indicator 2.2b: In the latest quarterly report, it is reported that 234 solar lanterns were distributed to 1170 people in the last quarter by a project of an NGO (Send A Cow Rwanda). With a national average of 4.3 members per household[10], this would give approximately 272 households with improved access to off-grid clean energy against a target of 400 (scored as a B).
[10] Source: Fourth Rwanda Population and Housing Census, National Institute of Statistics Rwanda, 2012.

Output Indicator 2.3: This target follows from the implementation and operation of clean energy projects. There has be no progress against this indicator in the period, but the recent implementation of projects will now start to deliver (scored B).

Output Indicator 2.4: The performance of this indicator is 93,110 beneficiaries supported to cope with effects of climate change, or 40% of the set milestones for June 2015 (scored B). However, the original logframe had a lower target of 15,000. It is unclear why this target was reviewed upwards so dramatically: as a result, whilst the programme has substantially exceeded the original target, it is now significantly below the revised (over-ambitious) revised target.

Summary of responses to issues raised in previous annual reviews (where relevant)
The overall score during the previous AR was B. Compared to the previous AR, the wording of some indicators have been revised as a result of the logframe review. However, a number of indicators still need to be revised, because they are technically unachievable, i.e. installed capacity and CO2 saved indicators require time as projects have to be built and in operation, or recent revisions have been over-ambitious. There is also some possible confusion around the exact variables to measure (e.g. the type of ‘support’ for the indicator 2.4, which is not clearly explained in the Metadata Handbook); and greater attention should be put on reporting the correct data against milestones (e.g. for indicator 2.2b, the number of households, and not people, should be reported against also in the Fund’s quarterly reports).

Recommendations: The same recommendations that were made under Output 1 also apply here (flexible logframe approach based on experience and strategic direction). Also, attention should be given to the timing of impacts to ensure that the milestones are realistic and consistent. A clear methodology should be provided for measuring indicator 2.4.

Output Title	Environment and climate change issues mainstreamed into policies, programmes, plans and activities for public and non-public agencies
Output number per LF		3	Output Score	B
Risk:		Medium	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones (June 2015)	Progress (March 2015)
3.1 National level MIS with sufficient environmental & climate change data to inform policy decisions	FONERWA Knowledge and Information Management System effectively implemented	On track [note – performance against this milestone is not currently clearly reported in the logframe]
3.2 Number of approved PDs for incorporating additional climate and environment interventions into SSPs, DDPs and other plans	5	1 / (however, this project covers all 30 district plans under one project)
3.3 Total number of programmes of action in the Green Growth Strategy supported by approved PDs fund	9	7
3.4 Total number of green jobs created as a result of the fund	13,792	3,473 / Only three permanent jobs ( > 6 months)
3.5 Number of people involved in climate resilient income generation activities	11,375	160

Key points. The programme is generally underperforming against the Output milestones, with two indicators meeting expectations (scored as A), one moderately not meeting expectations (scored B) and two underperforming quite significantly (scored as C). However, indicator 3.2 does not accurately capture the true performance of the Fund against the output objective, thus bringing down the overall score. It is also highlighted that the indicators where there is underperformance appear over-ambitious. Nevertheless, weighting each indicator equally, gives an overall score of B.

Output Indicator 3.1: The FMT reported that a management and information system (MIS) for M&E will be operational by May 2015, so the Fund is on track to meet the June milestone (scored A). They also reported that a project from Meteo Rwanda was approved for funding in January 2015 which will contribute to the output indicator. This project will improve the range of weather and climate information available to inform decision making at all levels in Rwanda, and promote its understanding and application.

Output Indicator 3.2: One Project Document from the Ministry of Local Government was approved for funding to support integration of green growth and climate resilient aspects into all 30 District Development Plans. This project will ensure that multiple district plans will incorporate climate and environment interventions, pointing to the fact that this indicator does not currently capture the performance of the Fund, and might need to be considered for revision future (score A).

Output Indicator 3.3: 7 programmes of action in the Green Growth Strategy have been supported by approved Projects against a target of 9 (scored B). This is likely to increase further by June 2015.

Output Indicator 3.4: 2,873 temporary green jobs were created in the last quarter, which are additional to the 600 jobs created in the previous quarter, showing a major increase. However, only 3 of these jobs were identified as being permanent (for longer than 6 months); gender disaggregation data are not available. By March 2015, the number of green jobs created was 3,473 or about 25% of the June 2015 milestone of 13,792 jobs, thus this target is unlikely to be met over the next three months (scored C).

Output Indicator 3.5: This is a new indicator added during log frame revision on October 2014 and is not subject to the previous AR. Performance against this indicator is 160 people supported, against a milestone of 11,375, hence substantially under-performed (scored C).
Summary of responses to issues raised in previous annual reviews (where relevant). Recommendations in the previous AR concerning revising the wording and methodology for 3.1 have been addressed, and performance corrected accordingly.

Recommendations: Monitor closely performance of indicators 3.4 and 3.5 and assess whether milestones are excessively optimistic. Re-set milestones if necessary and on the basis of more realistic assumptions and strategic direction of the Fund. Review wording of 3.2. Following the options paper on the future role of FONERWA, it is likely that greater attention will be given to a strategic role, which would be particularly relevant for indicator 3.2.

Output Title	The Fund is sustainably, cost effectively and transparently managed
Output number per LF		4	Output Score	A+
Risk:		Medium	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones (June 2015)	Progress (March 2015)
4.1 % of documents reviewed within agreed timescales, and in accordance with agreed screening procedures, which is a) 20 working days for PPDs and b) 30 working days for PDs	a) 90 / b) 80	a)100 / b) 0 / [source: quarterly report. Metadata handbook needs updating]
4.2 Cumulative % of total funds / a) committed to approved projects; b) disbursed to approved projects / (both disaggregated private sector/GoR/CSOs – no targets)	a) 65 / b) 25	a) 57.3 / b) 8.2
4.3 % of implementing projects that demonstrate a) transparent community participation; / b) a significant gender focus	a) 60 / b) 60	a) 100 / b) 63
4.4 Evidence that lessons learnt are being used to adapt programme implementation	evidence of lessons learn being incorporated, as assessed through annual review	yes

Key points. There was a positive trend for all indicators, with a number substantially exceeding expectations, but also some cases of underperformance. Overall score is A+.

Output Indicator 4.1: This indicator shows that compared with the previous AR, all PPDs were reviewed within the 20 day limit, exceeding the June 2015 milestone (A+). However, the PD screening process exceeded the 30 days as a result of the postponement of a scheduled FMC meeting (B), hence the indicator did not meet the target of 80% (overall scored as an A).

Output Indicator 4.2: This indicator (which was revised following previous AR’s recommendations) shows that cumulative funds committed was 57.3% for all recipients, including private sector (6%), Government (50%), CSO (1.3%). This is close to the June 2015 targets of 65%, so there are good possibilities that this target will be met. Disbursement rate remains low at 8.2% compared to the 25% target, but went up significantly during the last quarter (from 1.4%). Funds committed and disbursed to the private sector (6% and 0.3% respectively) remain low compared to the 20% target set in the Fund’s Operational Manual[11] though the 6th CFP led to a number of good quality private sector PDs which would increase this by June. Overall this indicator is scored as a B.
[11] Available at http://static1.squarespace.com/static/537dea6de4b00847c54026be/t/53f1df74e4b0439bf8d475cd/1408360308901/fonerwa_operationalmanual.pdf

Output indicator 4.3: The wording of this indicator has changed following the recommendations of previous AR. It is reported that 100% of the project documents have demonstrated community participation during proposal development and during implementation, and 63% have a significant gender focus, substantially exceeding expectations (scored A++). For example, in their PDs project applicants explicitly commit to supporting women and youth employment. The reviewers spoke to beneficiaries of a terracing project in Gisagara district, who reported that at least 50% of people employed in the project were women.

Output indicator 4.4: A lesson learning template and guidelines have been drafted to ensure lessons are collected and disseminated, and workshops and knowledge sharing session are held regularly. For example, given the difficulties encountered by project applicants in filling the VfM section in the PD, the FMT is currently considering ways of simplifying templates and requirements. A list of tools has been prepared and are already completed or under development. This includes an Excel tool for fund level M&E reporting which has been developed and tested. This will collate project indicator data and aggregate them to get Fund level scores (scored A+).

Summary of responses to issues raised in previous annual reviews (where relevant). Recommendations in the previous AR, which concerned revising the wording and methodology for 4.2 and 4.3, have been addressed. However, there is still only one indicator capturing private sector participation in the Fund, and no target is set in the logframe.

Recommendations: Consider setting explicit targets for private sector participation (it is recommended to set a minimum 20% target for private sector participation in the logframe to reflect the Fund’s Operational Manual) and explore further aspects to increase participation of the private sector.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
At the time of the last AR, there had been a delay in setting up the Fund, and thus it was not possible to carry out a detailed cost review. For this AR, the two last quarterly reports have been used, which contain the actual financials for the period Oct-Dec 2014 and projections for the period up to the end of March 2015.

Total expenses of FRW 3.9bn (£3.8m) have been incurred over the two last reporting periods, 91% or FRW 3.6m were for project costs, and only 9% or FRW 340m covered fund management finances, including compensation for employees, use of goods and services and other expenses (excluding the FMT costs covered by DFID of £2.2m). In this period, UNDP contribution to FMT was of FRW 210.5m (£204K), or 62% of total fund management costs.

Between the last two quarters (Oct-Dec 2014 and Jan-Mar 2015) ,the Fund saw a five-fold increase of project costs compared to the previous quarter. Conversely, administrative expenses went down by 25% over the two quarters. During the last quarter ending in March 2015, the FMT received a contribution by UNDP (FRW 145m, or £ 141K) which was used to cover all administrative expenses (excluding those covered by DFID).

Revenues to cover project costs included fees, fines, licenses and penalties, transfers from other Government institutions (MINIRENA), and donors contributions (DFID). As per end of March 2015, the Fund is running a surplus of FRW 4.8bn – mainly because the FMT disbursement forecasts were overly optimistic - which is projected to decrease by 55% to reach FRW 2bn (£2.14 m) in June 2015.

Transfers to Government-led projects represented the largest component of total costs in the last quarter (70%), and are expected to increase slightly in the next quarter (by 6%). Transfers to private sector- and NGOs-led projects represented 27% and 3% of total project costs in the last quarter respectively; however, both costs components are expected to diminish during the next quarter, by 50% and 84% respectively.

Discussions between FMT and the Government regarding the collection mechanisms of forestry fees and fines and EIA fees is still ongoing and risk causing delays in the further capitalisation of the Fund. The Fund has been actively engaging with GoR to discuss future resource mobilisation, a priority activity for the next quarters.

VfM performance compared to the original VfM proposition in the business case
The VfM of the Fund itself is driven by the VfM of the projects it supports. Fund applicants are asked to explain how they will ensure good VfM in their proposed project and how this will be measured. Applicants are referred to FONERWA VfM guidelines. Technical support is also available, through a pool of consultants contracted through the FMT and available on a call-down basis. Currently, project developers are requested to report on a quarterly basis against economy indicators capturing unit costs incurred. For efficiency, applicants carry out cost benefit analysis (which are included in the PD for approval) to generate Net Present Value (NPV) and Benefit Cost Ratio (BCR) metrics. For effectiveness, applicants are asked to identify outcome indicators and demonstrate how well the project outputs are expected to produce the intended outcome (in the PD). They are also asked to report on a quarterly basis on the results achieved, though not on whether those results differ from the original PD. A new template is currently under review by the M&E unit in FMT; an a new online database is being designed to collect and aggregate VfM data at the project level.

The business case proposed a set of VfM measures (first column in the table). Following the last AR (June 2014) a set of revised measures has been proposed by DFID and is currently under review by FMT. In the last quarterly reports, the Fund has not provided DFID with aggregate data on VfM. Performance is assessed against the revised indicators, and some recommendations are made:

VfM / measure	Indicator	Recommendation
Economy	Average day rate of the technical experts employed by projects	The Fund has not provided this information yet. / It is recommended that projects report on specific costs of equipment items and that these are benchmarked to ensure that they are not over-inflated in project proposals. At the Fund level, average costs could be reported against benchmarks. / A clear definition of admin costs should be agreed in order to allow comparison across projects.
	Average costs of specific items of equipment
	Admin/overhead cost per £1 of programme spend under each project
Efficiency	Unit cost of securing one hectare of land against erosion	The first projects have only recently started implementation and gathering data. As more projects are approved and start to report against logframe indicators, it should be possible to track VfM using these indicators and report performance in future quarterly progress reports. / However, some clear guidelines should be given on how to calculate these indicators. e.g. what costs to include in the calculation of ‘unit costs’ for the first three indicators; and ‘operational cost for proposal’ (which requires clarification - a better indicator could be days (in monetary terms, i.e. admin costs) spent by all level of governance (FMT, FMC and FTC) and call down experts on individual proposal before approval.
	Unit cost of giving a person improved access to clean energy
	Unit cost per person supported to cope with climate change
	Operational cost per proposal considered by the FMC
Effective- / ness	Amount of public finance leveraged	As reported in the logframe, at the time of this AR the amount of public finance leveraged was $6.2m which met the target of $6.2m.
	Amount of private finance leveraged	The amount of private finance leveraged was $3.2m against a target of $7.2m.
	% of projects successfully implemented	In the logframe performance against this indicator is indicated at 28%. However, during the field visit, the FMT reported that actually 8 of the 21 approved projects have started reporting quarterly, bringing the percentage to 38%. More projects are likely start implementation and gathering data by June 2015.
	Net Present Value	NPVs and BCRs are calculated in Project Documents (PDs) and subject to review before approval. Weighted average could be calculated at portfolio level. / It is recommended to conduct an annual exercise to monetise results at output level as far as possible so that these VfM metrics can be calculated for the Fund as a whole. Because only a few projects have so far been approved, this exercise has not yet been attempted.
	Benefit Cost Ratio

Feedback from project applicants[12] is that the VfM section is the hardest section of the application to complete. It is reported that public sector applicants (districts) find the requirement to calculate NPV and BCRs particularly challenging. Anecdotally, it is especially challenging for innovative proposals and those seeking funding for proof-of-concept or feasibility studies to asses VfM as the benefits of the project are likely to be highly uncertain, difficult to monetise and/or difficult to attribute. Furthermore, the VfM criterion is given a high weighting at the project screening stage, counting for 40% of the total score. This may mean that some good projects are rejected, because they find it particularly challenging to present VfM metrics.
[12] Direct feedback from successful and unsuccessful applicants to the Fund and indirect feedback from CDKN who are providing support to districts wishing to develop proposals for FONERWA.

Assessment of whether the programme continues to represent value for money
FONERWA has been operational for less than two years since capitalization, and projects only started being funded in January 2014. Results will therefore take longer to emerge than originally planned, so the performance against some of the VfM indicators proposed cannot be evaluated just yet. Further, it is recommended that some indicators are further reviewed to ensure they are transparently monitored and reported against.

In the absence of specific project data to assess VfM, an initial VfM evaluation was undertaken in late 2014 on the current FONERWA portfolio, building on a centrally funded DFID value-for-money study. This reviewed the first four rounds of FONERWA covering 20 projects, and assessed them against several criteria, including their geographical focus, distributional impact, ability to address current climate variability vs long term climate impact. The review found that FONERWA is delivering high value-for-money. In the adaptation domain, for example, it has concentrated on low- and no-regret activities that address current climate variability and build resilience for the future. It is also notable that it has funded some early low-regret adaptation to address longer-term issues (such as urban resilience plans). However, the focus on VfM has led to a focus towards more established projects, such as soil conservation and terracing (6 of the 20 projects), rain-water harvesting (8 of the 20) and biogas (6 of the 20). The fact that these options appear frequently is positive, as these all represent high value-for-money. However, this also means that there is less focus on other sectors and projects. This is raised as an issue, especially if as part of the strategic / options review, the Fund wishes to move towards supporting more innovative projects.

Recommendations:
- During the M&E template review (currently on-going), to consider special requirements around the VfM section for more innovative projects, especially if this issue emerges as part of the options review.
- Ensure calculation methods are clearly explained in guidelines.

Quality of financial management
DFID contracted KPMG to conduct an audit of FMT and FONERWA funds in October 2014. The findings were presented to the FMC in January 2015, and did not raise any significant issues. However, a number of recommendations were directed at FONERWA Implementing Partners (i.e. project implementers) including: a need for proper documentation of minutes, to avoid delays in implementation, timely submission of reports and clear segregation of duties and implementation follow up of the noted issues is planned quarterly during the project quarterly reporting system. Overall, based on the latest quarterly reports, it appears there are some further opportunities for enhancing financial management. These include:
To ensure the Fund is sufficiently capitalised (consistently with the strategic direction agreed for the Fund). Attention should be given to both short-term and long-term capitalisation measures, with a view to ensuring the fund can support a healthy pipeline of projects (short-term), and is able to fund projects with a transformational impact (long-term) (recommendation 2.1).

Adopt a more conservative forecasting approach, which accounts for some risk of not disbursing (i.e. reduce forecasts by 20%). FMT should report on the difference between forecasts and actual disbursements on a monthly basis. Improve the financial analysis and monitoring provided in the quarterly reports. This should present a better overview of the financial performance of the Fund, and include e.g. a breakdown of funds committed during the reporting quarters, funds disbursed and to be disbursed to projects over the next two quarters and comparison with previous forecasts, and also revenues from credit lines (actual and projected) (recommendation 3.3).

To improve the monitoring of implementing partners (recommendation 3.4).

Date of last narrative financial report	February 2015 (covering the period up to end December 2014)
Date of last audited annual statement	October 2014

E: RISK (½ page)

Overall risk rating: Medium

Overview of programme risk
Overall, the programme risk is considered to be MEDIUM. FONERWA has been fully operational for less than two years and the Fund has undertaken or is in the process of undertaking several actions that will strengthen its performance and are expected to lower the programme risk further, including:
- Review and analysis of the institutional positioning of the Fund and implications for future resource mobilisation [led by CDKN];
- Review of the strategic role of the Fund [led by Paul Watkiss];
- Knowledge management system improvement;
- Capacity building and recruitment of GoN staff members;
- Implementation of M&E action plan;
- Review of financial instruments (ongoing).

The highest risks faced by the Fund are around a) its financial sustainability; and b) handover to GoR, particularly around the high reliance on a small number of key people in the Fund leadership team.

On a) the Fund has been able to secure additional resources domestically, including from Environmental Impact Assessment (EIA) fees, and directly from the Ministry of Finance, who have committed to funding USD 500,000 per year over the next 3 years. To date, cumulatively the GoR have committed USD 4.2m to the Fund. This is a significant amount given competing budgetary pressures, particularly at a time when aid resources are falling, and indicates a high degree of government buy-in to the Fund. In the Risk Matrix the risk of securing MINECOFIN to contribute to the Fund is rated as amber (medium risk). Furthermore, the recent additional capitalisation from a second development partner (KfW) and the future opportunities from the Green Climate Fund (GCF) present a very promising position for the Fund. A further analysis of future resource mobilisation for the Fund is planned later this year.

On b), the current FMT (supported by DFID funding) comprises of six consultants which occupy key positions. This includes the Fund coordinator and Fund management and risk specialist, who are both Rwandan. The current coordinator has a large input at proposal development level and in day-to-day Fund operations, while simultaneously playing a much wider strategic role in raising awareness of the Fund domestically, and as a catalyst for international resource mobilisation. Given the key role these individuals have played since the beginning of the Fund’s operations, and their institutional memory and experience, it is important to ensure that they transfer over as part of the transition to GoR, or that they are able to provide sufficient mentoring and over-lap with their successors. It may also be worth broadening management and other responsibilities to avoid too many activities and responsibilities being concentrated in few individuals. In the future a new organogram should be developed to help broaden responsibilities across a wider team (recommendation 1 in the FMT’s annual review).

The possible change in the institutional home for the Fund, following from the current CDKN funded review and the resulting position adopted by the FMC and government, could have implications on donors’ fundability and the need for new due diligence requirements.

It is still too early to assess the risk of projects not delivering their intended outputs and outcomes. The M&E plan will need to include a strategy on mitigation measures to reduce risks as they materialise.

Outstanding actions from risk assessment

To undertake a future resource mobilisation strategy (currently planned) with a view to ensuring the Fund is sufficiently capitalised (consistently with the strategic direction agreed for the Fund). Attention should be given to both short-term and long-term, domestic and international capitalisation sources, including GCF (recommendation 2.1);

Considering legal status and institutional home of the Fund including implications on its effectiveness, and resource mobilisation strategy (recommendation 2.2).

To put in place a succession plan to manage changes in key staff members. Consider a new organogram to streamline responsibilities across a wider team (recommendation 1 in the FMT’s annual review).

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
Due to the initial (substantial) delay, the Fund is running behind in meeting the originally agreed milestones. In 2014-15, DFID’s disbursements to FONERWA have been lower than originally projected, or £3.7m against a ceiling of £5m. In the previous year, disbursements were lower or £2.5m against a ceiling of £5m. However, progress has been made and there are major signs of improvements with respect to operational effectiveness (the review processes have been speeded up), its endowment of skills (through capacity building activities), its engagement with Government and other development partners (for resource mobilisation), and with the private sector and project proponents (to improve the quality of the proposals). Implementation of projects, however, remains slow and is highlighted as an area to address in the recommendations.

Performance of partnership (s)
During the period, KfW capitalised the Fund with USD 9.3m, and UNDP committed to supporting FMT with USD 5m up to 2018. CDKN continues to provide some additional support to the FMT in targeted areas (particularly around support to districts). Other development partners are considering support.

Asset monitoring and control
Currently, all assets owned by the FMT are recorded and managed through the asset register.

Project developers receiving loans are subject to BRD due diligence and scrutinised with respect to their collateral and ability to repay.

CONDITIONALITY (½ page)

Update on partnership principles (if relevant)
DFID support to the programme is provided as non-budget support financial aid.  The Partnership Principles are used as part of the management and monitoring of this programme. The Government of Rwanda’s commitment to these principles was reviewed most recently in November 2014 with the following conclusions:
- Partnership principle 1: There continues to be a clear positive trend and strong Government of Rwanda commitment to poverty reduction and the Millennium Development Goals.
- Partnership principle 2: The medium term trend is flat and there continues to be concerning patterns and limited commitment in relation to some areas of human rights.
- Partnership principle 3: There is a positive trend and strong commitment to strengthening financial management and accountability, and reducing the risk of funds being misused through weak administration or corruption.
- Partnership Principle 4: The medium term trend is flat and there continues to be concerning patterns and limited commitment in relation to important areas of domestic accountability.

There has been no deterioration in commitment since the November 2014 assessment.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

The reviewers found no new evidence that would challenge the programme design or rationale. However, the programme is gathering evidence at project as well as fund management level that will contribute to the wider evidence base. This annual review presented a series of recommendations to improve knowledge management through learning and sharing at different levels, including:
- FMT could submit a periodic (6 monthly) summary of lessons learned at project and portfolio level (summary of lessons learning templates submitted by projects, and from FMT overall) and consider publishing online.
- FMT to consider providing examples (e.g. six monthly) of projects where communities and gender issues have been addressed.
- A series of information and dissemination notes could be developed. These would include higher level policy briefs as well as more technical orientated areas (e.g. building on the technical data sheets on specific projects such as terracing or rain water harvesting, or information on climate projections for Rwanda).
- To develop this material into an on-line resource, centred around the Fund web-site.
- To consider learning events, e.g. country workshops to bring development partners in Rwanda together, or regional / African workshops to share learning with other countries looking to develop funds.
- To feed the knowledge and lessons from the points above back to the International Climate Fund (ICF) – which funds this programme - to provide lessons on what works (and does not) and experience of learning by doing.

An Evaluation team of independent consultants has recently started the analysis of the baseline for the Fund’s impact evaluation, and will publish results in 2016.

Monitoring progress throughout the review period

Two reviewers conducted a desk review as well as a field visit to Kigali to meet with different stakeholders and visit a project site. The different stages of the review process can be summarised as follows:
- Review of background documentation (BCs, ARs, Quarterly reports, workshops docs)
- Visit to Kigali during 18-25 March 2015 to:
    - Assess the Fund’s performance and risks
    - Better understand the institutional context in which the Fund operates
    - Recommend way forwards (to the Fund and DFID)
    - Visit one project to speak with beneficiaries
- Meetings with:
    - Government of Rwanda: Ministry of Finance (MINECOFIN)
    - FONERWA: FMT, CIDT
    - DPs: DFID, KfW
    - Beneficiaries

The review of the Fund’s documentation together with the interviews during the field visit helped the reviewers understand the current performance of the Fund and identify key areas for improvements and challenges lying ahead. These have been fully incorporated in the recommendations of this AR.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessment
Key points
Summary of response to the programme issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process