## Log Frame
PROJECT TITLE | Implementation of the Agricultural Model Intercomparison and Improvement Project (AgMIP) for South Asia and Sub-Saharan Africa -- Phase 2(v.2014.09.16)
IMPACT (GOAL) | Indicator | Baseline (2014) | Milestone (End of 2015) | Milestone (End of 2016) |  | Assumptions/Notes
Developing country stakeholderswill have the long term capability to access more accurate estimates from regional researchers of how climate change will affect agricultural productivity and food security and how adaptation and/or policy strategies will be effective responses to changing conditions. | Target stakeholders in Sub-Saharan Africa and South Asia make more informed policy and planning decisions based on AgMIP assessments. | 0 stakeholders capable of analyzing climate impacts on regional agriculutral systems using AgMIP results in online presentation system. | Written comments of 1 stakeholder group from each of 8 SSA and SA regions evaulating the potential utilty of AgMIP preliminary regional integrated assessment results. | Written comments from at least 2 stakeholder group documenting utility of decision-support for stakeholders in 8 SSA and SA regions using AgMIP final regional integrated assessment results. |  | National and regional reports have their own schedule and vary from region to region; some regions may not have reports timed to take immediately advantage of AgMIP results
Source: Documented stakeholder decisions supported by AgMIP research.
| Indicator | Baseline (2014) | Milestone (End of 2015) | Milestone (End of 2016)
| AgMIP's improved regional projections of climate impacts and adaptation options inform major regional reports. | AgMIP Phase 1 Handbook chapters from each of 8 regional research teams peer-reviewed with preliminary climate impacts projections and one tested adaptation package available for citation. | Preliminary publication/report with improved climate impact projections made available to stakeholders from each of the 8 regional teams. | Summary publication/report made available to stakeholders from each of 8 regional research teams with improved climate impact projections and the evaluation of multiple policies and adaptation/mitigation strategies.
Source: Citations in regional or global plans and/or reports issued by WBDR, FAO, WFP, IFAD, SADC, AGRA, CGIAR.
OUTCOME (PURPOSE) | Indicator | Baseline (2014) | Milestone (End of 2015) | Milestone (End of 2016) |  | Assumptions/Notes
Stakeholders collaborate with regional research teams in utilizing AgMIP multi-model integrated assessment framework to test and prioritize adaptation and policy options to prepare for climate change impacts. | Stakeholders engage in development of policies and adaptation packages to be tested by AgMIP regional integrated assessment modeling framework. | 1 scenarios of future development and adaptation developed and evaluated for each region using Phase 1 AgMIP Modeling framework. | 2 policy scenarios and 2 adaptation packages developed and evaluated with stakeholders for each target region using Phase 2 AgMIP Modeling framework. | 3 policy scenarios and 3 adaptation packages developed and evaluated with stakeholders for each target region using Phase 2 AgMIP Modeling framework. |  | Each group will partner with a stakeholder for close collaboration and co-development of policy and adaptation assuming willing partners are identified.
Source: Records of stakeholder participation, AgMIP white papers; AgMIP Agricultural Impacts Explorer; peer-reviewed publications
| Indicator | Baseline (2014) | Milestone (End of 2015) | Milestone (End of 2016)
| Documented evidence of Stakeholder decisions informed by AgMIP results. | 0 decisions documented within SSA and SA that are directly informed by AgMIP results | 4 decisions documented within SSA and SA that are directly informed by AgMIP results | 16 decisions documented within SSA and SA that are directly informed by AgMIP results
Source: Media reports; AgMIP white papers; Stakeholder reports; peer-reviewed publications
| Indicator | Baseline (2014) | Milestone (End of 2015) | Milestone (End of 2016)
| Number of institutions capable of identifying and testing more effective adaptation strategies | 0 | 8 | 16
Source:
INPUTS (£) | DFID (£) | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 1 | Indicator | Baseline (2014) | Milestone (End of 2015) | Milestone (End of 2016) |  | Assumptions/Notes
Improved crop, livestock, and agricultural economic models linked into calibrated framework capable of evaluating climate impacts and the potential benefits of adaptation and policy strategies. | Improved representation of extreme events in decision-supporting modeling framework | Correlation and probability of detection of extreme years for current models with district-level yield anomalies. | Updated crop/livestock model components improve correlations and/or probability of detection for extreme events over last 30 years. | Apply improved models as part of climate-crop-livestock-economics integrated assessment with future scenarios including shifts in climate extremes.
Source: AgMIP Protocols and white papers available on www.agmip.org; peer-reviewed publications
| Indicator | Baseline (2014) | Milestone (End of 2015) | Milestone (End of 2016) |  | Some groups may dramatically enhance one parameter rather than enhancing diverse parameters, e.g., one RRT may run in three new regions.
| Enhanced scope of regional integrated assessments | Target regions and farming systems modeled in Phase 1 | Each team documents increases in one of the following parameters: geographic extent; model types utilized; number of models in ensemble; extreme climate scenarios; elements of the farm system modeled; time frame examined | Each team documents increases in three of the following parameters: geographic extent; model types utilized; number of models in ensemble; exteme climate scenarios; elements of the farm system modeled; time frame examined
Source: AgMIP white papers available on www.agmip.org; peer-reviewed publications
IMPACT WEIGHTING | Indicator | Baseline (2014) | Milestone (End of 2015) | Milestone (End of 2016) |  | RISK RATING
30% | Increased linkages to national and/or global scales | No AgMIP protocol for coordinated regional and global assessment | Preliminary protocol for coordinated regional and global assessment | Policy brief on sub-national, national, regional, and global assessment of agricultural impacts of climate change on SSA and SA.
Source: AgMIP Protocols and white papers available on www.agmip.org; peer-reviewed publications
INPUTS (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 2 | Indicator | Baseline (2014) | Milestone (End of 2015) | Milestone (End of 2016) |  | Assumptions/Notes
Assessments of food security and economic implications of development policies and adaptation packages co-developed with regional stakeholders. | Number of development policies configured for model-based assessment in each region co-developed by AgMIP and stakeholders | 1 | 2 | 3 |  | stakeholders will be forthcoming about policy and adaptation options and will be receptive to co-development of new strategies.
Source: AgMIP White papers; peer-reviewed articles
| Indicator | Baseline (2014) | Milestone (End of 2015) | Milestone (End of 2016)
| Number of adaptation packages configured for model-based assessment in each region co-developed by AgMIP and stakeholders | 1 | 2 | 3
Source: AgMIP White papers; peer-reviewed articles
IMPACT WEIGHTING | Indicator | Baseline (2014) | Milestone (End of 2015) | Milestone (End of 2016) |  | RISK RATING
40% | Number of assessments of policy and adaptation strategies to inform stakeholder decisions in each region | 1 | 2 | 3
Source: AgMIP White papers; peer-reviewed articles
INPUTS (£) | DFID (£) | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 3 | Indicator | Baseline (2014) | Milestone (End of 2015) | Milestone (End of 2016) |  | Assumptions/Notes
AgMIP Impacts Explorer | AgMIP Impacts Explorer usage and diffusion | Mock-up only | AgMIP IE prototype utilizing preliminary results shared with 200 visitors within the AgMIP community. | 5000 visitors to online version of AgMIP Impacts Explorer |  | The AgMIP IE will be designed to meet the needs of sub-national, national, and international stakeholders, including farmer collectives, national agricultural agency policymakers, private breeders, international negotiators, and international aid/development agencies.
Source: AgMIP white papers and data services on www.agmip.org
| Indicator | Baseline (2014) | Milestone (end of 2015) | Milestone (end of 2016)
| AgMIP Impacts Explorer User Panel | Stakeholders have not been exposed to the AgMIP IE | AgMIP IE User panel has been established and provided feedback. | AgMIP IE improvements based upon AgMIP panel input.
Source: AgMIP White Papers and blog posts on www.agmip.org
IMPACT WEIGHTING | Indicator | Baseline (2014) | Milestone (End of 2015) | Milestone (End of 2016) |  | RISK RATING
20% | AgMIP Data Interchange to store project data and results for access by AgMIP Impacts Explorer | Results from AgMIP Phase 1 stored in data server with no online manipulation functionality. | Preliminary input data and outputs from Phase 2 regional integrated assessment included in Pilot AgMIP Data Interchange with prototype tools supporting AgMIP Impacts Explorer text and images. | Final AgMIP Data Interchange stores all documentation and results from regional integrated assessment and has background data AgMIP Agricultural Impacts Explorer key indicator sets
Source: AgMIP white papers and data services on www.agmip.org
INPUTS (£) | DFID (£) | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 4 | Indicator | Baseline (2014) | Milestone (End of 2015) | Milestone (End of 2016) |  | Assumptions/Notes
Project, stakeholder interaction, and communications support for AgMIP Phase 2. | Stakeholder needs assessment. | None | Stakeholder needs assessment completed and reflected in protocols for regional research team activities (by Mid-2015) | Stakeholder needs assessment reflected in the development of AgMIP Impacts Explorer. |  | Stakeholders are receptive and forthcoming with stakeholder assessment activities.
Source: www.agmip.org; peer-reviewed journals
| Indicator | Baseline (2014) | Milestone (End of 2015) | Milestone (End of 2016) |  | Capacity survey will include comfort with Phase 1 protocols, interactions with sttakeholders, Phase 2 protocols/methods/tools, and the interpretation and communication of project results.
| Capacity gains for project participants. | RRTs familiar with Phase 1 protocols and models. Initial RRT survey of capacity at kickoff regional workshop | RRT survey of capacity at mid-term regional workshop documents capability gains. | RRT survey of capacity at closing/writing workshops documents gains.
Source: AgMIP White papers, workshop reports, and blog posts
IMPACT WEIGHTING | Indicator | Baseline (2014) | Milestone (End of 2015) | Milestone (End of 2016) |  | RISK RATING
10% | Communications | 0-1 blog posts for each region on www.agmip.org | 1 policy brief/fact sheet, updated webpage, and communications strategy informed by stakeholder needs assessment for each RRT | 3 policy briefs/fact sheets, an updated webpage, and 2 blog posts for each RRT
Source: www.agmip.org;
INPUTS (£) | DFID (£) | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
Notes:

## Task Estimate
N° (and WP) | Major Tasks (by year and quarter) | 2014 | 2015 |  |  |  | 2016 |  |  | Future activities enabled
|  | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | è
1 | Assemble project teams | bar: 2014 Q4 to 2015 Q2
2 | Contract Stakeholder Assessment Unit and conduct stakeholder needs assessment | bar: 2014 Q4 to 2015 Q3
3 | Develop mock-ups and prototypes for AgMIP Impacts Explorer | bar: 2014 Q4 to 2015 Q2
4 | Identify partner stakeholders in adaptation test beds | bar: 2014 Q4 to 2015 Q3
5 | Hold regional project workshops including end-users and stakeholders
6 | Build capacity of regional research team participants | [8 empty] | è
7 | Develop methodologies for coordinated regional and global assessments of food security and agricultural economics | [8 empty] | è | bar: 2014 Q4 to 2015 Q3; 2016 Q2 to 2016 Q3
8 | Identify policy and adaptation/mitigation packages for integrated assessment | bar: 2014 Q4 to 2016 Q1
9 | Identify and implement priority improvements to multi-model regional integrated assessment framework for each region | bar: 2014 Q4 to 2015 Q4
10 | Perform integrated assessment of first round of adaptation/mitigation and policy options | bar: 2015 Q3 to 2016 Q1
11 | Develop functioning version of AgMIP Impacts Explorer | [8 empty] | è | bar: 2015 Q3 to 2016 Q1
12 | Interpret outputs for stakeholders and co-develop adjustments to adaptation/mitigation and policy strategies accordingly | bar: 2015 Q4 to 2016 Q2
13 | Perform integrated assessment of additional round(s) of adaptation/mitigation and policy options | [8 empty] | è | bar: 2015 Q4 to 2016 Q3
14 | Launch AgMIP Impacts Explorer via www.agmip.org | [8 empty] | è | è | bar: 2016 Q1 to 2016 Q3
15 | Prepare project communications and post policy briefs/fact sheets on www.agmip.org | [8 empty] | è | bar: 2015 Q1 to 2016 Q3
Legend:
| Preparatory or ongoing activities | 2014 Q4: Primary Work Package:; 2015 Q4: WP1; 2016 Q3: WP3
| Priority activities | 2015 Q4: WP2; 2016 Q3: WP4

## WP & Task Summary
Overview |  | Indicators |  | Baseline (2014) | Milestone (2015) | Milestone (2016)
Impact (Goal): Developing country stakeholderswill have the long term capability to access more accurate estimates from regional researchers of how climate change will affect agricultural productivity and food security and how adaptation and/or policy strategies will be effective responses to changing conditions. |  | Target stakeholders in Sub-Saharan Africa and South Asia make more informed policy and planning decisions based on AgMIP assessments |  | 0 stakeholders capable of analyzing climate impacts on regional agriculutral systems using AgMIP results in online presentation system. | Written comments of 1 stakeholder group from each of 8 SSA and SA regions evaulating the potential utilty of AgMIP preliminary regional integrated assessment results. | Written comments from at least 2 stakeholder group documenting utility of decision-support for stakeholders in 8 SSA and SA regions using AgMIP final regional integrated assessment results.
|  | AgMIP's improved regional projections of climate impacts and adaptation options inform major regional reports. |  | AgMIP Phase 1 Handbook chapters from each of 8 regional research teams peer-reviewed with preliminary climate impacts projections and one tested adaptation package available for citation. | Preliminary publication/report with improved climate impact projections made available to stakeholders from each of the 8 regional teams. | Summary publication/report made available to stakeholders from each of 8 regional research teams with improved climate impact projections and the evaluation of multiple policies and adaptation/mitigation strategies.
Outcome (Purpose): Stakeholders collaborate with regional research teams in utilizing AgMIP multi-model integrated assessment framework to test and prioritize adaptation and policy options to prepare for climate change impacts. |  | Stakeholders engage in development of policies and adaptation packages to be tested by AgMIP regional integrated assessment modeling framework. |  | 1 scenarios of future development and adaptation developed and evaluated for each region using Phase 1 AgMIP Modeling framework. | 2 policy scenarios and 2 adaptation packages developed and evaluated with stakeholders for each target region using Phase 2 AgMIP Modeling framework. | 3 policy scenarios and 3 adaptation packages developed and evaluated with stakeholders for each target region using Phase 2 AgMIP Modeling framework.
|  | Documented evidence of Stakeholder decisions informed by AgMIP results. |  | 0 decisions documented within SSA and SA that are directly informed by AgMIP results | 4 decisions documented within SSA and SA that are directly informed by AgMIP results | 16 decisions documented within SSA and SA that are directly informed by AgMIP results
|  | Number of institutions capable of identifying and testing more effective adaptation strategies |  | 0 | 8 | 16
Output | Work Package | Indicators | Tasks Involved | Baseline (2014) | Milestone (2015) | Milestone (2016)
1. Improved crop, livestock, and agricultural economic models linked into calibrated framework capable of evaluating climate impacts and the potential benefits of adaptation and policy strategies. | Work Package 1. Science toward more robust projections of climate change impacts on agricultural systems | Improved representation of extreme events in decision-supporting modeling framework | Task 2; Task 6; Task 9 | Correlation and probability of detection of extreme years for current models with district-level yield anomalies. | Updated crop/livestock model components improve correlations and/or probability of detection for extreme events over last 30 years. | Apply improved models as part of climate-crop-livestock-economics integrated assessment with future scenarios including shifts in climate extremes.
|  | Enhanced scope of regional integrated assessments. | Task 2; Task 6; Task 9; | Target regions and farming systems modeled in Phase 1 | Each team documents increases in one of the following parameters: geographic extent; model types utilized; number of models in ensemble; extreme climate scenarios; elements of the farm system modeled; time frame examined | Each team documents increases in three of the following parameters: geographic extent; model types utilized; number of models in ensemble; exteme climate scenarios; elements of the farm system modeled; time frame examined
|  | Increased linkages to national and/or global scales | Task 7 | No AgMIP protocol for coordinated regional and global assessment | Preliminary protocol for coordinated regional and global assessment | Policy brief on sub-national, national, regional, and global assessment of agricultural impacts of climate change on SSA and SA.
2. Assessments of food security and economic implications of development policies and adaptation packages co-developed with regional stakeholders. | Work Package 2: Applied research on adaptation: Co-generation with users in vulnerable regions | Number of development policies configured for model-based assessment in each region co-developed by AgMIP and stakeholders | Task 4; Task 8; Task 10; Task 12; Task 13; | 1 | 2 | 3
|  | Number of adaptation packages configured for model-based assessment in each region co-developed by AgMIP and stakeholders | Task 4; Task 8; Task 10; Task 12; Task 13; | 1 | 2 | 3
|  | Number of assessments of policy and adaptation strategies to inform stakeholder decisions in each region | Task 4; Task 8; Task 10; Task 12; Task 13; Task 14; Task 15 | 1 | 2 | 3
3. AgMIP Impacts Explorer | Work Package 3: Tools to Inform Adaptation Decisions | AgMIP Impacts Explorer usage and diffusion | Task 3; Task 11; Task 14; Task 15 | Mock-up only | AgMIP IE prototype utilizing preliminary results shared with 200 visitors within the AgMIP community. | 5000 visitors to online version of AgMIP Impacts Explorer
|  | AgMIP Impacts Explorer User Panel | Task 4; Task 12; Task 14 | Stakeholders have not been exposed to the AgMIP IE | AgMIP IE User panel has been established and provided feedback. | AgMIP IE improvements based upon AgMIP panel input.
|  | AgMIP Data Interchange to store project data and results for access by AgMIP Impacts Explorer | Task 3; Task 11; Task 14 | Results from AgMIP Phase 1 stored in data server with no online manipulation functionality. | Preliminary input data and outputs from Phase 2 regional integrated assessment included in Pilot AgMIP Data Interchange with prototype tools supporting AgMIP Impacts Explorer text and images. | Final AgMIP Data Interchange stores all documentation and results from regional integrated assessment and has background data AgMIP Agricultural Impacts Explorer key indicator sets
4. Project, stakeholder interaction, and communications support for AgMIP Phase 2. | Work Package 4: Management | Stakeholder Needs Assessment | Task 2; Task 4; Task 5; Task 6; Task 8; Task 12; Task 14 | None | Stakeholder needs assessment completed and reflected in protocols for regional research team activities (by Mid-2015) | Stakeholder needs assessment reflected in the development of AgMIP Impacts Explorer.
|  | Capacity gains for project participants | Task 1; Task 6; | RRTs familiar with Phase 1 protocols and models. Initial RRT survey of capacity at kickoff regional workshop | RRT survey of capacity at mid-term regional workshop documents capability gains. | RRT survey of capacity at closing/writing workshops documents gains.
|  | Communications | Task 5; Task 6; Task 15 | 0-1 blog posts for each region on www.agmip.org | 1 policy brief/fact sheet, updated webpage, and communications strategy informed by stakeholder needs assessment for each RRT | 3 policy briefs/fact sheets, an updated webpage, and 2 blog posts for each RRT