Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Improving the Quality of General Education in Ethiopia
Programme Value: £130 million		Review Date: Updated in March 2015 / (Review Period: 18 October 2013 – March 2015)
Programme Code: 203396	Start Date: 18 October 2013	End Date: July 2018

Summary of Programme Performance
Year	2014
Programme Score	A
Risk Rating	Medium

Main Acronyms Used
DP / EMIS / GEQIP	Development Partner / Education Management Information System / General Education Quality Improvement Programme
GoE / MDTF	Government of Ethiopia / Multi Donor Trust Fund (MDTF)
MoE	Ministry of Education
MoFED	Ministry of Finance and Economic Development
QESSP / SIP	Quality Education Strategic Support Programme / School Improvement Programme

Remark: This review of GEQIP II is an update to the first annual review that was carried out in September 2014 only six months after the effective start date of the programme. The September 2014 review had recommended a light touch review to be conducted in March 2015 to incorporate data from the latest Education Statistics Abstract, the programme’s first annual progress report, audit and costing data from the procurement processes – all of which were not available then. As a result the light touch review did not require introducing interim milestones for 2015 and is reporting back on progress against the 2013/14 milestones using the newly available data. This update review will also streamline the timeframe of future reviews by timing them to be completed after key sector data are released and before DFID makes annual disbursements in May/June each year.

Summary of progress and lessons learnt since last review

The Business Case for “Improving the Quality of General Education Programme in Ethiopia” was approved by DFID in October 2013 to support the Government of Ethiopia’s (GoE’s) general education sub sector. It is a four year (January 2014 – July 2018) £130 million programme with two components:

Component 1:- £120 million to the GoE through a World Bank Multi Donor Trust Fund to support the second phase of GoE’s General Education Quality Improvement Programme (GEQIP II). GEQIP II is being implemented by the federal Ministry of Education (MoE) through decentralized modalities including 11 regions, all districts, 20 universities, 36 Colleges of Teachers Education and approximately 40,000 schools and Alternative and Basic Education centres; and

Component 2:- £10 million for the second phase of DFID’s Quality Education Strategic Support Programme (QESSP II) delivered through a contracted Fund Manager (British Council). QESSP II is designed to maximise the impact of GEQIP II by providing support for research and evidence building, capacity building and technical assistance to the MoE.

GEQIP II is expected to contribute to improved learning conditions and institutional capacity for enhanced learning outcomes for 21.6 million children (of which 10.54 million will be girls). Some of the results anticipated are:
- All 40,000 plus government primary and secondary schools and Alternative and Basic Education Centres receiving a per capita grant of on average of £1.90 per pupil enrolled to focus on improving learning achievement (35% of the grant attributable to DFID);
- 1,600 principals and supervisors trained to ensure better managed, more accountable, primary and secondary schools and Alternative and Basic Education Centres (training for 560 principals and supervisors attributable to DFID);
- approximately 140,000 more qualified teachers and Alternative Basic Education Facilitators trained to use more participatory and inclusive teaching approaches in classrooms (46,000 teachers and facilitators attributable to DFID);
- 83 million more textbooks and supplementary materials effectively utilised by teachers and students to promote learning for all students, including the provision of braille books for the blind (29 million attributable to DFID);
- 200 secondary schools use new Information and Communication Technology equipment to enhance learning outcomes of students (equipment for 70 schools attributable to DFID);
- Skills and capacity of education officials in all 900 plus districts enhanced to monitor and support schools and Alternative and Basic Education Centres performance and help them to improve learning (training for staff in 315 districts attributable to DFID); and
- A national monitoring and evaluation system that builds on the existing infrastructure to provide more comprehensive feedback on progress and helps identify bottlenecks.
In addition to this by using a mix of instruments and working closely with government and partners, the education sector development plan is expected to produce the following outcomes:
- An increase in overall primary enrolment to 21.6 million (of which 10.54 million will be girls), from 17 million in 2012/13;
- Improved enrolment in the developing regional states, especially in pastoralist communities;
- A million more students completing grade 8 of primary school and 500,000 more completing lower secondary school (grade 10);
- Improvements in the gender parity index, especially at secondary level, by making schools more conducive to girls’ participation and learning;
- Better access to education for students with special needs; and,
- Improved learning outcomes for students with a minimum of 10 million students scoring above the basic level in the National Learning Assessment for language and mathematics at grades 4, 8, 10 and 12.
Key start up activities that were reported in the initial review were:

- The launch event in January 2014 where key messages on the purpose of GEQIP II were delivered by the Prime Minister of Ethiopia, DFID Ethiopia Head of Office and other development partners;
- The completion of DFID’s due diligence assessment conducted on the World Bank and the signing of administrative agreement for Multi Donor Trust Fund (MDTF) management for GEQIP II;
- The signing of a Memorandum of Understanding between the GEQIP II partners and the GoE;
- The signing of a financial agreement between the World Bank and Ministry of Finance and Economic Development (MoFED);
- The disbursement of $55 million from the World Bank to the MoFED in April 2014;
- The disbursement of £30 million from DFID to the World Bank’s MDTF in June 2014;
- The first semi-annual GEQIP implementation support mission was conducted from June 16-27, 2014; and
- The development of a work plan for the fourth quarter of the 2013/14 Ethiopian financial year (April-June 2014), and for the full year covering July 2014 to June 2015.
Major developments since the last review include:

- A second disbursement of $55 million from the World Bank in December 2014
- A re-planning exercise in February 2015 including revisions to the procurement plan to capture activities that were found to be immediate priorities
- The ongoing education financing review (private and public) commissioned by the World Bank. This is expected to be completed by June 2015 providing us useful information on financing trends and unit costs.
- The second semi-annual GEQIP implementation support mission was conducted from January 26 to February 6, 2015 including field visits to Amhara and Harari regional states. See section B below on the mission’s major findings.

Summary of recommendations including actions taken since the initial annual review

1. Consider supporting the GoE to conduct an analysis of the different sources of funding for primary and secondary schools, including school grants, private contributions from parents/communities (in kind as well as monetary) and support from NGOs and how this varies from one region to another, and from one school to another. This will enable the government and partners to better understand the resources available in the sector. Financing review is ongoing
2. Use of a standard template for preparing School Improvement Plans should be considered by the MoE to improve consistency in planning and budgeting at school level, and to provide simpler guidelines for less experienced school committees and Parent Teacher Associations. Guideline is under revision
3. The MoE needs to work hard in creating more awareness at the district level on the importance of timely disbursement of school grant to schools to implement School Improvement Plan. Strengthening school grant fund monitoring by preparing monthly cash follow up sheets for all regions is also important. The MoE also needs to share the audit finding with Regional Education Bureaus on a timely basis for strengthening the school grant disbursement mechanisms at district level. The World Bank and MoE agreed that school grant calculation and disbursement process will be de-linked from the planning process for the rest of the components. This is because school grants are calculated per capita using enrolment data from the previous academic year, the transfer of grants need not be subject to unnecessary delays from other planning processes. ToR for school grant audit bring finalised.
4. DFID, MoE and the Fund Manager for QESSP should prioritize procurement and monitoring and evaluation capacity building support to ensure that the key areas of institutional weaknesses, particularly at district level, are addressed as quickly as possible. Organisational capacity assessment completed as part of QESSP inception phase and annual work plan including for technical assistance and capacity building activities approved by the steering group.
5. Improvement in the Education Management Information System (EMIS) needs to be prioritised to deliver educational data on a timely fashion. This has been identified as one areas of support for QESSP in 2015/16 particularly technical statistical support to MoE.
6. The design of the teacher licensing process should be finalised and rolled out to ensure better progress towards the 2016 milestone. Ongoing.
7. The planned impact evaluation of the Teachers Development Programme should measure the logframe’s outcome indicator pertaining to the proportion of teachers using student centred approach. The ToR is being finalised
8. Revise the DFID programme log-frame to refine indicators, milestones and the Value-for-Money (VfM) approach by the end of May 2015.
9. The World Bank, MoE and MoFED need to closely monitor the budget utilisation of the project which was low in the first year, to identify bottlenecks and take corrective measures - ongoing;
10. The programme’s joint review missions to assess progress towards the recommendations of GEQIP II Social Assessment and to proactively identify and manage risks to and from the programme. In this regard, DFID should update the risk matrix for the programme and work with the World Bank to enhance the scope of future review missions.
11. Update the annual review by March 2015 to incorporate data from the 2014 Education Abstract, GEQIP II’s first progress report and audit and costing data from the procurement processes – all of which are not currently available. Completed.
12. Prepare enhanced approach to monitoring risk.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-203396/documents/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-203396/documents/

Outline of the programme

Increasing equitable access to quality general education has been a high priority of the GoE, especially since the launch of the Education Sector Development Programme (ESDP) III in 2006. Over the past ten years, impressive progress has been made in Ethiopia including enrolling 92%% of primary school age children into schools. Other key accomplishments include:

- Increased Net Enrolment Ratio (NER) for primary education (grades1-8). The NER has increased from a low base of 24.9% in 1996/97 to 92%% in 2013/14. Number of children enrolled in primary enrolment has reached 18 million, and the number of out of school children has dropped from 6.5 million to around 3 million between 1999 and 2008;
- Improved enrolment of girls. The gender parity index (girls to boys ratio) in primary education has increased to 0.96 in 2013/14 in comparison to 0.7 in 2001/02; and,
- Increased secondary enrolment. The Gross Enrolment Ratio (GER) has increased from 17.1% in 2001/02 to 39.3% in 2013/14 (38% for girls up from 13.7% in 2001/02). Despite improvement, only two out of five eligible children are in secondary schools.

Ethiopia has also put in place most of the building blocks for improving quality of education, including:

- Strong government commitment and clear policy direction;
- Expanded and well managed teaching force;
- Equitable provision of education services;
- A decentralized implementation structure;
- Accountability of schools to communities; and,
- A relatively robust Education Management Information System (EMIS).

Despite these accomplishments in expanding equitable access to schooling, and putting in place the foundations for quality improvements, levels of learning achievement are still very low. The 2011 National Learning Assessment has shown very low levels of learning outcomes: the average score of sampled students in grade 4 and grade 8 was below basic proficiency; the average score of majority (57%) of the students in grade 4 in four subjects was below basic level; and, the average score of majority (56%) of the students in grade 8 in five subjects was below basic level.

Recognising the urgent need to improve the quality of primary and secondary education, the GoE launched GEQIP as an eight year (2009 – 2017) programme. The UK contributed £95 million to the first phase (2009 – 2013) of GEQIP I. The first phase of DFID support, along with government and other donor’s contribution, achieved the following results:

- Over 88 million high quality textbooks and teachers guides were developed, printed and distributed to primary and secondary schools;
- The proportion of qualified primary teachers (grades 1 to 8) increased from 38% in 2009 to 56% in 2012; and,
- More than 98% of the schools received grants and used them to fund their school improvement plans that were developed and agreed with school communities.

However, at the end of the first phase, there remain many challenges pertaining to quality of primary and secondary education. Also, there was a strong need to consolidate the work done in GEQIP I and sustain its gains. To respond to these needs, in October 2013, DFID approved the Improving the Quality of General Education Programme to contribute to delivering DFID Ethiopia’s Operational Plan commitment to support 1.94 million children in primary and 240,000 children in lower secondary by 2015, of which at least half will be girls. This will be achieved by providing:

£120 million to the GoE through a World Bank Multi Donor Trust Fund (MDTF) to help improve the curriculum and availability of textbooks, to undertake teacher training; to continue to provide grants to schools to implement school improvement plans, to improve the capacity and management of educational leaders, and to develop the information and communication technology system to improve the quality of teaching and learning; and,

£10 million for QESSP II to improve evidence based programming, programme coordination, Monitoring and Evaluation. This support will be provided through a Fund Manager engaged by DFID.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

The outcome of GEQIP II is ‘Improved learning conditions and institutional capacity for enhanced learning outcomes’. There are plans to conduct evaluations to be able to assess and report on outcome indicators such as the ‘degree to which teachers demonstrate student-centred teaching approaches’ and ‘percentage of schools using at least half of their school grants allocation for the SIP teaching and learning domain’. The planned evaluations are not yet due and we will be able to report on this in the outer years.

Developments so far are indicative of a positive trajectory towards the outcome and impact. The second joint implementation support mission[1] assessed that one year after effectiveness, the project is making progress toward the objectives of improving learning conditions in schools and strengthening system management, but the progress is uneven. There is significant progress in printing and distribution of textbooks (2,123,810 copies) and teachers guides (53,839 copies) in the mother tongue, including the launching of the tenders for 5 new and re-printing textbook contracts (approximately 47 million books). Over 45,000 (40.5% female) teachers have completed training last year and two tranches of school grants have been transferred to regions. The first transmission of grant from regions to schools was delayed in some areas as funding for the grants was transferred too close to the end of the academic year when schools close. In improving teacher competencies, the project Annual Work Plan for the year 2014/15 includes teacher professional development in subjects such as English, Mathematics and Sciences as well as general Continuous Professional Development (CPD) though the implementation was limited. Regarding school grants, though disbursement was significantly delayed, there is a shift towards school grants being used for activities and resources directly supporting teaching learning. One of the progresses in system strengthening is reflected in a minor reduction of grade 1 dropout rate (a reduction from 22.5% in 2012/13 to 21.4% in 2013/14). There is also good progress in school inspections with 20% of schools nationwide established the baseline of school classifications and have known their classification.
[1] Aide-memoire GEQIP II, World Bank February 2015

Overall output score and description

A: Outputs meet expectation

Key lessons
Transition between the two phases of GEQIP has been slow in terms of planning, procurement, communication structures, and finance. In future, it might be worth considering an inception or bridging phase of 3-6 months linking the first phase and second phases of a large nationwide programme.

Although the co-ordination and communication structures in GEQIP II are quite well defined, and build on already well-established relationships, it is always worth reviewing them and improving where necessary. In the case of GEQIP II, it would be valuable to have monthly co-ordination meetings, not least to clarify disbursement schedules from partners, and key capacity building actions with the GoE.

Based on experience from GEQIP I and from the first year of GEQIP II there is need to further build the capacity of procurement, financial management and monitoring and evaluation functions at national and regional levels. QESSP will have a complementary role helping the implementation of GEQIP providing additional technical assistance.

Key actions

MoE should consider de-linking the process of calculating per-capita school grants from the iterative Annual Work Plan (AWP) as the former is a straightforward and need not be subject to unnecessary delays. Agreed by the World Bank and MoE

Follow up by the World Bank on MoE’s budget preparation (both in terms of timeliness and quality) and the budget utilisation of the project to ensure timely disbursement of funds and to avoid holding up resources unnecessarily.

DFID and World Bank to ensure that future review missions are enhanced to look at social safeguards issues and to assess whether the recommendations of the GEQIP II social assessment are effected and that risks are identified and managed.

Has the logframe been updated since the last review? No

However, the logframe has been updated since the indicative logframe submitted with the Business Case to improve the relevance and objectivity of a number of indicators and to reflect processes in the first year of the programme. It will be updated based on the recommendations given by this light touch review.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Improved curriculum, textbooks and inspection
Output number per LF		1	Output Score	A+
Risk:		High	Impact weighting (%):	15%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
% of schools using the full set of printed curriculum documents in the regional language	Selecting a printing company to produce the full set of curriculum documents in mother tongue	Two printing companies have been selected for the printing of the regional language curriculum documents and using money from a previous phase of Teacher Development Programme (TDP) materials are produced in 7 regional languages (Amharic, Somaligna, Tigrigna, Afan Oromoo, Hadiya, Sidamigna, Wolayitigna). The printing process has been completed 2,123,810 copies of textbooks and 53,839 copies of teachers’ guides have reached regional textbook distribution centres. Regions are in the process of distributing the materials to schools. / (Indicator Score: A+)
Number of textbooks and teacher's guides (based on new curriculum) distributed to schools (cumulative)	0	Procurement is in progress in all textbook bid packages with risk of delays in grades 5-8 lot as a result of technical procurement issues identified in the bid evaluation process. / Evaluation criteria and technical specification agreed with the World Bank for the production of books in braille for visually impaired students. The World Bank to issue no objection on the bid document. Teachers guide in visual arts, music, and physical education: evaluation criteria agreed with the World Bank. The World Bank to issue no objection on the bid document. The estimated earliest completion time of these two lots is December 2015 because of the nature of the procurement process. / (Indicator Score: Milestone for this year is zero. The indicator will be assessed in 2016)

Key Points

Two printing companies have completed the printing process and regions are distributing materials to schools. The year’s milestone for the second indicator is ‘zero’. Therefore, Output 1 has moderately exceeded expectations for this review.
- The MoE curriculum directorate is preparing to conduct an assessment on the impact of the new curriculum that has been developed and implemented in GEQIP I. This will help to identify the possible learning gaps in the curriculum, observe changes in students’ behaviour and interventions to close gaps and respond to students’ other learning needs.
- The National Association for the Blind is highly engaged with the MoE curriculum directorate in the bid preparation process of the Braille materials. The association has given support for the preparation of the technical specification and will also be engaged in proof reading activities.

Summary of responses to issues raised in previous annual reviews (where relevant)
No formal training is being organised by the World Bank on procurement but the World Bank is working with the MoE procurement directorate very closely and a kind of on job training is ongoing.

Recommendations

Both indicators in use for output 1 focus on the printing and distribution of textbooks. School inspection is one of the integral parts of this component of the programme which is working towards improving schools performance. This review recommends the cancellation of one of the indicators and replacing with an indicator that could help to assess the progress in school inspection - measured by for example the % of schools inspected each year.

Output Title	Strengthened teacher training programme
Output number per LF		2	Output Score	C
Risk:		Medium	Impact weighting (%):	15%
Risk revised since last AR?		NA	Impact weighting % revised since last AR?	NA

Indicator(s)	Milestones	Progress
Number of teacher trainees completing programmes with updated curricula (% female) including Alternative and Basic Education (ABE) facilitators upgraded each year	28,000 (40% female) teachers and 1,000 ABE facilitators	45,566 (40.5% female) teacher trainees completed teacher-training programmes in 2013/14. However, it is not clear whether or what proportions of these graduates have completed the programmes with the updated curricula. The annual education abstract from the MoE EMIS does not show this. 1,161 ABE facilitators have been upgraded in Somali region in 2013/14. / (Indicator score: B)
No. of teachers licensed (cumulative)	100,000	No performance assessment has been carried out so far and hence no certification. / The Teacher Licensing and Relicensing directorate is finalizing the development of teacher performance assessment tools and it has also started the process of selecting the performance assessors. Next step is to start assessing performance and then the certifications will follow. / (Indicator score: C)

Key Points

- There is no clear and well organised information on the list of curriculum and modules developed (or planned to be developed) by level of programmes and institutions, including status of their implementation in Colleges of Teachers Education and universities. Hence, it is difficult to get data on the number of teacher trainees completing programmes with updated curricula. This has meant that it is difficult to measure the first milestone for Output 2.
- Significantly small numbers of teachers were selected to be enrolled in the universities for post graduate diploma teacher training programme. Despite the government’s affirmative action the proportion of female students joining the teaching profession is also low (20%).
- One of the modalities of the teachers and school leaders licensing process, the performance assessment, is not yet started as it requires intensive preparatory works and hence no certification has been issued to any of the teachers or school leaders. Thus, the milestone for the second indicator of output 2 has not been achieved.
- The number of universities training secondary school teachers in GEQIP I were only 10. In GEQIP II the number increased to 20 and this has a budget implication for the project. The MoE and DPs need to take into account the overall budget implication of this expansion.
- The low rate of per diem has hampered the effectiveness of the practicum programmes in both universities and colleges of teachers’ education.
- A TOR has been developed by the Teachers Development Programme directorate to conduct a Teachers Development Programme (TDP) impact study which will inform the MoE how well pre-service and in-service training has changed teacher classroom behaviour, in line with the government’s policy of increasing the use of student centred teaching methods, and which will also generate data on teachers’ classroom behaviour.

Summary of responses to issues raised in previous annual reviews (where relevant)

The 2013/14 Education Management Information System (EMIS) abstract has been delayed. It was only in February 2015 that the MoE shared the draft statistical abstract covering 2013/14. This has been raised with the Minister of Education.

One of the modalities in the teacher licensing and relicensing assessment, written tests (content and pedagogy), has been rolled out only on new post graduate diploma programme for secondary schools teachers. The second modality, performance assessment, is not yet operationalised.

Recommendations

- MoE should be supported to track percentage of teacher training delivered through the new curriculum and report to DPs.
- MoE, World Bank and DPs to consider the budget implication of the new universities with secondary teacher training programme.
- The MoE needs to re-think its teachers selection strategy to encourage applicants as well as increase females participation in the teaching profession and speed up the implementation of the licensing process.

Output Title	Improved school improvement programme including Provision of school grant
Output number per LF		3	Output Score	B
Risk:		Medium	Impact weighting (%):	30%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
% of schools receiving school grants. (Academic year begins in September)	October -10% / November - 60% / December -30%	There were two tranches of school grant disbursement so far, in April and November 2014. However, except for some regions, school grants did not reach schools as per the anticipated timeframe. The milestone assumed that the project would start at the beginning of the last academic year (September 2013) however it effectively started in February 2014 and donors’ disbursement was therefore delayed. / (Indicator Score: C)
% of rural, isolated area schools, ABEs, and schools with fewer than 200 students using revised, simple and pictorial School Improvement Plan (SIP) guidelines that are judged to be satisfactory	School grant allocation revised, SIP guidelines revised and agreed	The school grant guidelines revision is completed having gone through the validation process. It is updated to include small, disadvantaged, remote schools, and ABEs. Schools and ABEs with fewer than 200 students are receiving school grants as if they have 200 students. Additional 5% funds were also allocated to schools for the 2014/15 disbursement to cover the divergence in enrolment as a result of MoE using old enrolment data to calculate school grant. Discussion is underway how to provide more per capita grants to schools with special need children. / (Indicator score: A)

Key Points

- There was substantial delay in disbursement of school grants funds both at the federal level and from district to schools. The MoE has agreed with the World Bank to delink the school grants calculations from the annual work plan of other GEQIP II components to allow the timely disbursement of school grant from federal to the regional levels and to schools. To strengthen the monitoring of the disbursement of school grants, the School Improvement Programme (SIP) Directorate at MoE will undertake spot–checks via phone calls to a random sample of school. The spot- check would be collected at three points June, September, and November.
- Although there is a standard process for school development planning involving a school management committee consisting of principals, teachers, parents, and students, there does not appear to be a format or template which might guide schools to plan, prioritise and cost better, as well as making it easier for districts/Regional Education Bureaus to assess plans for funding.
- A strong feature of the school grants guidelines are the accountability mechanisms. Each school is required to erect and maintain a School Grants Notice Board and display, details of the date each School Grants was received, and how the grants have been spent. Income from other sources, and the details of major expenditures made by the school with those financial resources, are also required to be included on the School Grants Notice Board. The School Grants Cash Book is retained by the school or Alternative Basic Education Centres, along with all receipts, invoices and quotations, and is always open for examination by members of the Parent Teachers Associations, the school community at large, school inspectors, and auditors.

Summary of responses to issues raised in previous annual reviews (where relevant)
The World Bank commissioned education financing review which covers not only public financing (PER model) but also household and other types of education spending.  For public spending, the district level spending data will be used which will match with the district EMIS data (enrolment, survival and completion rates) to have a map of where and whether funding produces results in Ethiopia.

Recommendations

- The MoE to follow up on a swift printing, translation and distribution of the revised school grant guideline.
- The MoE to strengthen the accountability and compliant management at various levels of the educational management to support efficient and equitable management and use of the school grants focusing on activities directly related to the teaching and learning domain of the school improvement plan and that have the most effect on learning outcome.

Output Title	Strengthened education management and administration
Output number per LF		4	Output Score	A
Risk:		Medium	Impact weighting (%):	15%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
No. of capacity building proposals supported by Quality Education Strategic Support Programme (QESSP) II	QESSP Fund Manager selected and contract signed.	The British Council selected as QESSP Fund Manager and contract signed in December 2014. The inception phase successfully completed and the steering committee endorsed the annual programme of work approved with activities focusing on capacity building, technical assistance and evidence generation. / (Indicator score: A
No. of supervisors and directors exposed to quality and relevant short term leadership training annually (%female)	0	N/A

Key Points

- Beyond inception phase deliverables, QESSP has already delivered some immediate priorities including preparatory work for the development of a 10 year road map and the next five year education sector development plan (ESDP V). First indicator exceeded expectations.
- QESSP steering committee formed consisting of the Minister of Education, the State Minister for General Education, DFID, British Council as the fund manager, and the current co-chair of Education Technical Working Group (ETWG). Representatives from the Regional Education Bureaus (REBs) are being sought and will be confirmed soon.

Summary of responses to issues raised in previous annual reviews (where relevant)

N/A

Recommendation

There was a long delay in releasing the 2013/14 EMIS annual report. The MoE needs to re-think how to enhance its EMIS capacity so as to generate a timely report on the education data. The scope of QESSP support to this area has been agreed.

Output Title	Improved use of ICT to enhance the quality of education
Output number per LF		5	Output Score	A
Risk:		High	Impact weighting (%):	15%
Risk revised since last AR?		NA	Impact weighting % revised since last AR?	NA

Indicator(s)	Milestones	Progress
Information and Communication Technology in Education Policy formulated, approved and used by all stakeholders to guide initiatives.	Terms of Reference (TOR) / developed and agreed	TOR developed and reviewed by the World Bank technical experts. The MoE to incorporate and send the bid document to the World Bank for no objection. / (Indicator score: A )
Schools equipped with energy efficient Information and Communication Technology (ICT) labs	Sample schools selected	The MoE has identified 300 secondary schools based on the following criteria: access to internet; availability of power; availability of suitable and furnished computer labs; and distance from main road. / (Indicator Score: A)

Key Points

- The milestones for both indictors have been achieved. However, as this is a new component that was not part of GEQIP I, successful procurement will be critical.
- MoE needs to commission local/international consultancy to help with the development of e-learning applications, content development and technical assistance to conduct capacity assessment of the ICT centre and development of a proposal for an autonomous education ICT agency.

Summary of responses to issues raised in previous annual reviews (where relevant)

NA

Recommendations

The yet to be appointed team of consultants together with the MoE need to identify lessons learnt and good practice (and failures) from other African countries and factor these into the ICT policy and implementation strategy.

The MoE ICT directorate will need to build maintenance contracts into the costs of this component.

Output Title	Improved co-ordination, monitoring and evaluation
Output number per LF		6	Output Score	A
Risk:		Medium	Impact weighting (%):	10%
Risk revised since last AR?		NA	Impact weighting % revised since last AR?	NA

Indicator(s)	Milestones	Progress
% Implementing Agencies providing timely inputs to GEQIP annual planning exercise and GEQIP six monthly reports	80%	All implementing agencies contributed to the annual work planning exercise. Implementing agencies include 11 MoE directorates, 11 REBs, 10 universities and 36 Colleges of Teachers Education. MoE has also received six monthly reports from all implementing agencies. This ensured 100% involvement from all relevant implementing agencies. However, the semi-annual progress report submitted to the World Bank and DPs, covering the period Feb to July 2014 was late, incomplete and lacked information on key indicators outlined in the project document. / (Indicator score: A)
Evidence base on impact of reforms aimed at improving the quality of education	No milestone as QESSP only started the implementation phase	N/A

Key Points

- Milestone for this output is met. However, although participation in the annual work plan exercise was high, the actual quality, timeliness and consistency of different institutional plans and reports varied considerably.
- A significant number of contract staff are not in place in the project coordination office and component directorates because the salary cap MoFED has put in place has failed to attract suitable candidates. The way forward on this is currently being discussed.
- The MoE organised a workshop to revise the 2014/15 Annual Work Plan in February 2015 and it will submit the 2015/16 work plan by May 2015.
- Monitoring & Evaluation has already been identified as a challenge, and in particular access to accurate data. However, the impact and management of school grants for GEQIP I has been independently evaluated and captured in the evaluation report. In addition GEQIP I school grant audit has been conducted by the audit service corporation under the Office of the Federal Auditor General (OFAG). This process will be maintained for GEQIP II.
- Co-ordination, joint government and partner reviews, are carried out every 6 months. The scope of these reviews will be enhanced to ensure effective management of risks to/in the programme.

Summary of responses to issues raised in previous annual reviews (where relevant)

N/A

Recommendations

Consider amending the first indicator and/or its milestones to focus on quality rather than just quantity and timeliness of information.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

The key cost drivers for GEQIP II, as set out in the Business Case are:

- Cost of school grants
- Unit costs of textbooks
- Unit cost of enhanced pre-service training for primary and secondary teachers
- Unit cost of upgrading teachers qualification (in-service training)
- Cost of Information and Communication Technology (ICT) infrastructure in secondary schools

The table below describes how much of the financing will be directed to the cost drivers in the life time of the project.

Cost driver	Estimated cost	% from the total project cost
School grant	USD $248,950,000	45%
Teaching and learning materials	USD $ 104, 264,814	19%
Pre-service teacher training	USD $ 19,700,000	3.6%
In-service teachers training	USD $ 29,800,000	5.4%
A national ICT infrastructure Improvement	USD $ 28,430,000	5.2%

The Value for Money (VfM) framework[2] developed for DFID Human Development Programmes suggested additional VfM indicators as only a few of the indicators in the business case lend themselves to be a valid VfM indicator for this programme. The following are additional VfM indicators suggested by the study and the progress on some of the indicators since the September 2014 annual review:
[2] Itad ltd

1. Average cost per textbook (a measure of Economy): Average cost calculation needs to include not only cost of printing of books but transportation and distribution costs to schools, and this measure needs to be compared with the unit costs in sub-Saharan African countries. Ethiopia’s current primary text book unit costs of £0.7 is also much lower than in most sub-Saharan African countries (Tanzania £1.5, Kenya £2.43, Nigeria £3.2).
2. Total cost per primary teacher trained (a measure of Economy): This measure needs to take account of both initial teacher education and continuing professional development costs – for example of upgrading primary teachers from certificate to diploma. This will need to assess the extent to which student-centred strategies are in use and needs to look the data from comprehensive evaluation. Currently it takes about £120 per year to upgrade the qualification of a teacher through in-service training. The World Bank’s financing review is expected to provide full cost data on this and the above indicator;
3. Average price of computer labs installed and operational in secondary schools (a measure of Economy): This measure should include both purchase and installation. Maintenance might also have to be included if there is a standard maintenance contract. This measure needs to be compared with the cost in other African countries. We could not assess this indicator at this stage as procurement of computers is not yet finalised and computer labs not installed in secondary schools;
4. Cost per primary pupil educated (a measure of Cost-Effectiveness): The ultimate measure of this cost driver will rest with learning outcomes of students and needs to look at the data from the National Learning Assessment which is not yet available. According to DFID’s 2013/14 updated VfM Matrix in Education, getting a child into primary school in Ethiopia costs an average of £22 a year compared to £42 in Tanzania, £60 in Mozambique, or £166 in Nigeria. This is as a result of low wages and low cost of teacher training.
5. Procurement processes completed on time (a measure of Efficiency): The theory behind including this is that key deliverables such as textbooks, computer labs, training delivered early are more likely to lead to achievement of programme objectives and milestones. Procurement of textbooks and goods and services is progressing slowly and future reviews will assess their efficiency.
6. Receipt of school grants - speed of delivery by system (a measure of Efficiency): The timely receipt of school grants means more immediate impact on provision of necessary inputs that can impact on the quality of education. However, the school grants disbursement has been significantly delayed this year partly because of the late start-up of the programme and late disbursement of funds.

VfM performance compared to the original VfM proposition in the business case

It has been a year since the project has effectively started however, procurement of many of its components are still underway and complete data and information on costs is not yet available to make a valid assessment at this time. Procurement of many of the components is expected to be finalized by December 2015 and the next annual review will be in a position to assess VfM using the proposed matrix above. The next review can also use costing data coming from the procurement processes and the most up to date expenditure data from the financing review.

Assessment of whether the programme continues to represent value for money

Based on the above and given that GEQIP II builds on arrangements (e.g. bulk purchases of text books and use of government systems) that were assessed to have delivered good VfM in the first phase of GEQIP, the programme will continue to represent VfM. There are opportunities to increase VfM in the second phase based on lessons learnt from the previous phase. VfM cannot be fully assessed at this stage of the programme as many of the inputs are still being procured and that effectiveness assessment would partly depend on data on improved learning outcomes as a result of GEQIP II. Future reviews will continue to track VfM at economy, efficiency and effectiveness levels.

Quality of financial management

The 2nd joint implementation support mission conducted from January 26 - February 6, 2015 concluded that there is a reasonable adequacy that the financial management system in place provides the necessary assurance that donor funds are being used for the intended purposes and that reports produced by the system can be relied upon to monitor the project. However, the following are identified as key issues requiring management attention, action and follow up:
- Budget Preparation: - The budget preparation of the project needs be further strengthened with regard to its timeliness and quality. The annual work plan and budget preparation for 2014/15 fiscal year initially required series of revisions to get approval from the World Bank hence the approved budget for the project was available only after one quarter of the fiscal year has ended. Losing a quarter’s implementation will affect the implementation of the programme;
- Budget Utilisation: - Utilisation of budget has been reported low during the first year. However, two factors explain this (i) delayed start-up of the project and as a result delayed approval of work plans and disbursement of funds, which subsequently caused (ii) delayed transfer of school grants. In many places, districts did not transfer funds to schools as the first tranche reached them too close to the end of the last academic year when schools close. This meant that Interim Financial Reports (IFRs) report very low utilisation rates because the grants that represented about 70% of total disbursement during the year cannot be treated as expenditure until funds reach schools. The latest IFR covering quarter ended 07 January 2015 indicated improvement budget utilisation of 26%. However, the World Bank together with the Development Partners need to continue to push and support the MoE to put plans in place to speed up implementation of the programme.
- Budget Monitoring and Control: - The Interim Financial Report (IFR) submitted to the World Bank show the budget versus actual expenditure of the programme components. However, there is no explanation provided as to the low budget utilisation rate not allowing management to easily identify the bottlenecks and challenges noted during the implementation. Future IFR needs to capture the bottlenecks and challenges noted during the implementation to take corrective measures.

The project has one senior accountant at MoFED Channel One Project Coordination Office and the recruitment of another accountant is underway. All regional Finance and Economic Development offices have recruited accountants except Dire Dawa and Tigray which opted to assign their staff. MoE is also adequately staffed with finance officers for the programme.

The initial training for all GEQIP accountants which was planned for October 2014 has not materialised to date and MoFED has planned to conduct the training in March 2015. The World Bank needs to follow up on this for the training to happen on the newly planned period. On the other hand, 4 accountants consisting of MoFED and MoE had travelled to Nairobi to take a course on project financing and Financial Management in World Bank operations. The project has submitted the IFRs timely with acceptable quality to the World Bank.

Summary of Disbursement

Year	Disbursement to MoFED from the World bank	Expenditure	Variance
2013/14 / 2014/15	$55 Million - April 2014 / $55 Million – December 2014	Out of the total ($110 million) resources so far disbursed only 33% has been utilised which is around $37 million	$73 Million (Much of this balance includes school grant transfers to districts that are not treated as expenditure until they reach schools).

The financial management challenges have been discussed in the second implementation support mission of the project and key action points have been identified including closer monitoring of the budget utilisation of the project. Action plans are in place to improve utilisation and we will continue to monitor levels of expenditure through the quarterly IFRs. The next IFR due by the end of March 2015 is expected to show better levels of utilisation.

Date of last narrative financial report	The second Interim Financial Report (IFR) for 2014/15 is expected by the end of June 2015.
Date of last audited annual statement	The first audit report of the project covering the period from project effectiveness of February 18, 2014 to July 7, 2015 will be submitted to the Word Bank in January, 2016.

E: RISK

Overall risk rating: Medium

The solid foundation developed under the GEQIP I is a good justification for retaining this assessment in the Business Case. The strengthening of financial management particularly budget utilisation at various levels, procurement and Monitoring & Evaluation, particularly at decentralised levels, will be a key factor in ensuring that the risk level remains at medium throughout the life of the programme.

Overview of programme risk

There may be some possible risks in relation to supporting government to improve the quality of general education and their resettlement programmes. Since GEQIP II is a nationwide programme supporting schools in all parts of the country including in newly established Commune Development Programme (CDP) areas. Per capita grants are calculated based on the enrolment of students in each government schools and hence it is possible to trace the school grant allocation for each school including schools CDP/ and other resettlement areas.

The World Bank’s Indigenous People’s Safeguard (OP4.10) was triggered during the project appraisal and an enhanced social assessment was conducted. The entire GEQIP II Multi Donor Trust Fund, including DFID’s funds, is subject to this safeguard, known in Ethiopia as the policy for Vulnerable and Marginalised Groups. The enhanced social assessment conducted during the design of GEQIP II did not identify any issues to do with resettlement. DFID has worked closely with the World Bank, the GoE and other donors to ensure that safeguards are well incorporated throughout the key guiding documents of GEQIP II and are applied to all donor funds. We will continue to monitor operational risks arising from the implementation of other programmes in CDP/ and other and resettlement areas.

The first and second implementation support missions did not specifically look at safeguards issues since not much has been implemented as part of the project activity. It is agreed that future implementation support missions will look closely monitor issues related to safeguards and associated risks. We do have on-going concerns on the World Bank’s capacity to monitor and mitigate the risk associated with GoE resettlement programmes. We are pushing them to increase their capacity in this area. We are in discussion with the World Bank on how future supervision missions can be enhanced to review progress against the recommendations of the social assessment.

There are still some risks related to procurement capacity at all levels of the GoE and limited understanding of the World Bank procurement procedures. The agreed institutional arrangement for the implementation of the procurement aspect of the project is partially in place and a procurement team has been established for the GEQIP II under the procurement directorate of MoE. It has been noticed that procurement of textbooks and goods and services is progressing including the procurement of a consultant who has been involved in the processing of procurement of goods and services. But this needs to be monitored closely to make sure that other procurement processes for goods and consultancy services are in place on time.

Outstanding actions from risk assessment

How the monitoring of social safeguards is being undertaken needs to be assessed during the next annual review. DFID need to follow up with the World Bank on regular bases and ensure it is going to be done as planned.

Need to make sure that all procurement staff have a good understanding of the World Bank procurement procedures.

The World Bank should arrange more regular coordination meetings and demonstrate their commitment to regularly communicate with all the Development Partners.

DFID should update the risk matrix for the programme on a quarterly basis

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

In general, GEQIP is making progress towards its objectives although progress is uneven. The main exception is the School Grant disbursement which has experienced major delays. The MoE has now agreed to delink the school grant disbursement timeframe from other components of the project which could make a significant difference.

Regarding the establishment of QESSP II; a winning Fund Manager has been identified and contract has been signed in December 2014. There was a long delay in identifying QESSP Fund Manager however; things are moving as planned after the signing of the contract.

Fund disbursement table

Programme	Forecasted	Disbursed
GEQIP II	£30 million - May 2014	£ 30 million- June 2014

Performance of partnership (s)

Overall the performance of partnerships appears to be satisfactory. The GoE through the MoFED and MoE have maintained their political commitment to improving quality of education through GEQIP. The Planning and Resource Mobilisation Directorate continues to lead on the coordination of the programme and they have managed to act on several of the initial processes (such as the annual work plan and re-planning). Progress on identifying additional staff for capacity building in financial management and procurement has also been made.

Contributions by financing partners have been good. DFID, the Embassy of Finland, Italian Development Cooperation, the World Bank and Global Partnership for Education (GPE) have maintained their commitments.

Asset monitoring and control
All GEQIP II assets are governed by the Ethiopia’s public finical management systems. The QESSP Fund manager has a well organised assets register system. All assets from the project so far have been captured by the assets register system and DFID will conduct asset spot checks bi-annually including surprise checks and the outcome of the check will be acted upon and documented.

G: CONDITIONALITY

Update on partnership principles (if relevant)

DFID has judged that the provision of DFID’s funding to this programme should be dependent to the Partnership Principles. The 2014 assessment judged that the Government of Ethiopia remains committed to the partnership principles to continue sector financial aid; however, continuing concerns with regard to civil and political human rights prevent us from considering a return to general budget support. DFID’s new Partnership Principle Assessment (PPA) guidance (March 2014) recommends that offices may want to consider undertaking a programmatic partnership principles assessment ahead of disbursements for specific programmes that are channelled through government systems. To inform the disbursement in June 2014, DFID Ethiopia conducted a Programme Level PPA. The Programme Level PPA judged that there is no new or additional information since the country level PPA was conducted and judged that the Government has shown strong commitment to improving education services and there was sufficient evidence of their commitment to the partnership principles to allow DFID’s first disbursement to the Multi Donor Trust Fund.

Another programme level PPA will be completed before the next disbursement in June 2015.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

The GoE and development partners have agreed on a Results Framework to conduct timely assessment of results generated by GEQIP II including its impacts on institutional strengthening and improving learning outcomes of students. The key indicators of the Results Framework are: student textbook ratio, use of active teaching approaches by teachers, utilization of the school grants for improving teaching and learning at the school level; completion of school report cards at the district level; and, reduction in dropout rates at grade 1 and improvement in the ratings of schools.

Three surveys are envisaged to be carried out during the project period. These are i) an assessment of the impact of the Teacher Development Programme, ii) school grant evaluations (mid-term and exit), and iii) mid-term and comprehensive evaluation of the project. In addition, the MoE and DPs have agreed to have joint high – level monthly meetings, and a jointly monthly field visits to the implementing entities.
Accordingly two high - level meetings were held in November and December 2014 focusing on textbooks and Teacher Development respectively. Field visits to Oromia and Southern regions were also undertaken in September and October 2014 respectively. In addition, the MoE reported that the State Minister for General Education undertakes regular meetings with component directorates to follow-up implementation and address key challenges.

The GoE and GEQIP II funding partners carried out the second joint implementation support mission in January 2015. This mission reviewed GEQIP II progress by component and provided support to resolve key technical issues; including timely disbursement of school grant and sound budget utilisation; and carried out a procurement and financial management review.
Monitoring progress throughout the review period
The review is updated by Rahel Yergashewa - (DFID-E Education Adviser). The core team of the original review included Richard Arden (DFID South Sudan, Essential Services Team Leader, and Senior Education Adviser) and Rahel Yergashewa. The review team carried out interviews with key stakeholders from the GoE at federal level including MoE (Director, Planning and Resource Mobilisation, GEQIP Operation Manager, MoFED (GEQIP II accountant), and a primary school head teacher. Meetings and discussions were also held with the World Bank, Finland, and DFID Ethiopia Human Development team members and economists.

A number of key documents were also consulted as part of this review including:

1. GEQIP BC and Logframe
2. Report on Strengthening DFID Ethiopia’s Tracking of Value for Money in its Human Development Programmes
3. Ethiopia GEQIP II World Bank first and second Implementation Support Missions – Aide Memoires – July 31st 2014 and January 2015 respectively
4. MoE School Grant Guidelines
5. MoE Work Plan Template
6. World Bank Results/Outputs Template

The updated review has been quality assured by Belay Addise (DFID –E Education Adviser and Senior Responsible Owner (SRO) for the programme). The original review has been Quality Assured within DFID Ethiopia by Jyoti Shankar Tewari (Senior Human Development Adviser) and Angela Spilsbury (Human Development Team Leader) and OPEX. Their comments have been incorporated.