Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Animal Health and Veterinary Science Specialist / Livestock Inc. Ltd
Programme Value: £100k		Review Date:15/06/2015
Programme Code: / 204823	Start Date: / 01/08/2014	End Date: / 31/07/2015

Summary of Programme Performance
Year	2014/15
Programme Score	A
Risk Rating	L

Summary of progress and lessons learnt since last review

The Department for International Development does not hold in-house the expertise to provide specialist inputs and advice on aspects on a range of animal health research programmes. For this reason the Agriculture Research Team contracted Livestock Inc. Ltd for a 1 year period to provide this specialist input. .

This support covers advice on inter alia Trypanosomosis, Bovine TB, brucellosis, East Coast Fever, Contagious Bovine Pleuropneumonia, Newcastle Disease, Hermorrhagic Septicaemia, Contagious Caprine Pleuropneumonia, Rift Valley Fever, Sheep and Goat’s Pox, Peste des Petits Ruminants and Classical Swine Fever.

It was anticipated that this would involve up to 2 days per week on a call down basis and would include a small amount of overseas travel. The duration of the work was initially for a 12 month period, with a 6 month review point and an option to extend.

The consultant has provided high quality technical advice in a timely manner. The advice provided is well grounded in development realities and the consultant has very quickly established excellent relationships with all external partners.

Summary of recommendations for the next year

The contract with Livestock Inc Ltd should be extended to 31/07/2016.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	Insert link here
DevTracker Link to Log frame:	n/a

Outline of the programme

The Department for International Development required specialist inputs and technical advice to the Research and Evidence Division’s Agriculture team on the technical animal health aspects of a range of agriculture and animal health programmes.

This was to cover technical specialist advice on inter alia Trypanosomosis, Bovine TB, brucellosis, East Coast Fever, Contagious Bovine Pleuropneumonia, Newcastle Disease, Hermorrhagic Septicaemia, Contagious Caprine Pleuropneumonia, Rift Valley Fever, Sheep and Goat’s Pox, Peste des Petits Ruminants and Classical Swine Fever.

Specifically we required technical support to the following programmes:
GALVmed Phase 2. http://www.galvmed.org/ DFID established and funds in collaboration with Bill and Melinda Gates Foundation (BMGF).

Biotechnology and Biological Sciences Research Council (BBSRC)

a) Combating Infectious Diseases of Livestock for International Development (CIDLID) programme

b) Zoonoses and Emerging Livestock Systems (ZELS)

1. Agresults. The component programmes of AgResults which include a livestock disease element.
2. DFID-BMGF Strategic Collaboration on agricultural research: Bovine TB, East Coast Fever, and potentially CBPP, as well as funding to Diagnostics for All (including low cost diagnostic tools for aflatoxins, estrus, milk spoilage, bovine heat detection).
3. Development Impact Bond for Sleeping Sickness in Cattle - Inception work for a new private sector financing instrument (DIB Inception Programme).

Specific tasks:

Technical advisory inputs on GALVmed, particularly with regard to an external evaluation and participation in Steering Committees.

Technical inputs to annual reviews and monitoring progress of all BBSRC programmes with a livestock component.

Technical inputs to finalise programme design of GALVMED Tryps Phase 2, including preparing a Business Case for DFID support and provide on-going technical inputs.

Technical advice on AgResults design work for new pull mechanisms for research and development of livestock vaccines (tryps and brucellosis) and research and development and delivery work on Newcastle Disease.

Technical advice to DFID-BMGF strategic research collaboration on bovine TB, East Coast Fever, Contagious bovine pleuropneumonia (CBPP) and Diagnostics for All.

Technical advice on an inception phase of a development Impact Bond for Sleeping Sickness to reduce the prevalence of sleeping sickness in cattle.

The consultant has provided high quality technical advice in a timely manner. The advice provided is well grounded in development realities and the consultant has very quickly established excellent relationships with all external partners.

In particular the technical advice provided to assist the team to manage the creation of a private sector Development Impact Bond for sleeping sickness in cattle would not have been possible without the technical support provided. The consultant was able to provide extensive technical expertise around the treatment of the disease in cattle and provide guidance on the sampling done to identify the disease. In addition a detailed financial analysis of actual costs involved in this complex programme which allowed us to verify whether the costs of the impact bonds offered by Social Finance offered value for money.

The consultant also provided high quality inputs to the AgResults programme. In particular providing inputs on the Newcastle Disease vaccine pilot for Odisha in India, and the development of the brucellosis pilot. He attended the AgResults steering committee meeting, and provided inputs on the Annual Review. He has quickly become well respected by the AgResults SC, Secretariat and Evaluator for his technical inputs and advice and is providing valuable technical assistance and guidance to the design process.

B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

The consultant is expected to continue to achieve the outcomes of this consultancy. He has provided high quality technical advice in a timely manner. The advice provided is well grounded in development realities and the consultant has very quickly established excellent relationships with all external partners.

Overall output score and description

A

Key lessons

Having the appropriate technical skills to manage complex animal health programmes is vital to the management of our substantial livestock programmes. Without this there is a reputational risk to DFID that we cannot effectively manage our substantial investments in this area.

Key actions

As DFID still do not have Animal Health expertise in house it is recommendation that the existing contract is extended to cover a second year of technical support to 31/07/20-16. There are currently sufficient funds remaining in the original BC to cover this.

Has the logframe been updated since the last review?

This programme does not have a logframe.

C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	To provide specialist inputs and advice on aspects on a range of animal health research programmes. Including inter alia Trypanosomosis, Bovine TB, brucellosis, East Coast Fever, Contagious Bovine Pleuropneumonia, Newcastle Disease, Hermorrhagic Septicaemia, Contagious Caprine Pleuropneumonia, Rift Valley Fever, Sheep and Goat’s Pox, Peste des Petits Ruminants and Classical Swine Fever. / A longframe was considered not necessary for this programme.
Output number per LF		N/A	Output Score	A
Risk:		Low	Impact weighting (%):
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
N/A	N/A	N/A

Key Points

The consultant has worked to the terms of reference provided and
exceeded expectations. He has provided high quality technical advice in a timely manner.

To do this, the consultant has worked well with a number of DFID technical/programme staff and key external partners. He has provided the high level specialist veterinary support necessary to monitor a number of high profile programmes including the development of Impact Bond for Sleeping Sickness in Cattle - Inception work for a new private sector financing instrument (DIB Inception Programme) and DFID-BMGF Strategic Collaboration on agricultural research: Bovine TB and East Coast Fever.

Summary of responses to issues raised in previous annual reviews (where relevant)

This is the first annual review.

Recommendations

Having the appropriate technical skills to manage complex animal health programmes is vital to the management of our substantial livestock programmes. Without this there is a reputational risk to DFID that we cannot effectively manage our substantial investments in this area.

D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

VfM performance compared to the original VfM proposition in the business case

This programme continues to offer DFID good value for money.

Assessment of whether the programme continues to represent value for money

Yes. Costs have been held as agreed in the initial contract.

Quality of financial management

There have been no concerns around the financial management of this contract.

Livestock Inc Ltd invoice on a quarterly basis against actual days worked and travel costs incurred. Time sheets are provided with invoices. Details of actual fees and travel expenses are detailed in the attached proforma invoice. The travel expenses are an up to amount and are expended as per requirement. All travel expenses are reimbursed, against receipts.

Date of last narrative financial report	Add
Date of last audited annual statement	Add

E: RISK (½ page)

Overall risk rating: Low

Management risk is low. Payments are made quarterly in arrears. And the consultant has a reliable track record of supplying good quality technical support.

Overview of programme risk

Outstanding actions from risk assessment

N/A

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

This programme has delivered against its planned timeframe.

Performance of partnership (s)

N/A

Asset monitoring and control

N/A

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

N/A

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

N/A

Monitoring progress throughout the review period

A rolling workplan has been agreed throughout this year by the RED Agriculture Research team leader and research manager which has worked very well. Feedback has also been generated from the Programme teams who call down on the consultant’s time. Feedback on the technical support provided has been very positive.

Smart GuideThe Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessmen
Key points
Summary of response to iprogrammessues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process