Project Completion Review - Top Sheet

This Top Sheet captures the headlines on the programme performances performance over the course of its lifetime. Teams should attach summary sheets from each annual review over the life of the programme.

Review Date:	June 2015

Title: Short Term Technical Co-operation support to the St. Helena Government to deliver public services and help prepare for air access from April 2014 to March 2015
Programme Code: 203507	Start Date: 01/04/2014	End Date: 31/03/2015

Summary of Programme Performance

Year	2014/15
Programme Score	A
Risk Rating	Low

Financial Position

Original Programme Value	£2,000,000
Extensions/ amendments
Log-frame revisions (with dates)	Gaps in the logframe were filled in May 2015 as part of the Project Completion Report (PCR) process.
Total programme spend	1,902,266.00

Follow up actions required following closure
DFID paid St Helena Government (SHG) £1,902,266 in respect of Short Term Technical Cooperation for 2014/15. SHG’s forecast spend for the full year in March 2015 was £1,747,694. DFID and SHG need to discuss this possible underspend.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/4437396.odt
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/4437395.xlsx

Outline of programme and what it has achieved

- As a result of physical, social and human capacity constraints, three Overseas Territories (Montserrat, Pitcairn and St. Helena) have substantial budget deficits resulting in long-term financial dependence on the UK Government.
- The DFID Overseas Territories Operational Plan includes two pillars relevant to St Helena.
  - Pillar 1: To meet the “reasonable assistance needs” of OT citizens cost effectively.
  - Pillar 2: To accelerate aid-dependent OTs towards self-sufficiency
- This project supported these priorities. It provided the St. Helena Government with short-term technical co-operation expertise where these needs could not be met from local resources and human capacity (in critical areas such as education, health, access and social protection).
- During the course of FY 2014/15 Short Term Technical Cooperation support was delivered through this standalone project. Long Term Technical Cooperation support was delivered through Budget Aid. For 2015/16 both forms of Technical Cooperation will be delivered through Budget Aid.

Planned outputs
- (i) Improved effectiveness of public service provision measured against SHG’s Sustainable Development Plan targets;
- (ii) Improved human resource capacity available in SHG and in accordance with the Technical Cooperation Protocol 2012.

Performance on some logframe indicators has been disappointing. However DFID OTD staff are confident that public service delivery standards would suffer in the absence of support provided through Short Term Technical Cooperation.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Overall Outcome Assessment
- Outcome: Improved effectiveness of public service provision measured against SHG’s Sustainable Development Plan (SDP) targets.
- Outcome Indicator 1: Number of SDP targets achieving “green status”
  - 2014/15 Target: 75% rated green, reds are not above 19%
  - 2014/15 actual achieved: 39% Green, 22% Amber, 17% Red, and 3% Amber-Red. For the remaining 19% benchmarks/targets were still being established for the indicators.
- The evidence provided on actual achievement suggests this outcome was not met.
- However SHG has explained that indicators and targets were changed during August 2015. This change included more stretching targets in areas such as utilities and visitor numbers.
- It is difficult to draw strong conclusion about the effectives of public service provision given the mid-year changes. In June, before any changes were made only 5 out of 27 indicators were rated green (data was reported for 21 indicators).
- In any case this is a composite indicator that aggregates too much and is not particularly informative or revealing.
- Given the information available it is difficult to definitively conclude that outcome was met.

Output Score and Description
- Output 1: Improved effectiveness of public service provision (measured against STTC outputs and a selection of prioritised SHG sector targets.
  - Score: B
- Output 2: Improved human resource capacity available in SHG and in accordance with the DFID TC protocol.
  - Score: A

Lessons and how these have been shared
DFID OTD has concluded that Short Term Technical Co-operation should no longer be funded through a distinct project. For 2015/16 Financial Year it will be funded through Budget Aid, as is the case for Long Term Technical Co-operation. This will reduce transaction and time costs for both DFID OTD and SHG staff.
- SHG reviews Technical Cooperation and seeks to implement lesson learning through fortnightly meetings of the SHG Business Delivery Group (BDG) chaired by the Chief Secretary. The SHG BDG seeks to reduce Technical Cooperation costs by encouraging more succession planning and training to build local capacity.
- DFID now has an updated Technical Cooperation protocol based on lessons learned over the 2014/15 Financial Year.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Output 1: Improved effectiveness of public service provision (
Output number per LF		1	Output Score	B
Risk:		Medium	Impact weighting (%):	50%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
1.1: Effective use made of the STTC budget provision measured by percentage of TC outputs/reports delivered on time and to standard	SHG inputted target: / % of officers completing against total posts (28%) / % of officers delivering to required standard on time against total completing (100%)	SHG inputted achievement / % of officers completing against total posts (29%) / % of officers delivering to require standard on time against total completing (58%).
1.2: Percentage of prioritised capital programme delivered	100% prioritised capital programme delivered	30%
1.3 Completion of the child safeguarding action plan and delivery of 2014/15 objectives.	Target March 2015: Completion of the child safeguarding action plan and delivery of 2014/15 objectives	SHG input: “The Action Plan is a live document and will be updated continually. In terms of the original Plan, drafted in early 2014, around 85% is complete or in hand.”

Key Points
Output Indicator 1.1:
(a) This indicator measures the % of Short Term Technical Cooperation C officers who leave their posts (for whatever reason). This is of little intrinsic interest. 12 out 42 officers left their post.
(b) Of those 12 individuals leaving post, 58% delivered to required standards, falling short of the 100% target. SHG have explained:
  - One officer did not complete an end of contract report.
  - One officer did not fully meet their targets
  - Two officers Terms of Reference were affected by staff turnover and shifting demands :
Output Indicator 1.2: The Capital Programme, has 17 projects, at the end of March 2015 these were rated as follows:
    - 3 Green
    - 1 Amber
    - 13 Red
The following factors, identified in the recently completed Annual Review, have contributed to this situation:
- Lack of clarity about project requirements and the scope and specification of the work to be undertaken, resulting in frequent adjustment and delay.
- Poor quality of project concept notes and Project Information Documents (PIDs). And related to this, over ambitious project milestones, which have not been reviewed since the project start date.
- Limited human resources to undertake project work, especially sub-contractors and individual specialists. This is in part due to the airport project offering more attractive and /or better re-numerated work to the limited number of on-island contractors or individuals.
- The high degree of project inter-dependency, e.g. the start of one project activity being dependent on the completion of another.
- Limited capacity of project managers to foresee and mitigate issues before they occur, coupled to limited accountability to deliver results on time and on budget. This is related to the Capital Programme’s management structure.
- SHG has recognised these problems and is responding to them with a raft of measures including the establishment of Project Boards, the recruitment of a project manager for the Capital programme, and a review of all Project Initiation Documents. In general, the Capital Programme Delivery Group is demanding more accountability from Departments undertaking capital projects. The situation is slowly but steadily improving.
- Output Indicator 1.3: The Safeguarding Children’s Board are implementing the Child Safeguarding Action Plan and have made significant improvements to Safeguarding arrangements on the island. This has included:
  - the development of the Safeguarding Directorate,
  - recruitment of key staff,
  - delivery of training,
  - specialised equipment such as body worn cameras for the police
  - raising the profile of Safeguarding across all agencies and the general public.
- For 2015/16 DFID has provided additional resources in its budget settlement specifically to increase SHG’s resources for child safeguarding and this will enable the island to deal with new and historic cases of sexual abuse, support victims, improve resilience, improve staff competencies and improve SHG’s residential estate. DFID OTD staff believe SHG is making good progress on this issue.

Summary of responses to issues raised in previous annual reviews (where relevant)

Recommendations for future programmes
- Logframe is kept up to date.
- SHG respond to issues raised in the Key Points section above in relation to the Capital Programme.
- DFID and SHG discuss measures to improve the quality of Technical Cooperation officers (only 58% met required standards). This could include being even more selective and filling fewer high priority vacancies.

Output Title	Output 2: Improved human resource capacity available in SHG and in accordance with the DFID Technical Cooperation protocol 2012.
Output number per LF		2	Output Score	A
Risk:		Medium	Impact weighting (%):	50%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
2.1 Percentage of critical STTC posts agreed between SHG and DFID filled, and accompanied by agreed ToRs and contracts	SHG input: 95% posts successfully recruited (May 2015)	71% of posts successfully recruited
2.2 Streamlined recruitment and induction processes for Technical Co-operation.	December 2014: Action Plan implemented	Recruitment process was agreed at BDG in October 2014

Key Points
- Output Indicator 2.1
  - 95% was a stretching target. There was some overprogramming – SHG spent most of the approved budget – there was not room to recruit additional expertise.
  - Recruitment of Technical Cooperation officers to St Helena is difficult for various reasons:
    - St Helena is remote and isolated.
    - TC roles often cut across disciplines and need individuals who can specialise as well as offer general skills.
    - Remuneration packages are not sufficiently attractive/competitive.
    - Quality/calibre of interested applicants is often low.
- Output Indicator 2.2: A new recruitment process was agreed in SHG’s Business Delivery Group meeting in October 2014. DFID OTD staff are satisfied SHG made reasonable efforts to recruit staff where needed.

Summary of responses to issues raised in previous annual reviews (where relevant)

Recommendations for future programmes
Logframe should be kept up to date with realistic targets.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

- Key cost driver: The salary, allowances (COLA and housing) and transportation required in the provision of international technical expertise.
- SHG expect recruitment will be easier when air access to St. Helena is established.
- DFID paid out less than expected: £1,902,266 instead of £2,000,000. SHG’s forecast spend for the full year in March 2015 was £1,747,694. DFID will discuss the difference between these sums with SHG.

Performance
Performance on logframe output and outcome indicators did not meet expectations in several areas. However the value and benefits of this programme are not fully captured by the logframe indicators. DFID OTD staff believe public service delivery standards would suffer in the absence of Short Technical Cooperation support.

VfM performance compared to the original VfM proposition in the business case
- DFID Advisory and Programme Management staff approve all Terms of Reference with a view to ensuring value for money. Programme staff and Advisers should continue to ensure ToRs include succession plan and building local capacity.
- DFID OTD require SHG to prioritise Technical Cooperation requests/needs and review priority lists to ensure they provide value for money. DFID funding is restricted for priority posts identified by SHG ensuring VfM is maximized.

Assessment of whether the programme represented value for money
- DFID OTD staff, based on the experience of Budget Aid Missions and other advisory visits, believe that public service delivery standards would suffer without technical co-operation.
- The UK Government is committed to meeting the reasonable assistance needs of St. Helena citizens. SHG would be unable to access relevant expertise without DFID financing. Short Technical Cooperation support helps DFID meet the reasonable assistance needs through SHG cost effectively.
- Without such support DFID would face higher transaction costs and difficulties in its engagement with SHG. It would need to intervene and monitor SHG much more closely. This would require DFID OTD employ more staff to work on the St. Helena portfolio. St. Helena is remote and difficult to access; regular and short notice trips to St Helena are not an option. Risks to DFID’s reputation could also increase.

Quality of financial management during programme
- This was one year project to finance SHG’s use of Technical Cooperation expertise. 2014/15 is now complete.
- The Memorandum of Understanding (MoU) statement for Short Term Technical Co-operation for 2013/14 have been approved by the St Helena Audit Service. The statement for Short Term Technical Co-operation 2014/15 are now with the St. Helena Audit Service for completion.
- SHG are required to provide audited accounts within 9 months from the end of the project (31/03/2015) – that is, by December 2015.

Date of last narrative financial report
Date of last audited annual statement

E: RISK (½ page)

Quality of risk management over the life of the programme
- A key risk was SHG not being able to spend most of its allocation as a result of not recruiting enough individuals (the difficulties of recruiting to St Helena have been discussed above). DFID provides enough funding to cover the posts SHG is likely to fill. Based on previous experience SHG cannot run a full complement of posts due to delays in recruitment and people leaving post during the year. Therefore an adjustment is made to the budget required.
- Another risk is that SHG is unable to manage Technical Cooperation to deliver effective outcomes. The Chief Secretary is responsible for the effective use of Technical Cooperation. SHG Directorates have performance management and appraisal/reporting systems in place to ensure Technical Cooperation inputs deliver desired outputs.
- A Fiduciary Risk Assessment (FRA) was completed in April 2015. The FRA concluded that there is substantial fiduciary risk and moderate risk of corruption. Reasons given for this assessment included: limited strategic vision for the development of the island; absence of a structured PFM programme; weak political ownership over existing PFM initiatives; absence of technical PFM support from DFID; lack of fiduciary risk management in subsidiary bodies; limited capacity; and risks identified by the PEFA (e.g. effectiveness of measures for taxpayer registration and tax assessment, classification of budget).
- OTD and SHG are currently discussing which recommendations need to be addressed as highest priorities. It is likely that the recommendations will be divided into two distinct areas: Those to be implemented through new actions and those that can be addressed through broader engagement e.g. budget aid planning. Many of the recommendations cover progress that has already been made since the FRA.
- New Actions to mitigate Fiduciary Risk include: Better oversight by SHG of selected statutory bodies (especially Enterprise St. Helena, Bank of St. Helena, St. Helena Line, Solomon’s and Connect); Review of IPSAS (International Public Sector Accounting Standards) compliance plans to enable Corporate Finance & External Audit to urgently recover the backlog and to generate future unqualified Financial Statements; Development of a structured methodology to improve the identification, monitoring and mitigation of fiduciary risks – both within SHG and its subsidiary bodies. This would inform a corporate risk register [SHG have a draft strategic risk register]; A review of taxation procedures and internal control systems - and the development of a new Procedure Manual.
- Actions to mitigate Fiduciary Risk Addressed through Broader Engagement include: Review of Technical Cooperation support; engaging professional & technical support from UK Government ministries, departments and agencies, ongoing improvements to SHG services through the quality improvement programme
- All actions will be reported through one framework which will be reviewed by the DFID OTD Governance Advisor.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
This was project to fund St. Helena Government’s use of short term technical co-operation expertise over the course of 2014/15. SHG spent the majority of the budget to fund short term technical co-operation over the course of 2014/15. The project is now complete.

Performance of partnership (s)
No specific conditions were attached to this programme. The commitments against which partner governments are normally assessed for financial aid (that is the commitment to (i). poverty reduction and the Millennium Development Goals; (ii) respecting human rights and other international obligations; (iii). improving public financial management, promoting good governance and transparency and fighting corruption; and (iv). strengthening domestic accountability) are not applicable for Overseas Territories. Accordingly the Partnership Principles are also not applicable.

Asset disposal and value obtained by DFID
This project funds SHG’s use of Short Term Technical Co-operation expertise. SHG owns and retains ownership of its own assets.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
- DFID OTD staff are satisfied from their engagement with SHG, including through annual Budget Aid Missions, that without Short Term Technical Co-operation public service delivery standards would suffer and the professionalisation of services would not happen.
- SHG’s continued demand for technical co-operation provides some evidence of its need and effectiveness.
- There are no significant changes from the evidence outline in the business case. St. Helena continues to need assistance as the opening of airport nears and the next phase of its economic development begins.
- From 2015-16 Short Term Technical Co-operation has been incorporated into budget aid. OTD plans to have a three year business case for Budget Aid commencing 2016-17 which will be subject to a full evaluation.

Monitoring progress throughout the programme
- SHG review Technical Cooperation fortnightly through the SHG Business Delivery Group. Among other areas, they consider:
  - Opportunities to reduce Technical Cooperation costs.
  - The need to build local capacity through succession planning and training.
  - The two-tier culture (well paid Technical Cooperation officers vs. local employees) that results from the heavy presence of Technical Cooperation on the island.
- The SHG Chief Secretary is accountable and responsible for the implementation of SHG’s strategic priorities including t the use of Short Technical Co-operation. The Financial Secretary provides management support of DFID’s financial contributions towards these priorities.
- The DFID OTD St Helena Team consider a range of issues, including risks in the St. Helena risk register, at its monthly Better Delivery Group meetings.
- DFID reviews the financial performance and priority listings of SHG’s use of Technical Cooperation funds over the previous year at Annual Budget Aid Mission.

Smart Guide

The Programme Completion Report is the opportunity to reflect on the entire programme, its performance, achievements, lessons and how learning will be shared to inform future programming.

The Programme Completion Report assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with headline information on the programme and any follow up actions
Introduction and Context
Briefly outline the programme, results achieved and contribution to the overall Operational Plan and DFID’s international development objectives. Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Outcome Assessment / Brief assessment of whether the programme achieved the Outcome
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessment
Key points
Summary of response to issues raised in previous annual reviews (where relevant)
Recommendations for future programmes
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case. Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme represented value for money? / Overall view on whether the programme was good value for money
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Quality of risk management over the life of the programme. How were risks managed, the degree to which they were realised and/or mitigated.
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / Could DFID be a more effective partner
Asset disposal and value obtained by DFID / How were assets managed throughout the programme? How have they been (or will they be) disposed to get maximum value?
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the programme / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process