Programme Completion Report - Top Sheet

Review Date:	30/06/2015

Title: Tackling Maternal and Child Undernutrition Phase 1
Programme Code: 201927	Start Date: November 2011	End Date: 30 March 2015

Summary of Programme Performance

Year	2012	2013/14	PCR
Programme Score	A	A	A
Risk Rating	L	L	L

Financial Position

Original Programme Value	£3.6m
Extensions/ amendments	THET – three amendments to the Accountable Grant
	UNICEF – three amendments were made to the Contribution Arrangement; Two to increase value, one to change end date of the programme. / amendments increase value from £150,000 to £1,085,000 to support Child Health Week activities / amendment to add £64,500 for the Measles Campaign / to change end date of the programme
	ColaLife – two amendments. First amendment to increase the value of the programme and change end date of the Exchange of Letters
Log-frame revisions (with dates)	Logframe was revised to include major milestones for the trials. Approved as part of 2013 Annual Review
Total programme spend	£3.3m

Follow up actions required following closure

The following actions are required after closure of the programme.

- Sustaining the results of the pilots implemented under this project. Work in four areas of the pilot have been taken forward under the Scaling Up Nutrition (SUN) Fund under Phase II of the programme; Vitamin A Biofortification by IFPRI, Colalife through local Keepers Zambia, CSO SUN and the Nutrition Degree by THET.
- Tracking the use of the balance of funds on the UNICEF component. An agreement was reached for UNICEF to use the £89,000 to procure Ready to Use Therapeutic Foods (RUTFs).
- Finalise the transfer of assets to CARE for the components continuing under Phase II.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/3717065.docx
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/3904449.xls

Outline of programme and what it has achieved
The UK provided up to £3.6 million through a range of financing agreements to implement Phase 1 of a larger Nutrition programme between 2011- 2015. This support aimed to draw attention and generate interest in nutrition in Zambia. It was developed against the backdrop of high child mortality rates and poor nutrition outcomes for children under the age of five. At the time of approval, Zambia had one of the highest rates of childhood undernutrition in the world[1]: 46% of under-5 children were stunted, 6% acutely malnourished (wasted) and 15% underweight[2], 53% of Zambian children had Vitamin A deficiency and 46% iron deficiency anaemia[3], 9.3% of the children are born underweight indicating poor maternal nutrition[4].
[1] Lancet Series 2008
[2] Living Conditions Monitoring Survey 2010; CSO 2014
[3] NFNC 2003
[4] CSO 2014

Under-nutrition is likely to be the most significant factor in child mortality and morbidity, underlying up to 50% of under-five deaths in Zambia[5]. Children who are stunted by the age of two will never meet their full potential of physical and mental development. Direct nutrition interventions have been proven to be highly cost effective when they reach children in the ‘critical 1000 days’ between conception and age two. Despite this evidence, proven effective interventions are not carried out to scale in Zambia because of weak health systems, lack of human resources, knowledge gaps, poor coordination and lack of investment. This support was intended to establish a base to enable the Zambian Government to begin addressing the underlying causes of undernutrition.
[5] UNICEF 2010

The programme sought to have impact on the health and nutritional status of children under five measured primarily by a reduction in stunting from 46% to 39% by 2015. This meant having at least 100,000 less[6] children under 5 stunted. The actual reduction was up to 40% which shows that stunting is still a major challenge in Zambia. The 2013 Zambian Demographic Health Survey (DHS) further records a reduction in Under 5 mortality rates from 119/ 1000 live births to 75/1,000. Despite this reduction, progress is still less than the 56/1000 live births that was envisioned. During the lifetime of the programme the prevalence of low-birth weight babies (<2.5 Kg) remained static at 9%, meaning that more work is required to address this under phase 2.
[6] Estimates have been revised based on the 2010 Census figures from 120,000 to 100,000 children under five

Summary Achievements
The original timeframe for the programme was until end 2015. However, the SUN Fun started full operation in 2014. The objective of the SUN Fund is to have a national coordinated nutrition approach, and several of the successful Phase I components receive continued support and funding under Phase II through the SUN Fund. This was early than envisioned, and indicative of the successful coordination under the SUN Fund. It was therefore decided to close Phase I early[7].
[7] The logframe included Target indicators for end 2015 which are beyond the new end date. In reporting on the logframe indicators in this report, we have indicated when we use 2014 milestones and 2015 targets.

At output level the overall achievements of the programme are as follows:
- 5 cumulative rounds of Child Health Weeks undertaken out of 8 rounds
- Increase in coverage of vitamin A and Deworming tablets of over 80% at national level and above 90% in nine DFID focus districts
- Development, costing and approval of the 1,000 Days programme.
- 7 districts currently implementing programme activities, with an additional seven planned to come on board in 2015
- BSc Nutrition Degree developed with enrolment of 59 students across four cohorts
## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Overall Outcome Assessment: A
The programme outcome was “Strengthened national nutrition response focused on addressing direct and underlying causes of stunting”. The overall outcome score is A, there has been good progress against the outcome indicators as indicated below:

Outcome Indicators	Baseline	Target (2015)	Progress
Reduced prevalence of Vitamin and mineral deficiencies (improvement in micronutrient status in children <5	46% iron deficiency anaemia; 53% Vit A deficiency	20%	Result not known as updated data not available from the Micro Nutrient Survey
Innovative channels for delivery of nutrition interventions developed	Global call for investing in new nutrition interventions	Further scale up of successful interventions	Target met: / Two trials (Colalife, Bio-fortified maize) from phase 1 are being scaled up under Phase 2
Total funding for nutrition interventions	US$75,000 (MoH); US$ 1 million NFNC; MCDMCH (unknown)	NFNC - US$1m	Target met: / NFNC $1.5m (2014 figures). / Nutrition budget was transferred from MoH to MCDMCH.
National 1,000 critical days strategy developed, costed and supported by multiple stakeholders	ToR for 1,000 days plan developed	Implementation ongoing in 10 districts; higher political oversight of nutrition in place	On track to meet target : / Implementation on-going in 7 districts in 2014; all 14 by middle of 2015.

This programme sought to strengthen the government’s response to nutrition and that has been achieved. The implementation of the programme coincided with the launch of the Global campaign on Scaling Up Nutrition (SUN) Movement. This increased focus on nutrition at a global level provided a platform put nutrition on the political agenda, and the design of the national 1,000 Most Critical Days Programme (1000MCDP) is evidence of this. The establishment of the SUN Fund, co-funded by SIDA and Irish Aid, was developed during Phase I and continued to provide support to implementation of the government’s 1000MCDP.

We are unable to access progress on the first outcome indicator, micro nutrients deficiency (Iron and Vitamin A), as updated result from the survey are unknown. The outcome indicator on innovative approaches was met as was that of government funding for nutrition (US$1million for NFNC). However, it must be noted that NFNC isn’t the only government agency implementing nutrition interventions and nutrition funding across different line ministries is still insufficient for the sector to implement effective programmes to address undernutrition. Continued tracking of the government’s budget on direct and indirect nutrition intervention allocations and expenditure is recommended, and continues through the CSO SUN Alliance under Phase II. The target on the development of and implementation of the SUN Fund will be overachieved during the course of 2015 when implementation will be live in all 14 districts rather than the planned 10 although it won’t be rolled to all wards within those districts yet.

The expected impact of the programme was improved health and nutrition status of children under 5. This was to be achieved by:
- A reduction in under 5 mortality from 119/1,000 births to 56/1,000 by 2015.
- Reduction in under 5 prevalence of stunting from 46% to 39% by 2015
- Reduction in prevalence of low birth weight babies from 9 to 6% by 2015

The impact milestones set for this programme for 2014 were not measured as the release of the Demographic Health Survey (DHS) was delayed. The report was finally released in the first quarter of 2015 and shows a marginal reduction in the three impact indicators. However these results cannot entirely be attributed to the DFID support as it was clear that rapid progress was not to be expected over a short time period. During the life of the programme under 5 mortality reduced to 75/1000 births, stunting went down from 46 to 40%, the percentage of children with low birth weight remained static at 9%.

Output Score and Description A: outputs have met expectations

There was positive progress towards the target on each of the outputs, with some mixed results particularly on the first one.

Output 1 had a mix of results on its output indicators. The commissioning of the Analytical Study, one of the three indicators was not met, largely due to the shift of responsibilities from Ministry of Health to Community Development, Mother and Child Health (MCDMCH). The challenges faced in meeting the target were externally driven and outside the control of the two ministries. The other two components registered good results in terms of the number of rounds of Child Health weeks and the level of coverage for the Vit A and deworming tablets. The graph below shows coverage of Vit A supplementation in 2013.

Vitamin A supplementation coverage by district
July & December 2013

UNICEF 2014

Output 2 was related to the implementation of the two innovative nutrition trials namely the Colalife Operational Trial and the Vit A Bio-fortified Maize trial by the International Food Policy Research Institute (IFPRI) through Harvest Plus. There was positive progress throughout the life span of the programme despite slight delays in the inception phase and the delayed release of the final results for the bio-fortified maize trial. The Colalife trial has been heralded as a highly innovative initiative by the Ministry of Health and has received several international awards.

Output 3 related to the design of a multi-sectoral nutrition programme. This output has registered the most significant progress during programme implementation. A new programme has been designed which is aligned to the National Food and Nutrition Strategic Plan. DFID supported the design of the First 1,000 Days Programme and tailored its support under phase 2 towards the implementation of the programme by establishing a joint SUN Fund.

Another key development related to this component was the establishment of the Nutrition Degree managed by the Tropical Health and Education Trust (THET) Programme at the University of Zambia. The degree seeks to address serious human resource shortages required to prevent stunting. So far, four batches totalling 59 students are pursuing the BSc Human Nutrition, with first graduates expected in October 2015.

The Civil Society Scaling Up Nutrition Alliance (CSO SUN) has been instrumental in generating interest and debate about nutrition in the country. The work on the CSO SUN came as an addition to the programme with additional funding of £316,000 secured from a central programme. Since inception, the CSO SUN has been conducting budget analysis of allocations to nutrition and been very active in advocacy, engaging regularly with the media and Parliament on nutrition.

Lessons and how these have been shared
The two trials supported under this project have demonstrated the importance of having a strong professional and technical team. The Vit A trial was conducted by a combined team from IFPRI and John Hopkins University who have worked hard to ensure credibility of the research results. The team invested time in securing interest and ownership from the Zambian government. Similarly, the Colalife trial was endorsed as a highly innovative and potentially ground-breaking initiative by the Ministry of Health.
Another lesson learnt from the Colalife trial was that the main innovation of the programme was not the packing as initially envisaged but the ability to get small quantity, single-use anti-diarrheal kits to very remote areas. This design prevented wastage and ensured that mothers could easily measure the correct amount. This provides a good lesson for future innovative programmes in that some of our projects’ success could look different than what was envisaged. It also provides a lesson that innovation programmes may not always work as we expect them to.

The implementation of this programme also brought to the fore the fact that running a large number of small projects under a single programme requires intensive staff time, which is an important point to bear in mind for Phase 2 or similar programmes

The key lesson with regards to the initiation of the BSc was the need to obtain approval from the Health Professionals Council of Zambia (HPCZ) as this affected the students’ ability to apply for sponsorships and get deployment after they graduate. THET is currently supporting the development of the MSc and work with UNZA to ensure the programme is fully sustainable when the external grant ends in 2016. Another related issue currently affecting the start of the MSc course is the length of time the University approval process takes; these will have to be taken into account when setting milestones in future.

There has been strong collaboration between THET and UNZA; they worked very closely to develop the BSc. UNZA also contributes all of the office and lecture space and the associated costs, so the contribution from DFID directly supports the capacity building and the provision of long- and short-term lecturers. This partnership will support the programme moving forward as THET moves into the second phase, supported by the SUN Fund.
Also, the launch of 1000 Days Programme has attracted much attention from government and donors alike and served to raise the profile of nutrition in Zambia. With the plans to scale up the Social Cash Transfer programme, there is a lot of interest by the MCDMCH in enhancing linkages between the 1000 Days and the cash transfers, as well as to compare programmes outcomes – in isolation and combined. This demonstrates that much awareness and interest has been raised. In addition, three donors have committed new and additional funding for nutrition: the EU, SIDA and the World Bank.
Finally, the SUN CSO Alliance advocacy work has been instrumental in the emergence of new national nutrition champions, including several members of Parliament and in getting a national voice for nutrition. The director of the SUN CSO was nominated as one of the top ten global twitters on nutrition by the Guardian in January 2014.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Strengthened implementation of Child Health Weeks Programme (in 9 focus districts)
Output number per LF		1	Output Score	B
Risk:		Low	Impact weighting (%):	35
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Target (2013/2014)[8]	Progress
1.1 Study to identify how best to address gaps with a focus on underperforming districts	Study conducted by 2013[9]	Target not met: / Not done, superceded by change in policy to remove vaccinations from CHWks
1.2 Cumulative round of CHWks completed	2 new (6 cumulative)	Partially met: there were 2 rounds in 2014, but only 5 rounds rather than 8 completed by the close of the programme
1.3 Coverage nationally and in nine underperforming districts / a)Vitamin A / b) Deworming tablets	> 90% in all nine districts / > 90% Vit A coverage in nine focus districts	Exceeded: Average of 102% coverage in the 9 underperforming districts.
[8] Reporting on the 2014 target as that was the last year of CHW support.
[9] Reporting on the 2013 target, which is the final one on this milestone

Key Points
Output indicator 1.1: The Analytical study was not done due to delays caused by the shift of responsibilities between the Ministry of Health (MoH) and the Ministry of Community Development, Mother and Child Health (MCDMCH). The study was meant investigate how to improve coverage of vitamin A and deworming using Child Health Week.

In 2013 MCDMCH made a decision to remove child immunisations from CHWks and focus only on the nutrition components, namely Vitamin A and deworming tablets distribution. It must be noted that Child Health Week is meant to be used as a catch-up strategy to increase immunisation of children under 5. The Ministry prefers that these services are provided routinely rather than through CHWs. However, is it yet to be seen whether the routine system has sufficient capacity to reach the high coverage achieved by the CHWks. There is a real risk that this change will reduce immunisation coverage especially in rural areas.
Output indicator 1.2: UNICEF supported 5 rounds of Child Health Weeks. Eight rounds were planned initially with the intention to carry out 2 rounds in each year of implementation. In the first year, only one round of the CHWks programme was completed in September 2012 largely due to the transition of responsibilities between the two Ministries and a joint government-donors’ decision to integrate a nation-wide measles campaign within the programme, which meant more complex logistics and preparations were involved. A cost-effectiveness study published in 2012 (Fielder et al) concluded that the exercise was very effective in achieving high coverage particularly in remote areas which lack access to services through the routine system.
Output indicator 1.3: The CHWs have contributed to sustained increase in the coverage of vitamin A and deworming tablets. DFID support focused on nine underperforming districts (Chavuma, Zambezi, Mufumbwe, Kalabo, Mongu, Kaoma, Kaputa, Mpulungu, Mbala). Initially these districts had recorded coverage of less than 80% in more than one round and were therefore targeted for additional support to improve their performance in the form of preparatory planning, orientation of volunteers, mobilisation and distribution of suppliers. Following this support, the districts are performing better and have attained a coverage of more than 95% coverage which is better than the national average of 80%.
Although not reflected in the log-frame, UNICEF has also managed a Micronutrient and Food consumption survey with DFID and Irish Aid support. The objective was to estimate the prevalence of micronutrient deficiencies, specifically of Vitamin A, iron, zinc, Vitamin B12 and folic acid intake, as well as to assess the adequacy of nutrient dietary intakes in children and women. This survey was implemented by Tropical Disease Research Centre (TDRC) and the NFNC with technical support from UNICEF and covered Luapula and Northern Province. The survey results were disseminated in January 2015.
DFID and UNICEF had raised some concerns regarding the presentation of data and analysis of the dietary and blood data which have not been resolved and therefore, limit the use of the survey findings.

Summary of responses to issues raised in previous annual reviews (where relevant)

The last Annual Review noted the need for UNICEF to review the implementation of CHWks in districts where coverage was below the target. This was acted upon by providing additional support to the concerned districts, results from the last round show significant improvement i.e. Kalabo - 112% and Mbala - 103%.

The second recommendation was for DFID and other partners to continue monitoring the impact of removing immunisation from the Child Health Weeks by analysing reports from the Health Management Information System. However, given that funding for CHWks was channelled through nutrition and not Extended Programme of Immunisation (EPI), the indicator on immunisations was not linked to this support. There is therefore need to engage MDCMCH to learn how they will monitor immunisation levels. This is incorporated in the implementation of phase 2.

Previous Reviews also included several recommendations for future programming, such as promotion of diversified diets, support to iron and folate acid during pregnancy and support to promote hygiene and hand washing. These recommendations were taken up during the design of Phase II and feature strongly in that programme’s interventions and results’ monitoring.

Output Title	Support to promising, well-designed innovative approaches provided and lessons disseminated
Output number per LF		2	Output Score	A
Risk:		Medium	Impact weighting (%):	25
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Target (2014)[10]	Progress
2.1 At least two innovative interventions tested	At least 2 papers for publication produced; plans to scale up	Target met: / Both trials are being scaled up, and have had a series of publications over 2014.
2.2 COTZ trial implemented and contributing to evidence base	Discussion on lessons learnt and possible scale up/replicability held with government and partners; at least 1 publication	Target Met: there are many publications around the trial (see Colalife website) and now scale up through the SUN Fund.
2.3 Bio-fortified maize efficacy trial implemented and contributing to the evidence base	At least 1 publication	Partially met: Trial completed successfully; Final report to be finalised in August 2015. A series of papers have been released in 2014.
[10] Logframe did not include targets for 2014/2015; we use the 2014 milestones here instead.

Key Points
DFID provided support to two nutrition interventions; the ColaLife Operational Trial in Zambia (COTZ) and Maize bio-fortification through Harvest Plus. Overall progress has been positive. The targets were met and this is reflected in the score of A.
Colalife Operational Trial – Zambia (COTZ)
Diarrhoea is the third leading cause of both clinic visits and death for children under five years of age in Zambia after malaria and pneumonia. Therapeutic zinc supplementation reduces diarrhoea duration and subsequent incidence of diarrhoea and acute-lower respiratory infection. The Colalife Operational Trial aimed to promote a new anti-diarrhoea kit known as ‘Kit Yamoyo’ which was designed for the treatment of under five children in remote and underserved rural areas. The kit contains Zinc, Oral Rehydration Salts and Soap for hand washing. The trial was implemented from December 2011 to June 2014 to addressed two main questions; 1) To what extent can the informal Coca-Cola distribution chains be used to improve access to ORS, zinc and other simple interventions through ‘last mile’ retailers in under-served rural communities? 2) What effect does this have in supporting mothers/care-givers in home-based management of diarrhoea in children 0-59 months of age?

An end line survey demonstrated that the project had had an impact on increasing awareness, use and accessibility of the World Health Organisation (WHO) recommended combined diarrhoea treatment of ORS and Zinc. The project also achieved results in terms improving access to simple, effective interventions and impacting the home-based management of diarrhoea in children. The key findings were as follows;
- COTZ has shown that informal Coca-Cola distribution chains have improved access and availability to ORS and zinc by making it available in rural retail shops which are on average 4 to 5 Kms closer to communities than health centres
- By improving access and availability to ORS and zinc, the project has increased use of ORS and zinc for the home-base treatment of diarrhoea from almost zero at baseline to 45%
- Improved access, availability and training of retailers, who tell mothers and carers how to use the Kit Yamoyo, has led to a reduction in treatment delay from 2 days at baseline to 1 day at endline, with potentially life-saving impacts
- Lastly, increasing availability of zinc, which was very limited at baseline, together with the training of retailers and marketing of Kit Yamoyo has led to increased awareness on the use of zinc for the home-base treatment of diarrhoea from 2% to 50%.

Colalife has been successful in getting a local pharmaceutical company, Pharnova, to produce the kit on a commercial basis. Colalife has also secured additional funds to scale up the project from the SUN Fund. ColaLife has received over six innovation awards and Kit Yamoyo was featured at the September 2013 UN General Assembly as one of the top ten maternal and child health innovations of the year.

Vitamin A bio-fortified trial
This trial was aimed at assessing the efficacy of Vitamin A bio-fortified Maize (orange maize) in improving Vitamin A status and reducing the prevalence of Vitamin A deficiency among children in rural Zambia. Preliminary findings from the trial were shared at the International Congress on Nutrition in Spain in September 2013. Johns Hopkins University group identified some inconsistencies during their quality control check and decided to re-analyse over 2,000 blood samples to ensure the highest confidence in the reported findings. The results are expected to be ready by August 2015 and the final report will be ready by end of December 2015. The trial showed that “orange maize” is efficacious, improves Vitamin A status, and therefore should be supported as a food-based strategy to address Vitamin A deficiency.

Summary of responses to issues raised in previous annual reviews (where relevant)
A Private Sector Development Advisor consultant was hired to review Colalife’s work and plans for transition. Overall, findings of this review were that the intervention could not be scaled up in its currently form. The report recommended that DFID should treat proposals which combine establishing a commercially sustainable business with achieving a health objective as linked but distinct, and involve both the private sector adviser and the health adviser in appraisal and monitoring. The final report was shared with ColaLife but they were not in agreement with all the conclusions of the review.
DFID has continued to engage with Harvest Plus on the need to finalise and compile the research findings. Further work is being supported under the SUN Fund.

Recommendations for future programmes
Both interventions are being scaled up and are receiving support from the SUN Fund.

Output Title	Design of multi-sectoral approach completed
Output number per LF		3	Output Score	A
Risk:		Low	Impact weighting (%):	40
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Target (2015)[11]	Progress
3.1 Mapping of nutrition interventions & gap analysis completed; development & costing of 1000 Days Programme; phase two of nutrition programme approved	Programme launched in 10-14 districts	Met: / The 1000 Days programme is in its second year of implementation. 7 out of 14 districts have already started implementation. The other 7 will start implementation in 2015.
3.2 Capacity building plan for NFNC and key sector Ministries developed & costed	Effective team for the management of the 1,000 Days Programme in place	On track: / There is good progress towards meeting the 2015 target. The capacity strengthening plan for NFNC has been drafted and submitted to the Steering Committee for approval
3.3 Development & implementation of appropriate degree course (BSC and MSC) in nutrition at UNZA	BSc continues and 1st cohort of MSc students begin course	On track: / BSc course progressing well. MSc not started, pending approval by the Health Professionals Council. Still planned to have MSc Cohort start by end-2015.
[11] As the SUN Fund is continuing in 2015 and THET received direct support over the first quarter of 2015, we report against December 2015 targets here.

Key Points
There has been positive progress on this output as costed plans for all 14 districts have been developed. 7 districts have already started implementing in 2014, the remainder will begin activities within the course of 2015. Outputs 3.2 and 3.3 are on track to be met by end of 2015. DFID Zambia has been supporting the implementation of the 1000 Days Programme through the second phase of the Tackling Maternal and Child Undernutrition Programme.
The implementation of the 1000 Days programme is focused on reducing stunting and the operationalisation of the National Food and Nutrition Strategic Plan. The programme is being implemented through five line ministries supporting the implementation of the 1000 Days Programme across its five components in at least 14 districts. It is managed through the Scaling Up Nutrition (SUN) Fund by CARE International with funding from DFID, Irish Aid and SIDA.
The districts have received support to develop and draft District Plans and budgets to implement the programme across the five line ministries coordinated by the District Nutrition Coordination Committees (DNCCs). NFNC has recruited 14 District Nutrition Coordinator (DNCs) to coordinate activities at district level. The start-up phase of the 1000 Days programme was delayed leading to subsequent delays in the disbursement of funds to the districts which commenced towards the end of 2014.
The World Bank has commissioned an institutional assessment of NFNC expected to generate recommendations for strengthening the NFNC and the broader governance of the nutrition sector. The final reports are yet to be released.
NFNC Leadership: Towards the end of 2014, NFNC appointed a new Executive Director this along with the appointment of a new Board are seen as key steps in addressing management and governance issues in the sector.

Nutrition Degree: This component was a direct response to Zambia’s urgent need for well-qualified nutritionists and dieticians. The project aimed to address current human resource gaps to support the implementation of the National Food and Nutrition Strategy and the First 1000 Most Critical Days Programme. Until the BSc was introduced, the diploma course offered by Natural Resource Development College (NRDC) was the only nutrition course offered in the country. The targets for our support to UNZA for the development and implementation of the Nutrition Bachelor of Science (BSc) and Master of Science (MSc) degrees, were partially met. The BSc has been progressing well, so far four batches of student have been admitted and are in training since the programme started in July 2011. The MSc curriculum was developed and is awaiting approval by UNZA’s Senate and the Health Professionals Council of Zambia (HPCZ). THET had expected to start the MSc by October 2014 but have had to postpone this until the relevant approvals are obtained.

Summary of responses to issues raised in previous annual reviews (where relevant)
The previous annual review noted the UK Independent Commission for Aid Impact (ICAI)’s recommendation that DFID Zambia should consider further support to the programme. This has been taken on board and THET has signed a grant for additional funding through the SUN Fund.

Recommendations for future programmes
Recommendations have been imbedded into Phase 2.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
The business case did not identify specific cost drivers, although it did outline how much the programme would spend on each component:

Component	Output	Spend	% of budget	Key cost drivers within the component
UNICEF/Child Health Weeks	Output 1	796,648	24%	Staff time; Procurement; Food Consumption Survey and Micronutrient Survey
IFPRI / Vitamin A	Output 2	680,000	20%	Staff time, equipment (incl cars), travel
COLALIFE	Output 2	852,000	26%	Staff time; Sub Contractor fees, Commodities
THET/Nutrition degree	Output 3	692,770	21%	Zambia staff salaries; costs for volunteers; Scholarships; Equipment (mainly computers)
Design of Phase 2	Output 3	138,498	4%	Consultancy
CSO SUN	Other	162,889	5%	Staff time
Other Costs	Other	14,981	0%	App & Design, M&E
TOTAL		3,337,786

These were adjusted somewhat during the life of the programme. Most of the funding identified in the business case has been allocated to during the programme, although there were some small increases to THET and ColaLife with fewer costs to the design of Phase II and UNICEF. The major additional component was funding to the CSO SUN for which DFID Zambia received central funding. The table also indicates some of the key cost drivers per component, which in most cases was staff time. Previous Annual Reviews highlighted management fees, salaries of project staff, subsistence, travel and trainings. This has been the same throughout the programme.

VfM performance compared to the original VfM proposition in the business case
The original business case did not identify indicators around the 4Es of Economy, Efficiency, Effectiveness and Equity. It did include a comparison of costs and benefits, and proposed VfM metrics for some components, which offer opportunities of comparison of VfM performance against expectations:

	Costs	Benefits	VfM Metric
CHWks (Output 1):
In BC:	£930,000 (over 4 years)	- 161,000 children covered with vitamin A supplements & deworming drugs twice a year for 4 years. / - 3,860 infant deaths & 127,000 DALYs	Unit cost: £0.72 per child per year / Cost effectiveness: £240 per infant death averted, £7 per DALY
Actual:	£796,648	- Children covered 231,884 (2012), 197,721 (2013), 260,765 (2014)	Unit cost (economy): £0.76 /child / (CHW £523,148 reached 690,370 children) / The intervention reached fewer children than originally intended, but with fewer rounds. The costs per child were slightly higher than the metric set at the programme’s start. A 2012 study[12] found that national average cost of the CHW per child was $0.46. The costs per child in our intervention districts are likely to be higher because focus lay with underperforming and far-out districts. / This same study found a cost of $1093 per life saved and $45 per DALY saved. These are higher than predicted at the start of the programme, again likely due to the sparse and dispersed population. We did not calculate the infant deaths averted or DALYs saved for this intervention separately, and these might also be higher than the national average as found in the study due to distance. The WHO classifies an intervention as very cost-effective if cost per DALY are below the country’s GDP/capita, which is $1845 in Zambia. Therefore, even with potentially higher costs due to the distances in our intervention districts, the costs are sufficiently below GDP to be assessed as cost effective.
ColaLife pilot (Output 2, completed in 2014)
In BC:	£750,000 (over 2 years)	- 20,000 anti-diarrhoea kits delivered, 15,000 children reached / - Knowledge gained on effectiveness of innovative delivery mechanism / - Income generation opportunities for low income rural micro-retailers	Direct cost per kit: £2.30 / Distribution cost: £1 per kit
Actual:	£852,005	40,945 kits assembled / 26,250 diarrhoea kits distributed (21,823 through vouchers; 4,427 sold for cash) / Income generation opportunities for low-income retailers / Knowledge gained on effectiveness of innovative delivery mechanism / Interest from local pharmaceutical company to scale up in Zambia	£8 per child reached / £60 per DALY averted (average estimate from a number of studies. Source: Horton 2004). Very cost-effective by WHO standards / The project has made significant strides at bringing the price of the Kit down by reducing the costs of packaging and localising production of zinc and soap. The reduced price will be used during the scale up phase – likely two versions one for ZMW 8-10 and one for ZMW4-5.
Harvest Plus Biofortification pilot (Output 2, completed in 2014)
In BC:	£0.68m	- Knowledge gained on efficacy (nutrition impact) of innovative delivery mechanism	No metrics identified
Actual:	£0.68m	Knowledge gained on the efficacy of innovative food based approach to tackle Vit A deficiency; results will inform future policy for Vitamin A Deficiency Control programmes in Zambia and possibly other settings	Bio-fortification is considered as one of the top best development buys and highly cost-effective (Copenhagen Consensus). Results from this and another trial show that Vit A maize is bio-available (it is absorbed by the body) and efficacious (it increases Vit A liver stores)
Supporting the development of a national nutrition degree through THET (Output 3)
In BC:	£0.55m (over 4 years)	- Increased pool of highly trained nutrition professionals / - 200 students achieving Bachelors and/or Masters level professional qualification in nutrition	No metrics identified
Actual:	£692,770	59 students – far fewer than the 200 expected at BC / New cadre of highly qualified professionals in nutrition and dietetics / Stronger capacity for nutrition at UNZA	£11,742 per student / 2014: £8,863 per student (this is likely to decrease as more students enrol and regional lectureship support is sought) / A nutrition degree in the UK would cost £34-36,000 per student in addition to living and accommodation costs. Much higher costs would be spent for students to study abroad, the only option given that this is the first Human Nutrition BSc in Zambia.
[12] Fiedler et al (2012). Child Health Week in Zambia: costs, efficiency, coverage and a reassessment of need. Health Policy and Planning.

DFID Zambia agreed to allocate additional funds for THET from programme funds (£162,166) to support the BSc course. This was mainly due to expected support from UNZA which did not materialise, in particular the lack of teaching capacity on nutrition and dietetics. This increased the fee per student. However, a partnership with UNZA does ensure that some of the programme costs are shared. UNZA currently provides classrooms, laboratory space, office space and relevant equipment for students and lecturers, to cover the needs of the BSc programme. These resources should be viewed as part of UNZA’s on-going contribution to the Nutrition Programme. Also not included in the budget are costs of utilities (electricity, water) and internet access.

The design of Phase 2 and support to CSO SUN were the final two components, there were no metrics identified for these two components. Support to the CSO SUN Alliance for advocacy around nutrition is hard to value, especially without setting prior metrics. However, we do have anecdotal evidence of the effectiveness of their presence in Zambia, for example the fact they get invited to give evidence before the Parliamentary group on budget estimates, based on their yearly analysis of the budget for nutrition. Advocacy by the Alliance has been vital to put nutrition on the agenda in Zambia.

Overall costs for the design of the 1000 Days Programme were actually lower than expected. This was largely due to the ability to negotiate a bulk contract through DFID HQ’s human development resource framework. This was well-managed by London which negotiated a good budget based on centrally agreed costs whilst allowing for some flexibility in the contract within the agreed budget.

Implementation of Phase II is ongoing as is tracking of VFM indicators following the design VfM-matrix in order to comment on the 4Es. Depending on similar tracking in other SUN countries, it is recommended to compare VfM performance in Zambia of Phase II with other countries.

Assessment of whether the programme represented value for money
In the UNICEF/CHW component, coverage in the underperforming districts was brought up. The Colalife trial reached more children with slightly more funding, but has also been very successful in widespread publication and awareness raising and in partnering with a local pharmaceutical, and contributing to the evidence-base. This component therefore represented very good value for money, and continues to do so in the scale up. Similarly, the HarvestPlus component contributes to the evidence-base, although the delays in publication and application of the study’s findings to inform policy on Vitamin A Deficiency Control mean that we cannot yet comment on the effectiveness of this component. As indicated above, financial support to THET was above the level originally planned. Funding per student ended up higher, and fewer students are trained than originally expected, but the costs are still below that of sending students abroad and Zambia now has its own nutrition degree programme. Economy of the intervention is therefore still valid, but as none of the students has yet graduate, an assessment of the efficiency and effectiveness of the intervention in terms of having more, well trained nutritionists, is not yet possible.

The Business Case argued that a combination of implementing rapid interventions (CHWks) and operational trials, while laying the institutional and political groundwork for a Phase II through the support for design of the SUN Fund would provide strong Value for Money. Both sets of interventions build on strong international evidence on cost-effectiveness throughout implementation and design, and are contributing to it. As evidenced by the A in terms of output and outcome results, the programme has been successful in achieving most of the benefits it set out in the business case. It is therefore judged that overall the programme represented value for money.

Quality of financial management during programme
Overall budget of the programme was £3.5million with and addition of up to £318,000 for the CSO SUN Alliance. The budget was adjusted from time to time to reflect changes within the programme .e.g. some components closed earlier than planned and all left over funds were released. By the close of the programme, over 95% of the revised budget was spent. Table 1 below summarises the financial position of the programme.

Table 1. Programme Budget and Spend
Component	Budget Original	Revised Budget	Spend
UNICEF	1,035,000	796,648	796,648
Design of Phase 2	155,000	138,498	138,498
IFPRI	680,000	680,000	680,000
COLALIFE	600,000	852,005	852,000
THET	555,000	781,383	692,770
CSO SUN	0	162,889	162,889
Other Costs: (App & Design, M& E, FLD)	625,000	15,489	14,981
TOTAL	3,650,000	3,426,912	3,337,786

Despite having several project partners with different funding arrangements (MoU with UNICEF, Accountable Grants with THET and CSO SUN etc), adequate care was taken to ensure timely and accurate reporting. Partners provided regular narrative and financial reports as well as annual audited statements. No organisation registered qualified audits in the entire life of the project.

The CSO SUN successfully reimbursed left over funds after the end of the grant agreement with Save the Children. UNICEF has been authorised to use the balance of funds from the Child Weeks budget to procure therapeutic foods which are used in the treatment of malnutrition.

The last certified statement from UNICEF is expected by 30 June 2015.

Date of last narrative financial report	UNICEF(23/03/2015);THET (30/03/2015)
Date of last audited annual statement	ColaLife (20/11/2014)

E: RISK (½ page)

Quality of risk management over the life of the programme
Throughout the life of the programme, the risks were identified as low thus requiring minimal risk management. Some of the main risks included:
1. Lack of political leadership
2. Increased food insecurity due to unfavourable climate conditions.
3. Weak human resource capacity
4. higher than expected estimates of micronutrient deficiencies.

These were all tracked throughout the life of the programme and where possible addressed through the interventions. Risk 1 and 3 are key components of the SUN Fund support to the government for example.

In addition, the risk of funds not being used as intended were also considered low throughout the programme. No funding was directly channelled to government, strong fiduciary risk assessments were conducted and strong expenditure management throughout the programme’s life.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
The project has been closed earlier than planned which implies that some of the targets set for 2015 will not be met. Work on most of the components ended in 2013/14. The Colalife component was closed in June 2014 following the decision by the Secretary of State to close TMSA which was the management agent for Colalife. Support to UNICEF for the Child Health Weeks was schedule to finish at the end of 2015 but a decision was made to close it earlier to reflect DFID’s effort to reorient nutrition work away from supporting specific stand-alone activities such as the Child Health Weeks, to an integrated multi-sectoral approach.

Performance of partnership (s)
Project partners performed well overall.

UNICEF successfully conducted two rounds of Child health Weeks in 2014 and this is expected to be the case in 2015. The results of the Micronutrient Consumption Survey were published in 2014 following a delay of over a year. The decision by MCDMCH to remove vaccinations from Child Health Weeks bears the question of whether UNICEF should have been more proactive in supporting these interventions.

ColaLife was very engaged with stakeholders and responsive to information requests from partners.
The results of the trial have been widely published and this has earned them extensive recognition internationally. ColaLife was negatively affected by the closure of COMESA/TMSA as this disrupted the flow of funds and delayed the finalisation of the last phase of the programme. DFID worked to minimise this but could have done more to ensure that sufficient arrangements were put in place to facilitate completion of programme activities with minimum disruption.

IFPRI provided adequate technical and financial information when needed. They took overall responsibility for the Vitamin A trial with additional quality assurance support from John Hopkins University. They were responsive and constructive with partners and reacted adequately to feedback to discuss unexpected and conflicting findings.

THET has performed well and has been consistent in meeting their deadlines. They have continued to engage actively in the sector and their role is well appreciated by other stakeholders.

Asset disposal and value obtained by DFID
No value has been obtained by DFID as all the items are still in use by the partners who are continuing to receive DFID support through the SUN Fund. Arrangements have been put in place to ensure that the assets are still recognised as DFID property. These assets will be reported on as part of the assets procured under the SUN Fund by CARE. This applies to THET, CSO SUN and Colalife. The programme partners will be communicated to and appropriate arrangements will be put in place

.H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
The design and implementation of this programme has been driven largely on the basis of global evidence. Both the Colalife and Bio-fortified Maize trial underwent an extensive evaluation process. Three rounds of survey data were collected for the Colalife trial i.e. Baseline, Mid-line and End-line Surveys. The results were quality assured by the Research Technical Committee set up by UNICEF and this ensured good quality of the research products.

The Vit A trial had two rounds of data collection; Baseline and Endline surveys. Both rounds were completed and the results were analysed extensively. During the analysis of the final data, the research team from John Hopkins University identified some inconsistencies in the results as part of their quality control check. They decided to re-analyse the samples and are expected to complete by August 2015.

The findings of these trials have contributed to the global evidence base on innovative interventions to address nutrition problems.

Monitoring progress throughout the programme
The Project Completion review was brought forward to June 2015 in line with the decision to close the programme earlier than initially planned. Progress towards programme outcomes was monitored on a regular basis. Quarterly meetings were held with the different project partners at which issues were raised and decisions for corrective action taken. For partners like THET, quarterly reporting was tied to disbursements.