Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Public Private Partnership (PPP) Unit Support, Sierra Leone
Programme Value: £1.2 million		Review Date: 30/06/2014
Programme Code: 203819	Start Date: 10/07/2013	End Date:11 /Nov/ 2015

Summary of Programme Performance
Year	2014	2015
Programme Score	B	A
Risk Rating	Medium	Medium

Ebola Note: Approach to this Annual Review in the context of the outbreak of Ebola.

The outbreak of Ebola in West Africa has had a direct impact on the whole of the DFID-SL portfolio, including this programme. Transport restrictions and bans on non-Ebola-related public gatherings (including community meetings on public health) were introduced in August 2014 and some were still in place in June 2015, although the scale of the epidemic and the impact of the restrictions were by then decreasing. A substantial amount of the resources available to government, NGOs and the private sector were also diverted to the effort to control Ebola, resulting in less capacity to continue work in other development areas. Those directly affected by Ebola, including those infected with the virus and those quarantined due to contact with people with the virus, were unable to maintain normal household activities, and a substantial number of people have died.

The Ebola-outbreak affected this project in particular as the Freetown-based PPP Technical Adviser was withdrawn to the UK and there were subsequent difficulties agreeing a revised workplan for the year. Disagreement centred around selection of projects for the workplan, activities which could be completed by the PPPTA remotely, and how soon the PPPTA could return to Freetown. At a practical level, restrictions on travel from EVD-outbreak countries affected plans for staff study tours under the second output.

Given the scale of the outbreak and the impact on all DFID funded programmes, annual reviews are reflecting progress against targets and milestones agreed with partners at the beginning of the crisis, rather than against logframe targets set before and outside the current context. This AR therefore assesses the originally planned progress adapted according to the agreement between DFID and partners in August and September 2014.

Summary of progress and lessons learnt since last review

Although the outbreak of Ebola presented significant challenges to Sierra Leone and the completion of this project, some progress is being made towards the output milestones. It is important to note that, due to the implementing partner only beginning work in November 2013, this annual review is taking place after only eight months into Year 2. Some milestones are being met but for others it will be important to accelerate activities to make up for ‘lost-time’ if the full benefits of this intervention are to be realised.

DFID’s support to this project has played an important part in advising on a number of potential PPPs in areas including health, agriculture, and infrastructure including Freetown Water and the Deep Sea Port though the actual completion of a PPP will take somewhat longer, as is to be expected with complex PPP agreements. There are elements of progress on staff capacity-building though further progress will be required to enable the PPP Unit to become fully sustainable and it has become clear that high staff turnover is a critical risk to the success of this model. Although not a specific milestone in the DFID lograme, the passing of the PPP Act in 2014 was a significant step towards creating a sustainable PPP Unit. Work by the PPP Technical Adviser (PPPTA) with the PPP Unit to produce a 5 year Strategic Plan covering 2014-2019 and a Sustainability Report further support these efforts towards long term sustainability.

Donors need to carefully consider their second phase of support to the PPP Unit, and DFID should consider carefully whether to remain involved beyond the end date of this project of support. It is clear that the PPP unit needs to accelerate the delivery of the pre-feasibility studies, which are the most tangible evidence of progress towards delivering an effective, value for money PPP in Sierra Leone. There are some areas of good progress this year, in particular with regard to the sustainability of the PPP Unit (output 2). But elsewhere on capacity building and in advancing PPPs t where have been delays to delivery against the logframe. Much of this is attributable to delays in Year 1, [1] the outbreak of Ebola and subsequent delays agreeing a workplan, and is therefore not necessarily a poor reflection on work carried out in this reporting year.
[1] In year 1, there were persistent delays with the World Bank producing their Pipeline study of PPP projects to prioritise, which was not concluded until October 2014. The Pipeline study was not an output of this project and funding, but without the finalised study it was not possible to select which PPPs would receive support from DFID.

It will be important for DFID and other donors to co-ordinate carefully as we approach the end of our support, to ensure that robust plans for knowledge-transfer and sustainability are in place, but also for donors to work with the Government of Sierra Leone to consider carefully the utility of PPPs in the Agenda for Prosperity, when set against the context of post Ebola and Iron Ore crises. It is clear that a number of factors are currently affecting the country’s ability to attract high quality investors

Summary of recommendations for the next year

Define with donors and GoSL the function and utility of PPPs in the new economic environment and the level of resource needed for the PPP unit going forwards.

Ensure delivery of quality pre-feasibility studies in the remaining time of this project. The first two studies (King Jimmy Mall and Freetown Estuary study), expected in June 2015, should act as a demonstration of how DFID’s intervention in the PPP Unit can deliver value-for-money, and also how the remaining pre-feasibility studies can be most effective.

Recognising the delays to the project initiation and setbacks this year, DFID should consider a no-cost extension to the end of this financial year (March 2016) to allow completion of the pre-feasibility reports on PPPs. A decision should be taken by end of August 2015, following the completion of the first two studies.

Co-ordinate closely with other donors involved in this project (AfDB, UNDP, AGI) as we approach the end of our agreed support. The PPP Unit should be clear in its expectations of DFID as we enter this period, and donors should put in place appropriate plans. A meeting of the Steering Committee should be held in July or August 2015 to manage this.

Ultimately, sustainability of the Unit will depend on the capability of staff to negotiate and manage a quality PPP. This will require either high quality capacity building and expertise in PPPs both in the Unit and in MDAs, or the contracting in of expertise on important turn-key projects which may actually offer better Value for Money due to high staff turnover rates

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/3805179.doc
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/4048168.xlsx

Outline of the programme

Sierra Leone has poor infrastructure which severely restricts economic growth and leads to highly unequal access to government and private sector services. The Government of Sierra Leone’s (GoSL) priority until 2017 in the Agenda for Prosperity is to rapidly develop electricity, transport, water, and sanitation infrastructure and establish an environment where the private sector can flourish. The need is urgent in order to take advantage of the current surge in the economy led by investment in mining and agriculture, and to improve poor people’s access to public and private sector services and income generating opportunities.

GoSL has neither the financial resources nor the technical capacity to develop major infrastructure projects. It is committed to working with private investors to share the costs, benefits and risks of infrastructure development through PPPs. There is an estimated pipeline of $1.7 billion of proposals by foreign investors and GoSL has set up a central PPP Unit to help line ministries to manage deals. GoSL created the PPP Unit in order to:

1. Promote sustainable PPP solutions for infrastructure projects within the country and to foreign investors
2. Align investment into priority areas laid out in the Agenda for Prosperity and the Public Investment Plan
3. Ensure that employment creation and local-sourcing objectives are adequately embedded in the large PPP contracts
4. Bring in the core expertise required to negotiate deals and attract investors
5. Assist GoSL to negotiate strong, sustainable deal terms that ultimately benefit the people of Sierra Leone
6. Give investors the confidence that they are dealing with informed and professional counterparts
7. Introduce strong process, transparency and governance standards into the often ad-hoc and opaque area of deal negotiation.

The Government, African Development Bank and UNDP are all providing resources and DFID was also requested to provide support. The UK agreed to provide £1.2 million over two years in order to establish, support and build capacity within a PPP Unit in the Government of Sierra Leone. This support, provided by DFID, includes £125,000 for office equipment and vehicles, £575,000 for a PPP Technical Advisor and a £400,000 fund for pre-feasibility studies. The overall contributions to the PPP Unit are shown in the following table:

Item	Funder	Amount
Staff salaries and running costs	GoSL	£490,000
International PPP Advisor	UNDP	£250,000
Financial and legal advisors and training	AfDB	£200,000
Equipment, technical assistance and studies	DFID	£1,200,000
Total		£2,140,000

DFID’s support therefore contributes substantially to the outcomes of the PPP Unit (56% of funding). The expected impact is inclusive green growth that leads to prosperity and improves human development. The expected outcome is accelerated economic growth through the development of a sustainable and an enabling infrastructure. This will be achieved more rapidly, at lower cost and with less risk to government. The key outcomes for the PPP Unit are:

- Electricity generation rising from 76.5MW in 2013 to 120MW in 2015
- An additional 120,000 people with access to electricity by 2015
- Over $500m invested in PPPs in electricity, roads and other infrastructure in 2014 and 2015.
- An effective system of prioritising, negotiating and implementing PPPs

To achieve this, the two outputs for this project were: quality assurance and an increase in the number of PPP transactions; and increasing capacity to facilitate, negotiate and implement PPPs.

Following the outbreak of Ebola, the main technical adviser to the PPPU was evacuated in August 2014 and only permitted to return in May 2015. An interim strategy for work during the Ebola outbreak was agreed in September 2014, but not implemented until January 2014. The key outputs in the interim strategy are:

- Completion of Strategic Plan for PPPU
- Preparation of a paper for reorganisation the PPPU to that of a Project Management Office.
- Preparation of guidelines and presentations to advice local government and MDAs on PPPs.
- Amendment of pipeline study and review of PPP guidelines created by CRISIL (an infrastructure advisory service) to make them suitable for local use.
- Write high level Local Government guidelines for small PPP Projects
- Finalise presentation for MDA workshop and local Government

Work is now continuing toward meeting the indicators and outputs in the revised logframe from autumn 2014.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

The expected outcome of our support to the PPP Unit is accelerated economic growth through development of a sustainable and an enabling infrastructure. The Ebola outbreak has significantly impacted upon the economy and by extension, the impact of this project. While progress is being made against the outcomes of cumulative value of private investment in infrastructure and electricity production, these cannot be attributed to PPPs in which this project is directly responsible. On the outcome measure of number of PPPs for which transaction structuring guidance is being given, the Unit has advised on thirty projects, showing progress towards the 2015 target but not quite meeting it yet. While the project is not meeting the targets in these areas, this is understandable given the circumstances and should not detract from the elements of progress against the outputs.

Overall output score and description

B - Outputs have moderately not met expectations

At the time of writing there was limited progress on the completion of pre-feasibility studies, but the PPP Unit is showing commendable ambition to complete these studies before the end of the project in November 2015. Two pre-feasibility studies (for the King Jimmy Mall and the Estuary) are expected to be concluded in June 2015, and a further five studies are projected to be concluded by end October 2015.

Despite the initial start-up delays in Year 1 of the programme and the Ebola outbreak in Year 2, some progress is being made against the agreed outputs and towards the eventual delivery of a PPP. The Government has now passed the PPP Act, which enshrines in law the role of the PPP Unit in assessing PPP proposals. Consideration has also been given to the future strategy, structure, and resourcing requirements of the PPP Unit through the five year Strategic Report 2014 to 2019 and Sustainability Report and the Project Management papers.

There has been limited progress in improving the capabilities of staff in managing PPPs. In total ten staff were enrolled in the specialised PPP (“IP3”) qualification with three successfully completing stages one to three, although there are discussions underway to allow them to complete the final stage. Two study tours are also proposed to learn from PPPs in Uganda and Senegal (covering roads, water, power, and fisheries sectors) during the remaining duration of this project and could be useful ground-truth learning tools if they are well planned. The PPP unit still seeks further support capacity-building and is also starting to deliver workshops with MDAs and local authorities on PPPs. Plans are in place to extend PPP training and guidance to MDAs, which should reduce the resource demands of the PPP Unit staff.

Key lessons

PPPs themselves are inherently risky endeavours and the importance of establishing an affordable balance of risk and reward for the Government is absolutely critical. Therefore ensuring that PPPs are negotiated by competent technical and experienced experts is essential. Recent efforts at capacity-building were undermined by a relatively high turnover of staff in the last year (three out of ten in advisor roles) which should give the GoSL and Donors cause to pause and reassess the current strategy in place to enable GoSL to negotiate and manage PPPs more effectively. It might make better economic sense to contract in expertise for delivery of a cut down list of critical PPP projects.

There have been some attempts to address retention of staff. The August 2014 organisational development Report aimed at strengthening the PPP unit adopted a project management working model to ensure better retention of staff. This PPP Unit organisational plan will go some way to support overall retention of staff in line with best international practice. This is reiterated in the PPP Unit Sustainability Report. But it is likely that retention of staff will still limit the efficiency and effectiveness of the PPP Unit going forwards.

The Ebola outbreak was an unprecedented emergency; it placed huge strains on the relationship between IMC, PPP Unit and the PPPTA. Following the evacuation of the PPPTA, there were substantial disagreements about the work that should be completed and whether the PPPTA could return to Freetown, with DFID being required to step in to moderate discussions. In the future, clearer expectations should be made about the responsibility of the service provider to agree workplans with the PPP Unit and advisor.

Key actions

Co-ordination and clear expectations among donors and the PPP Unit will be required as we approach the end of the project. The Steering Committee should ideally look into reducing the number of transactions that the PPP unit are taking forwards so that critical PPP projects are prioritised effectively, obtain sufficient focus and are provided with adequate level of resource in the form of experts and technical staff. Action: PPP Unit Steering Committee to be held by August 2015 to clarify expectations and requirements.

The PPP Unit has ambitious plans to complete more than six pre-feasibility studies in local government, transport, energy, health, roads maintenance, regional distribution, and waste management, in the remaining four months of this project. Action: IMC and PPP Unit to agree process for concluding these pre-feasibility studies, including potential funding for seventh study, before 5 July.

The PPP Unit plans to complete feasibility studies and send newly recruited staff on study tours to Uganda and Senegal with the DFID grant. Both are important initiatives but this will require careful resource management to achieve. Action: PPPTA to work with PPP Unit Director to ensure robust resource planning is place to achieve both aims.

Has the logframe been updated since the last review?

The logframe was updated in August – September 2014. This has formed the basis for the Quarterly Reports since then and this Annual Review.

An update is recommended to reduce the 2015 milestone to ten staff who are trained in PPPs, to reflect the latest staffing management documents.

A further update is recommended to reduce the number of DFID-funded study tours from six to four, taking into account that three other study tours to South Africa, Nigeria, and India took place with non-DFID funding.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Quality Assurance to PPP transactions provided: increase in a number of quality PPP transactions
Output number per LF		1	Output Score	A
Risk:		M	Impact weighting (%):	50
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones		Progress
	2014	2015
Number of feasibility (pre-feasibility) studies for PPPs completed	4	6	Not met but plan to accelerate progress (7/8 studies by Nov 2015)
Evidence of VFM from pre-feasibility studies (review findings)	Positive VFM	Positive VFM	Insufficient information
Number of line ministries and Local Councils requesting support from PPPU	7	10	Met. 24 projects from 13 MDAs at various stage of consideration

Key Points

The evidence suggests mixed results on the indicators of this output, which were largely limited directly as a result of restrictions posed on travel and holding large gatherings which resulted from the Ebola crisis. A large number of projects from line ministries and local councils are under consideration and this indicator has been met. However, there have been delays to pre-feasibility studies on PPPs, and therefore there is insufficient evidence at present of these producing VFM at this point of the project. The PPPU is now making plans for accelerated progress on the pre-feasibility studies. However, the timetable for completing these is ambitious and more time may be needed to allow their conclusion.

In particular, the PPPU is accelerating work on a number of high priority projects.
- FCC Mall and King Jimmy Mall: the PPPTA has provided comments and advice on the final draft of the report, which will mark the delivery of the first DFID pre-feasibility report.
- Freetown Estuary Study: inception report has been produced and pre-feasibility study is now underway to conclude by end June 2015.
- Solar Project: pre-feasibility study is underway to conclude by end of August 2015.
- Health post-Ebola. The IFC-World Bank consultant is investigating various projects relating to health and will be concluded by end of July 2015.
- A number of other post-Ebola Pipeline projects of Affordable Housing, Local Content Distribution, Recycling and Waste, and Road-maintenance are also planned to receive pre-feasibility studies to be completed by end of September 2015.

It is not possible at this point to assess the second indicator on VFM in pre-feasibility studies, due to the lack of any finalised studies. Once the first studies are finished (expected June 2015), these should be looked at carefully to understand whether value for money is being delivered. On VFM more widely, the PPPTA has provided advice to the Unit on a number of PPPs not covered by the pre-feasibility studies, such as on agriculture, the Deep Sea Port, and Freetown Water. This helps to demonstrate that the PPPTA’s service are providing value for money for the Unit overall. Further, the PPP Operational Manuel, which contains clear criteria for shortlisting a PPP and guidance on dealing with unsolicited proposals, provides a framework for ensuring that GoSL does not enter into PPP deals representing poor value for money.

The PPPU has demonstrated good progress against the final indicator relating to the number of requests from ministries and local councils requesting support. Annex A shows the full pipeline list and the MDAs requesting support. This indicator has been met and exceeded and demonstrates the strong recognition of the positive role the PPPU can play.

Summary of responses to issues raised in previous annual reviews (where relevant)

The previous Annual Review highlighted the need for an agreed PPP Pipeline study to prioritise projects and then for pre-feasibility studies to be quickly tendered and completed. The World Bank Pipeline Study faced constant delays but was finalised in October 2014. This was subsequently agreed with the Government to produce a prioritised list of projects. The outbreak of EVD and decision to withdraw the PPPTA prevented progress from being made on the pre-feasibility studies, but plans are now in place to catch up.

The previous Annual Review also recommended accelerating the plans to design of appropriate PPP guidelines and capacity building for local councils. Progress has been relatively good in this area. The Crisis Pipeline study was amended for MDAs and guidance and presentations were given at a workshop for MDAs and local government in April 2015.

Recommendations

Pre-feasibility studies should be completed as soon as possible and monitored carefully to ensure delivery. An assessment should be made by end August on the likelihood of the studies’ completion, and if it is necessary to make a no-cost extension to the project.

While it has not yet been possible to demonstrate value for money in pre-feasibility studies, evidence should be sought in the two PFS’s concluded in June 2015. This value for money evidence should be communicated widely so as to enhance the credibility and reputation of the PPP Unit within government.

MDAs’ capacity and understanding of PPPs should continue to be increased so that the PPP Unit can support them in the most effective way.

Output Title	Capacity to facilitate, negotiate, and implement PPPs improved
Output number per LF		2	Output Score	B
Risk:		M	Impact weighting (%):	50
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones		Progress
	2014	2015
2.1 - Evidence of sustainability of PPP Unit beyond 2015 (review findings)		Sustainable Unit	PPP Act in place and 5 Year Sustainability Report produced
2.2 - Number of staff trained and managing PPPs, including technical advisers	12	15	Not met, but progress made – 10 staff received training.
2.3 - Successful regional study tour: links to regional partners established (number of links)	4	6	Not met, but special circumstances. Plan is place

Key Points

Although performance against the indicators is mixed there is some strong evidence that the PPPU had been sufficiently empowered and enabled by the GoSL to facilitate, negotiate and implement PPPs. However there is also enough evidence to suggest that it will always be hard to ensure that the PPP unit retains expertise that has been built up through capacity building support provided by donors.

In the past year there has been an improvement to the legal and institutional frameworks in which the PPPU operates, making it more sustainable. The passing of the PPP Act marked an important milestone towards increasing the robustness of the process for agreeing PPPs. This Act requires for feasibility studies and Cabinet approval for any public sector organisation to enter into a PPP, giving an important level of scrutiny and oversight to this process. As part of this review it was commented several times that the number of unsolicited PPP bids, and the time spent considering these, has subsequently decreased.

The PPP Unit Strategic Plan 2014 to 2019 and “Sustainability Report” (May 2015) and “Project Management Report” sets out a considered assessment of the PPPU’s future strategy and capability requirements, which is now being put into action. In these respects, there is greater clarity about the role and responsibilities of the PPPU in the future, which does represent evidence of the Unit’s sustainability.

The PPP Act also provides the PPPU with its own budget allocation from the Ministry of Finance and the ability to retain a proportion of the funds it raises as part of its activities. In June 2015, le 103 million was approved for the PPPU and it is expected that a similar amount will be agreed for Q3 and Q4 of 2015. Given the increased political and financial support for the PPPU, the organisation is much closer to being a sustainable unit. However, ongoing support is likely to be required to ensure the Unit has sufficient funds to cover all its costs, and to continue improving staff skills’ in managing PPPs.

Progress has been made against the second indicator but it has not been met. Staff were enrolled on the rigorous and specialised PPP IP3 training course. Four completed stage one of the training and are progressing to stage II, while a further three staff have completed stage III. This is complemented by commitment to on-the-job learning and shadowing of more senior staff. This gives a reasonable degree of confidence about staff training but there will be a challenge to retain this specialised knowledge and experience going forward, particularly when the PPPTAs leave at the end of this project.

Indicator three has not been met but the ability of staff to go on study tours was severely restricted by the Ebola outbreak; it is likely that the PPPU would have carried out more study tours without this. In addition, three study tours to Nigeria, India, and South Africa were completed in Year 1, the latter with support from the PPPTA, but using funds provided by other donors are therefore not counted against the DFID logframe. They have subsequently made plans for two study tours to Uganda and Senegal in the remaining time of the project. Given the exceptional circumstances around this indicator, an A grade for this output overall is judged appropriate.

Summary of responses to issues raised in previous annual reviews (where relevant)

The previous Annual Review recommended a pricing and charging arrangement to provide non-donor based financial stability for the PPPU. This has been achieved through the PPP Act. However, there is still limited evidence of co-ordination among donors and their associated PPPTAs ahead of their withdrawal at the end of this project.

The previous Annual Review also recommended PPP staff complete a formal certificate programme and for regional study tours to be taken forward. The certificate recommendation is addressed through the IP3 training and qualification. Regional study tours have been disrupted given EVD travel restrictions but will be addressed in the coming months.

Recommendations

Study tours took place in 2013 but using other donors’ funding, underlining the need for co-ordination between donors. No study tours have taken place yet using DFID funding. The target for the remainder of the project is unlikely to be met and funds should be reallocated to other priority activities in support of critical PPPs.

Building on the existing reports of the office structures, action should be taken to address the high level of staff turnover and to ensure that staff are incentivised to remain in their jobs Some of the staff turnover can be attributed to the onset of the Ebola Crisis, but there are other cases whereby the staff through capacity building become more marketable and presented with new job opportunities. It may be the right time to consider the contracting in of expertise to negotiate critical PPPs as a better solution that serves the current needs of Sierra Leone in this new macro-economic environment of post Ebola and Iron Ore crises.

DFID and other donors should co-ordinate immediately to ensure a consistency in their support and to ensure a smooth exit in their support from the programme. The Steering Committee should be reconvened in July or August 2015 to discuss this with donors and staff.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

Only £568,364 (74%) of the budget has been utilised to date. The underspend falls well short of what had been profiled to spend by this stage in the project lifetime within the contract (£765,712). The budget line is split into two. One component is for the provision of the PPP Technical Assistance (PPPTA) which is for actual costs only and paid at regular intervals according to the payment schedule. The other budget line is for equipment and the provision of pre-feasibility studies.

The low budget use is largely due to the low utilisation of the allocation for pre-feasibility studies to date, which in turn is a symptom of the delays setting up this project and the impact of the Ebola outbreak. If pre-feasibility studies are completed during the remainder of the contract then we expect this money to be spent accordingly. In addition, in the revised workplan agreed in January 2015, there is a small reduction in the number of days to be worked by the PPPTA.

VfM performance compared to the original VfM proposition in the business case

The business case proposed achieving value for money by delivering on the outcomes of improved electricity access, and by managing the project expenses for the PPPTA and pre-feasibility study fund in an effective and efficient way. This review found that financial reports and invoices have been submitted on time, and that the pre-feasibility fund is being managed efficiently; in this regard the service provider, IMC, is meeting expectations to deliver value for money.

Given the EVD outbreak and the evacuation of the PPPTA, progress on the pre-feasibility studies has been slower than expected. However, given that invoices are based on actual costs only this does not impact upon the value for money that is spent on this project.

Concerns were raised in the 2013/14 Annual Review over the added value being delivered by IMC’s involvement. This does not appear to have been substantially addressed. IMC’s overall role remains focussed on managing the pre-feasibility study fund procurements and payments, and quality assurance to the work carried out by the PPPTA. IMC carried out work on the training needs analysis and specific documents throughout the year, but there may be scope for provide more detailed technical input on the actual PPPs, provided this input can be agreed with the PPP Unit.

Although IMC took responsibility for managing the tender of the two PFS’s in September-October 2014, there were long disagreements between IMC, the PPP Unit, and the PPPTA about the revised workplan during the EVD-outbreak and the role the PPPTA could play while adhering to IMC’s Duty of Care policy. The result was that a DFID employee eventually had to step in to mediate in an issue which DFID would normally expect the implementing partner to manage. Clear expectations should be set about the responsibility of the implementing partner to agree such issues with the PPP Unit and clients.

Assessment of whether the programme continues to represent value for money

There is little tangible evidence that this project currently represents value for money, due to the lack of tangible progress towards implementing a PPP. However, the Value for Money argument outlined in the Business Case is still relevant. The total cost of running the PPP Unit is extremely small compared to the size of transactions that it will be involved with.

As the payments are currently made only on actual costs, the lower expenditure during the past nine months of slow activities means that the money paid still represents value for money. This was a departure from a milestone based approach in order to improve VfM and financial controls for DFID whilst resources were being prioritised for the Ebola response. An extension of the project life-span to allow conclusion of the pre-feasibility studies would ensure value for money if it allows the reports to be produced to the required standard. Any consideration about extending the project longer should consider whether IMC and the PPPTA are the most appropriate partners for this project, and exactly what value they both add.

Quality of financial management

Invoices for this project were submitted on time, and to the required level of detail and accuracy. Invoices have been in line with forecasts, despite the exceptional circumstances in Sierra Leone discussed in this review. The 2014/15 audited annual statement has not yet been received and needs chasing now that two months have passed since financial year closing of accounts.

Date of last narrative financial report	19 June 2015
Date of last audited annual statement	2014-15 statement outstanding

E: RISK (½ page)

Overall risk rating: Medium

The overall risk rating for this project has not changed since inception and is still assessed as medium risk overall in the likelihood of this project meeting its expected goals. However, there is a high risk that badly negotiated and managed PPPs could end up being unaffordable to the GoSL. DFID should consider whether a no-cost extension to this project would enable time for Donors to draw together a joint position on continued support to the PPP unit.

Overview of programme risk

The risk assessment on fiduciary and fraud risk is still assessed as low. Sufficient safeguards, as outlined in the business case, remain in place to protect DFID funds. No updates have been made to the risk register this year.

Outstanding actions from risk assessment

There are no outstanding risks from the assessment at this point.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

The milestones in the Logframe for this project were based on the assumption that this annual review would be undertaken one year after the start of on the ground implementation. The project was agreed in June 2013 but the procurement was not concluded until autumn 2013. After this, IMC quickly deployed the DFID-sponsored Technical Adviser for the PPP Unit t Sierra Leone to Sierra Leone on 11th November 2013, at which point work actually started. Therefore this review only covers eight months of the project’s second year of work. Information about the PPP Unit’s expected outputs at the end of the year has been taken into account in this review.

Performance of partnership (s)

It is clear that there have been tensions in the relationship between the PPP Unit, the PPPTA, and IMC. IMC, the implementing partner, reported difficulties in agreeing a governance and oversight mechanism with the PPP Unit and the PPPTA. The EVD outbreak represented exceptional circumstances but the three parties failed to reach a consensual decision on the best way to respond in terms of the activities and number of days worked by the PPPTA during this time. The result was that DFID was required to mediate in November 2014, which is not a role that DFID usually expects to play when tendering for the services of an implementation partner.

Asset monitoring and control

£97,184 of assets have been provided to the PPP Unit. Assets supplied included office equipment, generator for power and three vehicles. A complete asset register for this project held by the implementing partner was provided to DFID on 28 November 2014.
G: CONDITIONALITY

Update on partnership principles (if relevant)

Sierra Leone is a recipient of general budget support from the UK.  This arrangement is guided by a memorandum of understanding between DFID and the Government of Sierra Leone that requires it to demonstrate commitment to the UK’s partnership principles, in line with the UK’s conditionality policy.  A comprehensive assessment is made each year and updated each quarter, prior to budget support disbursements.

The establishment of the PPP Unit by the Government of Sierra Leone, and its continuing support for the remit of the Unit can provide evidence to support delivery against two of the four partnership principles:

- Progression and completion of PPPs could be used as evidence to show that Partnership Principle 1 - a commitment to reducing poverty and achieving the Millennium Development Goals (MDGs), is being upheld
- Evidence is needed on the role of the PPP Unit in providing an additional check, and service to Government in quality assuring tendering, negotiation and implementation of PPPs and therefore GoSL delivery against Partnership Principle 2 - a commitment to strengthening financial management and accountability, and reducing the risk of funds being misused through weak administration or corruption.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

There is evidence in many countries for the value of PPPs; similarly there is lots of evidence of poor quality and bad VfM PPPs also. PPPs are inherently risky for Governments and sometimes they are completely unaffordable for the public sector when set against other priorities.

It is important to remember that the PPP Unit existed prior to DFID funding in this project. Therefore, when monitoring this project we are looking for a positive improvement in the capabilities and process for managing PPPs.

DFID undertook a review of evidence of the costs and benefits for centralised PPP Units as part of the original Business Case for this project and although finding that there is no quantitative evidence, the findings did identify a number of factors which can contribute to the success of central PPP Units. These were incorporated into the design of the project.

This review found that the four key factors that were incorporated in the design of DFID’s support to the PPP Unit are being addressed but there is still work to do to fully meet all of these. The Unit can be viewed to have a good level of authority at the centre of government and a transparent process is in place to assess PPP proposals. However, technical expertise and capacity still needs to be enhanced if the PPP Unit is truly able to manage complex PPPs.

Monitoring progress throughout the review period

Monitoring of this project has been undertaken through the review of quarterly written progress reports provided via IMC worldwide from inputs provided by the PPP-TA and PPPU.

Monitoring has been taken forward through DFID’s direct engagement with the PPP Unit (with PPP-TA in attendance), the IMC, and donors supporting the PPP Unit.

This Annual Review has been completed by a DFID policy adviser temporarily working in the Sierra Leone office on “surge”. He has drawn from progress reports from the implementing partner and from meetings with the PPPTA, IMC, the PPP Unit, and other donors working with the PPP Unit.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessment
Key points
Summary of response to programme issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process