Amendment Letter

To increase DFID’s contribution to The British Red Cross Society (BRCS) for supporting the International Federation of Red Cross and Red Crescent (IFRC) Appeal- Amendment 03 to the Memorandum of Understanding.

ARIES Code: Component 205268-110
Purchase Order Number: 40108035
Emergency Appeal- Bangladesh Population Movement 2019

I refer to the Memorandum of Understanding between the Government of the United Kingdom of Great Britain and Northern Ireland acting through the Department for International Development (“DFID”) and the British Red Cross Society (BRCS-220949) signed on 25/10/2017, followed by Amendment 01/2018 on 06/09/2018 and Amendment 02/2019 on 23/03/2019.

Following recent discussions on the Emergency Appeal 2019 of the International Federation of the Red Cross (IFRC), DFID proposes to increase the amount made available to British Red Cross Society by GBP 1,000,000 (one million pounds sterling.)

I propose that the figures and words GBP 3,500,000 (Three million, five hundred thousand pounds sterling) in paragraph 2 of the amendment 1/2018 be deleted and replaced with the figures and words GBP 4,500,000 (Four million, five hundred thousand pounds sterling).

As soon as this Amendment Letter comes in to operation DFID will make payment in accordance with the following payment schedule:
£1,000,000 by 31st August 2019

I also propose that the end date of 30th September 2019 in paragraph 1 of the Amendment 2/2019 be deleted and replaced by 30th June 2020.

The BRCS will submit to DFID the following reports, which is a revision of the paragraph 14 of the original MOU:

- Submit a progress report on 1st October 2019 and Final Progress (narrative) and Financial Report on 1st Jan 2020 against the previous contribution (£3,500,000) made as per Original MOU and Amendment 1 & 2.
- Submit a standard progress report along with financial expenditure against the £1,000,000 contribution to the Emergency Appeal 2019 - by 1st January 2020 and 1st April 2020.
- Within 3 months of completion of the Project, a standard final progress and financial report on the Emergency Appeal 2019 (£1,000,000) by 1st of October 2020.
- An annual external audit report of IFRC’s consolidated accounts conducted by external auditors by 30th June 2020 against previous contributions (£3,500,000) and for the contribution to the Emergency Appeal 2019 (£1,000,000) by 30 June 2021.

This letter of amendment will place on record our common understanding of the above change and will come into operation on the date you sign the confirmation below. This note will be known as Amendment No. 03/2019

Signed on behalf of DFID:

DATE:
Name:
Position: DFID Country Representative Bangladesh
Address: British High Commission, UN Road, Baridhara, Dhaka

Signed on behalf of BRCS:

DATE:
Name:
Position: BRC Executive Director, International
Address: British Red Cross UK Office, London