Business Case and Intervention Summary

Intervention Summary

## Title: Short Term Technical Co-Operation support to the St Helena Government to deliver public services and help prepare for air access from April 2014 to March 2015
What support will the UK provide?
This package of support to the St. Helena Government (SHG) will provide short-term technical cooperation expertise where the needs cannot be met from local resources and human capacity. The UK Government will provide up to £2,000,000.

Why is UK support required?
The UK is responsible for meeting St. Helena’s reasonable assistance needs. The Budget Aid settlement recently approved addresses the recurrent budget deficit. However, it does not address SHG’s need for short term technical cooperation expertise. An island with a small resident population and limited local revenue cannot provide either the personnel or the funding for all technical expertise required. / As St Helena moves towards air access, with the associated economic development, SHG requires a professionalization of the services it delivers and Short Term Technical Cooperation expertise will support this by providing technical knowledge and expertise that would otherwise be beyond the reach of its budget. / What will we do to tackle these challenges? / DFID and SHG will agree a prioritised listing of posts or activities to be funded. DFID Advisory Cadres will support SHG by proving advice and guidance on the input and outputs from short term technical cooperation assistance. / Who will implement the support we provide? / Funding will go directly to SHG who are responsible for implementation.

What are the expected results?
What will change as a result of our support? / This support ensures that short term gaps in public service delivery will be filled; this allows SHG to continue delivery in critical areas such as education, health, access and social protection. / SHG will be able to continue improvements of service delivery to the island’s residents. The Capital Programme is an example of where SHG improved its ability to deliver projects over the last year as a direct result of Short Term Technical Cooperation. / SHG will be able to expand its portfolio of services to address ministerial and SHG Directorates’ priorities. An example of where 2014/15 funding will address the HMG’s as well as SHG’s priority area of protecting vulnerable children and Women is the proposal for improving the social worker and policing capacity. These inputs are deemed to be necessary based on the findings of the Lucy Faithfull Foundation Report[1]. / Short Term Technical Cooperation also provides cover for posts which allows Saints the opportunity to gain the qualifications required to take up posts which would otherwise be filled with Long Term Cooperation support. / What are the planned outputs attributable to UK support? / There are two planned outputs: (i) improved effectiveness of public service provision (measured against SHG’s Sustainable Development Plan targets); (ii) improved human resource capacity available in SHG and in accordance with DFID’s TC protocol. The TC protocol will be reviewed this year and agreed with SHG to improve TC management. / How will we determine whether the expected results have been achieved? / SHG is responsible for oversight of its budget as well as the regular monitoring of public service delivery, capacity and access to the island. It publishes monthly financial and performance management information, corporate risks, capital expenditure and capital programme milestones on its website with an accompanying narrative. All funds provided by DFID to SHG are subject to audit from the independent St Helena Audit Service. / Where performance of the overall project and of individual short-term TC appointees is not in line with expectations, remedial measures will be agreed. DFID Advisers and Programme staff visit the island annually to review the adequacy and efficiency of service provision. The Departmental Annual Planning Mission will review progress against the Sustainable Development Plan targets and this will include a review of Short Term Technical Cooperation.
[1] The Lucy Faithful Foundation undertook a child risk review in 2013 which found failings in child-safeguarding prevention, management and response. Critical senior social work technical assistance is required, as the island has no local qualified social workers; capacity needs to be built in several departments to improve child safeguarding and deliver a multi-agency approach. The Action Plan will provide the framework for this.

Business Case

Strategic Case

The UK’s relationship with Overseas Territories is different from that with independent developing countries. The International Development Act 2002 specifically exempts aid to the OTs from the poverty reduction criteria that apply to the rest of the DFID aid budget. With the exception of the European Union (EU), the UK Government is the only source of significant grant funding. The UK’s obligation to the OTs derives from the United Nations’ Charter: “to promote to the utmost, within the system of international peace and security established by the present Charter, the well-being of the inhabitants of these territories”. / In 2012[2], the UK Government published a White Paper that set out a vision for Territories as vibrant and flourishing, proudly retaining aspects of their British identity and generating wider opportunities for their people. The paper had three main strands: (1) to strengthen the engagement and interaction between the UK and the OTs; (2) to work with OTs to strengthen good governance arrangements, public financial management and economic planning; and (3), to improve the quality and range of support available. / The UK’s responsibilities to St. Helena, and to all the OTs that receive aid, are: / to meet the territory’s reasonable assistance needs for public services; / to accelerate the territory towards economic self-sufficiency, where this is possible; / to manage the risk of contingent liability. / The signing in November 2011 of a contract between SHG and Basil Read to construct an airport provides the context for the 2014/15 budget aid settlement. The airport provides the means for St. Helena to develop, over time, a self-sustaining economy. / Airport construction remains on time and on budget. Preparation continues for an opening date in February 2016, with UK Government support for a wide range of measures being planned and implemented by SHG, Enterprise St Helena, local businesses and potential external investors to ensure that the airport delivers economic benefits for the island. / As an aided OT, St. Helena faces HMG restrictions on borrowing. In practice, this means that grant-funding from DFID and the EU are the only resources currently available to help SHG finance its budget deficit as well as public investments in infrastructure aimed at helping stimulate private sector growth. / The need for DFID subsidy for St Helena is based on two key factors. First, there is limited ability to pay for public goods and services from local revenue. Second, there is limited ability to reduce services or the cost of them, especially as the majority of goods are sourced and shipped from the UK and South Africa, and local wages are already very low. / The island’s low income base limits the volume of domestic revenue that can be raised and its isolation and small population inflate the costs of providing a range of basic public services such as adequate secondary education, policing, social welfare protection and a standard range of health services. / The lack of socio-economic data remains an acute challenge in understanding poverty, inequality and socio-economic trends in St Helena and constrains the development of evidence-based policy-making. SHG’s Senior Statistician, Economist and Social Policy Planner are currently developing data sets to address this problem and in 2013 carried out a Household Expenditure Survey, the results of which are pending. Earlier analysis shows that between 1998 and 2008 whilst child dependency has halved, age dependency[3] has nearly doubled, rising from 14% to 26%. This underpins a declining birth rate, with fewer children to meet future skills needs and a greater number and proportion of older people (over 64) with increased need for and thus pressure on services for the elderly. With low wages fuelling economic migration of those in the 20-40 years of age group, this indicates a constrained labour market and indeed this is the case[4]. / In 2013 SHG undertook a light touch labour market survey for the Shortage Occupation List[5], which forms part of the new points-based immigration system. The survey highlights shortages of skilled labour in the construction sector, hospitality and catering, and transport; and unskilled labour shortages within the agriculture and construction industries. In the public sector, SHG faces severe capacity constraints across the board and especially in key service delivery areas such as the police (including immigration and rescue services), education, and health and social services. / The population of St Helena declined from 5,750 in 1990 to a low of around 4,000 in the 2008 population census. The ageing population, combined with a low unemployment rate perpetuate the aforementioned labour market skills gap, which further underpins the need for our support. This skills gap is a critical factor in managing public service delivery and seriously constrains private sector growth. There is some limited evidence of underemployment and weak productivity which could provide some labour market slack. / Recent data suggests that the declining population trend has started to reverse. At the end of 2013 the estimated population stood at approximately 4,500. In 2013 an additional 166 Saints returned to the island with a long-term intention to stay. At the end of 2013 Basil Read were employing 486 people on island of whom 349 were Saints. Basil Read now employs between 10 – 15% of the local workforce. There is also the potential for tourism jobs to substitute for construction when the airport is completed, with a more permanent impact in reversing decades of outward net migration. / This intervention offers important opportunities for SHG to manage improvements in public service delivery as the island moves towards having air access in less than 2 years’ time. It will provide SHG with the necessary technical assistance which would normally be beyond the islands capacity, capability and budget.
B. Impact and Outcome that we expect to achieve / This intervention will help develop more efficient and effective public services by enabling SHG to access international technical expertise in a range of policy areas critical to public service delivery and economic development. Through supporting improved technical capacity the project impact will be a contribution to meeting reasonable assistance needs and to the key SDP goal of accelerating sustainable social and economic development. This will be supported through expected outcome results that will contribute to improved effectiveness of public service provision (measured against SHG’s Sustainable Development Plan targets).
[2] FCO, June 2012.The Overseas Territories: Security, Success and Sustainability. Crown Copyright, London.
[3] Economic dependency refers to the ratio of economically active people to those who are not economically active. The latter are dependent on the contributions of those in employment. The economically dependent are usually subdivided by children and the elderly who do not make economic contributions. An aging population means that there are fewer workers supporting increasing numbers of elderly people with consequent strains on the public purse.
[4] SHG,2013. Draft Socio-Economic Paper.
[5] Ibid.

Appraisal Case

What are the feasible options that address the need set out in the Strategic case? / Option 1 – meet full SHG’s short-term technical cooperation requests / Option 2 – meet core short-term technical cooperation priorities / Option 3 – do nothing
B. Assessing the strength of the evidence base for each feasible option / In the table below the quality of evidence for each option is rated as Strong, Medium or Limited. / Option Evidence rating / 1 – meet full requirements Medium: There is evidence that short term technical cooperation can strengthen intended outcomes, but is most effective when it is demand driven by the partner Government and strongly aligned to their immediate objectives. Effectiveness can be hindered where inputs are not considered in the context of the current capacity of the public service, including capacity to absorb technical advice and incorporate into sustainable reform. / 2 – meet core requirements Medium: As above. / 3 – no intervention Strong: Strong evidence gathered during the Development Aid Budget Mission 2014 confirms that with no resource for short term technical cooperation, public service delivery standards would suffer and the professionalization of services will not happen.
C. For each feasible option, what is the assessment of local capacity? Is the intervention likely to strengthen capacity in a durable manner? / For Options 1 and 2 - It is expected that each technical cooperation officer will be required (where practicable) to identify a local counterpart for the duration of his/her contract. In addition, a strong focus on training and knowledge and skills transfer will be an integral part of the role/responsibilities of each STTC officer (as reflected in terms of reference) to support SHG’s workforce/succession planning processes. / For Option 3 SHG would have insufficient funding for training and on-the-job coaching that would be essential to building the capacity of local staff. / The intention is also to manage TC funding in a flexible manner according to SHG priorities in line with the 2012 DFID-SHG Technical Cooperation Protocol.
D. What measures can be used to assess Value for Money for the intervention? / As this is an umbrella project, each individual request for a STTC input can be assessed for Value for Money. DFID Advisory and Programme Management staff approve all Terms of Reference and financial proposals for each input. DFID has an overview of the Short-term Technical Cooperation recruitment process through monthly monitoring reports. Furthermore, SHG prepares end-of-contract performance reports and each STTC officer is expected to submit a concise end-of-contract report summarising achievements against ToRs and any recommendations to further advance services.
E. If any, what are the likely major impacts on social development? / The STTC project is important to social development progress in St Helena, particularly through helping to strengthen the delivery of the Sustainable Development Plan (SDP) across the board but in particular the Social Policy Plan (SPP). The SPP is a key SDP pillar focussed on reducing relative poverty and supporting vulnerable groups, improving equality of opportunity in socio-economic development, and facilitating social cohesion across the island. We have already seen the benefits of STTC to support a welfare reform process in St Helena, culminating in new and improved policy. Continued support to education, health and social service delivery will strengthen delivery of the SPP, bridging critical short-term gaps and enabling analysis for improved policy and programme delivery. The Budget Aid Settlement, especially Long Term Technical Cooperation will have a much larger impact in addressing social development issues.
F. For fragile and conflict affected countries, what are the likely major impacts on conflict and fragility, if any? / N/A
G. What are the costs and benefits of each feasible option? Identify the preferred option. / Option 1 – meet full SHG’s short-term technical cooperation requests / This option is not considered Value for Money. This could lead to SHG recruiting for posts for which the justification is not strong and/or for which the capacity to deliver sustainable improvement might not be available on St Helena. . Costs in excess of £2.7m. (It should be noted that the original bid from SHG for Short Term Technical Cooperation was £3.4m) / Option 2 – meet core short-term technical cooperation priorities / The preferred option. This option ensures that SHG maintains their ability to access international advice that will lead to more effective and efficient delivery of public services. The intervention allows SHG to (1) improve their own efficiency and maintain and further improve essential public services and (2) call on resources that are required to take full advantage of the opportunities that air access will bring. / Option 3 – do nothing / This option has not been considered as the island needs technical assistance to deliver public services and help prepare the island for air access.
H Theory of Change

Commercial Case

Delivery through a third party entity (multilateral organisation; civil society organisation or support to government

Why is the proposed funding mechanism/form of arrangement the right one for this intervention, with this development partner? / The proposed mechanism is Non-Budget Support Financial Aid. The preferred approach is that all TC posts are contracted directly to SHG. This approach is seen as best practice, not only reducing DFID transactional costs (such as recruitment, contracting, administration and other support), but also increasing local ownership of the process and offering SHG the ability to hold TC officers to account. In line with DFID’s Blue Book Guidance, a Memorandum of Understanding (MoU) between DFID and the SHG’s Finance Directorate will be used.
B. What assurance has been obtained on capability and capacity to deliver? / SHG are confident in their capability and capacity to manage this STTC project and sustaining public service improvements that are the outputs of this intervention. Sufficient management resource is available either locally or will be supplemented through the use of TC funds.
C. Is there an opportunity to negotiate on anticipated costs? / This intervention is not expected to open up opportunities for further negotiation.

Financial Case
A. Who are the recipients of all proposed payments? / SHG is the only direct recipient of all proposed payments under the MoU that formalises this Short Term Technical Cooperation Project.
B. What are the costs to be incurred directly by DFID? / The total cost to DFID is up to £2.0 million.
C. What are the costs to be incurred by third party organisations? / There are no third party organisations that contribute support to the Short Term Technical Cooperation budget of SHG.
D. Does the project involve financial aid to governments? If so, please define the arrangements in detail. / DFID will make four disbursements of programme funds (in July, October, January and March) upon receipt and approval of written disbursement requests from SHG’s Corporate Finance. DFID Accounts transfer funds directly to SHG’s bank account. / DFID will reimburse SHG for short term technical cooperation costs in arrears on receipt of their detailed and certified claim. Funds will be paid from DFID Accounts direct to SHG’s bank account. / These arrangements will be set out in a Memorandum of Understanding.
E. Is the required funding available through current resource allocation or via a bid from contingency? Will it be funded through capital/programme/admin? / Funds will come from OTD’s current resource allocation budget. This can be accommodated in DFID’s Overseas Territories Department’s aid framework in 2014/15.
F. What is the profile of estimated costs? How will you work to ensure accurate forecasting? / Costs are forecast by SHG’s Human Resource Department and quality assured by the Chief Secretary. DFID will review the spending profile on a monthly basis using SHG’s monitoring sheet.
G. What is the assessment of financial risk and fraud? / As with the Budget Aid Settlement, it is not possible to design this intervention to directly reduce fiduciary risk, and in particular the risk of leakage. The 2010 Fiduciary Risk Assessment concluded that there was a moderate overall level of fiduciary risk, incorporating a moderate risk of corruption. Key weaknesses included account code classification, timely accounting information, procurement practice and bank account reconciliation. The Annual Statement of Progress against the FRA produced in February 2013 concludes that SHG has made progress during the course of 2012/13, including through the introduction of joint HR/payroll procedures, publication of monthly management accounts and more complete reconciliation of bank accounts.
H. How will expenditure be monitored, reported and accounted for? / Accounting functions will be undertaken by SHG Corporate Finance under the supervision of the Financial Secretary. SHG’s monthly monitoring report is shared with DFID. / The Chief Auditor will audit the annual financial statements of SHG which will include short term technical cooperation spend. / Protocols governing the management of both long term and short term technical cooperation funding were first agreed with SHG in 2010. In December 2012, DFID and SHG revised the Protocol in line with lessons learnt including making SHG’s use of funds more effective and flexible to meet its needs.
I. Are there any accounting considerations arising from the project? / There are no specific accounting considerations during the lifetime of this project.

Management Case

What are the Management Arrangements for implementing the intervention? / As head of the public service, the Chief Secretary is accountable and responsible for the implementation of SHG’s strategic priorities, with the Financial Secretary providing management support of DFID’s financial contributions towards these priorities. / DFID’s St. Helena Programme Manager will be responsible for the implementation of the programme. They will be supported by other advisory staff within OTD, / OTD’s St. Helena Programme team works closely with OTD’s St. Helena Airport Team to ensure integration between programmes.
B. What are the risks and how these will be managed? / The overall risk assessment is low. / Risk Factor Impact Probability Mitigating Measures / SHG are unable to recruit the range of technical inputs envisaged in an economic and effective and manner Medium Medium Some inputs will be harder to source than others but offering international market rates mitigates. / The Chief Secretary closely oversees the Director of HR’s work to ensure improved management of STTC funds. / The selection of Option 2 mitigates by restricting support to the level necessary to recruit priority inputs. / SHG are unable to manage the technical inputs such that TC outputs are used to achieve desired outcomes Medium Low Chief Secretary as the most senior SHG official has a leading role in ensuring STTC is effective. / Performance Frameworks required for Directorates include outputs to which STTC inputs contribute. / Directors’ using STTC inputs have personal performance criteria on efficient management of staff and resources and all report to the Chief Secretary. / DFID Advisers monitor and support the quality and relevance of many STTC inputs and outputs / Both SHG and DFID approval procedures for each TC input cause delay in recruitment Low Medium SHG and DFID agree a turnaround time frame on submission and approval of ToRs and budget proposals for STTC. / The Chief Secretary oversees the Director of HR’s work to ensure improved management of STTC funds.
C. What conditions apply (for financial aid only)? / Not applicable.
D. How will progress and results be monitored, measured and evaluated? / This intervention is subject to DFID’s project management guidelines that require project completion reviews. As such, each DAPM reviews the financial performance and priority listings of SHG’s use of TC funds over the previous year to ensure that results meet expectations and, ultimately, that value for money is attained. The process may involve direct requests for evidence gathered from end-of-contract reports and progress reports as well as individual’s annual performance reviews.
Logframe / Quest No of logframe for this intervention: 201415