Annual Review – 2018/2019

Title: Increasing Economic Opportunities for Marginalised Youth in Northern Nigeria (Mafita)
Programme Value £ (full life): £29.9Million		Review Date: August 2019
Programme Code: 202584	Start Date: 20/04/2015	End Date: / 31/07/2020

Summary of Programme Performance
Year	2015	2016	2017	2018	2019
Programme Score	A	A	A	B	A
Risk Rating	Medium	Major	Major	Major	Major

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/5191568.odt
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/4519325.xlsx

A. Summary and Overview (1-2 pages)

Description of programme (1/2 page)
The Mafita programme is a six-year programme across four states (Kaduna, Katsina, Kano and Jigawa) in Northern Nigeria, implemented by Adam Smith International (ASI). It was originally designed to enable 68,000 marginalized young people to find full time skilled employment or self-employment through increasing their skills and opportunities by 2021. These targets have been revised down in the subsequent years, and the project is being closed early, as a result of factors which are discussed in this annual review.

The programme aims to increase employment and self-employment in Northern Nigeria for particular groups of marginalised and vulnerable youths - Almajirai[1]; Islamiyah Qur’anic Education (IQE) girls[2]; People with Disabilities (PWD); and Orphans & Vulnerable Children (OVCs) in Northern Nigeria. In 2017, the programme targeted an increase in employment and self-employment by the equivalent of 26,262 full time net jobs and 21,789 full time equivalent self employed by 2021[3] following revisions to the logframe. It aimed to assist 23,500 Micro, Small and Medium Enterprises (MSMEs) to increase their annual turnover by an aggregated £70 million by 2021; and contribute to a reduction in grievances relating to access to economic opportunities and thus help to improve social cohesion and stability.
[1] Almajirai are boys and young men across the North who have come through the Tsangaya system (informal Islamic boarding schools), where they mostly learn the Quran by rote. Most leave the schools with no skills adequate for the labour market and thus face a particularly difficult transition from education to work.
[2] IQE girls are those who have attended Islamiyah or Qur’anic schools at primary level, from which very few progress to secondary or tertiary levels.
[3] This is lower than the 68,000 figure above due to some expectation of labour market displacement.

It is the first skills programme in Nigeria to target these marginalised youths who have been prevented from accessing basic education, skills development and employment opportunities due to a specific set of socio-economic barriers and stigmatization rooted in values, cultural and religious beliefs.

The programme is designed to intervene in both the supply and demand sides of the labour market, increasing both the human capital and productivity of marginalised youths while also working to increase the demand for labour amongst businesses in the North. Mafita is working in these four main components:
- Community Skills Development Centres (COSDECs). – renovation and equipping of existing centres and training of youth.
- Apprenticeship scheme - Master Crafts Persons (MCPs) & Homebased Crafts Persons (HMCPs) – subgroup of the MCPs.
- Technical and Vocational Education Training (TVET) – training the trainers for the COSDECs and MCPs; and related quality assurance.
- Local Economic Development (LED) - Access to Finance (A2F), Business Development Services (BDS) and Transition to Work (T2W).

A two-and-a-half-year testing and piloting phase came to an end in March 2018; with a 3 year scale up phase envisaged, should successful models be demonstrated. The programme intended to take a flexible, adaptive approach to interventions, recognising both the complexity of the environment[4] and that the evidence base on what works in the area of youth employment is weak. Hence it combined rapid, small scale pilots with rigorous real-time monitoring and evaluation to ensure that the programme was able to learn lessons and iteratively develop successful intervention models.

The Business case recognised that ‘the programme will be operating in a risky and uncertain environment, and hence will need to be able to learn and adapt its approach and footprint as it proceeds (nevertheless remaining faithful to the original programme objectives)’. The Business Case further recognised ‘explicitly that the absence of an accepted theory or paradigm for labour market outcomes in developing countries makes it a high risk undertaking that calls for careful testing of interventions to see if they will work in the regional context before committing large amounts of time and resources….. The mix of activities and resource allocation will need to be flexible, with regular adjustments possible so that resources flow to where they are most effective…. allowing for a suitable period of gestation, progress on would be reviewed with the explicit objective of killing off failures and scaling up successes. At the mid-term review, key assumptions will be assessed for their validity and a decision made as to which activities are worth continuing.’

External factors have reduced the feasibility of achieving programme outcomes. In particular, a decline in the economy (an oil-price driven recession and weak recovery) has resulted in:
- Higher unemployment in Northern Nigeria that has made it harder for marginalised youth to compete for formal and full-time job opportunities. It is harder than envisaged in the original Business Case to find jobs for youth in the formal sector.
- Budget constraints have reduced the likelihood that State Governments will take on and fund a skills development system that is targeted at the most marginalised.

While some new industries operate in the North, and some old industries continue (notably leather tanning), many manufacturing, pharmaceutical, assembly and food beverage plants that lost competitiveness in the 1980s remain shuttered, while the economic slowdown and ongoing business environment challenges severely limit new investment opportunities. The limited formal sector employment opportunities are dominated by low paying jobs in local government.

In this context, the Mafita model appears to be limited. Whilst training has been delivered effectively, designing a sustainable system that tailors to the needs and limited employment opportunities of this group has proved a challenge. The sustainability of this model in COSDECs focussing on marginalised youth beyond the lifetime of the project is doubtful. While some significant commitments have been made by State Governments by allocating budget to schemes piloted by Mafita indicate some promise, at the time of this review, they had not yet been converted into budget disbursements.

In addition to this, it has become clear that although the skills training offered form part of the National Occupational standards (NOS), they are not yet highly valued by private sector employers and consumers of services, while the local labour markets also do not have the necessary absorptive capacity for graduates to find employment at the level to which they have been trained. The combination of these two factors has led to a low percentage of beneficiary graduates being engaged in full time employment, despite encouraging initial commitments from employers.

Critically, the original Business Case envisaged Micro-Finance Institution and Bank lending to MSME’s and to increase business turnover and create demand for skilled labour. This has not happened at scale. As few formal jobs materialised, more emphasis was being placed on self-employment following training but finance at scale has yet to materialise for graduates to set themselves up in business.

Overall, the high cost of reaching beneficiaries and delivering results limits value for money, and the potential for scalability. In view of this DFID have taken the decision to responsibly exit from this programme in July 2020. The attached logical framework, against which this AR is scored, and which was agreed following the 2018 review, reflects lower targets than those in the original Business Case. The score of ‘A’ is therefore consistent with the decision to exit the project early. A further reduction in logframe results is also recommended to enable resources to be dedicated to sustaining gains made, rather than delivering maximum outputs in the project’s final year; this revision is currently going through an approval process.

However, despite the early closure and target reductions, Mafita has delivered important improvements to the system, identified some approaches with strong potential; and has valuable lessons which can be more widely shared. Highlights include mobilising additional £3 million into 2019 state budgets for the purpose of targeting marginalised groups for training. In some states like Jigawa, the relevant budget increase between 2017 when the intervention started in Jigawa, and 2018, has been about 25%. One of the programme’s most notable achievements is therefore that it has more firmly placed the upskilling and economic empowerment of marginalised youth on the agenda of the governments of four focal states. This review’s recommendations focus on ensuring these gains are identified and secured.

Summary supporting narrative for the overall score in this review

Output 1. Improve provision of relevant, quality vocational training.
The majority of the indicators under this output have been achieved and the output was scored at ‘A’.

Output 2. Improvement of skills acquisition in the informal sector
The majority of the indicators under this output have been achieved and the output was scored at ‘A’.

Output 3. Strengthen TVET systems and integrate competency-based training for skills development in target states.
The majority of the indicators under this output have been exceeded and the output was scored at ‘A+’.

Output 4. Improve the local capacity to develop business opportunities that create jobs
Some of the indicators under this output have been exceeded although there is a shortfall on access to finance and the output was scored at ‘A’.

Recommendations for the year ahead

Recommendations are detailed output by output in Section B below. They fall into seven main categories and relate largely to securing and sustaining the gains of the programme before closure next year, ensuring lessons from the programme are captured and shared, and a further logframe revision that allows more focus on sustainability at some cost to further output delivery, and which reflects the lower assessed likelihood of reaching outcomes:

1. Securing continued and greater State government commitment and finance, where economic or social returns represent good value for money for continued State investment;
2. Strengthening the private sector partnerships that can secure commercial decisions to invest in trainees and trainee schemes;
3. Effective handover of regulatory and policy work to local government partners;
4. Further develop programming to deepen the impact of Business Development Service Providers. This includes continuing to seek sustainable sources of finance;
5. Seek new funders/sponsors for elements of the programme that may benefit from further investment, and would generate value for money;
6. Ensure an effective lesson learning and communication process, that covers local partners and stakeholders, but also the DFID and the global development community;
7. Revise the logframe to reflect the latest assessments around the theory of change, and to ensure the best balance between efforts placed on sustaining the gains of the programme vs delivering additional outputs.

It is important to remain alert to the risk of encouraging government investment in a system with poor returns on that investment, or which cannot realistically reach adequate scale. With that caveat in mind, however, continued government attention to strengthening quality, management and reach of TVET systems is welcomed, and there are some cost-neutral, or good value, opportunities for adopting the improved practices and approaches introduced by the Mafita project.

## B: DETAILED OUTPUT SCORING (suggest 1 page per output)

Output Title	Improve provision of relevant, quality vocational training
Output number per LF		1	Output Score	A
Impact weighting (%):		20%	Impact weighting % revised since last AR?	Yes 30% to 20%

Indicator(s)	Milestones	Progress
1.1 - Number of COSDECs established to offer skills training programmes tailored towards marginalised youth	13	12 / 6 Katsina, 3 Kaduna, 2 Kano, 1 Jigawa
1.2 - Number of privately funded or Hybrid training centres established to offer skills training programmes tailored to include marginalised youth	1	1
1.3 - Cumulative number of graduates with NVQs of supported centres	2,337	2435
1.4 - Number of graduates COSDEC accessing finance facilitated by Mafita	285	288 (252 through Kaduna State Women’s Empowerment Fund)
1.5 - Number of trainees from demand led short courses. These are directly related to jobs.	75	76

Indicator 1.1 Number of Community skills Development Centres (COSDECs) offering skills training programmes tailored towards marginalised youth
Renovation of six additional COSDECs was completed bringing the total number of COSDECs to 12. The additional COSDECs include three in Katsina (Dutsin Ma, Mani and Malumfashi), two in Kano (Rumfa College and Dawakin Tofa and one in Jigawa (Dutse). The supply of procured tools and equipment has commenced across five COSDECs. Additionally, government has provided trainers for the centres and training is on-going. At the time of the review, the Jigawa Government was unable to complete renovations in the Kazaure COSDEC as a result of delayed release of funds.

1.2 - Number of privately funded or Hybrid training centres established to offer skills training programmes tailored to include marginalised youth
Mafita signed MoUs with two private training providers in Kano State. The centres include the Over-One Consult and Investment Limited (OCIL) and the Hadiza Imam Women Centre (HIWC).
Under the partnership, Mafita provides technical support towards the running of the centres as commercial skill acquisition centres. In return the, centres provide free training opportunities to some marginalised youth. Currently OCIL has enrolled 40 beneficiaries while HIWC has taken on 13 Mafita beneficiaries as at the end of July 2019. The arrangement will further compliment government efforts at providing skills training and increase access to vocational training for marginalised youth.

Indicator 1.3. Cumulative number of graduates with NVQs of supported centres
 In year four, a total of 1,999 beneficiaries have completed formative assessment and are currently awaiting summative assessment. The trainees from 6 pilot COSDECs have completed level two training and Work Experience Learning (WEL) while trainees from four COSDECs are currently undergoing WEL. While summative assessment has been finalised, with the cumulative log frame target of 2,337 NVQ graduates achieved.

Indicator 1.4 Number of graduates COSDEC accessing finance facilitated by Mafita
The Kaduna state team worked towards identifying alternative sources of finance for graduates from COSDECs, and successfully engaged the State Ministry of Women Affairs to include Mafita female beneficiaries in the Kaduna State Women Empowerment Fund (KADSWEF) scheme. Mafita supported the beneficiaries through the application and vetting processes for accessing the funds which required information on the trade types, operating costs, raw materials needed and profit levels of their businesses. The efforts of the team resulted in 252 female beneficiaries in Mando, Sabon-Gari and Kagoro COSDECs to access the state loans. The loans had a tenure of 6 months. Meanwhile in Katsina, Mafita engaged with a local association, the Dakin Kara Entrepreneurship League to tap into their grant initiative. As a result of this, the best COSDEC graduates from cohort 1 were selected to receive grants from the Association. 36 beneficiaries benefited from this scheme. In total, 288 COSDEC beneficiaries were able to access funds.

Indicator 1.5 Number of trainees from demand led short courses. These are directly related to jobs.
Mafita increased its level of private sector engagement in year four: a series of meetings and negotiations took place between Mafita and state agencies and the enterprises (corporates) after medium and large enterprises had been identified. Objectives, goals and benefits for enterprises participating in training of apprentices outlined above was discussed to secure buy-in of participating enterprises. After several discussions, some enterprises agreed and accepted apprentices into their corporations. A full breakdown showing the summary of apprentices in training by enterprise can be found in the attached Annex 5.

On a more qualitative note, the Mafita undertook the following:
- Establishment of COSDEC Management Committees to improve COSDEC management
- Establishment of monitoring teams for COSDECs
- Implementation of Asset Management policy
- Successful implementation of career counselling and open days

The Review team recognised significant effort and considerable activity by Mafita on this output to meet the majority of the targets. Progress was assessed as meeting expectation. – “A”.

Lessons identified this year, and recommendations for the year ahead linked to this output
Key actions
At the end of 2019 Mafita must capture lessons of what has worked and importantly what has not worked in the interventions; how things could have been improved (from inception to March 2020) so that learning is available to be shared with all Mafita staff, State governments, other stakeholders and a wider audience.

Key lessons revolve around the government budgetary commitment principally:
- Non-payment of stipend to beneficiaries that has led to a 28% drop out from the training; and
- Inadequate funding affecting the management and operations of the COSDEC

Recommendations
In response to the two major lessons above Mafita will need to work with government to:
Assess the return on investment to increasing fund allocation for payment of stipend; and
to the COSDECs
Strongly promote commercialization activities that will make the COSDECs self-funding.

There is evidence that progress is slow on establishing opportunities for Business Development Support Services and funding for MCP’s and graduates as envisaged in the original project design and recommended in previous reviews and this needs to be prioritised over the coming months.

It is recommended that Mafita:
Focus on the quality of BDSP (and how they might be reimbursed for their services) and access to finance to ensure MCP’s and graduates are able to receive loans.
- Continue to strengthen governance systems of COSDECs to embed the drive for quality improvement in skills training.
- Continue to strengthen COSDEC Management Committees to actively take part in managing COSDECs.

Output Title	Improve skills acquisition in the informal sector
Output number per LF		2	Output Score	A
Impact weighting (%):		35%	Impact weighting % revised since last AR?	Yes 30% - 35%

Indicator(s)	Milestone(s) for this review	Progress
2.1 Number of MCPs offering apprenticeships to programme beneficiaries	5,070	5951 MCP’s trained and in database but in view of beneficiary numbers in last logical framework change, only 3,563 were needed. Reduction justified.
2.2 Number of apprentices graduating from the apprenticeship programme with NVQ’s	9,611	9,599 (70% graduation rate)
2.3 Number of APPC graduates accessing finance facilitated by Mafita	175	179 / Grants from Trade Associations

2.1 Number of MCPs offering apprenticeships to programme beneficiaries
Currently, there are 3,563 MCPs offering apprenticeship training to programme beneficiaries, whilst 1,150 new MCPs have met the selection criteria to offer apprenticeship to programme beneficiaries. The existing number of MCPs (3,563) is sufficient to cater for the Y5 net target of apprenticeship graduates (7,787). The new MCPs will be kept on a reserve Master list to cover for any existing MCPs who drop out of the system.

2.2 Number of apprentices graduating from the apprenticeship programme with NVQ’s
Due to delays related to the start of activities in Y4, and a recent pause in training as a result of a lack of Personal Protective Equipment, the graduation of the second cohort of beneficiaries was delayed. However, 7,736 new apprentices have graduated from the apprenticeship programme, which will bring the total number of apprentices graduating from apprenticeship to the total of 9,599 as specified in the programme logframe.

2.3 Number of APPC graduates accessing finance facilitated by Mafita
An ongoing crowd funding scheme was conceptualised to target ultra-marginalised beneficiaries (divorcees, PWDs, women in male dominated trades, etc). The Grassroot Micro Finance Bank is the fund custodian that undertakes direct payments to vetted and shortlisted vendors to ensure due process and transparency in the operation of the scheme. The sum of N1.4m (approximately £3,000) was mobilised from third parties and was utilized to support 36 beneficiaries with tools and equipment.

In addition to the crowd-funding scheme, Trade Associations in Kano were engaged by Mafita to support graduate apprentices with grants to support the procurement of basic tools and consumables. A total of 143 graduate apprentices from cohort 1 received grants of Naira 5,000 (about £11) each from the Trade Associations in various trades. This brought the total number of graduate apprentices for whom Mafita facilitated A2F to 179.

The Review team recognised significant efforts by Mafita and considerable activity around this output to meet the majority of the targets and assessed progress as meeting expectation. – “A”.

Lessons identified this year, and recommendations for the year ahead linked to this output
- Mafita has been supporting clusters and Trade Associations with governance frameworks to strengthen their internal processes and make them more organised. This training has led to some MCPs resisting elite capture within the current trade associations and exploring the opportunity to set up their own platforms. An example of this is the Nigerian Automobile Technicians Association (NATA) where four clusters in Kano under the Association came together and set up a parallel trade association, Guild of Automobile and Allied Technicians of Nigeria (GATAN). The new association already has branches in 11 states with current membership at about 6,000 members already. This is fostering competitiveness and ultimately better service delivery.
- In Kano, some MCPs reported that some apprentices have already started their own business in the same trade area while still in training.
- More females than the initial target number met the recruitment selection criteria in the original enrolment. Though this might create some saturation in the more female dominated trades (hospitality, garment/fashion design), it could also have a positive outcome of getting more females into male dominated trades. The implications will continue to be monitored.

Recommendations
During 2019/2020 Mafita should:

- Mafita should develop, communicate, and embed within its partners, a clear and plausible vision for how, and at what scale, the apprenticeship scheme will continue after the programme ends direct support. This will require a careful understanding of role, incentives and relations of stakeholders including cluster groups, MCPs, and state and federal agencies.
- Continue to support and train stakeholders including trade associations, state steering committees and state agencies (public and private sector) to strengthen their management of the apprenticeship programme;
- Develop an Apprenticeship Policy that clearly outlines roles and responsibilities for adoption at state level, recognising where State expenditure has the best returns on investment;
- Scale back apprenticeship for cohort 4 in line with state capacity i.e. number of apprentices, MCPs, trades and locations.

Output Title	Strengthen TVET systems and integrate competency-based training for skills development in target states including capacity building to government and private sector for sustainability
Output number per LF		3	Output Score	A+
Impact weighting (%):		15%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 - Number of individuals trained	2,227	4,929 Government officials, private executives, COSDEC managers / trainers, MCPs and BDSPs
3.2 - Number of national occupational standards (NOS) developed or reviewed with the support of the programme	18	18
3.3 - Number of training providers trained to implement quality assurance guidelines	267	359 Accredited by awarding body, National Business and Technical Examinations Board (NABTEB)

3.1 - Number of people trained
Stakeholders such as government officials, technical assistants, business executives COSDEC managers, COSDECs trainers, MCPs and BDSPs have been trained to internalize best practices in Quality Assurance (QA); implement Competency Based Training and Assessment (CBET); provide innovative business development services to MCPs and Mafita beneficiaries; and to adopt sustainability frameworks developed by the programme in year 4. Evidence of the quality of training of trainers is found in the outcomes of the training then passed on to beneficiaries – the most recent, second, cohort of beneficiaries saw a pass rate of 94%, up from 72% in cohort 1. BDSP training will be judged by business outcomes in the PCR.

3.2 - Number of National Occupational Standards (NOS) developed or reviewed with the support of the programme
In collaboration with the National Board for Technical Education (NBTE), Mafita also reviewed all the existing NOS in Nigeria and developed, in collaboration with NBTE, a short-course framework that defines new demand-driven qualifications that will be delivered as modular and competence-based short-courses to further enable industry to benefit from trained graduates with specific skills targeted to opportunities.

3.3 - Number of training providers trained to implement quality assurance guidelines
To further deepen the quality and relevance of learning in Apprenticeship Training Centres (ATCs) and Community Skills Development Centres (COSDECs); it is imperative to ensure that the training centres implement quality assurance guidelines, which are a prerequisite of recognition by the national and sub-national regulatory institutions. Mafita has supported training providers (COSDECs and apprenticeship clusters) to implement quality assurance guidelines which led to the accreditation of a total of 359 training providers in Kaduna, Kano, Katsina and Jigawa by the awarding body, National Business and Technical Examination Board (NABTEB). This surpassed the 267 training providers targeted. The accredited training providers improved on the key quality assurance indicators such as trainers’ competence; use of appropriate tools and equipment and capacity to implement Competence Based Education and Training (CBET) assessment and record keeping.

The Review team recognised significant efforts by Mafita and considerable activity around this output to exceed targets and assessed progress as moderately exceeding expectation. – “A+”.

Lessons identified this year, and recommendations for the year ahead linked to this output
The Review Team concluded that this output, in its revised format and with the targets established during the review in 2018 is now largely complete and recommended that no additional effort be applied on these milestones. However, the Review Team recommended that some additional qualitative indicators be applied to this output. These included:

Recommendation
Putting in place all legal and regulatory frameworks, policies, etc. that are required to ensure effective hand -over of responsibilities to States, and to identify and mitigate against the risks of the system losing the gains supported by Mafita.

Output Title	Improve local capacity to develop business opportunities that create jobs.
Output number per LF		4	Output Score	A
Impact weighting (%):		30%	Impact weighting % revised since last AR?	Yes. 25% - 30%

Indicator(s)	Milestone(s) for this review	Progress
4.1 - Number of MSEs accessing finance	1,775	1642
4.2 - Number of MSEs and beneficiary start-ups supported by MSE support centres	3,008	4,449
4.3 Number of MCP clusters developed	254	362

4.1 - Number of MSEs accessing finance
As an approach towards facilitating Access to Finance (A2F) for Micro and Small Enterprises (MSEs), Mafita identified, assessed and trained a total of thirty-eight (38) Micro-finance Banks across the four states of intervention (Katsina, Kano, Kaduna and Jigawa States) in Year 3, with the aim of building their capacity. The assessment brought to light knowledge and capacity gaps, which were addressed in subsequent trainings in order that the MFBs could provide better services for the MSEs.

The training was tailored to meet identified needs on specific topics:
- Designing Market-driven Products
- Portfolio Management Strategies for MFBs
- Business Plan and Financial Reporting
- Effective Loan Analysis
- Management Information Systems (Reporting, Fraud & Internal Control Issues)
- Microfinance and Corporate Governance
- Microfinance Relationship Management
- Introduction to Savings mobilization
- Loan Administration and Clients Appraisal Strategies (Processing and   Disbursement Procedure in Microfinance)
- Product Development and Marketing Strategies to Deepen Outreach
- Perspectives in Project Appraisal, Monitoring & Assessing Loan Performance for MSE Lending
- Managing Risks in Savings and Credit Operations (Overview of Microfinance Risks)
- Portfolio and Delinquency Management (Early Warning Signals of Problem Loans)
- Strategies for MFB Business Model: Concept of Sustainability and fund Raising

An assessment of the outcome of the training conducted in Y4 revealed that out of the MFBs trained, six (6) of the banks adopted the proposed systemic changes and ideas, which led to an increase in MSEs accessing finance from them.  These MFBs report an increase of between 15% to 20% in the number of individual MSEs who have able to access finance from them, representing an overall total of 1,642 MSEs

4.2 - Number of MSEs and beneficiary start-ups supported by MSE support centres
Memoranda of Understanding were signed with 6 MSE Support Centres at tertiary educational institution level (both public and private, across all four focal states); and the managing staff of those centres participated in a workshop to create a shared vision for BDS provision, and to come up with solutions to providing services that target the peculiar needs of Micro-enterprises and beneficiaries. The Centres worked with Business Development Service Providers to support COSDEC and Apprenticeship beneficiaries with Career Counselling services before graduation.

Business Development Service Providers from MSE Support Centres have also facilitated entrepreneurship trainings for Trade Association Master Trainers and Cluster Champions in all four states.
An additional 1,441 MSEs/beneficiaries were served by the MSE Support Centres bringing the cumulative number of supported beneficiaries and MSEs to 4,449 which exceeds the logframe target of 3,008 set for Year 4.

The Review team recognised significant efforts by Mafita and considerable activity around this output to exceed some of the targets and assessed progress as meeting expectation. – “A”.

Lessons identified this year, and recommendations for the year ahead linked to this output
Despite these successes, accessing the MSE support Centres continues to be a challenge for most MSEs. The reasons for this include:
1. As most Centres are located within tertiary institutes, most MSEs/beneficiaries find them too far and remote to access.
2. There remains a disconnect between the Centres and most MSEs; with low awareness on both sides.
3. The successes achieved within this output refer mostly to businesses rather than the target demographic group, who remain effectively un-bankable, so the ultimate assumption of the theory of change around securing access to finance is not holding.

Recommendations
In general, it is accepted that some further investment and effort in this area during 2019/2020 could generate positive returns by increasing access to finance on a sustainable, commercial basis. The project should:
- Work with Business Development Service Providers to run Business Clinics that are located within close proximity to clusters/beneficiaries.
- Equip BDSPs with relevant skills and knowledge to deliver better services to MSEs and beneficiaries
- Expand the BDS delivery structure for MSEs and beneficiaries.
- Facilitate access to finance for MSEs and beneficiaries from different financial institutions.
- Explore the development of financial products and services adapted to the needs of micro enterprises by financial institutions.
- Commence an active fundraising campaign by engaging potential donors – with the caveat that the case for future return on further donor investment should be clearly made.
- A learning session with the DFID funded EFInA programme (and possibly other market development programming) should be scheduled to ensure the lessons of the A2F component are shared.

The project should remain mindful of the possibility of early closure of activities if evidence suggests further investment is unlikely to have a positive return.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change and any major changes in the past year
The original Theory of Change was modified during the 2017/2018 Annual Review as some of the original assumptions had not held. Experience in 2018/2019 is annotated in the assumptions below and should be recognised going forward into the last year of the programme.

Key Assumptions

Link No:	DFID Intervention/Outcome	Assumptions
1	Support selected vocational training institutes to pilot reforms	State governments and training centres are willing to support the programme and target groups are able to access centres. / 2018/19 - State government support has been variable and delayed significantly. Target groups are able to access the centres.
2	Provide training grants to master crafts persons and stipends to apprentices	Monetary incentives will help overcome social discrimination and gender bias in taking on apprentices. 2018/19 - Equipment and Business Development Services are being provided. Government have been slow in providing stipends and some states have provided none resulting in an Apprenticeship drop-out rate of 28%.
3	Contracting private service providers to provide services	Capable providers and sufficient jobs for placement. 2018/19 - Weak service providers, particularly Business Development Services that have, and continue to need, extensive capacity building.
4	Entrepreneurship training & start up credit from commercial MFIs	Aptitude for entrepreneurship amongst target group (low %). 2018/19 - Start up credit only now starting to materialise and extremely limited. Evidence of aptitude and self-employment but income levels low.
5	Transformative MSEs provided with finance and BDS	Capable banks, MFIs and BDS providers willing to innovate, / 2018/19 - Start up credit only now starting to materialise and extremely limited. MFI’s extremely cautious when considering loans to target group as default rate in Nigeria is above 18%
6	Increased demand for labour	Investment climate conducive of growth of MSEs, growth of MSE turnover leads to job creation. / 2018/19 - Yet to materialise as limited credit has been available and businesses have not expanded. Continued economic downturn exacerbates the problem.
7	Improved chance of finding skilled work	Creation of skilled jobs by programme overcomes displacement, leading to net job creation. / 2018/19. Formal jobs still not available in sufficient numbers due to economic situation
8
9
10
11	Improved chance of finding productive (non-retail) self-employment	Sufficient share of target group population displays characteristics conducive to entrepreneurship and focal state economies accommodate productive self-employment. 2018/19 – Evidence of graduates showing required characteristics and self-employment but income levels low and opportunities are far from the Full Time Equivalents anticipated in programme design.
12
13
14	Increased incomes	Skilled jobs and productive self-employment increase incomes. 2018/2019 Valid, although skilled jobs not available and self –employment income variable and still relatively low (below national minimum wage)
15
16	Increased social cohesion and stability	An increase in economic opportunities reduces some of the key grievances that underlie conflict, and raise the opportunity cost of engaging conflict, thus leading to lower propensity to joint violent groups or commit violent acts. / 2018/19 Surveys indicate this is valid

A decline in the economy has resulted in:
- Higher unemployment in Northern Nigeria that has made it harder for marginalised youth to compete for formal and full-time job opportunities. It is harder than envisaged in the original Business Case to find jobs for the youth in the formal sector.
- State budget constraints have made it difficult to envisage a situation, post-programme, in which government will take-over a skills development system that is purely targeted at the marginalised.

The formal sector of the economy remains depressed with limited capacity to generate employment. Most of the textile, spinning and weaving mills as well as other major industries across the economic sectors, notably food & beverages, pharmaceuticals, steel and aluminium and automobile assembly, are no longer functional having lost viability and competitiveness in the national economy. Outside the informal sector, the public sector makes the largest contribution to employment.

The original Mafita business case was premised on the assumption that ‘If we provide access to skills development for marginalised young people, we increase their chances of finding gainful employment while reducing the likelihood that they will be radicalised’.

At the time of this review, this model still appears to be limited. Whilst improving economic opportunities for marginalised youth is a central objective for the project, designing a system that tailors exclusively to the needs of this group, and generates a sufficient return, is a challenge. The sustainability of this model in COSDECs focussing on marginalised youth beyond the lifetime of the project is therefore doubtful.

In addition to this, it has become clear that although the skills training offered form part of the National Occupational Standards (NOS), they have not been highly valued by private sector employers and consumers of services. This may improve over time, as the changes are new and not all industries would be aware of the updates, and how it could improve the availability of skilled labour. To date, however, the combination of these two factors has led to a low percentage of beneficiary graduates being engaged in full time employment, despite continued encouraging initial commitments from employers.

The most promising sources of employment for this project in the current economic climate continues to be micro-level self-employment and part-time or casual labour in the informal sector. The logical framework was reviewed at the last Annual Review to reflect this. However, the definition of self-employed needs to be considered carefully as numbers of Full Time Equivalents (FTE’s) was the indicator of success.

In addition, the original Business Case envisaged Micro-Finance Institution and Bank lending to MSME’s and graduates. Mafita are still only now starting to get some traction in this area (with MFIs rather than commercial banks).

Overall, the cost of delivering training and support services, compared to the value of labour market returns, lowers the value for money of the programme, and has helped lead to Mafita’s early closure.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead (1/2 page)
Lat year there were significant reductions of deliverables at outcome and impact level as shown below.

		Business Case	Targets agreed post 2018 AR
Impact	Impact Indicator 1
Increased economic opportunity for young, marginalised people in Northern Nigeria	Number of people recording positive change in incomes	85,624	30,506
	Impact Indicator 2
	Aggregated change in cumulative income	£ 92,083,262	£36,733,341
	Impact Indicator 3
	Change in Employment (FTE Jobs, employed or self-employed)	43,314	9,396
	Impact Indicator 4
	Reduced grievances amongst marginalised youth relating to access to economic opportunities
Outcome	Outcome Indicator 1
Increased numbers of young, marginalised people finding skilled employment & enter non-retail self-employment.	Number of beneficiary graduates/apprentices finding full time skilled employment	55,910	7,909
	Outcome Indicator 2
	Number of beneficiary graduates/apprentices becoming self-employed. Full Time equivalent	12,090	23,411
	Outcome Indicator 3
	Increase in annual turnover of assisted MSEs	£ 70,496,500	£9,851,810

Yearly figures were changed to reflect these overall figures and for year 4 were:
Impact
	Indicator	Planned / 2018/2019	Achieved / 2018/2019
1	Number of people recording positive change in incomes. (Average total annual income increases to reach 15% or more)	2035	2155
2	Aggregate change in cumulative annual income	NGN 265,825,403 / £1,063,302	NGN 161,625,000 / £646,500
3	Change in Employment (FTE Jobs, employed or self-employed)	2213	1617
4	Reduced grievances amongst marginalised youth relating to access to economic opportunities. / Ongoing rolling baseline of new cohorts. Past cohorts continue being interviewed again. Increasing evidence that economic grievances fall from 2 years after training and continue to fall.		Evidence provided

Outcome
Indicator		Planned / 2018/2019		Achieved / 2018/2019
1	Number of beneficiary graduates/apprentices finding full-time skilled employment	1,917		435 / 1635 predicted
2	Number of beneficiary graduates/apprentices becoming self-employed	5,459		927 / 3488 / predicted
3	Increase in annual turnover of assisted MSEs	£3,570,804		£3,570,126
Outcome Score
Outcome Performance / Outcomes did not meet expectation			B

Contribution to Impact

Impact indicator 1. Number of people recording positive change in incomes. (Average total annual income increase to reach 15% or more). Mafita has reached 2173 against a target of 2035.

Impact indicator 2. Aggregate change in cumulative annual income. Mafita has achieved £1,214,707 against a target of £1,063,302.

Impact indicator 3. Change in Employment (FTE Jobs, employed or self-employed). Mafita failed to achieve the target, with 1163 FTE jobs against a target of 2213.

Impact indicator 4. Reduced grievances amongst marginalised youth relating to access to economic opportunities. An ongoing rolling survey shows increasing evidence that economic grievances have indeed fallen, from two years after training and appear to be continuing to fall.

Contribution to Outcome
Outcome indicator 1. Number of Beneficiary graduates / apprentices finding full time jobs
The target for 2019 was 1917 and this was downsized in 2018 from an original target of 6,139.
Of the 2874 graduates and apprentices so far only 435 have found full time jobs in the formal sector (although the prediction for this year is 1635). A further reduction is proposed in the logframe revision currently under review.

Outcome indicator 2. Number of Beneficiary graduates / apprentices becoming self-employed
Of the planned 5459 graduates and apprentices, 927 have been reported as being self-employed (against a logframe prediction for this year of 3488). There is potential to increase this number with the early success of the Apprenticeship scheme, but a further reduction is still proposed in the logframe revision currently under review.

Results are also further undermined by the definition of self-employed which the original programme envisaged as Full Time Equivalent. In fact, the programme reported that telephone surveys have revealed an average wage per month of N9256 (range NGN 1200 – N40,000) and some graduates working as little as three hours a week.

Outcome 3 – Increased annual turnover of assisted MSEs
This has been achieved. Mafita supported MCPs/MSEs with targeted capacity building aimed at improving their ability to grow their business and increase their profitability. Increases in turnover almost exactly matching the target were recorded.

Logframe updates since the last review?
Yes. Logframe was reviewed in September 2018 following the annual review and approved by the Head of Office in October 2018. The logframe showing the original and new targets is attached at Annex 1.

Planned changes to the logframe as a result of this review
Yes, to reflect a responsible exit over the next year, a reduced budget to £4.2 million, and a change in focus to ensure the best balance between sustaining gains made, and the delivery of additional outputs.
Qualitative indicators have also been introduced at Output and Outcome level to reflect the increased emphasis on sustainability and handover responsibilities to state governments. These include:

- State Governments adopting the skills development policy and job creation strategy.
- Number of State Responsible Agencies implementing the COSDEC component of the skills development policy and job creation strategy.
- Number of State Responsible Agencies implementing the Apprenticeship component of the skills development policy and job creation strategy.
- Number State Agencies implementing the delivery of the training of trainer (TOT) through technical colleges.
- Number of State Agencies implementing the Recognition of Prior Learning (RPL)
- Number of State Responsible Agencies that roll-out MSE support centres and realign their economic empowerment schemes to better target marginalised beneficiaries, MCPs and other MSEs.

## D: VALUE FOR MONEY
Assess VfM compared to the proposition in the Business Case, based on the past year
Mafita’s funds have principally been channelled towards the design, development and production of learning materials, capacity building, training of trainers and sensitisation and the programme has recorded some successes in delivering value for money.
On Economy, consultant fees remain the main cost driver on Mafita. Many programme results involve significant attitudinal and policy changes; therefore, the priority has been to recruit and retain experienced consultants who possess the skill-set to engage effectively with a range of stakeholders at different levels. The programme has successfully employed several strategies to lower fee costs without compromising the quality of our outputs. Some of the techniques used by Mafita include:
- Maximising the use of national consultants
- Recruiting quality consultants with a proven track record of delivering results
- Multi-variable cost modelling approach used to benchmark fee rates
- Maximising the use of consultants with experience in northern Nigeria
These techniques have enabled Mafita to increase national consultant utilisation and reduce average daily rate over the duration of the programme.
	Y1	Y2	Y3	Y4
Average Daily Rate (£)	£415	£392	£379	£335
National Consultant Utilisation (%)	74	78	80	87

Additionally, the supplier uses an office platform in Nigeria with significant savings across the projects that use it – including the use of the supplier’s core staff positions worth around £40,000 a year across which support programme activities at no additional cost to DFID.

Significantly improved economy was demonstrated in the second major procurement of tools and equipment. Following a significant overhaul of process, so far in procurement #2 (70% complete) there has only been a negligible number of rejections of goods received - six items only in total.
Savings on a day-to-day basis have also been achieved by holding programme activities at Mafita offices wherever possible, negotiating discounts at activity venues, and streamlining and combining different interventions’ activities to minimise overhead costs.
On Efficiency, Mafita used its influence at state level to trigger government spending, attracting over £260,000 of state government funds to achieve programme results. This was combined with programme funds and other in-kind resources from various stakeholders including free training provided by MCPs, state government renovations of COSDECs, and discounts on assessment and certifications from awarding bodies. The results obtained by the programme would not have been possible without these external contributions.

On Effectiveness, while Mafita overall has underperformed expectations of value for money, the programme has worked to secure additional impact and value for money beyond the outcomes in the logframe.

As a result of Mafita’s activities, marginalised youth are now a more integral part of the state governments’ vocational training projects, as evidenced by the fact that the states have introduced an additional £3 million into 2019 state budgets for this purpose. In some states like Jigawa, the budget increase between 2017 when the intervention started in Jigawa, and 2018, has been about 25%. Also, 2,935 marginalised youth have so far graduated in nationally accredited vocational training programmes, with a further 11,434 being assessed as a result of Mafita’s interventions.

In addition to supporting vocational training, Mafita has built the capacity of 3,563 Micro Small Enterprises (MSEs) and 172 Business Development Service Providers (BDSPs) and has also developed 17 National Occupational Standards (NOS). One of the programme’s most notable achievements is that it has placed the upskilling and economic empowerment of marginalised youth on the agenda of the governments of four focal states for the first time: a significant success, especially considering the relatively short time the programme has been in operation. The state government buy-in achieved by the programme to date in some cases, evidences the judicious use of funds to effect systemic and sustainable change; and it is worth noting that this has been accomplished despite Mafita having relatively few material incentives at its disposal.

Mafita has strong stake in Equity, as all its beneficiaries are drawn from highly disadvantaged groups, and its results are almost entirely targeted towards these group. As well as recording the results recorded in the Output section above, Mafita has benefitted from ASI’s in-house expertise on areas such as safeguarding and women’s economic empowerment, which has informed programme design and approach.

Despite these successes, overall VfM achievements to date do not meet the expectations set out in the business case. The high-level impact indicator from which the other impact indicators are derived in the logical framework is the number of people recording positive change in incomes. (Average total increase in annual income to reach 15% or more). The programmes original logical framework envisaged 85,624 people in this category. Simply dividing the total programme value by this amount would result in approximately £408 spent per person recording a positive change in income.

The target figures were however revised at the end of the last annual review to 30,506 people recording positive change in incomes by 2021. Although Mafita does not pay training centres (either formal or informal) to provide training to beneficiaries, the reduction in numbers increased the basic cost per beneficiary in the year under review from £408 to approximately £1037 broken down as follows:

Project Spend to Date	£18,714,974
Cumulative number of graduates	2,874
Beneficiaries in Training	11,434
Cumulative number of MSEs	3,563
Cumulative number of BDSPs	172
Total number of beneficiaries	18,043
Cost per beneficiary	£1,037.24

In addition, the proportion of funds devoted to the informal vocational training vis-à-vis the formal vocational training sector has also changed from the proportions estimated in the programme proposal. This can be attributed to assumptions about the prevailing economic situation in Nigeria which have not held - compelling Mafita to concentrate more on self-employment opportunities instead of wage employment as previously proposed.
It is also important to note that although state governments have begun to allocate funding for vocational training projects since the advent of the Mafita programme, actual disbursement has not reflected either agreed budgets or timelines.

Recommendation:
1. Mafita to continue to continue to work with state governments to support disbursement of allocated funds where economic, social or political returns can be made by providing economic opportunities for marginalised youth and embedding such groups as an integral part of State government objectives and planning.
2. The Project Completion Report and review processes should place the overall VFM figures in the context of other training and skills programmes, and reflect on how the costs and benefits of Mafita’s investments compare to other benchmarks.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio (1 page)

DFID Nigeria have taken the decision to exit from Mafita early, based largely on VfM considerations.

The business case for Mafita recognised the programme was working in a challenging area, targeting marginalised youths in an economically deprived part of Nigeria. There were a number of factors that would be beyond the control of the programme (such as Nigeria’s economic downturn) or State Government’s willingness and ability to provide counter-part financing. As discussed above, these factors were behind the decision to exit Mafita earlier than originally envisaged. In addition, weaknesses in programme management and procurement were identified that also affected VFM. The latter issues were addressed successfully in a Performance Improvement Plan that was completed in February 2019.

A recent DFID Economic Development Best Buys paper highlights strong evidence that Technical and Vocational Training (TVET) programs have not worked in the past or are not cost-effective. The best buy paper suggests that DFID should only do these if we have a specific reason to think they will work. In the context of Mafita, it was expected the programme could work through expanding MSME’s in securing access to business development services and access to finance to create the demand for formal skilled youth. This did not happen quickly enough and was compounded by the economic downturn in the northern states.

Mafita have started to have success in the provision of business skills to MSME’s and had objectives, yet to be fulfilled, of securing microcredit to trainees MSMEs and trainees. The increased annual turnover expected from provision of these services and access to finance was £70 million. In the revised logical framework this has been reduced to £5.4 million (based on the original exchange rate of Naira 250 - £1).

Mafita in the first three years focussed on formal TVET training. This has now been substituted by Apprenticeship training with the reduction in the number of training facilities that are to be renovated. However, regardless of method of training, evidence from the programme suggests formal jobs are not available to graduates from either the formal or apprenticeship system. The target number of formal jobs has been revised from 55,910 in original logical framework to 7,909. This is being replaced by non-formal self-employment where the income boosts to graduates at present appear significantly lower, some of whom may only work a few days a week or month. The analysis above suggests that the Mafita programme no longer demonstrates the Value for Money anticipated in its original design.

In view of the above, DFID Nigeria decided the best way forward was a responsible exit over 2019/2020, closing the programme one year early at a saving of some £6 million. This will provide enough time to make sure that the benefits of good work already done are safeguarded, relationships with State Governments are managed properly and that young and marginalised beneficiaries who were part of the control group of the evaluation who were promised the vocational training can receive this.

The logical framework was redefined to establish what could, realistically, be achieved within this period, and a further revision is currently underway.

E: RISK
Overview of programme risk (noting the rating from p.1) and mitigation
Mafita’s overall risk rating remains “Major”. A major risk to the programme in the year under review was the programme’s poor performance which was successfully addressed through the performance improvement plan (PIAP).

DFID and Mafita hold regular risk reviews. Mafita is responsible to identify, analyse and report the risks to DFID in the Quarterly Progress Reports and in fortnightly programme management meetings, which have held since the inception of the PIAP, Mafita also reports the emerging risks.

The supplier developed safeguarding policies and reporting systems including the code of conduct both for staff and partners/ contractors in December 2018 after the international Safeguarding summit in 2018. Each MCP and COSDEC trainer must sign the Mafita Code of Conduct before receiving beneficiaries for training. This is being rolled out with the latest Cohort 3 beneficiaries.

DFID manages the aid diversion risks in close collaboration with all programme partners. The programme has a detailed delivery chain risk map, which has been updated working in close collaboration with the programme during this annual review, to provide a clear line of sight of funds flow to the last beneficiary and a detailed risk analysis at different points within the delivery chain.

Recommendations from the last annual review included the replacement of missing COSDEC assets. This has now been completed and DFID’s commissioned audit team is currently in the process of verifying the delivery of these assets.

The current key programme risks include:
- Programme’s challenge in translating job commitments into job placements.
- Lack of government funding and ability of government counterparts to deliver on their funding commitments as to COSDECS as a result.
- Lack of capacity of MDAs to take over the different responsibilities of Mafita's interventions, especially the agencies that run the COSDECs and activities around apprenticeship.
- Ensuring beneficiaries recognise the value of the training or cannot attend due to late/lack of payment of stipends by state governments.

Recommendation:
1. Given that the programme will exit responsibly by July 2020, regular and frequent risk analysis should continue to be done and agreed with DFID to capture and escalate any new/emerging risks.
2. The main supplier and DFID to work together to agree a risk appetite of the programme by November 2019.
3. The Safeguarding policy should be updated to reflect reporting lines to DFID.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE
Programme Performance:
As picked up in the last annual review in August 2018 and in the early part of the year under review, Mafita programme performance was significantly below expectations in areas including financial management and reporting (including systems) and asset management. The Mafita programme was therefore placed on a 3-month Performance Improvement Action Plan (PIAP), starting in August 2018. This resulted in a number of major changes by Mafita including a change in the team composition, and 13 vacant positions filled.

Performance of ASI was reviewed in November 2018 and although some improvement was demonstrated across all identified areas, these did not lead to the overall transformational change expected for the Mafita programme. As a result, the PIAP was extended for a further three months until February 2019. PIAP was successfully closed following significant improvement of performance in the areas identified. These improvements have so far been sustained by ASI and will require continuous close monitoring from DFID until the programme comes to an end in July 2020.

Commercial performance:
Mafita is managed through three contracts: a) Main contract awarded for the overall delivery of the Mafita programme; b) Procurement contract awarded to AECOM for procurement of equipment used for delivery of the Mafita programme and; c) a small contract, awarded yearly for the independent programme audit, to provide assurance on performance and management of the programme. In addition, a portion of Mafita funds are contributed through a centrally managed programme, to cover an independent impact evaluation, which is currently being carried out by the World Bank Impact Evaluation (DIME). Partnerships between different programme stakeholders has worked out quite well as reported through quarterly meetings with all partners involved.

The main supplier’s performance summary, as assessed through the supplier review scorecard, highlights that after August 2018, ASI’s performance has positively improved by replacing and adding key staff into the programme delivery team. Consequently, ASI successfully completed the performance improvement plan in February 2019.

AECOM’s performance is assessed as under-performing and needing improvement. This is largely attributed to delays encountered at the beginning of the year under review, in the supply and delivery of equipment as a result of lack of agreed ways of working between ASI and AECOM. The lack of Personal Protective Equipment (PPE), for instance, led to a delay in the completion of Cohort 2 training. Following the PIAP, AECOM and ASI established an agreed way of working which includes an effective mechanism to inspect the quality and quantity of the equipment procured by AECOM before the assets are handed over to government counterparts.

PWC conducted the 2018 and 2019 audits on only ASI’s component. The 2018 audit came out unqualified and the 2019 draft audit report is also unqualified.

In light of the decision to responsibly exit the programme by July 2020, the overall contract value and timeframe of ASI’s contract is expected to decrease. This will be managed through a contract amendment. In addition, no further extensions or increases will be made to the current procurement contract with AECOM, which is currently valid until March 2020.

DIME’s engagement with the Mafita programme and ASI has so far been positive. This is evident in the quality of quantitative data provided in its baseline survey and subsequent workshops with DFID and ASI, which have reinforced the Mafita programme findings. Data collection for the end line survey is in progress and expected to be completed following this Annual Review.

Quality and timeliness of narrative reporting:
Mafita reports have been of good quality and have been mostly delivered on time following the implementation of the PIAP. The quarterly progress reports are detailed and cover political and economic analysis, progress on workstreams, progress against logframe targets, risk analysis, financial variance analysis against project and operational budget utilisation, Value for Money analysis against the agreed indicators of the VfM framework, progress made on audit and annual review recommendations, lessons learnt from previous quarter and its application in the next quarter and proposed activities for the next quarter.

AECOM provides monthly delivery updates which highlights progress on procurement, changes to delivery schedules and any associated risks. Reports have been fairly accurate and have helped DFID better manage risks and the impact on budgets.

DIME provides a quarterly Mafita Impact Evaluation report which highlights key DIME activities and decisions. DIME will be conducting a qualitative research among COSDEC participants from July 2019, which is the final element of their data collection. Findings from this research will be captured in the next annual review.

Quality and Timeliness of Audited Financial Statements:

Financial Audits:
DFID commissioned an independent audit for the period June 2015 – July 2017, completed in 2017, and a further audit in April 2019 for the period August 2017 – March 2019 for the main supplier implemented component. The 2015 – 17 audit was unqualified, but contained numerous important recommendations around strengthening financial systems, which were incorporated and monitored closely through the PIAP. The main supplier has successfully implemented all the audit recommendations to date and DFID is closely monitoring to ensure that the performance is sustained on all recommendations through bi-weekly updates.

From initial findings in the draft report of the audit of the 21-month period ending 31 March 2019 (received in August 2019), the report is likely to be Unqualified. However, lapses in relation to programme expenditure, non-compliance to statutory regulations and procedures, and asset management were among the key findings. These lapses appear to be of medium priority; recommendations from the audit report will be closely monitored to ensure compliance within the 2019/20 reporting year. DFID is also in process of commissioning a financial audit of AECOM for the period 2016 - 2019. This report is expected to be available by January 2020.
The main supplier contracts its own annual external audit, which is carried out by RSM GLOBAL. DFID has reviewed the 2017 audit, which was unqualified, and is reassured of ASI’s financial standing. The 2018 Audited financial statement is expected in August 2019.

Quality of financial management:
The quality of financial management for ASI’s component improved significantly from September 2018 onwards but still requires close monitoring and constant review by DFID. Total allocated budget for 2018/19 for ASI component was £5.8m. Total spend in this period was £5.3m, giving an 8.4% variance against the allocated budget which needs further tightening.

	Q1	Q2	Q3	Q4
	Actual	Actual	Actual	Actual	Total	Yr. 4 Budget
	1,330,799	1,217,765	1,432,197	1,332,955	5,313,716	5,800,000
% Variance						-8.4

Forecasting & Invoicing:
Forecasting and invoicing by ASI improved significantly from September 2018 onwards as evidenced in the chart below (excluding monthly 25% withheld fees by DFID as a standard measure for payment against achieved milestones):
Monthly Forecasting Accuracy

This improvement in reporting and financial management, including forecasting and invoicing, is a key outcome of the Performance Improvement Action Plan (PIAP).

Forecasting and invoicing by AECOM in the beginning of the year under review was unstable as a result of the initial delays encountered. This has improved significantly as procurement is now back on track.

There have been no variances to the forecasting and invoicing by PWC, the audit firm, in the year under review. Payment to DIME of £1.8m was a one-off payment.

Date of last narrative financial report(s)	ASI - March 2019 (Q4Y4 Report- January to March 2019) / AECOM: July 2019
Date of last audited annual statement (s)	ASI – 20 September 2018. / AECOM- Not Available / DIME – August 2018 (Unaudited Account for Multi-Donor Trust Fund)

Asset Monitoring and Control
AECOM procures the assets for COSDECs on the demand established and communicated by ASI and then, based on agreed procurement mechanisms and policies, AECOM imports and delivers to ASI. Both AECOM and ASI staff conduct a joint inspection of the assets at AECOM’s warehouse on pre-agreed dates. AECOM then delivers the assets to agreed delivery locations in states and ASI hands over these assets to state governments for onward distribution to MCPS, who are responsible for the operation and maintenance of these assets.

Following the 2017 annual review, it was established that the maintenance of the COSDEC asset registers is the responsibility of the COSDECs and state governments. Nonetheless, ASI supported the COSDECs in developing an asset management policy and the roll-out in all four partner states. ASI made efforts to ensure that all assets are thoroughly checked upon delivery and tagged, before finally being registered on asset lists which are handed over to the states.

The ongoing audit’s initial report suggests that ASI has a fairly good system in place for their own asset management. There are recommendations to further strengthen asset identification and asset register update which ASI needs to implement.

Recommendation:

1. DFID programme team to continuously and closely monitor ASI’s performance until July 2020 focussing on programme delivery, financial management and reporting to sustain the improvements, with particular reference to the issues raised in the PIAP;
2. ASI to agree the recommendations of the audit and develop a time bound action plan to be approved by DFID.
3. AECOM to agree the recommendations of the planned audit and develop a time bound action plan to be approved by DFID.

G: MONITORING, EVIDENCE & LEARNING
Monitoring
The Mafita team can describe an integrated monitoring system with different roles and responsibilities. The system is driven and quality assured by the Monitoring and Results Measurement team. Data are collected by the technical team (especially at activity and output level) and by third party enumerators (especially at outcome level) using impact surveys and focus group discussions. ASI reports that data and analysis drive decision making at the weekly Management Team meetings.

The process to formally document the data flow, and identify risks and weaknesses was still being undertaken at the time of this Annual Review.

This Annual Review was conducted by DFID Nigeria team comprising the SRO, Livelihoods Adviser, the Programme Management Adviser, Manager and Officer, and Statistics Adviser.

Evidence
The World Bank Development Impact Evaluation (DIME) are conducting an impact evaluation among the young people recruited for the first cohort of the COSDEC training and apprenticeship elements of the Mafita. The evaluation includes a randomised control trial between treatment and control groups of young people, as well as elements of qualitative research.

In September 2018 DIME hosted a workshop with Mafita and DFID to present baseline survey data and explore findings from qualitative research among the apprentices, their caregivers, and MCPs. There were many positive findings from this qualitative research that reinforce Mafita’s findings. For example:

- The apprentices report expanded social networks and improved perception of themselves. “We are different from our friends now”
- Young women apprentices reported participating more in family related discussions and eventually receiving praise from their communities, after initial criticism of their efforts to learn new skills
- However young women also said they face discrimination in their workplace based on sex, where they work with male MCPs and apprentices.
- Apprentices were not engaged in or supportive of violence

The end line quantitative data collection was being completed during the course Annual Review. This will provide strong evidence on the extent to which these training elements have contributed to outcomes such as increased earnings.

From July 2019 DIME will conduct the qualitative research among COSDEC participants, which is the final element of their data collection. The findings will explore issues such as altruism, aspiration, and grievances. The findings will be of broader interest to DFID Nigeria (for example in respect of conflict prevention) and DFID should ensure they are shared across the office and to other stakeholders

Learning
The programme monitoring systems (especially impact surveys and focus group discussions) and management discussions have identified a range of lessons over the period. Lessons that relate to specific outputs are referred to in Section B of this Annual Review. In addition, the programme learned broader lessons about the political and institutional environment:

Peer learning platforms are a very effective way of getting buy-in and commitment from stakeholders. Mafita found Joint State Steering Committee meetings between the state representatives very useful for sharing of experiences and providing inspiration for states that were lagging. Similarly, COSDEC Community Management Committees have had useful exchange visits which has given them the ability to adopt successful approaches.

Government alone cannot create the changes needed for a sustainable future. Community participation and buy-in are essential for the effectiveness of interventions. Traditional and community leadership, for instance, can provide tremendous support for such programmes. For example, the Zazzau Emirate Council in Kaduna State was mobilised to support Mafita in beneficiary and MCP identification and enrolment and COBTAC, a budget monitoring civil society coalition was mobilised to assist Mafita in tracking anchor -agency budgets and ensuring early disbursements of budgeted funds for Mafita activities.

Other lessons learnt include:	Mitigation and actions being applied include:
Financial institutions (including commercial banks) lack the depth of understanding of the needs and constraints of MSEs	Mafita continues to engage financial institutions with evidence to support the business case for MSE lending.
Job placement activities for Mafita graduates are extremely time-consuming and labour-intensive with minimal results.	Collaboration with job platforms is being pursued
The low capacity of existing BDSPs to offer support to MSEs resulted in dissatisfaction with the services offered.	Learning by Doing (LBD) efforts are being pursued to improve the capacity of the BDSPs
Managing the expectations of Stakeholders is critical to the success of the project.	Creating opportunities for dialogue with all MCPs and caregivers helps ensure that roles and responsibilities of all stakeholders are clearly understood by all.
The composition of SSCs and CMCs is significant determinant of level of ownership and commitment /general performance	States to reconstitute Steering Committees and CMCs with fewer politically-affiliated interests –such as Commissioners.
Capacity is generally in short supply in partner MDAs/anchor agencies- but there is willingness to learn	Prioritize Tool-kit development and implementation using hand-holding strategy.
Level of readiness of Apex Agency varies across the states, and is a significant determinant of willingness to adapt to new methods and cooperation	Prioritise the operationalization of the Apex Agency BUT ensure also that other structures (SSCs and CMCs) are strengthened to support the Apex Agency
Initial push back from the private sector has given way to more enthusiasm and support	Continue to increase level of private sector engagement to build an enduring partnership with public sector in skills development and job creation

It is critical that the lessons of the Mafita programme are well captured, and communicated to the range of local and international stakeholders who may benefit from them.
Progress on recommendations from 2018 Annual Review: / Recommendations from 2018 Annual Review: DFID comment Unit/Work Stream Q4Y4 Situation / Mafita needing to urgently establish the status of renovations at every COSDEC and report these accurately and clearly to DFID; including providing bi-weekly updates to DFID on the progress of renovation work. COSDECs Last COSDEC update report provided in May 2019. For the 13 COSDECs that became the focus of the project, all renovations have been completed the satisfaction of the programme. Kaduna COSDECs were the last to be completed in July. / That a plan is developed immediately to deal with the situation revealed during the field visits by the review team that many COSDECs were not in an appropriate condition to hold training. It was recommended that options be developed immediately for each COSDEC. This would include: / 1. An immediate stop to any training that had more than a month remaining for the Foundational Skills Training (FST - basic numeracy, literacy and integrated science) where conditions were entirely unsuitable – no water, no sanitary facilities etc: / 2. Stopping training at the end of any FST that had no more than 2 weeks remaining where conditions were entirely unsuitable. / 3. No resumption of training at any of the above centres until basic conditions had been provided by the state, and a full report submitted to DFID for approval. COSDECs Mafita followed this recommendation and ceased support to COSDECs while their condition and PPE equipment was not deemed fit for purpose or absent. Now, the 13 COSDECs that are still the focus of the programme meet the standards required, and have the PPE equipment. / Conduct more detailed deeper analysis to understand fully the local MSME economy in catchment areas including new viable trade areas and specialisation for clear high potential industry-driven skills development and job creation. PSE/LED A study of the target demographic commissioned during the period included an attempt to research and assess absorptive capacity of the local economies by trade and sector. However, the level of resource was insufficient (and the scale of the study which would have been required to do this effectively was beyond the capacity of the programme) / Deepen working relationship with potential Micro Finance Institutions (MFIs) and urgently facilitate the development of suitable financial products for transformative Micro Small and Medium Enterprises (MSMEs). PSE/LED A2F Work with MFIs to increase and improve the quality and availability of products and services to the target group is ongoing, but work on access to finance has remained very challenging. Agreement signed with Grassroot MFB in Kano to launch the crowd-funding scheme. So far, 34 ultra-marginalised beneficiaries have received equipment loans in Kano under the scheme. / A2F has basically not gone well – several models have been tried but only limited success has been achieved, largely with existing businesses rather than the direct target group. The direct target group of marginalized people only significantly benefitted from subsidised social investment schemes funded by government / Build further capacity of local MSMEs on business planning. In this context, the programme needs to consider how BDSPs will be reimbursed for their services. PSE/LED BDS Performance grant in place for BDSPs that will support MSEs in their business development and loan applications. Capacity building of BDSPs ongoing plus additional focus on MSEs to provide the business mentoring that they require to grow their business. MSEs are also being introduced to other concepts like common facility set-up for the effect of shared resources to enhance efficiency and productivity. / Explore the availability of non-interest (Islamic) finance. PSE/LED - A2F The financial product agreed with Sterling Bank is based on Islamic Finance principles. Discussions with Ja’iz bank are still ongoing. [Mafita has received confirmation that 10 Sterling applications have been approved, but have not yet been actioned] / Ensure the capacity building of local BDS providers is appropriate to the needs of the MSME clients. PSE/LED – BDS Various capacity building works on-going for BDSPs in various aspects (A2M approaches, value chain financing, etc), specifically targeted to the needs and constraints of MSEs and with a clear focus to allow them to grow their business and access finance and new markets. / Continue to explore ways to develop stronger partnerships and support shortlisted microfinance banks (licenced institutions) and other relevant financial institutions to develop suitable financial products following lessons learnt from the pilot of non-traditional Access to Finance (A2F) models – apply learning from pilots; and explore value chain finance (both internal and external models, i.e. both with and without participation of financial institutions). PSE/LED - A2F Products and partnerships have been developed with Sterling and Grassroots, which have resulted loan approvals, but overall the potential for scale and sustainability seem limited. / Explore linkages between high potential sectors and programmes such as PropCom (and in future LINKS) how these can be linked to trade areas being taught through the COSDECs and apprenticeship programme. PSE/LED LINKs has not yet started. A joint intervention with PROPCOM was explored, but was eventually deemed unworkable. However, Mafita continued to explore linkages with other programmes such as ENGINE II where some of the female beneficiaries of the ENGINE II Programme have been enrolled into Mafita’s Cohort 3 training. / Liaise with Enhancing Financial Innovation and Access (EFInA) – a DFID funded programme on financial inclusion either to access data and updated information or with regard to issues that need to be resolved at systemic level between regulators and industry, or through research, TA and capacity building on innovation for financial access (i.e. the areas of competence of EFInA). A particular area of collaboration could be non-interest finance given its importance for the target areas of the Mafita programme. PSE/LED - A2F EFInA and Mafita have had discussions but no direct supportive relationship was established. However, Mafita is encouraging its partner MFBs to tap into EFInA’s grant schemes and has been in discussion with a major EFInA grantee, Riby, to identify ways that their cooperative banking product can be harnessed for the benefit of Mafita’s beneficiaries / Note the 2019 recommendation above requiring that Mafita engages in a learning workshop with EFInA, and potentially other relevant programmes. / It is recommended that an urgent focus is applied on the quality of BDSP (and how they might be reimbursed for their services) and access to finance to ensure MCP’s and graduates are able to receive loans. PSE/LED – BDSP Capacity building is on-going for BDSPs in various aspects specifically targeted to the needs and constraints of MSEs and with a clear focus on allowing them to grow their business and access finance and new markets. Performance grant for BDSP already in place. Mafita supported SMEDAN to finalise the National BDS Framework to regulate and standardise BDS delivery. The Framework has been adopted, the curriculum developed, selection of pilot training institutions and initial training and assessment of 30 Mafita BDS has been delivered. However, as discussed above, assumptions around access to finance have not held, and Mafita has not been able to develop scalable and sustainable models in this area. / It is recommended Mafita limit the support to government COSDECs to the current 17 that the government has started to renovate, and that DFID has ordered equipment for, and not expand further which would put additional strain on limited government resources. The focus should be on ensuring the current ones are renovated, have adequate funding and have supporting governance and management structures to sustainably ensure quality training into the future. COSDECs This recommendation was followed. Mafita informed state governments of the c situation and focused on monitoring the renovations until they reached adequate completion Eventually the number of supported COSDECs was reduced to 13. / Mafita needs to address the issue of improving on the quality of products or services, and facilitate – where required - product design, development and innovation with MCPs and MSMEs committed to providing job opportunities to Mafita trainees. PSE/LED The Cluster Development Unit is working with MSME Clusters on ways to improve the quality of products and services offered by MSMEs. These processes include strategies for Common Facility Centres, as well as the wider ongoing training programmes. / Mafita should continue to support the strengthening of MCP clusters in view of benefits of economies of scale, learning and information sharing, the formation of social capital, etc. Cluster Dev. The Cluster Development Unit is working with various clusters to ensure the required governance frameworks are in place around clusters. Clusters are also being trained on access to market as this is a key indicator that drives access to finance especially for common facility centres. Clusters are also being encouraged to set-up common facility centres for more productivity and efficiency. / Recommendations from 2018 Annual Review: DFID comment Unit/Work Stream Q4Y4 Situation / It is recommended that Mafita urgently review scale-up possibilities within this programme. This would compensate for the reduced numbers of COSDEC graduates and maintain the overall numbers at outcome level. COSDECs/APPC In the light of the early closure of the Mafita Programme, the overarching focus is not to scale up the training, but to consolidate and ensure that states adopt the Apprenticeship model. This would entail (1) supporting the states to scale the intervention to the level they can fund (2) integrating the apprenticeship training system into the States’ skills delivery framework / The programme needs to engage professional counsellors to strengthen counselling services to beneficiaries on a choice of trades prior to enrolment - present facts and insights about trades with potential markets and growth. They also need to work at re-orientation of mind-sets of trainees as not everyone can start a business. Trainees need to see the value of learning on the job for a couple of years before becoming self-employment (where applicable). PSE/LED Job counselling Units have been set up in the COSDECs with specific capacity building being provided to the COSDEC managers and trainers. Additional efforts are being made at the Ministry level to ensure sustainability going forward. PTE and GRFB have also been reinforced to ensure beneficiaries have clearer options on what to do after training completion. Career counselling is also being embedded in the training for MCPs to ensure that MCPs can provide counselling to their apprentices / Mafita should also be more proactive in addressing anecdotal information that choice of trades was not made directly by some students, but that Centre managers made the choices to fill the quota for particular trades. COSDEC In the selection and recruiting for the 2nd Cohort of beneficiaries, the choice of trade has been clearer to avoid any misunderstanding. Choice of trade will always be respected wherever possible. Career counselling Units have been set up at all the COSDECs to ensure that trainees are guided in their choice of trade before, during and after enrolment. / Mafita needs to establish a clear understanding of the issue of age declaration with the enrolment committee in order to manage the issue around age of beneficiaries at the time of enrolment. These recommendations are still valid. SKILLS In the selection and recruiting for the 2nd Cohort of beneficiaries, the age requirement has been made clear. We have conducted in August and October 2018 and subsequently in March 2019, auditing sessions to ensure that this condition is respected and to remove any potential beneficiary that does not meet the age requirement. The monitoring teams will continue doing so. This is one of the key aspects that is being stressed to the enrolment teams from the states that will be taking over this responsibility in the selection of the 3rd Cohort and going forward in accordance with the approved Enrolment Toolkit. / It is recommended that Mafita urgently review scale-up possibilities within this programme. SMT In the light of the early closure of the Mafita Programme, the overarching focus is not to scale up the training, but to consolidate and ensure that states and Trade Associations adopt the training systems for sustainability / As in previous annual reviews, it is recommended that, as a matter of urgency, the matter of funding to MCP’s and Apprentices is addressed. APPC/PSE LED A number of A2F models have been put in place and legal agreements signed. Implementation will be pursued aggressively in Y5. BDSPs are being capacitated to provide the necessary hand holding support. / Mafita should continue to engage with the state governments to implement the states skills development and job creation policies and strategies. TVET / PECA Different states are at different stages in the implementation of the policies and strategies. State apex agencies that would continue to implement the skills to jobs activities have been agreed with Kano, Katsina and Jigawa States. Kaduna state initially opted for the creation of new agency but later decide to use an existing agency. / The programme should continue to ensure that the MCPs & COSDECs trainers gain the competencies in formative assessment to assess beneficiaries to national standards prior to the final assessment by NBTE and awarding bodies. TVET Mafita has already carried out several trainings for MCPs and COSDEC trainers to ensure that the required capacities are built. TVET has been conducting training on formative assessment for both MCPs and COSDEC Trainers throughout the year. / Urgent engagement and capacity building is required to both the BDSPs & MFIs. PSE/LED - A2F, BDS Capacity building for BDSPs and MFIs has continued during the year and a clear workplan is in place to continue building up these capacities while ensuring commitment and full understanding of what is required from them in return. For BDSPs, capacity building has centred around improving their knowledge of transaction structuring while capacity building for MFIs has centred around designing appropriate financial products.

Direct feedback from beneficiaries:

An Electrical Installation apprentice in Gadon Kaya, Kano said “Through this programme, I have improved my capacity to read, write, and carry out some mathematical tasks. I also learnt how to do modern business through the get-ready-for-business training, as well as trade theories. To me, this is the greatest thing that happened to me ever in my entire life”.

From the recently concluded beneficiaries’ satisfaction survey, a significant number of the Cohort 2 beneficiaries (apprentices and COSDEC trainees) interviewed stated that the training received has given them the needed employability skills and platform to be economically self-reliant. They acknowledged that vocational skills and entrepreneurship training have increased their opportunity to earn an income and improve their livelihoods significantly.

The opportunity to engage their minds in productive activity makes a significant difference for the beneficiaries. Apprentices under the carpentry trade in Katsina mentioned this during a Focus Group Discussion (FGD). One of them said “I use to sit idle without anything doing but now Mafita has come and changed our lives.”

Another apprentice echoed “Now I don’t have time to waste sitting down, I am rather engaged in learning a skill that improve my life.” An apprentice in Kaduna said “I will say there is great improvement in my life right now. Before now, all I do is roam the streets but right now I have something that keeps me busy and I even make little money out of it.”

There are beneficiaries who have started earning income while in training. One of the carpentry apprentices in Katsina said “I have an income now. I even have more clothes as a result of what am earning from this job.”

The gender dynamics to the vocational training have been quite revealing. Girls who were enrolled into male-dominated trades are excited to break the glass ceiling. One of the girls undergoing carpentry training in Zaria COSDEC mentioned, “As a woman, our society feel carpentry is not a female trade but my love for this trade and the desire to be different has really changed my perspective.

The beneficiaries also suggested areas of improvement. One key area they would like to see improvement is the availability of adequate training tools at the COSDEC. One of the COSDEC garment making trainees in Rumfa college, Kano said “Actually, the training here is excellent, the thing that needs to improve is the provision of adequate working tools for easy learning.”

Annexes Attached:

Annex 1: Proposed New Logical Framework for Year 5. Budget £4.2 million
Annex 2: Risk register
Annex 3: Delivery Risk Chain Mapping
Annex 4: Delivery Plan
Annex 5: Output Indicator