Annual Review

Title: Political Settlements Research Programme (PSRP)
Programme Value £ (full life): £4,366,612		Review Date: March 2019
Programme Code: 204326	Start Date: 01/04/2014	End Date: 30/03/2019

Summary of Programme Performance
Year	2015	2016	2017	2018	2019
Programme Score	A	A	A+	A+	A+
Risk Rating	Medium	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	4429922
DevTracker Link to Log frame:	5411051

A. Summary and Overview (1-2 pages)

Description of programme (1/2 page)

DFID provided £4.4m over four years (2015-19) to the Political Settlements Research Programme (PSRP). Based on PSRP’s strong performance, DFID has agreed a time and cost extension of £2.2m over the next 2 years from (2019-2021). The research explores how donors can shape ‘political settlements’ - the rules that regulate the access of elites to resources and power – to reduce poverty and reduce the risk of conflict. PSRP has established a database of over 1,500 peace agreements which, together with research from the programme, is informing the content, choice and targeting of interventions to reduce the risk of conflict and broker peace, by donors, diplomats, and civil actors, in fragile and conflict-affected states (FCAS).
This programme focusses on three broad themes:
1. How different types of political settlement emerge, and which actors, institutions, resources, and practices shape them;
2. How political settlements can be improved by internally-driven initiatives (i.e. by directly involved parties), including the impact of gender-inclusive processes and rule of law institutions;
3. How, and with what interventions, external actors can change political settlements.
The research is explicitly comparative and uses a mix of qualitative and quantitative methods, with substantial field work. Research to date has focussed on Afghanistan, the Democratic Republic of Congo (DRC); East Timor; Ethiopia (Ogaden); Liberia; Nepal; Nigeria; Philippines; Sierra Leone; and Somalia, with comparison with less fragile settings: Colombia and Northern Ireland.
Following a competitive procurement process a consortium led by University of Edinburgh was selected to implement the programme. The consortium was reduced in size as part of the extension. It currently includes: Edinburgh Universtiy, Conciliation Resources, Austrian Study Centre for Peace and Conflict Resolution and International IDEA.

Summary supporting narrative for the overall score in this review (1/2 page)
The overall outcome score is A+ (Output and performance exceeds expectations). PSRP has exceeded the targets set for the programme over 4 years. They have exceeded the targets set out in the logframe: publications including peer reviewed journal articles (Output 1), uptake through events and social media (Output 2) and engagement of southern researchers in the programme (Output 3). Impact from the research programme has been noted by DFID and detailed through case studies provided by PSRP.
UK Policy influence:
- UK Conflict Policy: Edinburgh University researchers have worked closely this year with HMG teams to make the case for longer term, evidence-based approaches to conflict resolution in countries that are high priorities for the National Security Committee (NSC) and for DFID’s future ‘Strategic Direction’. For example: Afghanistan, Somalia, The Sudans and Yemen. PSRP is also informing developing work in DFID to enhance programming on Conflict, Security and Justice. Edinburgh University presented at a Cabinet Office-convened event with DFID, FCO and Stabilisation Unit officials on peace processes, in September 2018 and this generated interest in inviting PSRP to present to a planned senior official meeting in 2019.
- UK Country Policy: PSRP has provided flexible advice, through direct phone calls and briefings, to senior officials (ambassadors, DFID heads of office) working on peace processes during times of crisis - a service for which there is growing demand. This advice is often sensitive and so cannot be detailed. PSRP ran sessions this year with FCO/DFID Yemen and Afghanistan in London and the DFID/FCO teams in Somalia, South Sudan, DRC and Kenya through the DFID convened Conflict and Stability event in Nairobi in June.
- PSRP provided rapid evidence reviews for FCO/DFID Yemen, Afghanistan, Zimbabwe, Syria, teams this year and for FCO Research Analysts. Topics covered: ceasefires, the role of multi-donor trust funds, local agreements, national dialogues, the role of economic resources. Feedback from all teams was that PSRP’s service was fast, relevant and of higher calibre than other knowledge services available to DFID advisers, enabling DFID to review clear options against comparative examples at critical moments in a political transition. This advice enabled teams to make decisions on how their programmes should adapt to political changes and allowed HMG officials to propose options to negotiators and mediators.

International Policy influence: engagement with the staff of international organisations:
Multilateral Policy on Peace Processes: PSRP research was referenced throughout the UN/World Bank Conflict Prevention Study[1] published last year.[2] PSRP continues to support the UN as it re-orientates its approach under the UN Secretary General’s ‘Sustaining Peace Agenda’. UN representatives participated in the PSRP event on ‘Inclusion in peace processes’ and have drawn on the research to shape the UN’s policy commitment to broadening inclusion. This helps address a major gap in the evidence which was one justification for DFID’s research investment in PSRP.
[1] United Nations; World Bank. 2018. Pathways for Peace: Inclusive Approaches to Preventing Violent Conflict. Washington, DC: World Bank. © World Bank. https://openknowledge.worldbank.org/handle/10986/28337 License: CC BY 3.0 IGO.”
[2] World Bank (2011) ‘World Development report on conflict’ https://siteresources.worldbank.org/INTWDRS/Resources/WDR2011_Full_Text.pdf
PSRP’s partner the Institute for Security Studies presented a paper on data and trends on conflict and political instability to the African Union High level panel of mediators and negotiators to inform their planning and prioritisation of future conflict risks.
Operational Support to Peace Processes: PSRP researchers have directly supported civic actors engaging in peace processes in Libya, Yemen, Syria, Columbia, Ethiopia and South Sudan.
  - Yemen: PSRP provides ongoing support to the office of the UN Mediator to the UN. This contributed to an agreement reached to improve humanitarian access into Hodeida port.
  - Ethiopia: PSRP has helped parties to resolve longstanding tensions in the Ogaden region.
  - Afghanistan: PSRP helped Afghan and international parties to better understand each other’s positions as appetite increases for peace talks with the Taliban. PSRP advice to the US former special representative, informed subsequent peace talks between the US and Taliban in Qatar, where draft agreements were discussed. Current US envoy Khalizad said: ‘It’s clear all sides want to end the war. Despite ups and downs, we kept things on track and made real strides.’
Recommendations for the year ahead (1/2 page)
PSRP and DFID will add new log frame targets on publication numbers and website hits, to reflect the reduced intensity of DFID expenditure in the 2 -year extension.

## B: DETAILED OUTPUT SCORING (suggest 1 page per output)

Output Title	High quality, relevant, timely and reliable research delivered on political settlements
Output number per LF		1	Output Score	A+
Impact weighting (%):		40%	Impact weighting % revised since last AR?	Yes, reduced from 60%

Indicator(s)	Milestone(s) for this review	Progress
1.1 Number of high quality policy relevant, new evidence on peace and political processes published (e.g. articles published in peer reviewed journals).	25 articles or book chapters published in peer reviewed outlets (cumulative).	Exceeded: 37 total. / (28 journal articles, 4 monographs and 5 book chapters).
1.2 New datasets capable of supporting ongoing research	All committed to data delivered with enhanced access in place. This refers to completion of the PA-X peace agreements Database.	Substantially Exceeded: The PA-X database was launched and completed last year. This year PSRP has made the database compatible with other global datasets and has developed new datasets on amnesties and local agreements. This is beyond what was originally agreed.
1.3 Number of high quality policy relevant publications, (e.g. number of policy briefs, working papers and blogs).	4 Accord, 40 briefing papers, 20 research reports (figures cumulative) and 30 blogs.	Substantially Exceeded: 4 Accord. 26 briefing papers, 60 research reports, and 74 blogs.

Provide supporting narrative for the score

PSRP has exceeded publication targets (1.1) and produced a wide range of policy relevant publications (1.3). These include a series on the sharing of power, territory and economic resources which explicitly addressed requests made by HMG colleagues last year. PSRP completed and launched the peace agreements database in 2018 and has developed a new database on amnesties this reporting period (1.2). Given this, the publications reach is impressive with citations in academic research, broadsheet and online media and demonstrated uptake among senior mediators (See Output 2).
PSRP and DFID asses policy relevance in two ways. Firstly, research gaps or trends are identified by international and national organisations involved in peace processes such as the UN’s Standby Mediation Network or the Network of Women’s Mediators. We also assess opportunities for research to inform pressing peace negotiations through direct requests from those involved. This year demand has been high in both Yemen and Afghanistan.

1.1	PSRP Journal articles are listed with web links in the Annex.
PSRP has delivered a series of journal articles, policy orientated research papers and blogs. Highlights this year include:

Jan Pospisil’s book, ‘Peace in Political Unsettlement: Beyond Solving Conflict’, was published by Palgrave Macmillan in the ‘rethinking peace and conflict studies’ series edited by Oliver Richmond. The book draws heavily on the PA-X Peace Agreements Database to explain how some deals entrench negative patterns that prevent progressive peace and recovery through the concept of ‘formalised political unsettlement’.
The Special Issue on ‘Transitional Justice from the Margins: Intersections of Identities, Power and Human Rights’ published in the International Journal of Transitional Justice shows how interim justice mechanisms can support the rights of women, young people and marginalised groups, and the role these mechanisms play in peace processes, see https://academic.oup.com/ijtj/issue/12/1.

Bell and Badanjak, have a forthcoming journal article in the Journal of Peace Research on ‘Introducing PA-X – a new peace agreement database and dataset’. This outlines the methods used by PSRP in the formal research community and demonstrates the unique contribution that PSRP data is making to the field of peace research.
PSRP consortium partner Conciliation Resources published 4 ACCORD papers on Afghanistan, Nepal, ‘Borderlands’ and ‘Inclusion’. These have already had significant policy impact, feeding directly into senior policy meetings with HMG, the UN and regional peacebuilders in Africa and Asia (See output 2 for detail). The launch of the Inclusion ACCORD attracted UN Special Representatives and Ambassador level representatives from the UN Mediation network. https://c-r.org/resources/accord-navigating-inclusion-peace-processes
PSRP also published a series of policy briefs covering the key features of peace processes: power sharing, economic power sharing, territorial power sharing, military power sharing, the role of central banks, the role of businesses, education in peace agreements, amnesties and the role of women. These were published at the end of the reporting period, so while they have been well received so far we expect to have detailed feedback next year. http://www.politicalsettlements.org/publications-database/

Lessons identified this year, and recommendations for the year ahead linked to this output

PSRP and DFID will add log frame targets on publication numbers and website hits, to reflect the reduced DFID expenditure in the 2 -year extension.

Output Title	Evidence of stakeholder uptake and research engagement.
Output number per LF		2	Output Score	A+
Impact weighting (%):		30%	Impact weighting % revised since last AR?	Yes, reduced from 40% ↓

Indicator(s)	Milestone(s) for this review	Progress
2.1 Number of tailored sessions run for key stakeholders (including DFID). Number of people reached by presentations and workshops.	12 tailored sessions, 800 people directly addressed (cumulative)	Substantially Exceeded: 24 tailored events have been run by PSRP. Over 850 people were directly addressed through these events. Over double that number were addressed through events where PSRP presented to audiences at events run by other institutions.
2.2 PSRP Research taken up and referenced elsewhere (cumulative totals)	15 peer review articles, two northern and two southern mainstream media articles cite PSRP work (not authored by PSRP)	Substantially exceeded: 22 publications were cited by 145 peer reviewed publications.
2.3 Number of stakeholders engaging with research and policy products through website, media and publication downloads	upward trend in website hits, upward trend in PA-X usage; 1 publication with 800 dl, 2 more with 500 dl, 8 more with 100 downloads	Substantially exceeded: / 30,736 website hits this year. / Over 2000 followers on twitter. / 3 papers = 1000 + downloads. / 2 papers = 500+ downloads and 18 papers = 100+ downloads.

Briefly describe the output and provide supporting narrative for the score

PSRP has met or exceeded all output 2 targets. Uptake has been demonstrated through events (2.1), academic citations (2.2) and internet uptake (2.3).

  1. PSRP exceeded the number of planned events. Highlights included:
  - PSRP presented research to HMG representatives from across the Horn of Africa and DRC in July 2018 at the annual RED-convened Conflict and Peace Research Event in Nairobi, now in its third year. This informed DFID’s strategy and programme planning in Africa and was commended by the UK High Commissioner to Kenya. The session helped DFID South Sudan review their programmes and support following efforts to reach a South Sudan peace deal in May. PSRP also supported the work of UN, HMG and African experts working on peace processes in Ethiopia-Eritrea, South Sudan, Somalia and Ethiopia-Ogaden region.
  - PSRP presented research on economic and political power-sharing at the annual OECD International Network on Conflict and Fragility (INCAF) task team meeting in May 2018. This supported INCAF’s work with donors to improve the sensitivity of aid to ongoing political crises. INCAF is the main international gathering of all bilateral and multilateral members of the Development Assistant Committee (DAC) concerned with conflict and fragility.
  - In Myanmar, PSRP’s Policy Paper, ‘Sub-state Constitutions in Fragile and Conflict-Affected Settings’ was translated and used to inform training by International IDEA, provided to state, and regional authorities, civil society as well as the Ethnic Armed Organisations (EAOs). This informed negotiations between the Government, Armed Forces and EAOs.
  - PSRP presented research to the Ogaden consultative group and Ogaden clan elders to support development of a political settlement in the Somali region (subsequently achieved). PSRP research on the Ogaden (2016/2017) was presented to donor governments (UK, Germany, Sweden) in Addis Ababa, the new President of Somali regional state and advisers.
  - PSRP held 2 roundtables with HMG’s Afghanistan teams. FCO colleagues subsequently shared copies of PSRP publication on the Afghanistan peace process with senior Afghan and international attendees at an International Contact Group meeting – including Hekmat Karzai, Afghan Deputy Foreign Minister, Alice Wells US Principal Deputy Assistant Secretary for South and Central Asia and former Taliban Ambassador to Pakistan and member of the Afghan High Peace Council, Mullah Zaeef. This subsequently informed the peace talks.
  - PSRP’s publication on how to strengthen ‘inclusion’ in peace processes was launched at an event convened at the British Academy in February 2018. This was attended by DFID RED and FCO deputy directors along with senior UN special representatives and mediators working on Somalia, Sudan, Ethiopia and Nepal.
2.2 PSRP has exceeded targets for citations and social media.
  - UK: Daily Mail cited PSRP research on peace agreements. (https://www.dailymail.co.uk/wires/pa/article-5581765/NI-peace-deal-lasting-impact-agreements-worldwide-study-finds.html ).
  - Ireland: Irish Times featured PSRP research on domestic violence (https://www.irishtimes.com/news/crime-and-law/use-of-guns-in-northern-ireland-domestic-abuse-cases-falls-1.3627073) and Irish News (https://www.irishnews.com/news/2018/09/13/news/study-first-of-its-kind-to-compare-years-during-and-after-the-troubles-on-abusive-relationships-1431700/ ). Further reports published by Belfast Telegraph, Irish Independent, News Letter, and Daily Mirror. )
  - South Africa: ISS research on political instability trends featured in the ‘Daily Maverick’. (http://firstthing.dailymaverick.co.za/article?id=126003#.XFCGu5NKjwc ).
  - Nepal: CR’s Nepal Accord was reported in the Nepalese ‘Kantipur Daily’ (https://www.kantipurdaily.com/diaspora/2017/04/04/20170404193210.html )
Summary of responses to issues raised in previous annual reviews (where relevant)
Recommendations
DFID asked PSRP to revise their website last year to make it more user friendly and to ensure that key publications are easily identified on the front page. PSRP have addressed this recommendation and are undertaking further work to enhance their social media interface over the next year in line with the 2 year extension.

Lessons identified this year, and recommendations for the year ahead linked to this output

No further recommendations are made for the year ahead.
Output Title	Enhanced research capacity, particularly in global south
Output number per LF		3	Output Score	A+
Impact weighting (%):		30%	Impact weighting % revised since last AR?	NA

Indicator(s)	Milestone(s) for this review	Progress
3.1 Number of Southern-based researchers involved in research projects, as evidenced by their active engagement, e.g. through co-authorship and presentations at events	Evidenced involvement of total 50 Southern-based researchers in publications, Co-authorship and research	Substantially Exceeded: 82 researchers have co-published or had evidenced involvement in PSRP research. / 43 have co-published papers. A further 39 have had evidenced involvement in publications.
3.2 New research methodologies/diagnostic tools for complex problems in FCAS tested and disseminated where effective	Outcomes for all 5 methodologies published and available; reflective publication on methodological issues published	Exceeded: 6 methods have been applied and research published. These are listed below.

Provide supporting narrative for the score
PSRP has substantially exceeded targets for involvement of southern researchers in PSRP research. Over 43 southern researchers have co-published with international partners as part of the research programme. A further 39 played key roles in research implementation and their roles are evidenced in PSRP research publications. The 6 specific research methodologies are:
1. Interview-based case study research used by several of the research partners.
2. Qualitative content analysis, used by several of the research partners.
3. Comparative action research-based lab methodology, used by Conciliation Resources to support the ACCORD publications on Nepal and Afghanistan.
4. Quantitative database work. A journal article reflecting on the PA-X database method by Bell and Badanjak is in print at the ‘Journal of Peace Research’.
5. Social network analysis was developed during the programme. Zoe Marks’ and Pat Stys’ article on social network analysis is currently in print in ‘African Affairs’.
6. The first longitudinal survey on sexual violence was completed as part of PSRP.

Lessons identified this year, and recommendations for the year ahead linked to this output

Conducting research on peace processes requires a nuanced understanding of both the political actors involved and the variety of mechanisms that can be applied to help peace processes succeed. Enhancing the capacity of researchers in the global south to conduct research on these topics has had a substantive contribution to peace processes. Peace processes take around 20 years on average to conclude, and many have longer term political implications. Building local capacity therefore improves the sustainability of our research investments by ensuring that the research will inform political processes in the long term. In Ethiopia and Nepal the process of writing down the discussions between different parties has in itself helped parties reach agreement on contentious issues.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES (1-2 pages)

Summarise the programme’s theory of change and any major changes in the past year (1/2 page)

PSRP’s contract and the proposed extension are based on a standard theory of change for DFID research programmes and this same ToC is reflected in the PSRP log frame:

- PSRP’s research strategy identifies priority research questions and themes that will contribute to the evidence base for policy makers and other interest groups, including DFID and its partners.
- PSRP consortium designs and delivers a portfolio of research projects (with fieldwork in specific settings and with appropriate methods and analysis) to deliver this new evidence. (Output 1)
- Throughout the research cycle, PSRP engages with policy makers to ensure that the research products are relevant and useable. (Output 2)
- PSRP produces a range of research outputs tailored to different audiences and actively disseminates these, including through publication, online media and events. (Output 2).
- Where required, PSRP builds capacity with research partners in order to deliver the research to expected quality and on time (Output 3.)

Ministers agreed to extend the programme in August 2018, and an amendment to the contract was signed in March 2019. The number of partners involved in the consortium has been reduced as part of the extension. Edinburgh University will work with the following partners to deliver the extension. Each partner brings important networks, expertise and research capability to the consortium.
International Idea provides comparative knowledge on democratic change and constitutional processes. It has good regional networks and a track record of uptake with the UN and EU.
- Conciliation Resources has a track record of connecting community perspectives to national peace processes and conducting research on peace-making through their ACCORD series.
- The Austrian Study Centre for Peace and Conflict Resolution (ASPR) contributes to the promotion of peace and peaceful conflict resolution through research and has good networks in Europe.

PSRP’s intended outcome is ‘Increased knowledge and uptake by policy makers of evidence-based policies and programmes for achieving policy and programmes for achieving open and inclusive, non-violent political settlements. The extension focusses on the provision of time-sensitive evidence and advice to policy makers, building on evidence from the database and in-house experts. This means that field work and the associated capacity support to southern researchers will be reduced.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead (1/2 page)

PSRP is a high performing programme and progress to date suggests that PSRP will deliver all it has committed to in the 2-year extension. PSRP has exceeded expected outputs, outcomes and impact over the first 4 years of the programme (Phase 1). PSRP has delivered a series of high-profile outcome case studies, showing how research has informed peace processes this year in Afghanistan, the Ogaden region of Ethiopia and in Yemen.

Having completed the database of 1,500+ peace agreements last year, PSRP subsequently expanded data on new areas such as amnesties and local agreements this year, filling important global gaps in research. PSRP has drawn on this data to deliver the legacy of high-quality policy guidance that was recommended in last year’s annual review (10 policy briefs on the following themes: power sharing, territory, economic resources, business interests, military institutions, inclusion, the role of women, amnesties and education.) PSRP has also met high demand for expert advice and evidence from UK officials, partners at the UN and national peacebuilders and mediators working to end complex conflicts.

Explain major changes to the logframe in the past year (1/2 page)
There have not been any changes to the logframe this year.
Describe any planned changes to the logframe as a result of this review (1/2 page)
Logframe targets for the 2 -year extension have been agreed with PSRP and will be finalised by May 2019. The annual volume of funding to PSRP in the extension period is half that of the first four years of the programme. Consortium partners have therefore been reduced in number to now include: The Austrian Study Centre for Peace and Conflict Resolution, Conciliation Resources and International IDEA. example. New logframe milestones will be agreed to reflect the changes.

## D: VALUE FOR MONEY (1-2 pages)
Assess VfM compared to the proposition in the Business Case, based on the past year (1 page)
PSRP is a high performing research programme that bridges the divide between academic research and operational needs. This is having clear value and impact across HMG and the international system.
Key cost drivers include staffing costs, research uptake and travel costs. In this reporting period, programme delivery and performance remain on track, continuing to meet agreed targets and expected standards.
Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio (1 page)
PSRP continues to deliver good value for money (VfM) across all indicators, with a focus on quality and cost. During the project, PSRP attracted additional funding from the British Academy, UN and ESRC which has helped to reduce unit costs. By using new technology to communicate with partners, PSRP has also reduced travel and venue costs. Using DFID’s 4 Es framework, specific examples of VfM savings this year include:

Indicator Category	Performance / Best Practice
Economy	Reallocation of PSRP travel budget to support computer development translation work, relating to the PA-X Database
	UoE continues to contribute extra resources to the programme, including the recent recruitment of a fixed-term Teaching Fellow in Human Rights Law.
	PSRP secured an initial UoE award of £5,000 from its ESRC Impact Fund, to further impact and engagement related effort. An additional £15,000 was awarded, allowing the Programme to continue to expand print publications; and allow commissioning of further infographics plus computer work needed to develop the PA-X Database.
Efficiency	Collaboration with the British Academy which hosted the launch of PA-X and the Navigating Inclusion report, the most cited output from Workstream 1 of the programme.
Effectiveness	PSRP has helped reshape the political settlement field by helping make ‘inclusion’ a central issue in conflict resolution. This is evidenced by the UN World Bank study which cites PSRP work, and by the impact of the British Academy Report on ‘Navigating Inclusion’, which directs future research to consider the relationship of inclusion to conflict
	PSRP presented PA-X at a UN Women High Expert Group meeting in implementation and peace agreements, which was intended to feed into the UN Secretary General’s Report on Women, Peace and Security. Laura Wise present findings from PA-X and PSRP on inclusion in peace agreements at the UNDP Oslo Governance Centre as part of their Expert Workshop on Inclusive Peace Agreement Implementation at the UNDP Oslo Governance Centre.
	There are more than thirty clear cases where PSRP’s work has influenced and shaped national and international policy development.
Equity	43 Southern-based researchers have published/co-published with PSRP, i.e.: 15 in regular PSRP publications; 3 in PSRP blog posts; 17 in Nepal Accord publications; 6 in Afghanistan Accord and 2 in borderland Accord.

Financial forecasting for PSRP has been accurate with actual costs in close alignment to forecasts. In the last year of the project, actual expenditure for the reporting against the forecast is 97.3% (see table below). Invoicing has been timely, good quality, and backed up with quarterly reports verifying progress against key performance indicators and outputs.

Figures in £	Q13	Q14	Q15	Q16		2018/19 FY Total
Forecast	286,412	248,177	233,623	274,153		1,042,365
Actual	285,045	209,312	246,939	273,403		1,014,699

% spend of forecast	100	84	106	100		97.3

E: RISK (½ to 1 page)

Overview of programme risk (noting the rating from p.1) and mitigation
Overall risk rating: Moderate
As PSRP approaches the end of phase 1 of the programme, the overall programme risk is assessed as ‘moderate’ going into phase 2. The risk framework will largely remain the same for the next phase.
The main risk this year is ‘failure to provide a broadly applicable evidence base to inform policy’. PSRP has mitigated this by establishing solid working relations with HMG and the UN following the publication of the PA-X database. The programme has delivered on core outputs and provided in-time advice to HMG and UN institutions.
There is a possible risk to programme delivery in the event UoE is unable to retain key programme personnel. Staff have been grouped into inter-organisational workstreams to mitigate this risk.
Management risks may arise as PSRP transitions into the extension in phase 2 – particularly as agreements with downstream partners change. This is a moderate risk. PSRP has addressed these successfully thus far through clear roles and responsibilities of partners and robust operating systems in place. PSRP has learnt lessons from the first phase and built reliable partnerships with a strong network and close connections with HMG. These will mitigate potential risks.
A detailed risk assessment has been provided in the PSRP annual report which has been discussed with DFID throughout the year.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE (1-2 pages)
Performance of partners and DFID, notably on commercial, and financial issues (1-2 pages)
This is a performance-based contract with expenses paid quarterly in arrears, based on actual costs. DFID retains 5% of each payment; with this retained amount then paid the following quarter providing all performance criteria have been met – to date, no funds have been withheld and the full 5% retention was paid in each subsequent quarter.
Financial management is covered in quarterly meetings, and expenditure and forecasts remain on track. An issue relating to variances in actual costs was highlighted during one meeting and detailed information is now provided to DFID in quarterly and annual reports to allow both parties to monitor this.
Key cost drivers include staffing costs, research uptake and travel costs. In this reporting period, delivery and performance for the programme remain on track, continuing to meet agreed targets. The project is on track against the current planned timeframe. PSRP provide regular budget updates and track expenditure.
In July 2018 DFID ministers approved a £2.2m two-year extension to PSRP. The extension will deliver additional results to the existing PSRP project logframe in the following areas: deepen data and high quality comparative research; strengthen international policy engagement with intellectual institutions and provide evidence based advice to DFID teams working on peace agreements or political changes. Discussions for the extension are in the final stages.
Asset Monitoring and Control
There are no physical assets associated with the contract.

Date of last narrative financial report(s)	31 Jan 2019
Date of last audited annual statement (s)	NA as a contract

G: MONITORING, EVIDENCE & LEARNING (1-2 pages)
Monitoring (1/2 page)
DFID and PSRP have formal quarterly meetings to discuss and monitor overall progress, and communicate at least monthly. PSRP submits annual and quarterly reports in a timely manner. Quarterly reports are detailed and rigorous for a programme of this size.
This annual review was carried out during February and March 2017 by DFID’s A1 Conflict Advisor (also SRO), and a B1 Programme Manager. Substantive feedback on PSRP’s performance was also received from FCO Research Analysts and DFID Advisers. PSRP’s Annual Board Meeting was held in December 2018 in London.
The DFID review team conducted a desk-based review of key documents, including a detailed report of the programme’s performance over the review period submitted by the partners. Key research and communication outputs were also reviewed. The review team consulted with all downstream partners included in the programme and with key policy audiences (e.g. the UN, mediators and HMG officials) to verify feedback provided by PSRP.
A project review meeting was held with Edinburgh University on 28/02/2019, and the Consortium Advisory Group also met in December 2018. The Annual Review report was shared with PSRP for fact checking in March 2019. Recommendations will be followed up at subsequent project meetings.
An evaluation has not been included in this programme. Given the nature of the research and the relatively small size of the programme, an evaluation was not considered to offer sufficient VFM over rigorous monitoring.
Evidence (1/2 page)
Qualitative feedback was provided by policy audiences alongside data on quantitative targets for this AR. Monitoring is targeted at the specialist policy audiences working on peace processes (the main consumers of PSRP research) and their feedback has been used over the last year to refine the research questions; and to specify the focus of policy briefs. PSRP records all the requests and feedback that they receive from policy audiences for their support. DFID also verifies the feedback provided by HMG staff on PSRP advice. Advice is provided confidentially, however common questions are turned into policy briefs where feasible.
Feedback from international mediators and HMG officials is systematically collected by PSRP and by DFID RED. Research and expertise are provided to national partners and negotiating parties to peace process where feasible, but this is difficult to systematically track because negotiations are often held in secret and under conditions where parties are at war.
Demand for research on political settlements is variable, and subject to fluctuating conflict cycles and international attention. Ongoing peace and political processes can take 20 years or more to reach conclusion. PSRP’s work to inform ongoing processes is therefore best reviewed through feedback from those involved in the processes rather than concrete signs of progress in contexts where an end to conflict may be some way off (e.g. Syria, Yemen and South Sudan). PSRP’s work on Columbia last year demonstrates the value that research can provide when the political conditions for a positive milestone emerge. While we would expect these outcomes to contribute towards reduced discrimination, fragility, deaths in conflict, and violent homicide rates (PSRP programme impact indicators), it is clear that direct attribution and measurability are unlikely during the timeframes of this research programme
Progress on recommendations from previous reviews (1/2 page)
Following last year’s AR, PSRP has focussed resources and research to meet a high demand from UK officials, and partners working on complex conflicts. The main recommendations were:
1. Complete 4 further policy papers by August (2018). Last year PSRP was required to deliver a report on each of 4 priority policy topics (peace process design and implementation, sub-national arrangements, power/resource sharing, security guarantees and justice provisions). Draft papers were submitted by Dec 2017 and will be published by April 2018. Additional papers on ceasefires, transitional justice, economic provisions and amnesties will be delivered by August 2018. Recommendation completed. All policy papers have been published on PSRP’s website.
2. Consolidate key facts from the database and wider research into a form that can be used by international mediators or other actors working on peace processes PSRP presented early analysis from the database at a launch event with DFID’s Permanent Secretary in February 2018. PSRP will provide an updated set of facts from the database with clear recommendations for policy makers by August 2018. Recommendation completed. Key facts have been presented to DFID and infographics developed.
3. Hold significant uptake events with OECD, UN and HMG staff on the database. PSRP should continue and deepen support to HMG country teams and to international mediators working on peace processes. PSRP has committed to organising events with key international partners; the OECD in support of the UK co-chairmanship, the UN Peace Building Support Unit and/or World Bank in either New York or Washington and the EU Mediation network. PSRP will also present research to the East Africa Conflict and Governance Advisers in Nairobi on the 2nd July and will provide at least 2 workshops for HMG staff in London. Recommendation completed. PSRP has conducted events with OECD, UN, and HMG staff on the database this year.
4. Consider Extension to the current contract. DFID and PSRP have agreed to consider an extension to the current contract to enable greater use of the database and PSRP expertise within ongoing peace processes. This would build on PSRP‘s strong record this year and meet demand from policy makers for well evidenced rapid response outputs and advice. Recommendation completed. PSRP and DFID signed a contract for a 2-year extension on 20 March 2019.

Annex 1: PSRP Publications and Blogs with links

1.2		Report		Gender in Political Transition: Bougainville’s Peace Process’, CR (London) and PSRP (Edinburgh). Available here: http://edin.ac/2HPav4d
4.1		Journal Article		Ni Aolain, ‘Gendering the Law of Occupation: The Case of Cyprus’, Minnesota Journal of International Law (27:1), 2017. Available here: http://edin.ac/2GQv1jL
4.1		Special Issue		Rooney/Ni Aolain, ‘Special Issue: Transitional Justice from the Margins: Intersections of Identities, Power and Human Rights’, International Journal of Transitional Justice, 12:1, https://academic.oup.com/ijtj/issue/12/1
4.3		Journal Article		O’Rourke, ‘Feminist Strategy in International Law: Understanding its Legal, Normative and Political Dimensions’, European Journal of International Law (38:4), 2018. Available here: http://edin.ac/2HPpxah
5.4		Briefing Paper		Brown, Political Commemoration: the Inclusion Dynamics of ‘Partisan Commemoration’, PSRP (Edinburgh). Available here: http://edin.ac/2GNhOIC
3.4		Report		‘Interactions between Elections and Constitution-Building Processes in Fragile and / Conflict-affected States’, Fourth Edinburgh Dialogue on Post-Conflict ConstitutionBuilding, International IDEA and PSRP. http://www.politicalsettlements.org/publicationsdatabase/interactions-between-elections-and-constitution-building-processes-in-fragileand-conflict-affected-states/
1.2		Report		Yousuf, ‘Navigating Inclusion in Peace Transitions: Beyond Elite Bargains’, Accord Spotlight, London: Conciliation Resources. / http://www.politicalsettlements.org/publications-database/navigating-inclusion-in-peacetransitions-spotlight/
4.5		Report		Close, ‘Gendered Political Settlements: Examining Peace Transitions in Bougainville, Nepal and Colombia’, Accord Spotlight, London: Conciliation Resources. / http://www.politicalsettlements.org/publications-database/gendered-political-settlementsspotlight/
1.1		Journal Article		Adhikari, ‘India in South Asia: Interaction with Liberal Peacebuilding Projects’, India Quarterly: A Journal of International Affairs, online first. / http://journals.sagepub.com/doi/pdf/10.1177/0974928418766731 (embargoed)
4.6		Briefing		Swaine, ‘Understanding and Addressing Conflict-Related Violence Against Women’, PSRP Briefing Paper, Edinburgh: GJA. http://www.politicalsettlements.org/publicationsdatabase/understanding-and-addressing-conflict-related-violence-against-women/
3.1		Briefing		Forster, ‘Quick Guide to Ceasefire Arrangements’, PA-X Rapid Reaction Paper, Edinburgh: PSRP, http://www.politicalsettlements.org/publications-database/psrp-pa-xrapid-reaction-paper-quick-guide-to-ceasefire-arrangements/
3.1		Briefing		Pospisil, ‘Building States while Building Peace? Statebuilding and Security Sector Reform in Peace Agreements’, ASPR / PSRP PA-X Policy Brief, Vienna/Schlaining: ASPR. https://www.friedensburg.at/uploads/files/2018_02_Statebuilding.pdf
4.6		Report		Doyle/Mc Williams, ‘Intimate Partner Violence in Conflict and Post-Conflict Settings: Insights and Lessons from Northern Ireland’, PSRP Report, Belfast: Transitional Justice Institute, Ulster University.
3.4		Report		Tierney, ‘Reflections on Referendums’ (Stockholm: International IDEA, 2018). / https://edin.ac/2Pfwqo2
	3.4		Report		Ellis, ‘Electoral System Design in the Context of Constitution-building’ (Stockholm: International IDEA, 2018). https://edin.ac/2Pbeif2
	3.1		Report		Molloy, ‘Assessing and Influencing Progress in Peace Processes Workshop Report’ (Edinburgh: Global Justice Academy, 2018). https://edin.ac/2PhmbzJ
	3.1		Journal Article		Wise, ‘Setting Aside the ‘Others’: Exclusion amid Inclusion of Non-dominant Minorities in Peace Agreements’, Nationalism and Ethnic Politics, 24 (3). https://edin.ac/2P92dHj
	3.1		Report		Bell, ‘Political Power-sharing and Inclusion: Peace and Transition Processes’ (Edinburgh: Global Justice Academy, 2018). https://edin.ac/2PbdXZO
	3.1		Report		Bell, ‘Economic Power-sharing, Conflict Resolution and Development in Peace Negotiations and Agreements’ (Edinburgh: Global Justice Academy, 2018). https://edin.ac/2PduU66
	3.1		Report		Wise, ‘Territorial Power-sharing and Inclusion in Peace Processes’ (Edinburgh: Global Justice Academy, 2018). https://edin.ac/2Nuo3oh
	5.2		Report		Larson & Ramsbotham, ‘Incremental Peace in Afghanistan’ (London: Conciliation Resources, 2018). https://edin.ac/2Nuoq29
	5.2		Policy Brief		Larson & Ramsbotham, ‘Incremental Peace in Afghanistan’ (London: Conciliation Resources, 2018). https://edin.ac/2Nq5wcK
	5.4		Journal Article		Brown, ‘Political commemoration and peacebuilding in ethno-national settings: the risk and utility of partisan memory’, Peacebuilding. https://edin.ac/2NACQ0Z
	6.1		Report		Bello Schünemann and Moyer, Structural pressures and political instability Trajectories for sub-Saharan Africa, PSRP ISS Report, Institute for Security Studies, / http://www.politicalsettlements.org/wp-content/uploads/2018/10/2018_ISS_Bello- / Schuenemann-Moyer_structural-pressures-and-political-instability.pdf
	3.1		Report		Molloy, Business and Peace Agreements, PSRP Research Report, University of Edinburgh, Global Justice Academy, http://www.politicalsettlements.org/wpcontent/uploads/2018/11/2018_Molloy_Business-Power-Sharing-Report.pdf
	5.4		Journal article		McNicholl, Stevenson, and Garry, ‘How the “Northern Irish” National Identity Is Understood and Used by Young People and Politicians’, Political Psychology, onlinefirst, http://www.politicalsettlements.org/wp- / content/uploads/2018/11/2018_McNichollEtalPP_HowTheNorthernIrishNationalIdentity.pdf
	5.5		Report		Plonski and Yousuf, Borderlands and Peacebuilding: a View from the Margins, Accord Insight 4, PSRP and Conciliation Resources, http://www.politicalsettlements.org/wpcontent/uploads/2018/11/Accord-Insight-4-Borderlands-WEB.pdf
	3.1		Report		Jamar, Victims’ Inclusion and Transitional Justice: Attending to the Exclusivity of Inclusion Politics, PSRP Research Report, University of Edinburgh, Global Justice Academy, http://www.politicalsettlements.org/wp-content/uploads/2018/11/Victims-ReportDIGITAL.pdf
	3.1		Journal article		Bell and Badanjak, ‘Introducing PA-X – a new peace agreement database and dataset’, Journal of Peace Research (in print, online forthcoming)

Table 2. Year Three Blog Posts/Opinion Pieces on PSRP Website

Date		Who		Blog post
18/12/17		Bell, (UoE) Pospisil (ASPR)		‘On selling “principled pragmatism” in transitions from violent conflict’. Available here: http://edin.ac/2CBZ7W7
18/01/18		Adhikari (UoE)		‘Ending the Political Transition? Analysing the Nepal Elections from an Inclusive / Perspective’. Available here: http://edin.ac/2DgQAZu
21/02/18		Nash (UoE)		‘Why PA-X Matters: Introducing the Peace Agreements Access Tool’. Available here: http://edin.ac/2HPqHm0
	22/03/18		Forster, UoE		‘Sequencing Ceasefire Agreements: First, Last or in the Middle?’. Available here: / http://www.politicalsettlements.org/2018/03/22/sequencing-ceasefires/
	17/05/18		Yousuf, CR		‘Balancing stability and inclusion in peace transitions: a way forward’. Available here: http://www.politicalsettlements.org/2018/05/17/balancing-stability-inclusion/
	18/05/18		Close, CR		‘6 ways to support gender inclusion in peace transitions’. Available here: / http://www.politicalsettlements.org/2018/05/18/6-ways-to-support-gender-inclusion/
	28/06/18		Ramsbotham, CR		‘The ceasefire is essential – but what should happen next for peace in Afghanistan?’. Available here: http://www.politicalsettlements.org/2018/06/28/afghanistan-ceasefires/
	10/07/18		Havens, UoE		‘PA-X Timeline: a Data Visualization for the Peace Agreements Database’. / Available here: https://edin.ac/2NIwCfU
	03/08/18		Ramsbotham, CR		‘10 steps for peace in Afghanistan’. Available here: https://edin.ac/2M0uyS8
	22/08/18		Havens, UoE		‘PA-X Timeline Progress’. Available here: https://edin.ac/2Ms2RTD
	28/08/18		Sapiano & Ozcelik		‘The Bangsamoro Organic Law: a Concrete Step Towards Peace in Mindanao’. / Available here: https://edin.ac/2PfMkPk
	18/09/18		Satish Chand		‘Economic Power-sharing as a Means of Conflict Resolution in Peace Agreements’. Available here: http://www.politicalsettlements.org/2018/09/18/economic-power-sharing/
	01/10/18		Sean Molloy, UoE		‘Monitoring and Measuring Peace Agreement Implementation’. Available here: / http://www.politicalsettlements.org/2018/10/01/monitoring-and-measuring/
	13/11/18		Astrid Jamar, UoE		‘Mind the Billboards: International Aid Conquering the Public Space in Burundi’. Available here: http://www.politicalsettlements.org/2018/11/13/mind-the-billboardsinternational-aid-conquering-the-public-space-in-burundi/
	13/11/18		Astrid Jamar, UoE		‘Mind the Billboards: The Paradox of Paternalism in Burundi’. Available here: / http://www.politicalsettlements.org/2018/11/13/mind-the-billboards-the-paradox-ofpaternalism-in-burundi/
	18/11/18		Kathryn Nash, UoE		‘Political Unsettlement and Continuing Conflict in Central African Republic’. Available here: http://www.politicalsettlements.org/2018/11/18/politicalunsettlement-and-continuing-conflict-in-central-african-republic/
	22/01/19		Bell, UoE		‘Gender Violence in Conflict and Peace Processes: the Neglect of LGBT Security’. / Available here: http://www.politicalsettlements.org/2019/01/22/lgbt-security/

 Annex 2: PSRP Risk Framework
Risk category	Likelihood	Impact	Management Processes and / Mitigating Activities
Risk Category 1: / Delivery – High quality, relevant, timely and reliable research products
Research fails to provide a broadly applicable evidencebase capable of informing policy	Rare	Major	Risk remains in place but given the now established good working relations with HMG after the publication of the PA-X database the chances are very rare. As a proactive response, PSRP II has written intime advice to HMG institutions as part of the core programme tasks.
Research fails to achieve high/international quality standards	Unlikely	Moderate	In-programme research assessment is against Research Excellence Framework quality standards; which shows successful outcomes. PSRP output has been published in highly renowned international outlets. The strong policy focus of PSRP II, however, needs a particular focus on research excellence. The topic has been adequately addressed with the programme team at the last PSRP ‘away day’.
Non-level playing fields between resources and attention given to the various work programmes proposed	Rare	Minor	Respective reallocation of funds has proved to be successful. PSRP II relies on the most productive elements of the first four programme years.
Research does not have any impact on potential users	Rare	Moderate	PSRP research has already shown this impact. We have established strong relationships on which to build on and have now focused our attention to cases where we likely can generate the best possible impact.
Research funded does not have any discernible impact on policy makers	Rare	Moderate	The international uptake of PSRP work is considerable, the usefulness of its inputs has been confirmed by policy partners. Research is increasingly being utilised by key stakeholders such as DFID and FCO. In its final year, PSRP has been able to generate impact on international organisations as well, in particular The / World Bank, UN (UN Women), OECD INCAF and OSCE. We will follow up these relationships with our upcoming products.

Overall risk assessment of risk category 1: RARE/MODERATE
Risk Category 2: / Operational – Research process, impact/capacity building, programme governance
Capacity building challenges with recruited Southern researchers	Unlikely	Moderate	With the PhD candidate from the Global South (Mona Adhikari) performing well and likely not only to submit in time, but to have a promising post-doc career, PSRP has one likely achievement in its capacity building endeavours. We see the engagement with Southern-based researchers as a considerable challenge in Phase II and have an invitation policy for our workshops in place that guarantees significant Southern involvement in order to facilitate subsequent research partnerships.
Unstable (politically or otherwise) working environment encountered in geographical area of / work	Unlikely	Minor	PSRP II will not substantially rely on field research but on Joint Analysis Workshops. We will have trips to unstable areas for further engagement. However, these trips can be cancelled if need be without substantially impacting the progress of the research.
Significant delay in project implementation due to unforeseen reasons	Unlikely	Moderate	PSRP has delivered the vast majority of its outputs on time in its four programme years, hence we are confident in our management and delivery structure. We see the ambitious improvements of PA-X as the most risky endeavour in this context, but have staffed accordingly, and keep consistently track of the respective timeline.
Inability to retain key / programme personnel to ensure delivery	Possible	Minor	Key staff from PSRP will remain in place also for the second phase, the core part of the management team (Bell and / Cornell/UoE, Pospisil/ASPR, / Ramsbotham/CR) remain in place and are highly unlikely to move on during the next programme phase. Regarding the / Edinburgh staff working on PA-X, however, movements are possible and have a potential risk regarding the development of the database. We have grouped the staff into inter-organisational workstreams in order to mitigate this risk.

Changing priorities from DFID and/or other donors active in this research area	Rare	Minor	PSRP has responded over its first years to the changing needs, as evidenced by the possible extension. We consider this risk to be very low.
Management issues / related to the transition to PSRP II, particularly in relation to the changing partnership structure.	Rare	Moderate	We have proactively started to transition into PSRP II, which is supported by key parts of the managing structure that remain in place. The role and responsibilities of partners are very clear and incorporate lessons learned from the first stage, so while we accept this risk we have all systems in place to successfully mitigate it.
Overall risk assessment of risk category 2: UNLIKELY/MODERATE
Risk Category 3: / Fiduciary risk
Fraud such as misuse of programme funds	Unlikely	Minor	Regular financial reporting, detailed monitoring, requirements to set-up traceable expenditure systems ensuring compliance with the Bribery Act. The first phase of the programme shows a remarkably trustful relationship between partners. No problems have occurred.
Underperformance by any sub-contractor and/or breakdown of relationship between / University of / Edinburgh and any of its sub-contractors	Rare	Minor	Our internal risk monitoring system worked well – we have had to handle one partnership challenge in PSRP and were able to contain the negative consequences even with delivering the minimal output at the same time. PSRP II’s partnership structure relies on the most reliable partners from PSRP, hence this risk remains very low.
Non-compliance with legislation, e.g. / Companies Act, Taxes / Acts, Health & Safety / Act, Bribery Act	Rare	Moderate	External Audits; Staff training and Advice from central University of Edinburgh resources if needed; great and close management of PSRP by UoE structures / (at college and school level)
Overall risk assessment of risk category 3: RARE/MINOR
Risk Category 4: / Safeguards
Risk level due to ongoing violent conflict and physical safety concerns for researchers	Unlikely	Minor	PSRP II will not rely on field work as much as PSRP did. However, there is a certain safety risk concerned for researchers attending the Joint Analysis Workshops, and for PSRP core staff (particularly regarding the Ogaden work). This risk is considerably lower compared to Phase I, the tested risk management structures remain in place and continue to work.

Direct impact of natural disasters on research, dissemination	Rare	Minor	After the field work in Nepal concluded, there is no upcoming risk in this respect.
Overall risk assessment of risk category 4: UNLIKELY/MODERATE
Risk Category 5: / External context
Unfavourable political environment hampers field research, dissemination	Possible	Minor	We see our work on DRC, Ogaden and Afghanistan as having the biggest risk in this regard, we are in continuous / discussion with our partners. Conciliation Resources will cover the bulk of the relevant work in PSRP II and has proven to have appropriate structures in place to handle this risk.
Environmental risks arising from the research	Unlikely	Insignificant	Research outputs and communication materials should be developed efficiently to minimise waste and be recyclable. The GJA works closely with the Department of Sustainability and Social Responsibility, and the Head sits on the GJA Steering Committee. Communication is done electronically, travel and attempts to minimise environmental impact are part of regular reporting.
Overall risk assessment of risk category 5: UNLIKELY/MINOR
Risk Category 6: / Reputational Risk
Public campaigning against programme / activities, use of funds, usability of programme	Rare	Moderate	PSRP is aware of the close public scrutiny of development money and is taking its spending decisions carefully and with the aspect of the best possible delivery of meaningful, excellent research in mind.
Accusations against programme/funder during case study research in contested contexts	Unlikely	Minor	With the main bulk of field research successfully delivered and the contextrelevant research in PSRP II focused on long-standing working relationships this risk variable turns back to ‘green’.
Ownership issues regarding programme ideas and output by	Rare	Minor	PSRP had to face a case with ownership issues that were related to a researcher moving on to another DFID-funded
competing research programmes			programme, but we have been able to mitigate this issue by means of proactive, open and trustful communication. If any such issue should arise in the future, we will draw on this experience.