Business Case and Intervention Summary
Title: Urban Humanitarian Crises

What support will the UK provide?
This new programme responds to the Humanitarian Emergency Response Review’s identification of urban areas as increasingly frequent locations of crises, and the widespread lack of confidence and capability within the humanitarian system to operate in urban environments. The main purpose of this programme is to increase DFID’s, its partners’, and the humanitarian system’s capability to respond to urban crises. By urban crises, we understand natural disasters impacting on urban areas; towns and cities affected by large flows of refugees and internally displaced people (IDPs); and urban areas directly affected by conflict. / The work builds towards the World Humanitarian Summit in 2016 and will generate outcomes in three core areas: / Generation and documentation of learning on how urban systems are impacted by humanitarian crises and how responses can best be tailored to the urban context. / Building operational capability to work in urban areas, through the development of tools and promotion of learning from best practice. / Evidence-based high-level policy engagement on system reform for improved response to urban crises. / This business case has 2 components covering the three core areas above. Component 1 is an advocacy and learning partnership with a large, international humanitarian NGO, the International Rescue Committee (IRC). Component 2 is a capability fund that will make grants to support documentation of and learning from good practice, and the development of practical tools for the humanitarian system. Grants will be managed and supported by a research institute and think tank that has a long history of engagement on urban development issues, the International Institute for Environment and Development (IIED). The proposed budget is £3.5m over the period October 2014 to December 2017.[1]
[1] A separate initiative to support innovation and evidence in urban humanitarian response may be developed in 2015/16 in collaboration with RED, and funded under the Humanitarian Innovation and Evidence Programme (HIEP). DFID may also seek other funds to support one or two larger projects should they emerge during the course of the programme.

Why is UK support required?
More than half of the world’s population live in urban areas, and this percentage will continue to grow. By 2030 almost 5 billion people will be living in urban areas. Projections from the UN and other international bodies also point to increased frequency and severity of natural disasters occurring in towns and cities. The impacts of climate change are likely to be compounded by existing vulnerabilities in urban areas, where low-income populations are often housed in poor quality accommodation on marginal land. / In 2009, UNHCR acknowledged that almost half of the world’s 10.5 million refugees were living in cities and towns, compared to one third who were living in camps at that time.[2] The current refugee crisis in the countries bordering Syria also highlights how urban areas are increasingly perceived as safe havens for people fleeing conflict and persecution. / Despite the numerous links between humanitarian crises and urban areas, governments, donors, United Nations agencies, development actors and Non-Government-Organisations (NGOs) have yet to become operationally effective when responding to crises in these environments. Responses and programming in towns and cities tend to be ad hoc and insufficient to meet the needs of both displaced populations and host communities or to promote longer-term self-reliance of populations. / This programme will seek to rectify gaps in knowledge, skills and confidence amongst donors, governments, humanitarian actors and development agencies on how to prepare for and respond to humanitarian crises in urban areas. This will include the development of practical tools and guidance for operations in urban areas, as well as documentation of good practice. It will also seek to bring about high-level policy change to facilitate the engagement of a broader range of actors, including urban development specialists and local governments, in responses to future urban crises.
[2] UNHCR (2009) ‘UNHCR policy on refugee protection and solutions in urban areas’. Geneva, United Nations Refugee Agency.

What are the expected results?
This programme responds to a series of policy commitments set out in the UK Government’s 2011 Humanitarian Policy, Saving lives, preventing suffering and building resilience. It will enable the UK Government to better respond to humanitarian need in the wake of urban crises, stemming from both natural disaster and conflict, while supporting the international community to do the same. / Key outputs from the programme will include policy and advocacy statements and high-level policy engagement, case studies and briefing papers, humanitarian technical notes, operational guidance and tools, and other specific inputs to strengthen the humanitarian system. A mapping exercise has already been undertaken. Preparatory activities have included a literature review and stakeholder consultation. / Ultimately the work will improve responses by governments and the international humanitarian community that save lives and reduce suffering in humanitarian crisis affecting urban areas.

Strategic Case

A. Context and need for a DFID intervention / Urbanisation, Natural Disasters and Conflict / In recent years, observers of the humanitarian system have frequently asserted that towns and cities will be the location of increasing humanitarian need. Over the past 6 decades, the number of people living in cities has multiplied by 8 times. The world is becoming increasingly urban, and already more than half of its population lives in towns and cities. UNFPA estimates that urban growth will continue, and that by 2030 almost 5 billion people will be living in urban areas, ‘with urban growth concentrated in Africa and Asia’, particularly in smaller towns and cities.[3] / Nearly three quarters of the world’s urban population and most of its largest cities are in low- and middle-income countries. Within these growing cities, the areas that are growing fastest are informal settlements: it is common for thirty per cent of the populations in cities in low- and middle-income countries live in informal settlements.[4] Thus in many cities of the developing world, large sections of the urban population are already vulnerable, with limited access to basic services and adequate housing and infrastructure. The Humanitarian Emergency Response Review (HERR) acknowledged this, giving prominence to the issue of urbanisation: ‘The concentration of populations in urban areas will change the nature of many humanitarian disasters. More people will be living on marginal land, in overcrowded and poorly planned housing, lacking access to adequate water and sanitation, healthcare and education.’ [5] This already existing vulnerability can be compounded by shocks such as natural disasters and large influxes of refugees. / The increasing vulnerability of cities and their populations is noted by Dodman et al.[6] who record that since the middle of the last century, there has been a ‘much-increased concentration of people and economic activities in low-lying coastal zones or other areas at risk from flooding and extreme weather events’. This has been mirrored by an increase in the number of ‘serious injuries and deaths from disasters in urban areas’ over the same period.[7] Looking ahead, the proportion of disaster related deaths and injuries in urban areas in low- and middle-income countries is also likely to grow, both because an ‘increasing proportion of the world’s population live and work there’ and also because ‘many successful cities are on sites where part of their population is at risk’.[8] The location of many of the world’s largest cities in low-lying coastal zones means that huge numbers of people are at risk of the effects of sea-level rise and increased numbers of extreme weather events. / Climate change looks set to increase the severity of urban emergencies. Natural disasters often seriously affect urban areas that have grown quickly and where low-income groups can only afford to build on land that is undesirable and at risk. The rapid and unplanned nature of much urban growth contributes to vulnerability, with large informal settlements and construction of infrastructure and housing without adherence to building codes. A disaster in an urban area can result in a rapid escalation of humanitarian needs, as existing vulnerabilities are compounded. The particular urban characteristics that put people at risk include population density, poor quality residential housing and infrastructure, and violence, including VAWG. The exacerbation of these vulnerabilities presents a new set of challenges to urban populations, governments and the humanitarian system. / Urban crises can also be triggered by conflict. Cities and towns can become the locus of conflict and unrest because key political or commercial interests are located there. But urban areas can also be a haven for those affected by natural disasters or conflict in other areas, who flee to them in order to access services, or to hide. Living outside of camps, they are harder to identify and may be placing a serious strain on vulnerable host populations. / The current crisis in the Middle East caused by large numbers of refugees fleeing into countries neighbouring Syria has drawn attention to the fact that refugees and internally displaced people (IDPs) often choose to relocate to towns and cities, rather than move to traditional camp settings. As the IFRC noted in its World Disasters Report of 2012: / Today approximately half of the world’s estimated 10.5 million refugees and at least 13 million internally displaced persons (IDPs) are thought to live in urban areas (UNHCR, 2009; IDMC, 2012). More and more displaced people are attracted to urban areas: in 2011 IDPs were living in urban areas in 47 out of 50 countries (IDMC, 2012). Several high-profile situations of urban displacement have occurred in the last decade including in Iraq, to various cities and towns in Sudan, from Somalia to Nairobi, Kenya and Sana’a, Yemen, and within and between cities in Haiti after the 2010 earthquake.[9] / Since this report was written, the number of refugees not living in camps is likely to have risen, since it is estimated that 75% of the more than 2.5m Syrians who have fled live outside camp settings, predominantly in urban areas. / A sudden influx of large numbers of displaced people may overwhelm existing services, resources and markets, negatively impacting host communities. Failure to respond in an appropriate way may leave the most vulnerable communities unaided, and create or exacerbate tensions between host communities and new arrivals. / The increasing interest in humanitarian crises in urban areas is reflected in a growing body of literature and studies examining urban crises and in recent policy developments. For example, the United Nations High Commissioner for Refugees (UNHCR) released its ‘Policy on Refugee Protection and Solutions in Urban Areas’ in 2009 and in 2010, the Inter-Agency Standing Committee (IASC) released its ‘Strategy on Meeting Humanitarian Challenges in Urban Areas’. Donor governments are also increasingly interested in urbanisation. USAID released a policy on ‘Sustainable Service delivery in an increasingly urbanised world’ in October 2013. ECHO is encouraging clusters to consider urban areas as a key cross cutting issue.[10] / Whilst such evidence suggests that urban areas will be the location of increasing humanitarian action, limited knowledge, learning and policy initiatives have been drawn from previous responses, and improvements to humanitarian policy and practice in these settings have been slow to emerge. Governments (both donors and affected countries), the UN (both humanitarian and development agencies) and Non-Government-Organisations (NGOs) have yet to become operationally effective when responding to crises in urban areas. While agencies are beginning to develop new ways of working to suit the urban environment, responses and programming in urban areas can be ad hoc and insufficient to meet the needs of both displaced populations and host communities or to promote longer term self-reliance of populations. As noted in a review by the British Red Cross, ‘While much work has been done on urban risk and vulnerability, the humanitarian sector has been slower to understand what this means operationally for agencies.’[11] / Limitations of traditional humanitarian response / A number of recent, high-profile urban crises have highlighted the difficulties faced by humanitarian actors who are used to working in rural and camp-based environments. The Kenyan election violence of 2008, the Haitian earthquake of 2010, Typhoon Haiyan in the Philippines in 2013 and the ongoing Syrian conflict, have demonstrated that traditional approaches do not effectively address specific urban challenges. ‘Urban areas present unique challenges in terms of complexity and scale, and many existing ways of working were originally developed to address rural crises, and may not work as well in cities.’[12] / Approaches developed for rural or camp contexts are generally designed so that humanitarian actors implement direct delivery of commodities and services. If translated to an urban setting, these may fail to give adequate consideration to the fact that prior to the disaster, a functioning urban government and private sector are likely to have been in place, providing a certain level of municipal services and diverse markets providing livelihood opportunities. Duplication of delivery can therefore occur and have a negative effect on existing market systems. / A simple but critical difference between urban and rural populations is density. High population densities in urban areas have a significant impact on humanitarian programming. The size of the affected population is likely to be higher requiring more funding and more capacity to provide support. Provision of goods and services such as water and sanitation must be undertaken on a much larger scale requiring more staff, more equipment and more frequent replenishment or cleansing. Formal and informal land and property governance systems must also be recognised by humanitarian actors in order to avoid causing conflict where space is at a premium and there is a great need for shelter. Cash transfer programming can be appropriate in urban areas where cash based markets are common, but humanitarian actors have yet to develop the capability to implement this approach at the scale of urban populations. / Urban areas are often seen as a place to escape from conflict, and they can be affected by rapid population influxes from other areas of the country, or neighbouring states. The arrival of large numbers of people will obviously have an impact on host communities and neighbourhoods, and can put a critical strain on service provision, even in areas where services were previous meeting needs. Where families affected by disaster or conflict settle in already deprived areas, the additional stress on inadequate basic services can also exacerbate social problems. Supporting both communities at policy and programmatic level is crucial to improving responses. As well as potentially causing resentment and divisions between hosts and the displaced, the creation of parallel systems for refugees may be more costly than attempting to integrate them into existing service provision. / An effective response to an urban crisis requires a comprehensive understanding of the city as a system to guide appropriate responses and support human and other capacities available at the local level. While humanitarian agencies tend to focus on sector-based assessments, there is a need for comprehensive city-wide analysis so as to build multi-sector responses. These should include analysis of the capabilities of host government, local authorities and other stakeholders. Comprehensive assessments would analyse critical city systems, including markets, governance and infrastructure, as well as social systems. / It is particularly important to work closely with governments in urban areas, where they are often more visible and powerful, and to understand and negotiate different tiers of government, from ward level to municipalities or districts, up to city or metropolitan level. Where host governments and local authorities are strong and have good disaster management capabilities, working with them to bolster basic services and support both host and displaced communities should be key to any response in an urban area. However, such an approach can be unfamiliar to humanitarian actors who are set up to implement services more directly. / In urban areas, the onus on humanitarian agencies should be to work with governments, and to play a facilitative role in restoring existing city systems, such as markets, where possible. In towns and cities, the private sector is likely to be well-developed, with markets in services (such as health and education) as well as in goods. Temporary measures are often essential in emergencies, such as the distribution of cash or in kind commodities, but these must be designed to mitigate negative effects on existing urban market systems, which can be sophisticated and intricately linked into rural and national value chains. / The vulnerabilities of people living in urban areas differ from those in rural areas. People in urban areas are more likely to be dependent on local markets, while in rural areas they are likely to be dependent on natural resources and agriculture.[13] / The dependence of urban populations on markets means that the private sector has a critical role to play in recovery. Where markets are functioning, affected communities can often access resources to recover quickly. Cash can be programmed as relief, rather than assets. Where markets are damaged, or the infrastructure they rely on is damaged, relief in the form of assets may be more appropriate, alongside rapid repair of infrastructure. / The boundary between humanitarian response and development programming is less obvious in urban areas, and there is a clear need for improved coordination and exchange of knowledge between humanitarian responders and actors that specialise in urban development. Whilst humanitarian crises might initially present acute humanitarian needs, the range of actors best placed to respond to such crises goes beyond humanitarian agencies. Effective responses require a greater role for urban development actors who are already working with governments to prepare for and manage urbanisation, and to promote self-reliance and resilience of populations in urban areas. To provide effective support to a humanitarian response, urban development actors need to become involved earlier in a crisis, and view support to displaced communities as a priority. / Coordination mechanisms could be better tailored to the urban context. To date, there have been limited attempts to set up coordination mechanisms in urban areas that better address the urban environment. The British Red Cross (BRC), in their ‘Learning from the City’ report, describe an area-based method of coordination, which may provide greater city and neighbourhood coherence. BRC trialled this approach in Haiti, and refer to it as the ‘integrated neighbourhood approach’. / Such an approach is appealing given the absence of many public and private actors from the cluster system convened by OCHA, with the exception of the logistics and emergency telecommunications clusters in terms of private sector companies. […] A geographic approach linked to urban systems is not without problems, for example knowing where a humanitarian mandate ends and that of development and government agencies begins, and what to do if state and development partners fail to meet the basic needs of vulnerable people. However, if well managed, such an approach provides a significant opportunity for a more joined up response from government agencies (including civil defence, emergency services, line ministries and service providers), the private sector and civil society.[14] / There are some emerging new forms of coordination arising from the response to the Syria crisis – bringing in government and development actors, but these are nascent, and any good practice to date has not been widely disseminated. / Why should DFID be involved? / The UK has made a commitment to respond to humanitarian emergencies according to need. Humanitarian emergencies are likely to arise more often, and become more acute, in urban areas as a result of rapid urbanisation, climate change and ongoing conflicts. / The humanitarian system does not yet have the tools, guidance, evidence and protocols that would underpin an improvement in interventions in urban areas, from the operational to policy levels. Whilst a number of organisations have identified the need for greater focus on responding to humanitarian need in urban areas, and for concerted policy advocacy at the highest levels to improve coordination, there is no obvious candidate for lead agency on the issue. / There are few examples of strong leadership on responding to urban crises from within the UN. The mandated agency for human settlements is UN-Habitat. It leads an IASC task force called Managing Humanitarian Challenges in Urban Areas (MHCUA), but this group has yet to galvanise humanitarian agencies into significant action. Meanwhile, the lead agency for refugees, UNHCR, only acknowledged in 2009 that urban areas are suitable destinations for refugees, and has yet to develop significant expertise on how to deal with sudden, large influxes of displaced people in to towns and cities as a result of humanitarian crises. / Commitment and leadership is required across the humanitarian sector to improve responses to humanitarian crises in urban areas. The Syria crisis has brought a range of issues to the fore and donors, host governments, UN agencies and NGOs are now increasingly focused on the issue. This receptiveness is an opportunity to affect real change which in turn can inform the humanitarian sector as a whole, particularly in the lead up to the World Humanitarian Summit to be held in the first half of 2016. / DFID, by partnering with specialist organisations that have approached the Department for support, has the opportunity to act as a catalyst for change and an advocate for improved emergency preparedness, coordination and response to urban crises. / Why act now? / The period 2014-16 provides DFID and key humanitarian partners with a number of opportunities to push forward the debate on urban crises and the role for government, humanitarian and development actors in response to those crises. A community of practice is beginning to form, and a range of actors, encouraged by DFID, have been involved in special sessions and side events in 2014, including at the World Urban Forum in Medellin, in April, and the Humanitarian Affairs Segment at ECOSOC in New York, in June. Further opportunities for engagement have been identified over the coming years, to build on the enthusiasm and interest in the topic. / In November 2015, the 32nd International Conference of the Red Cross Red Crescent Movement will be held, at which there will be opportunities for States and National Societies to adopt tools and methods for improved humanitarian shelter response in urban areas. Also in 2015, UNISDR will be holding its Third Conference on Disaster Risk Reduction, where urbanisation and the reduction of disaster risk in urban settings will be an important theme. / 2016 will be a key year, with the first World Humanitarian Summit in March, shortly followed by Habitat III (a UN General Assembly mandated conference on human settlements held every 20 years). / The urban aspects of humanitarian response are on the agenda for the World Humanitarian Summit and are specifically mentioned in relation to one of four thematic areas: ‘Serving the needs of people in conflict’. / Work under this theme will include identifying more effective strategies and methods of providing assistance to people affected by conflict and other forms of violence across lines of combat or hostility. It will also focus on finding more durable solutions to displacement, including displacement to and within urban areas, which exacerbates developmental challenges such as urban planning, lack of essential services and unemployment, as well as the unique and emerging challenges posed by conflict and other forms of violence in urban settings. It will explore strategies and mechanisms to coordinate work across the system on these issues post-2016.[15] / Summit participants will be able to announce new policy commitments, innovations or partnerships that they plan to implement after the Summit. A further cross-cutting theme of the Summit will be broadening partnerships for humanitarian assistance, which complements the aim of this initiative to increase the engagement of development and government actors in urban humanitarian response. An urban task team is also to be established under the theme of ‘Managing risk and uncertainty’. / Initiating work on this agenda in 2014 will put DFID in a strong position to engage in consultations prior to the WHS, and to shape the agenda. There are four consultations in 2015. / In sum, DFID has the opportunity to play an important role on the world stage over the next two years by championing improved coordination amongst government, development and humanitarian actors in urban areas, promoting innovative solutions to address the needs of the most vulnerable people affected by urban crises, and building a knowledge base of good practice to inform on-going and future humanitarian response in towns and cities. / Proposed approach to address issues identified / CHASE’s Humanitarian Response Group (HRG) has recently initiated a programme of work on urban crises. This new programme responds to the identification of urban areas in the Humanitarian Emergency Response Review (HERR) as emerging locations for crises, coupled with a widespread lack of confidence and capability within the humanitarian system to operate in urban environments. / The programme will focus on the aspects of working in the urban environment and with urban communities that are most distinct from rural areas. These include close working with governments (particularly municipal and metropolitan authorities), engaging with the social complexity of urban populations, addressing the built environment and supporting and restoring markets. The specific challenges of protection in urban environments will be a cross-cutting theme. While urban areas can be host to various drivers of poverty, HRG’s work with partners will focus specifically on humanitarian crises. This will include consideration of preparedness measures and resilience as part of response. / The main purpose of the programme is to increase DFID’s, its partners’, and the humanitarian community’s capability to better respond to urban crises. Outputs will include a literature review and stakeholder consultation, strategic approach papers, policy and advocacy statements, high-level policy engagement, humanitarian technical notes, a research programme, operational guidance and tools, and other specific inputs to strengthen the humanitarian system. / This programme of work is divided into two components: / Component 1: Evidence-based high-level policy engagement on system change for improved response to urban crises / Component 2: Building operational capability to respond to humanitarian crises in urban areas, through the development of tools, and the documentation and promotion of learning from best practice.
B. Impact and Outcome that we expect to achieve / Impact: A diverse range of actors have knowledge, skills and understanding to respond effectively to urban humanitarian crisis, in an enabling policy environment which recognises the specificity of urban crises. / Outcome: Humanitarian actors understand and accept the need for system change, and have increased operational capability to act in urban crises. / This business case has 2 components, costing £3.5m over the period October 2014 to December 2017. / What we expect to achieve: / Component 1: / Evidence-based high-level policy engagement on system change for improved response to urban crises / Component 1 will be a new policy and advocacy partnership with the International Rescue Committee (IRC). Within a framework of ‘co-production’, the two organisations will pool and share knowledge and skills to develop and implement a programme of work in the lead-up to the World Humanitarian Summit (WHS) and Habitat III (both in 2016) as well as other international forums. Together, IRC and DFID will act as convenors and catalysts in support of an enabling policy environment for improved response to urban crises by government, humanitarian and development actors. This will have a particular focus on working with local and national authorities, broadening the range of actors involved in responding to urban crises, and tailoring coordination and assessment mechanisms to the urban context. IRC will produce advocacy and practice papers based on their own programming in urban areas, and on the learning emerging from Component 2. They will further organise a series of side events and special sessions at WHS consultations and at the two 2016 summits themselves. They will also organise regional practitioner workshops to share learning. In the spirit of co-production there will be a three-month detailed inception phase (Oct – Dec 2014) during which IRC and DFID will work together to refine activities and outputs for the implementation phase of the programme. This will involve stakeholder mapping, an advocacy plan, a detailed workplan and a monitoring framework. Collaboration with IIED will be an essential part of both inception and implementation phases. / IRC will devote Ditchley Park conferences in 2014 and 2016 to the urban agenda, ensure senior management engagement and maximise the use of their networks and convening power to promote institutional change and improved urban humanitarian response and coordination. / DFID will fund two full-time equivalent positions in IRC to work specifically on urban crisis, and will dedicate 60% of a DFID urban advisor’s time to work on the programme with IRC for a period of 18 months. The terms of this arrangement will be agreed through an MoU between DFID and IRC. The DFID advisor will be based in New York, to facilitate engagement with the work of IRC’s Head Office (particularly their Research, Evaluation and Learning unit), and establish close working relationships with a range of relevant actors in New York and Washington DC, including thematic leads in the World Humanitarian Summit secretariat, OCHA, Rockefeller Foundation, the new urban team in the World Bank (known as the Social, Urban, Rural and Resilience Global Practice) and UN-Habitat. The arrangement has been designed so that the advisor will continue to devote 40% of their time to working directly with DFID (with the urban task team, urbanising development group, and colleagues working on the World Humanitarian Summit in New York and Whitehall). DFID will benefit from this arrangement, as it will open up an additional position that is dedicated almost 100% to urban humanitarian issues. This will ensure that policy development on this critical issue will be informed by high-quality technical advice, and that DFID has a strong voice in international policy arenas. Given current pressures within CHASE, and the multiple agendas advisers work on within the department, this level of dedication to the issue of urban crises would not otherwise be possible. The design of the arrangement is such that the advisor will be in regular contact with CHASE colleagues, and will be a member of the urban task team. This will reduce the management burden for the overall advocacy and learning partnership for CHASE. At the same time, the arrangement will serve to strengthen the institutional relationship between IRC and DFID, and ensure the programme can draw on strong institutional commitment from both agencies. / During the course of the programme, DFID advisers in CHASE will also engage in reflection and documentation of learning from on-going and past responses that have an urban component. Any case study material produced as a result will be fed in to the dissemination and advocacy work of IIED and IRC. A limited budget will be held in CHASE to cover travel and other costs related to documenting DFID experience and learning. / Component 2 / Building operational capability to work in urban areas / In order to build the capability of humanitarian actors, local civil society, municipal authorities and governments to respond to urban crises, DFID will establish a responsive fund that will make grants to a range of non-governmental, international and local organisations. These grants will support the generation and documentation of learning and good practice in recent and ongoing urban crises, and the development and testing of assessment tools, practical guidance and training. / DFID will work with the International Institute for Environment and Development (IIED) to manage the grants. IIED has a long history of policy-oriented research on urban settlements and climate change, and has an established track record of working with local institutions (including municipal government) and civil society organisations. IIED is also a grant-making organisation. Grants flowing through the organisation constituted 15% of its expenditure in 2012/13. DFID and IIED will establish a fund management board to assess and agree proposals submitted for the capability fund, and to commission small studies of specific initiatives and interventions. IIED will provide further thought leadership on urban crises through case study research and dissemination of best practice emerging from the work of grantees. / The proposed work by IIED will have two main outputs: / Managing the disbursement of ‘learning grants’ to operational organisations, including local and international NGOs already working in the field of urban humanitarian response. / Undertaking a programme of analysis, documentation and learning to provide the necessary conceptual frameworks and understanding to inform the activities and responses by the operational organisations, and to synthesise the outputs from the learning grants into useable lessons for local governments, national and international NGOs, and bilateral funding agencies. / IIED’s two outputs will be mutually reinforcing. In particular, the second will include substantial support to the organisations receiving funds under the first – who will also be expected to undertake documentation of past and current experience, and to share this through workshops and other means. / During the inception phase, IIED and IRC will clarify how they will ensure complementarity between their different roles and responsibilities within the urban crises programme. They will agree a joint overall workplan and engagement strategy, to ensure collaboration and that their individual contributions to the programme are maximised. / Compliance with the Gender Equality Act / According to the Gender Equality act, gendered differences in need must be taken in to account before humanitarian assistance is provided. There is no direct provision of humanitarian assistance in this programme: its aim is to improve the understanding, capability and confidence of DFID and its humanitarian partners to operate in the urban environment. The preparatory consultations and literature review for this programme considered the urban environment as a set of interlocking systems, including social, governance, infrastructure and market systems, and highlighted the gendered differences in women and men’s mobility in the city, their livelihood options and their ability to engage with local authorities prior to a crisis, and how this would be affected by a humanitarian emergency. The literature review has a specific focus on protection, and how particular groups, including women and girls, may become vulnerable to violence and exploitation as a result of displacement from their homes, and/or reduced access to basic services. The programme reflects these findings in the following ways: / Protection is a cross-cutting theme of the programme. One of the principal aims of the research and learning component is to develop tools and guidance for practitioners to improve their ability to understand vulnerability in the urban context. This will include vulnerabilities relating to gender that are caused by or exacerbated by humanitarian crises. / The advocacy component has a specific goal to engage with the international community to improve agencies’ ability to identify and provide services (including protection services) to vulnerable groups in urban areas, particularly in refugee/IDP situations where affected populations are ‘hidden’ amongst host communities, who may be equally vulnerable. Again gender will be one aspect, amongst others, of vulnerability in an urban displacement context.
[3] www.unfpa.org/pds/urbanization. Accessed Jan 2nd 2014
[4] Dodman, D. et al. (2013) ‘Understanding the nature and scale of urban risk in low- and middle-income countries and its implications for humanitarian preparedness, planning and response. London, International institute for Environment and Development (p. 36).
[5] P Ashdown et al. (2011) ‘The Humanitarian Emergency Response Review’ (p. 9). ﻿www.dfid.gov.uk/emergency-response-review Accessed 12th August 2014.
[6] Dodman, D. et al. (2013)’ Understanding the nature and scale of urban risk’ (p. 3).
[7] Ibid p.20.
[8] Ibid p.21.
[9] IFRC (2012) World Disasters Report: Focus on Migration and Forced Displacement. Geneva, International Federation of the Red Cross and Red Crescent Societies (p.113).
[10] Personal communication with representative of Sector Support Team, DG ECHO, Nov 2013.
[11] P Baizan, S Carpenter and A Kyazze (2013) ‘Learning from the City’. London, British Red Cross (p. 6).
[12] L Campbell, P Knox-Clarke and D Sanderson (2012) ‘Responding to Urban Disasters: Learning from previous relief and recovery operations’. London, ALNAP (p.1).
[13] P Baizan et al. (2013) ‘Learning from the City’ p. 25.
[14] Ibid p.43.
[15] World Humanitarian Summit 2016 Concept Note. http://www.worldhumanitariansummit.org Accessed March 21st 2014.

Appraisal Case

A. What are the feasible options that address the need set out in the Strategic case? / Four options have been assessed to address the need set out in the strategic case / Do nothing. / Accept the invitation from IRC and use an Accountable Grant to establish a learning and advocacy partnership with them to implement Component 1, and set up a DFID CHASE managed capability fund for Component 2. / Accept the proposal from IRC and use an Accountable Grant to establish a learning and advocacy partnership with them to implement Component 1, and launch an open competition to identify an organisation, or consortium, to manage Component 2. / Accept the proposal from IRC and use an Accountable Grant to establish a learning and advocacy partnership with them to implement Component 1, and approach IIED to manage Component 2. / Option 1: Do nothing / As noted above, while there is increasing interest within the international humanitarian community to improve response to urban crises, and a recognition that engagement of a broader set of actors working within improved coordination structures is needed, as yet there is little discernable leadership from the UN system, and an absence of a strategy to overcome current weaknesses. The majority of NGOs have not managed to go beyond the identification of complexities within the urban environment to come up with concrete plans to overcome these challenges. With the advent of a number of high-profile international events on the agenda for the coming two years, DFID and its partners have an opportunity to effect real change within the humanitarian system, catalysing the engagement of key development and government actors, and supporting the development of practical tools and guidance to ensure that the needs of the most vulnerable are met when towns and cities are impacted by humanitarian emergencies. Were DFID to do nothing at this point, it is likely that the humanitarian system will continue to be hindered by weak contextual analysis of urban systems, limited availability of tools designed for the urban environment and a lack evidence of good practice. The do nothing option has therefore been dismissed / Option 2: Accept the proposal and fund the IRC to implement Component 1 and establish a capability fund, managed by DFID, for Component 2 / Component 1 / CHASE has undertaken a thorough mapping of on-going initiatives in urban response and preparedness by donors, the UN and NGOs. The conclusion of the mapping is that while awareness of the issue is growing, there are, at present, very few agencies that have made a concrete policy decision to focus on urban humanitarian response. / During this mapping period CHASE was approached by IRC with the intention of instigating a new policy and advocacy partnership to progress the Urban Humanitarian Response agenda in the run up to the World Humanitarian Summit (WHS) and HABITAT III. The judgement has been made, and accepted by commercial advisors, that it is sufficiently distinctive that allowing others to bid for it would encroach on IRC’s intellectual property and so be inappropriate. / The IRC have a history of combining operational work with research, rigorous M&E and policy advocacy. They have proven capacity to take on an emerging issue, and, through a combination of research, learning from programming and evidence-based advocacy, increase international attention to that issue and bring about high-level policy change. Their achievement with regards to violence against women and girls is a case in point. No other agency has approached DFID with a clear plan to focus on improving the response to humanitarian emergencies in urban areas, and IRC are, to date, ahead of similar agencies in their level of commitment to this agenda. Urban displacement and crisis were identified by IRC-UK as a strategic priority in 2010, and adopted as an advocacy priority by IRC internationally in 2011. In October 2013, IRC held a two-day conference at Ditchley Park on urban displacement to inform its programme of urban work for the coming years, and encourage greater focus on the issue amongst its partners and other high-level stakeholders. The IRC has a proven ability to convene other NGOs, UN agencies and donors, and to act as a dynamic advocate for change, bringing new issues on to the international humanitarian agenda. / The IRC currently implements programmes in a range of urban areas, responding to both displaced communities and urban areas impacted by natural disaster, and is piloting innovative responses in urban settings to improve understandings of the urban context. IRC has already identified a number of its country offices where urban programming is on-going and staff are keen to engage in research and M&E of their own practice. / Component 2 / DFID could set up and manage a capability fund to respond to time-sensitive and innovative proposals to generate learning for the advocacy partnership, and increase operational capability in the humanitarian system. The fund would be designed to provide small-scale grants for a number of niche activities that would feed into the wider programme. This will produce a large administration burden for the fund manager. Even if we support a conservative estimate of four or five projects, the associated tasks such as the call for proposals, proposal assessment, contracting, financial administration and monitoring and evaluation would require significant inputs from CHASE. / Option 3: Accept the proposal and fund the IRC to implement Component 1 and launch an open competition for Component 2 / Component 1 / See option 2 for description. / Component 2 / Outsourcing the management of the responsive fund through an open competition would significantly minimise administrative costs associated with CHASE staff time. However, as the partner will be required to provide a level of autonomous oversight and direction, along with some research-based outputs linked to the evidence collected from the funds activities, it is essential that the fund manager has a high-level of technical expertise in urban humanitarian issues. It will be hard to find an organisation through an open competition with the required breadth of expertise and understanding on urban humanitarian crises, as demonstrated by a recent attempt to procure similar services through the Policy Research Fund process. Although the tender process would be led by PCD it would still have significant CHASE time and monetary costs attached to it, and as it is foreseen that the competition will only provide one suitable partner this option is discounted as it provides low VFM. The issue can be resolved by appointing a fund manager that has significant technical expertise and knowledge of urban issues and disaster risk, such as IIED, as outlined in Option 4. / Option 4: Accept the proposal and fund the IRC to implement Component 1 and approach IIED to manage Component 2. / Component 1 / See option 2 for description. / Component 2 / Outsourcing the management of the capability fund to IIED would significantly minimise administrative costs associated with CHASE staff time. As highlighted in the option above, there is no other organisation with the required breadth of expertise and understanding on urban issues and disasters, so it is wholly appropriate to directly approach IIED to manage this component. Whilst there is a risk that CHASE would lose control over the focus of the capability building initiatives that are supported through the fund, and the timeframe within which proposals are commissioned and funded, this risk would be offset by the skills and knowledge that IIED would bring to the programme. The aim of the fund is to be able to respond quickly to time-sensitive pieces of work that will build up capabilities within the humanitarian system, and improve the evidence base for DFID’s high-level advocacy. It is therefore important that the fund management partner has sufficient expertise in both the technical aspects of the programme and the financial processes of fund management to do this adequately. IIED have been identified as an appropriate partner due to their reputation as one the UK’s leading policy and research organisations on urban development, human settlements and disaster risk. They have links to a variety of networks of urban civil society organisations across Africa and Asia, built up over many years of supporting local organisations to engage with urban governance processes, and also have a history of engagement with federations of the urban poor across the developing world. They also have strong institutional capacity to manage and disburse grant funding, and are currently managing the Bill and Melinda Gates Foundation’s US$10m International Urban Poor Fund, in conjunction with Slum/Shack Dwellers International. / Recommendation: Accept Option 4 / A partnership between DFID and the IRC, combined with a responsive fund managed by IIED, will enable all three agencies to act as catalysts and convenors to bring about change in the humanitarian system, so that it is fit for purpose to respond to future urban crises. IRC’s experience in urban emergency response and advocacy is complemented by IIED’s experience in urban development, disaster risk reduction, and research. Bringing their expertise together will be key to helping bridge the humanitarian/development divide, which is a core aim of the overall programme. / Improving the humanitarian system’s response to displacement crises in urban areas requires addressing the barriers that prevent actors from being fully operationally effective in urban areas. The system would benefit from a comprehensive strategy to improve humanitarian, development and government actors’ response to urban crises, grounded in an improved evidence base and more appropriate coordination models. At an operational level there is a need for tailored tools, guidance and best practice in programming. To bring about these changes, DFID will need to engage with and leverage the influence of a range of actors, as well as draw on expertise across sectors and in research, evaluation, learning and advocacy. / An outsourced fund manager with DFID representation on a fund management board that oversees funding decisions is the preferred option, as it will allow DFID to maintain strategic oversight without the administration costs. Given the specialist nature of the fund and the desire for DFID to derive research-based outputs from it, it is appropriate that IIED is approached to manage the fund rather than opening up a costly and futile open competition process. IIED’s history of engagement on urban development and disaster risk reduction, means that they will be able to field senior staff with a technical background in areas related to urban humanitarian crises, and complement DFID’s in-house capacity.
B. Assessing the strength of the evidence base for each feasible option including delivery routes / In the table below the quality of evidence for each option is rated as either Very Strong, Strong, Medium, Limited (or No Evidence) / Option Evidence rating / 1 Strong / 2 Medium/Strong / 3 Medium/Strong / 4 Medium/Strong / There is evidence from a variety of sources on the likely increase of humanitarian crises in urban areas, and the importance of improving responses (as opposed to taking no action) as outlined in the strategic case. / For options 2, 3 and 4 the evidence relating to the ability of the IRC to deliver is the same, and is considered to be medium. The difference between the three options is the delivery route, and the quality of the evidence for all of the delivery routes is strong.
C. For each feasible option, what is the assessment of local capacity? Is the intervention likely to strengthen capacity in a durable manner? / A lack of local expertise and capacity to respond to urban crises is one of the main drivers of this programme. Component 1 would not address this capacity gap. Options 2, 3 and 4 are all likely to address this capacity gap. / Partners applying to the capability fund will be encouraged to build local capacity and do so in a way that involves collaboration with local authorities or the private sector.
D. What is the likely impact (positive and negative) on climate change and environment for each feasible option? / Categorise as A, high potential risk / opportunity; B, medium / manageable potential risk / opportunity; C, low / no risk / opportunity; or D, core contribution to a multilateral organisation. / Option Climate change and environment risks and impacts, Category (A, B, C, D) Climate change and environment opportunities, Category (A, B, C, D) / 1 C C / 2 C B / 3 C B / 4 C B / The likely impact of this action on climate change and the environment is classified as ‘low’ because this project will not fund large-scale responses to humanitarian crises, rather it focuses on the enabling environment for adequate responses to take place. This will be achieved through supporting research, evidence, developing tools, engagement with policymakers and other development actors on the urban stage. By the same measure, the likely impact of climate on this action is also low. / Given that climate change can have a major impact on preparedness and readiness in urban settings, there is an opportunity to better integrate climate risk within disaster response. Climate-related disasters, through increasing sea levels, global rainfall and storm patterns could affect 375 million people every year by 2015, up from 263 million from 2010. Current modelling forecasts a minimum increase of US$57m, and a maximum increase of US$2.7 billion in spending on climate-related disasters in certain regions[16]. / The project provides an opportunity for planners and policymakers in urban areas to better mainstream environment and climate change into their work. Potential opportunities include: / Working with mayors, local government, vulnerable people and communities to better understand the links between climate change, vulnerability, emergency preparedness, early warning, disaster risk reduction. / Improving the response from urban centres to climate-related crises and disasters by including climate and environmental elements in their modelling and forecasting. / Supporting city plans and efforts for adaptation and climate proofing, in for example minimising flood risk, enhancing storm defences and building resilience for the city’s most vulnerable people. / Improving mitigation by aligning policies with efforts to reduce emissions and creating incentives for the private sector and others to mitigate and adapt to climate risks. / Sharing lessons learnt on vulnerability, disaster risk reduction and climate change with other cities in country and the region.
E. If any, what are the likely major impacts on social development? / The programme will have a positive impact on social development, particularly with its focus on vulnerable groups and protection. One of the principal aims of the intervention is to develop tools and guidance for practitioners to improve their ability to identify and respond to the needs of the most vulnerable groups affected by urban crises. The proposed intervention draws attention to the vulnerabilities of displaced people, and will seek to find ways to ensure their needs and capabilities are recognised and supported in an urban environment. It also highlights the fact that host communities may have equal or greater needs than refugees or IDPs, but that their vulnerabilities are often overlooked by agencies that focus on the displaced. The proposed intervention will actively advocate for humanitarian agencies to give consideration to the vulnerabilities of host communities. / Advocacy work and innovative programming will also be aimed at ensuring service provision is extended to displaced people not living in camps, who often remain invisible to humanitarian agencies and to government authorities. These services will include education and healthcare, alongside WASH and shelter, and are likely to make a positive contribution to social development amongst the urban displaced. Ultimately it is hoped that local government capacity to engage with vulnerable groups will extend beyond the period of any emergency response, and have a longer-term positive impact on development outcomes.
F. For fragile and conflict affected countries, what are the likely major impacts on conflict and fragility, if any? / Experience from relief efforts in Haiti, the Syria Crisis and elsewhere would suggest that in countries affected by conflict and fragility (and especially in urban areas) delays in restoring key services, and perceived inequalities in the provision of aid, can result in civil unrest and, in turn, political instability. A key focus of the intervention is to build the evidence base to support greater collaboration and cooperation with host governments, and to bring in development actors from the early stages of an urban crisis. The aim behind the inclusion of development actors, and a stronger role for government, is to help ensure that considerations for longer-term sustainability, and future resilience, are built in to the response, with a view to speeding up recovery, and supporting a more equitable provision of services.
G. What are the costs and benefits of each feasible option? Identify the preferred option. / Strong and effective management of evidence building programmes is deemed critical in determining its impact. As there is insufficient evidence to quantify the costs and benefits of the proposed activities for this project without making arbitrary and subjective assumptions, the approach taken has been to identify and qualitatively describe the costs and benefit for the different delivery options. Where the necessary evidence for quantification is available, this is also provided. / We have not considered the option of tender process for Component 1 as the judgement has been made, and accepted by commercial advisors, that it is sufficiently distinctive that allowing others to bid for it would encroach on IRC’s intellectual property rights. / Option Benefits Costs / Option 1 Status quo There are high costs, in terms of lives lost, associated in doing nothing to improve urban humanitarian response, given the likelihood of future disasters impacting on urban areas, as set out in the strategic case. The international community will continue to provide responses that are not properly tailored to the specificity of urban crises. As noted in an ALNAP review, urban humanitarian response is a topic with ‘many unanswered questions’ where lessons are not being learned and findings are not being tested in a range of contexts.[17] There is also operational risk for DFID of not ensuring it is fit for purpose to respond to urban crises, given rapid and unplanned urban growth in developing countries, and the impacts of climate change on densely populated urban areas. / Option 2 Benefits of IRC as a strategic partner, plus the ability to maintain strategic oversight of the capability fund, and ensure tools and guidance are tailored to DFID and partners’ needs. / The preferred option of an Accountable Grant co-production arrangement will allow for DFID to benefit from the broad range of skills, expertise and networks that IRC possesses. The access that these characteristics bring will represent a multiplying effect on our investment in staff costs. DFID’s commitment of an advisor’s time to work with the IRC will ensure the partnership remains a focus within DFID, will strengthen the relationship between the two organisations and guarantee dedicated full-time DFID advisory engagement on the urban crises programme and other urban issues. / Co-production will also allow us to be flexible and better tailor the intervention to opportunities that present themselves during the period in the run-up to the Humanitarian Summit / Capability fund will generate tools, guidance and evidence products that will improve DFID partner organisation’s ability and confidence to respond in urban areas, and will increase the number of organisations DFID can work with in an urban crisis. / This option would keep the management of the capability fund in house and would allow for greater strategic oversight. Cost of IRC advocacy partnership incl dedicated DFID Urban advisor’s time and internal DFID learning £906,777. / Cost of activities financed through capability fund £ 2,591,908. / Cost of staff time in administering capability fund: / The staff time needed to manage the fund would be significant. / Year 1 / Head Humanitarian Policy Team (5%) / Humanitarian Programme Manager (20%) / Deputy Humanitarian Programme Manager (40%) / Urban Task Team Leader (50%) / Other advisory (50%) / Year 2 / Head Humanitarian Policy Team (5%) / Humanitarian Programme Manager (20%) / Deputy Humanitarian Programme Manager (40%) / Urban Task Team Leader (50%) / Other advisory (50%) / Option 3 Benefits of IRC as a strategic partner with convening power and high-level commitment to the urban agenda. / The preferred option of an Accountable Grant co-production arrangement will allow for DFID to benefit from the broad range of skills, expertise and networks that IRC possesses. The access that these characteristics bring will represent a multiplying effect on our investment in staff costs. DFID’s commitment of an advisor’s time to work with the IRC will ensure the partnership remains a focus within DFID, will strengthen the relationship between the two organisations and guarantee dedicated full-time DFID advisory engagement on the urban crises programme and other urban issues. / Co-production will also allow us to be flexible and better tailor the intervention to opportunities that present themselves during the period in the run-up to the Humanitarian Summit. / Capability fund will generate tools, guidance and evidence products that will improve DFID partner organisation’s ability and confidence to respond in urban areas, and will increase the number of organisations DFID can work with in an urban crisis. Costs of a tender process – Based on similar DFID projects the projected costs for the tender are circa £10,000 per full application. Based on an ideal scenario we would have 4 final bids = £40,000 / Cost of IRC advocacy partnership incl dedicated DFID Urban advisor’s time and internal DFID learning £906,777. / Costs of fund manager - Management costs under previous similar funds have ranged from a few percent to 40% depending on the complexity of the management task and the volume of funds to be disbursed. / The percentage cost for the fund management will directly affect the available money for activities financed through capability fund. The total available for disbursement plus management fee is £2,541,908 / Cost of DFID staff to oversee and administer the project. / Head Humanitarian Policy Group (5%) / Humanitarian Programme Manager (10%) / Deputy Humanitarian Programme Manager (20%) / Urban Task Team Leader (30%) / Other advisory (20%) / Option 4 Benefits of IRC as a strategic partner with convening power and high-level commitment to the urban agenda. / The preferred option of an Accountable Grant co-production arrangement will allow for DFID to benefit from the broad range of skills, expertise and networks that IRC possesses. The access that these characteristics bring will represent a multiplying effect on our investment in staff costs. DFID’s commitment of an advisor’s time to work with the IRC will ensure the partnership remains a focus within DFID, will strengthen the relationship between the two organisations and guarantee dedicated full-time DFID advisory engagement on the urban crises programme and other urban issues. / Co-production will also allow us to be flexible and better tailor the intervention to opportunities that present themselves during the period in the run-up to the Humanitarian Summit. / Capability fund will generate tools, guidance and evidence products that will improve DFID partner organisation’s ability and confidence to respond in urban areas, and will increase the number of organisations DFID can work with in an urban crisis. In addition, the technical input of IIED into the fund management will increase the quality and efficiency of identified projects and the dissemination of findings. Cost of IRC advocacy partnership incl dedicated DFID Urban advisor’s time and internal DFID learning £906,777 / Costs of IIED acting as fund manager - @ 5% of total fund amount = £95 000 / Money available for activities financed through capability fund = £1.9m / Costs of IIED’s additional analysis and learning inputs = £596 908 / Cost of DFID staff to oversee and administer the project. / Head Humanitarian Policy Group (5%) / Humanitarian Programme Manager (10%) / Deputy Humanitarian Programme Manager (20%) / Urban Task Team Leader (30%) / Other advisory (20%) / H. Theory of Change for Preferred Option / It is proposed that by supporting the development of tools and guidance tailored for the urban context, generating and disseminating research findings and evidence of good practice, and undertaking policy engagement with a range of stakeholders, DFID and partners will be able to promote increased acceptance and understanding that urban crises require different responses to rural ones. / This will lead to a situation where a more diverse range of actors have knowledge, skills and understanding to respond effectively to urban humanitarian crisis, and are operating in an enabling policy environment which recognises the specificity of urban crises.
[16] David D. Zhang, Peter Brecke, Harry F. Lee, Yuan-Qing He, and Jane Zhang. “Global Climate Change, War, and Population Decline in Recent Human History,” Proceedings of the National Academy of Sciences 104, no. 49 (December 4, 2007): 19214–19219.
[17] L Campbell, P Knox-Clarke and D Sanderson (2012) ‘Responding to Urban Disasters: Learning from previous relief and recovery operations’. London, ALNAP (p.1).

I. What measures can be used to monitor Value for Money for the intervention? / IRC is a pre-qualified RRF member, and has passed due diligence for this process, which included an institutional assessment of VFM. A formal due diligence assessment for IRC has also been undertaken, linked to their delivery of humanitarian assistance as part of DFID’s response to the Syria crisis. They received an Amber/Green rating and are considered to have strong internal policies and procedures to monitor and manage delivery and financial risks, most notably fraud, bribery and corruption. A detailed budget will be requested and input costs analysis will be done using this, and then tracked during implementation. / As the interventions for Component 2 are not yet known it is not possible to say exactly what measures will be used to monitor VFM at this stage. However each bid to the fund will be assessed on VFM by the IIED and internal fund management board, and those where VFM is inadequate will not be funded. In addition to this, each funded intervention will be required to include VFM indicators in the project design. IIED is currently undergoing a Due Diligence process for its main accountable grant with DFID, and this programme will comply with any recommendations for improvements that emerge from this process.
J. Summary Value for Money Statement for the preferred option / Studies have shown that there is substantial scope to improve the efficacy of urban responses. This includes, for example, ensuring that approaches and tools are properly tailored to the urban environment, providing the right expertise to support municipal or city governments, capitalising on the infrastructure, skills and markets available in urban areas and working with urban development actors to move as quickly as possible into the recovery phase, in a way that supports longer-term urban development goals. / If the project is successful there is potential that a relatively small investment of £3.5 million could have a big impact on the effectiveness of the humanitarian system in responding to urban crises. This amount is a tiny fraction of the sum spent to date in response to the earthquake that struck Port au Prince, Haiti, in 2010. As of September 2013, $3.5 billion had been raised and a further $1billion had been pledged.[18] However, the response has been widely criticised as inappropriate to the urban context of Port au Prince, badly coordinated, and undermining of national and local authorities and private sector service providers. Given the likelihood of further large urban crises occurring in coming years (with urbanisation, urban growth and climate change), an investment of £3.5 million over three years could potentially have a large impact on the efficiency, quality and relevance of urban humanitarian response by DFID and partners.
[18] http://www.reliefweb.int/rw/fts.nsf/doc105?OpenForm&rc=2&emid=EQ-2010-000009-HTI

Commercial Case

Delivery through a third party entity (multilateral organisation; civil society organisation or support to government)

A. Why is the proposed funding mechanism/form of arrangement the right one for this intervention, with this development partner? / Component 1 – Co-production with IRC / The programme will be funded through an Accountable Grant. IRC is a not-for-profit organisation registered with the charity commission. The Grant will be used to fund specific, focussed project activities, which are clearly defined in this business case. HQ Management Fees account for approximately 6.5% of the budget. / The relationship between DFID and the IRC has gradually strengthened over the past two years, and the organisation receives funding from DFID centrally, as well as from a number of country offices. IRC is a key partner in DFID’s Syria response, and is also delivering programmes on preventing and responding to violence against women and girls, and on governance, in partnership with a number of DFID country offices. / Founded in 1933, the IRC is one of the world’s leading humanitarian and post-conflict NGOs and has provided relief, rehabilitation, and reconstruction support to communities affected by conflict and natural disasters in over 40 countries. With an annual operating budget of over $390 million, the IRC promotes durable solutions by saving lives, strengthening institutions, and promoting social cohesion from the outset of crisis, laying the building blocks for long-term stability and development. / The IRC’s Research, Evaluation and Learning (REL) Unit was created in 2006 to spearhead the IRC’s design, monitoring, and evaluation systems. The unit builds evidence about what works in strategic sectors to increase the knowledge base about humanitarian programming and policy using randomised impact evaluation, and develops systems of learning to ensure that the IRC’s programmes are based on evidence from research and evaluation conducted within and outside of the organisation. / DFID will receive regular updates through the M&E processes put in place by IRC, and will specify satisfactory reporting requirements in the Accountable Grant letter. / IRC is a pre-qualified member of the DFID’s Rapid Response Facility, and have already provided accounts for last year. / Component 2 - Capability Fund / It is proposed that IIED will manage the capability fund. While IIED has a solid track record of managing similar grants, it is also excellently placed to provide technical support to grantees and to build on and disseminate information and learning arising from small projects supported by the Fund. / IIED is internationally renowned for its expertise on urban settlements and climate change and its staff members were leading and contributing authors to the chapter on urban areas in the 2014 IPCC report. IIED has a highly experienced and well-regarded team of researchers who also have considerable experience of working with local institutions and municipal governments. DFID would be able to draw on this expertise to ensure high quality proposals are selected to benefit from the fund, and that grantees are supported during the lifetime of the grant. / DFID’s overall confidence in IIED is reflected in a large Accountable Grant (£17.7m) that was agreed for four years in 2012. The grant focuses on four areas, two of which – building sustainable cities and climate change policy – are highly relevant to the urban crises programme. / The management of the capability fund will be undertaken by the Fund Manager, and will include appraisal of proposals, the review of progress reports, and checking financial request claims. The final decision on which bids are supported will be the responsibility of the Fund Management Board, on which DFID will be represented. The proposed mechanism, where IIED manage the fund and DFID sit as part of the fund management board, will allow DFID to maintain a large element of strategic control over the activities selected, ensuring that they meet DFID and partners’ needs for operational capability building, whilst also contributing to higher policy goals but without the high transaction costs of administering the fund in-house. The management board will meet as needed, but at least twice-yearly, in order to assess and make decisions around the bids presented by the Fund Manager (see the Management Case for more details). / The Fund Manager will be required to open an account solely for the capability fund. In order to keep account balances low, on a monthly basis the Fund Manager will provide DFID with a list of all claims received that month from fund recipients and a total figure for that month. This list would detail all of the actual expenditure being accounted for and the amount of advance funding requested for each on every individual programme allowing for “just in time payments”. / The Fund Manager will need to submit an assurance statement that all amounts claimed had been checked and verified by their finance team and that they were certifying the accuracy of the figures produced. They would also require fund recipients themselves to have certified the accuracy of all figures and that all advance amounts requested were appropriately justified. / DFID will review the claims list and, where satisfied that all the necessary assurances have been received, issue a payment to the project account. As part of the process we will undertake a fuller spot check of a small selection of payment requests from Fund Holders to ensure the accuracy and reliability of both the Fund Manager’s and the Fund Holder’s calculations. DFID will put in place an agreement with the contracted Fund Manager to ensure that all payments transferred by DFID into the project account are passed on to the organisations running the successful bids. The agreement with the Fund Manager will also stipulate that any interest accrued on this account will be used to offset any bank charges. Any interest over and above charges will be the property of HMT. / Reporting / Reporting and monitoring requirements will be included in the Terms of Reference. The Fund Manager will submit quarterly progress reports to DFID. This will enable DFID to make key decisions regarding the direction of the programme, to ensure efficiency levels are maintained and effective delivery against outputs achieved.
B. Is there an opportunity to negotiate on anticipated costs? / Component 1 / During the initial scoping and design phase, DFID and IRC staff will work together to produce a detailed workplan and budget for the second 24 month phase of the programme. This will be scrutinised by CHASE staff to identify possible savings. / DFID will transfer funds in tranches every quarter and will be able to assess and scrutinise expenditure in the previous quarter and make adjustments if further saving opportunities are identified. / Component 2 / The capability fund management board will review proposals to the fund and their budgets on a case by case basis and will negotiate anticipated costs accordingly.

Financial Case

A. Who are the recipients of all proposed payments? / Component 1 : IRC / Component 2: Unknown at present beyond initial payments to IIED for them to disburse. The capability fund will be open to multilaterals and NGOs who will be encouraged to partner with private sector companies, academic institutions and governments.
B. What are the costs to be incurred directly by DFID? / The maximum size of the programme is £3.5m over 3 years. This includes the necessary administration costs and will cover: / funding for co-production with IRC / costs of the DFID urban advisor ‘secondment’ to UKMis and IRC in New York / costs of internal learning and evaluation within DFID / operational costs for the Fund Manager / funding for additional analysis and learning by technical specialists in IIED / operational and evaluation costs for the individual programmes supported via the capability fund. / Staff Time per year / Head Humanitarian Policy Group (5%) / Humanitarian Programme Manager (10%) / Deputy Humanitarian Programme Manager (20%) / Urban Task Team Leader (30%) / Other advisory (20%)
C. What are the costs to be incurred by third party organisations? / N/a
D. Does the project involve financial aid to governments? If so, please define the arrangements in detail. / N/A

E. Is the required funding available through current resource allocation or via a bid from contingency? Will it be funded through capital/programme/admin? / Funding through existing resource allocation programme budget. / F. What is the profile of estimated costs? How will you work to ensure accurate forecasting?

Component 1 / Upon IRC’s written request, DFID will transfer funds in instalments based on an agreed payment schedule set out in the AG letter. Payments will be made subject to output-based reporting and to the DFID lead adviser and programme manager’s satisfaction. / Component 2 / DFID will transfer the full amount to IIED upon signing of the AG letter. They will then manage onward disbursement of the funds in instalments based on an agreed payment schedule set out in the AG letter/MOU/Contract (as appropriate). Payments will be made subject to output-based reporting to the fund manager’s satisfaction. IIED will take the agreed fund management fee from the total amount.
G. What is the assessment of financial risk and fraud? / Component 1 / In accordance with the Due Diligence methodology and assessment framework, IRC systems and processes have received an ‘Amber/Green’ rating indicating that IRC are meeting most of DFID due diligence requirements, but that there are some areas where IRC may require additional support/oversight to meet DFID standards, particularly where they are working with local delivery partners. However, due to the centralised nature of this partnership arrangement with IRC, it is unlikely the concerns highlighted will have a significant impact. / IRC are a reliable delivery partner funded by a variety of partners including OFDA, ECHO, SIDA and SDC. IRC have strong internal policies and procedures to monitor and manage due diligence with respective in-country and downstream partners to manage delivery and financial risks most notably anti-fraud, bribery and corruption. / Component 2 / Individual financial risk and fraud assessments will be built into the commissioning process overseen by the capability fund managers and each proposal for the capability fund will be considered on a case-by-case basis by the fund management board.
H. How will expenditure be monitored, reported and accounted for? / Component 1 / Monitoring and accounting of expenditure will take place according to standard DFID and IRC procedures. Invoices will be checked thoroughly to ensure VfM and compliance with the agreed budget. / IRC will request funds from DFID on a quarterly basis in arrears, providing details on the expenditure incurred in the respective quarter. At the end of every quarter, IRC will submit financial statements to DFID. The reports will lay out budgeted amount, actual expenditures, cumulative expenditure and variation, if any, from the original estimation. / IRC will submit audit reports annually. The audit reports will include information on the receipt of DFID funds, associated disbursements and unspent funds. IRC uses the UK’s National Audit Office framework of economy, efficiency, effectiveness and equity to monitor financial transactions and VFM. IRC’s current financial systems have satisfactory levels of cost control in place; its procurement processes are credible and transparent and deliver value for money through effective competition. / The Accountable Grant Agreement signed by DFID with IRC will set out the conditions for an exit strategy that DFID can employ if and when fraud is identified and if the project is found to be not achieving expected results. / Component 2 / Quarterly reports will be submitted by IIED to DFID for review, to allow key decisions to be made regarding the direction of the programme and to ensure efficiency levels are maintained and effective delivery against outputs achieved. / The management of the capability fund will be undertaken by the Fund Manager (see Management Case for more details) that will be responsible for leading the appraisal of proposals, the production of progress reports and checking and processing financial request claims. The final decision on which bids are supported will be the responsibility of the Fund Management Board. / The Fund Manager will be required to open an account solely for the capability fund. In order to keep account balances low, DFID will require, on a monthly basis, the Fund Manager to provide DFID with a list of all claims received that month from fund recipients and a total figure for that month. This list would detail all of the actual expenditure being accounted for and the amount of advance funding requested for every individual programme allowing for “just in time payments”. It will also achieve best value for money via a fund specific account through which all funds would be processed, resulting in a significant saving to DFID in transaction costs. / This list would include an assurance statement from the Fund Manager that all amounts claimed had been checked and verified by their finance team and that they were certifying the accuracy of the figures produced. They would also require fund recipients themselves to have certified the accuracy of all figures and that all advance amounts requested were appropriately justified. / DFID would review the claims list and, where satisfied that all the necessary assurances had been received, issue a payment to the project account. As part of the process we would undertake a fuller spot check of a small selection of payment requests from Approved Projects to ensure the accuracy and reliability of both the Fund Manager and the Approved Project calculations. / The agreement with the Fund Manager would also stipulate that any interest accrued on this account would be used to offset any bank charges. Any interest over and above charges would be the property of HM Treasury.
I. Are there any accounting considerations arising from the project? / N/A

Management Case

A. What are the Management Arrangements for implementing the intervention? / Component 1 – Co-production with IRC / The issue of urban displacement has been selected by senior staff in DFID and the IRC as an area for a new type of collaboration, based on ‘co-production’. Discussions with the head of profession for procurement in DFID led to an understanding that the innovative aspects of the new relationship would be focused on how the agencies work together, rather than on experimenting with new funding mechanisms. / To date, co-production has been interpreted as co-design, and has involved a series of meeting between DFID and IRC senior managers, and between technical staff from both agencies. The area of work is relatively new for both agencies, and as such it is proposed that the programme begin with a 3 month phase, during which technical staff from DFID and IRC work together to (i) examine current responses to urban crises within their own agencies, and across the humanitarian and development sectors, (ii) carry out a scoping mission to the Syria region to identify opportunities for research, M&E and learning, bringing in IRC country offices and DFID humanitarian advisers in the region (iii) agree a workplan for the following 18 months of the programme. / IRC has a full-time urban advocate based in London, who will work with CHASE’s urban specialists during the inception phase. / IRC does not currently have an urban specialist. It has a number of staff members in its New York office with some urban programming experience. These individuals are spread across a range of different thematic units. / During the partnership DFID will support two full-time equivalent positions in the IRC: an urban advocate and a learning manager. / DFID will also dedicate 60% of a DFID urban advisor’s time to work on the programme with IRC for a period of 18 months. The terms of this arrangement will be agreed through an MoU between DFID and IRC. The DFID advisor will be based in New York, to facilitate engagement with the work of IRC’s Head Office (particularly their Research, Evaluation and Learning unit), and establish close working relationships with a range of relevant actors in New York and Washington DC. The arrangement has been designed so that the advisor will continue to devote 40% of their time to working directly with DFID and will be a member of the urban task team. This will reduce the management burden for the overall advocacy and learning partnership for CHASE. At the same time, the arrangement will serve to strengthen the institutional relationship between IRC and DFID, and ensure the programme can draw on strong institutional commitment from both agencies. / This arrangement will further strengthen ‘co-production’ between the two organisations, and will help to ensure that the progress made on responding to urban crises is informed by, and helps to strengthen, DFID’s wider work on the issues of urbanisation and development. IRC’s interest in receiving this support from DFID was signalled by its President, David Miliband, in a meeting with DFID in November 2013. / Programme management from DFID will be handled by CHASE’s Humanitarian Response Group. / Component 2 - Capability Fund / The capability fund will be managed by IIED which will take primary responsibility for ensuring the aims and objectives of the programme are achieved. This organisation will provide technical and research inputs, manage the selection of beneficiaries, commission small studies, administer the scheme and ensure compliance with DFID’s financial and management requirements. / The alternative option for the management of the fund is for DFID to handle it internally which, given the number of expected projects within the fund programme is considered a cumbersome and expensive option. DFID will focus on strategic oversight and will, alongside IRC as part of component 1, ensure the capability fund interacts with other DFID and stakeholder programmes at both global and country level. However, DFID will retain a strong role in decision-making as the programme develops and will hold a key role on the fund management board. DFID will also be involved in the monitoring and evaluation process to ensure compliance with the aims and objectives of the programme as set out in this business case. / DFID CHASE / The DFID Urban Crises Task Team has the day-to-day oversight and management of the Fund Manager, and provides a secretariat function to the Fund Management Board. It is responsible for monitoring operational and financial progress, and to raise any issues that require attention to the Chair of the Fund Management Board. Programme management from DFID will be handled by CHASE’s Humanitarian Response Group. / Fund Management Board / The Fund Management Board will provide leadership of the capability fund. The Board will be responsible for receiving reports from the Fund Manager on the progress of the capability fund, and make recommendations for funding of proposals. It will meet at least six-monthly, and is likely to include the DFID urban task team leader, 1 DFID Programme Manager, 1 IIED technical specialist,1 IIED programme staff member and 1 external expert (TBC) and a representative of humanitarian/development agencies (eg BOND, Start network, CBHA). The ToRs and make-up of the Board will be decided during the inception phase. / Fund Manager / The Fund Manager’s role is to administer the capability fund by promoting and running competitive or commissioning processes, engaging with new providers, assessing applications for support against a set of criteria agreed with DFID, making recommendations to the Board for which projects to fund, and enacting Board decisions. The Fund Manager will undertake the day-to-day operation of the capability fund, working closely with the DFID CHASE Team.
B. What are the risks and how these will be managed? / Risk Mitigation / Lack of traction for change within the UN system DFID will work closely with IRC and IIED to use their networks of influence within the UN system. DFID will also engage with staff seconded into OCHA and the WHS in New York. / Lack of quality applications for funding under component 2 Work with humanitarian system and academic community to raise awareness of programme / Humanitarian space further limited in Syria region limiting scope for learning and research Identify alternative contexts which may offer opportunity for learning and research / Focus of World Humanitarian Summit drawn to other thematic areas Begin to lobby for increased focus on Urban crises from start of the programme.
C. What conditions apply (for financial aid only)? / N/a
D. How will progress and results be monitored, measured and evaluated? / Overall approach / Given the relatively low cost of the programme, its short time-frame, and its emphasis on knowledge products (rather than operational activities) CHASE’s evaluation adviser has recommended a light-touch approach to M&E for the overall programme. The focus will be on the measurement of outputs and some preliminary outcomes. / During the inception phase, DFID will work with IIED and IRC to agree a detailed theory of change and identify what evidence or indicators could demonstrate movement from the problem statement towards outcomes. Working from this theory of change, and the milestones in the logframe, the two partners will establish a monitoring strategy that they will manage over the course of the programme. The theory of change should make reference to other programmes within the humanitarian teams, particularly those supporting capacity development and preparedness. / Over the lifetime of the programme, partners will also be required to produce case study evidence, which should be systematically gathered from the outset (using a credible data collection strategy) to provide some evidence of what has been achieved, whilst recognising that a small programme will not have major systemic impact. DFID’s urban task team will produce a ‘template for this – following, for example, a modified version of the ‘impact templates’ used for the Research Excellence Framework exercise in UK academia.[19] Timings and numbers of studies will be agreed during the inception phase. / Both partners will be requested to provide quarterly narrative reports, alongside financial reporting, detailing the activities over the period, and progress towards milestones. / Monitoring and Evaluation of initiatives supported through the Capability Fund / The Fund Manager will set aside resources to support projects in their monitoring and evaluation responsibilities, and the projects themselves may require resources to collect data and report as directed. In addition to the wider lesson learning and evidence generating aspect of these activities, this is also to demonstrate results and value for money. There is an opportunity here to help fill a major knowledge gap and offer guidance to both policymakers and donors. / All bidders for funds under the capability fund will be required to propose monitoring arrangements for their intervention, proportionate to the level of funding. Recipients of larger grants (above a threshold specified by the Fund Management Board) will also need to show how they propose to monitor progress against milestones and targets in the intervention level logframe and feed into annual reviews. They will finally be required to submit end of project reviews to facilitate the project completion report. / The Fund Manager will be responsible for supporting successful bidders throughout the monitoring cycle. / The DFID Programme Manager and Urban Task Team Leader in DFID’s CHASE Department, and the fund management board, will be the primary recipient of monitoring reports and will quality assure the aggregated reports as well as add an assessment of the performance of the Fund Manager. / The evaluation role of the Urban Task Team will include: / quality assuring overall progress reports with a focus on ensuring robust tracking of performance based on agreed milestones and targets and challenging data and conclusions if necessary; / drawing out generic lessons on what works in urban humanitarian response, triangulated with other evidence, and reporting these to DFID. These lessons may be both immediate and used to inform the advocacy work undertaken within component 1; / tracking whether the results chains set out in the Theory of Change and logframe have held good and whether the Theory of Change proves to be soundly based, as well as linking evaluation back to the evidence base and challenging this and identifying additional gaps where necessary; / The evaluation role of the Fund Manager will include: / helping bidders to undertake their part in evaluation work; / advising individual implementers on what type of monitoring will be required; / working with DFID and IRC to produce and disseminate syntheses of lessons learned from the programme as a whole.
Logframe / Quest No of logframe for this intervention:
[19] http://www.ref.ac.uk/media/ref/content/background/impact/SocialWork_SocialPolicy.pdf