Programme Completion Report - Top Sheet

This Top Sheet captures the headlines on the programme performances performance over the course of its lifetime. Teams should attach summary sheets from each annual review over the life of the programme.

Review Date:	May 2015

Title: / Lablite: Moving DART (Developing Anti-Retroviral Treatment) implementation forwards into policy and practice in Africa
Programme Code: 202037	Start Date: January 2011	End Date: March 2015

Summary of Programme Performance

Year	2011	2012	2013	2014	2015
Programme Score	2	A+	A+	A+	A+
Risk Rating	High	High	High	High	High

Financial Position

Original Programme Value	£2,302,366
Extensions/ amendments	None
Log-frame revisions (with dates)	November 2014
Total programme spend	£2,302,366 (final claim awaited)

Follow up actions required following closure

Lessons learned from Lablite will be used to influence the design of future implementation health research programmes. For example the qualitative work was not part of the initial programme but was added during the mid-term review in response to feedback from stakeholders. Including a qualitative section from the onset of the project would have benefited the scope and depth of the work that was conducted through the second half of Lablite implementation.

The Lablite team are still writing up their results for publication and during the remainder of 2015 anticipate publishing a further 12 papers and one policy brief. The team will continue to engage with Ministries of Health (MoH) in the study countries and World Health Organisation (WHO) and other international organisations to input into future modelling work and the development of future clinical guidelines on the provision of HIV treatment.
A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-202037/documents/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-202037/documents/

Outline of programme and what it has achieved
Lablite was an implementation research programme, designed to demonstrate that the delivery of antiretroviral therapy using clinical monitoring, as developed in Developing Antiretroviral Therapy in Africa (DART), could be safely, equitably and cost-effectively decentralised in Africa, to lower level health centres.

One barrier to Antiretroviral Therapy (ART) roll-out in Africa is the perception that all patients on treatment need regular laboratory tests – to maximise the effectiveness of ART and minimise the potential side effects. This is a major obstacle, particularly in rural areas, because laboratory tests need substantial infrastructure (e.g. machines, electricity, reagents, supply chain), and trained personnel, which are costly to set up and then maintain. In addition, patients who have to walk many miles to access treatment would greatly benefit from decentralised long-term care provision. The results of the earlier DFID funded DART trial showed conclusively that it was safe to deliver ART with clinical monitoring, but without the need for a large number of routine toxicity tests to be carried out.

Lablite has shown that it is safe and effective to decentralise ART provision to primary care, that the implementation research approach, working very closely with MoH and other national stakeholders is an effective way to influence national policy and that the programme can be sustainably implemented. Work is still ongoing to analyse data about the costs, coverage and equity implications for decentralised ART provision.

Individual patient data have been collected, on >10,000 individuals initiating ART in secondary and primary health care facilities (7000 in Malawi, 1600 in Zimbabwe and 2000 in Uganda), including 1,000 children below 15 years. In Malawi and Uganda there were decreases in ART initiations at the district hospitals and large increases at primary care health sites, demonstrating that it is possible to reduce workloads in district hospitals. In all three countries data on roll-out of Option B+ (provision of lifelong ART to all pregnant and breastfeeding women) show that this can precipitate decentralisation. Follow-up data show inter-site variability in loss to follow-up and higher losses to follow-up among women initiating ART for Option B+, particularly during pregnancy, than among individuals initiating ART for clinical symptoms or CD4 below a threshold. An additional survey, the population survey (interviews with 2124 adults from 1351 households), conducted in Northern Uganda, showed that HIV-infected individuals travelled considerable distances to access ART services prior to decentralisation, and that children appeared to be under-accessing testing and referral for treatment. The repeat survey has been completed and data are being analysed.

This work to inform the WHO Guidelines recommended that resources should be committed to expanding ART availability, using lower cost approaches to monitoring. The 2013 WHO Guidelines made a strong recommendation in favour of routine Viral Load monitoring. However, the Lablite modelling/health economics study led to a high level of interest and; through dialogue by the team with key stakeholders (e.g. Global Fund to Fight AIDS, TB and Malaria (GFATM), WHO, UNITAID, Medicines Sans Frontiers (MSF), Clinton Health Access Initiative (CHAI) and the Bill and Melinda Gates Foundation) a greater understanding of the role of economic analysis to inform HIV policy. The paper is in the top 10 most cited papers ever in Lancet Global Health. In practice, the speed of viral load monitoring scale-up has been slow and testing costs have fallen dramatically since 2013. Practice is aligning with the study recommendations and the cost-effectiveness evidence has supported negotiations to reduce test costs (the team has been given this indication from CHAI and MSF).

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Overall Outcome Assessment:
The outputs from Lablite have successfully demonstrated that the outcome, to enable the use of effective approaches in the decentralisation of ART/HIV treatment programmes in Africa, can be achieved in the three participating countries.

Lablite has made a major contribution to the roll out of the initiation and effective management of ART. The programme has generated high quality evidence which has been taken up into policy and practice at local (lower level health centres) and national -level policy and practice in the three countries and contributed towards policy and guideline changes internationally.

Project Outcome

A+ - Outcome moderately exceeded expectations

Output Score and Description

A+ - Outputs moderately exceeded expectations

Lessons and how these have been shared

Implementation research presents a set of challenges very different from other types of research and the lessons learned in Lablite will be used to influence the design (including timings) of future implementation research findings.

The partnerships involve a far wider range of stakeholders and are likely to take longer to establish trust and confidence. The issues the partners have to negotiate are varied and include technical health issues, institutions, governance and management issues.

The research is carried out in a fast changing environment where International and National guidelines/guidance may change in a short period of time and policies evolve on the evidence generated by the programme.

Community support is essential and takes time to build up.

The team are sharing lessons learned through publication of peer reviewed and other articles, research dissemination meetings at national and international levels, participation in national and international technical expert groups and community based feedback. DFID will ensure that lessons learned are fed into the design of future implementation research programmes and bilateral health systems strengthening initiatives.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Effective Anti-Retroviral Treatment (ART) service packages tested.
Output number per LF		1	Output Score	A+
Risk:		Medium	Impact weighting (%):	50%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Targets	Progress
1.1 Baseline survey completed	Survey results analysed and reported by August 2014	Completed on time: An additional, repeat survey was carried out at demonstration project sites, to be reported by end of 2015
1.2 Training materials and tools developed and evaluated	Training rolled-out and evaluated by March 2015	Training designed and implemented ahead of target
1.3 Population survey designed and implemented	Comparative analysis by March 2015	Data collection completed and detailed analysis ongoing. Results to be reported by end of 2015
1.4 Data from demonstration sites collected and analysed	Data analysed and reported by March 2015	Data collection completed and detailed analysis ongoing. Results to be reported by end of 2015

Key Points
Lablite exceeded its objectives, and some of the indicators for this output were achieved well ahead of schedule. The training component of the programme has been an important building block in achieving the desired outcomes of the research in all three countries. The combination of effective training, mentoring on on-site supportive supervision has been important in institutionalising ART services in the demonstration sites.

In Zimbabwe the training packages and approach have been rolled out across Zvimba district. The combination of training plus mentoring and supportive supervision has clearly increased confidence levels and local problems and difficulties are quickly identified and solutions sought. In Uganda a key strength has been in working closely with the MoH AIDS Control Programme and district health administration to develop the mentorship structure and roll out the checklist. The symptom checklist, handbook and videos have been very well received by MoH and the team is currently working on accreditation of the training mode for national roll-out. In Malawi, a comprehensive training programme was rolled out around the time that Lablite started and the team concentrated on developing and strengthening the mentorship programme, and developing the video case-studies for use in this programme. The team is working with MoH to validate the case-studies for wider roll-out.

Summary of responses to issues raised in previous annual reviews (where relevant)
It was clear during the review visit in Malawi and Zimbabwe that the inclusion of a strong programme of mentoring and supportive supervision has been vital to ensure that the provision of training was effective.

The Lablite team have had interactions with number of multilateral and international organisations, including GFATM, particularly around resourcing issues for ART monitoring and economic evaluation approaches. The team will discuss this further and are currently considering timing for a meeting in Geneva, given that the main demonstration project data are still undergoing analysis.

Recommendations for future programmes
Programmes should have some outcome measure for training provided, and not rely on numbers trained. Programmes should continue for sufficient time to enable longer-term outcomes of training, mentoring and supportive supervision to be assessed.

Output Title	Economic and qualitative results contribute to knowledge and inform debate around design of services
Output number per LF		2	Output Score	A
Risk:		Medium	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Targets	Progress
2.1 Qualitative study informs debate around design of services	Study findings reported and disseminated to national stakeholders by March 2015	Completed: Data collection completed and paper drafted. Expecting to report by the end of 2015. Social science component was completed ahead of target
2.2 Equity study adds to existing information on the socio-economic aspects of decentralisation	Study findings reported by March 2015	Data collection completed and detailed analysis ongoing. Will report by end of 2015
2.3 Young lives methods developed to estimate quality of life among young people in Africa	Analysis and reporting by March 2015	Data collection completed and additional detailed analysis ongoing. Will report by end of 2015
2.4 Informal care and productivity costing techniques developed and applied in study countries	Study findings reported by March 2015	Data collection completed and detailed analysis ongoing. Will report by end of 2015
2.5 Effectiveness and cost-effectiveness modelling studies inform debates around national and international policy in HIV	Build collaborative relationships with key contributors to the debate around HIV policy which will last beyond the life of Lablite by March 2015	Important findings emerging which are already influencing policy recommendations. The team have been invited to join international debates (WHO and other organisations) on HIV policy. Strong links with MoH, WHO and GFATM which will last beyond programme.

Key Points
Lablite has achieved this objective, through a number of different qualitative and economic studies. Some results have been disseminated to national stakeholders in all three countries and Internationally. The team have used a number of innovative dissemination methods, including the use of three graphic novels to engage younger people, and their carers/guardians, in recognising the issues and supporting younger people growing up with HIV. The programme has provided evidence of issues to consider when rolling out the decentralisation of HIV services, taking into account the impact on the patients and health care workers, and ways to avoid stretching the existing workforce with the expectation that lower cadres of workforce will continue acquiring supplementary responsibilities. In addition the ground breaking work on methodological challenges in measuring health related quality of life in children in low-income countries has led to work on developing a new tool, which has the potential for widespread use in low income settings.

The combination of decentralisation with work on informal care and productivity costings is potentially ground breaking and the economic analyses are much needed by the Governments of each of the countries to aid decision making around decentralisation of services.

Recommendations for future programmes
- Partners should ensure sufficient in-house capacity to cover the range of research skills required for implementation research, including social science and health economics. Feedback from field visits indicates that in-house expertise is likely to have a greater influence on other research programmes across the board, not just implementation research.
- The economic and social science work should be closely integrated with the service delivery to ensure that scale-up happens in effective ways. There are assumptions that integration will increase workloads, but there is some preliminary evidence from Lablite that clinic workloads could reduce with more efficient ART services.

Output Title	Build the capacity of African researchers to carry out research in Africa, participating in all steps including presentation of results and written outputs
Output number per LF		3	Output Score	A
Risk:		Medium	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
3.1 The number of new and existing African researchers working on the programme. Capacity building of African researchers to carry out research in Africa.	African Lablite researchers are authors on Lablite publications	Achieved: current plans mean all African researchers working in programme (not including PI’s) will have lead authorship on at least one paper / Project Coordinators: 2 x male; 1 x female / Health Economists: 2 x male 1x female / Statisticians: 2 x female / Training Coordinators: 2 x male

Key Points
This output has been achieved. In Zimbabwe there is an impressive cadre of local researchers and a strategy to build the research leaders for the future. In Malawi there is a strong group of local researchers who have significant capacity for future research leadership roles. In Uganda the team has built on relationships with existing research partners and enabled their diversification into implementation and health services research. In particular the project has supported social science and health economics capacity building across all three countries. Lablite has been successful in generating South-South collaboration and learning between the participating countries. Annual meetings have deliberately included site visits and formal and informal learning opportunities.

All of the African researchers have had the opportunity to take lead authorship on one or more papers, and present their data nationally and internationally. Most of the planned papers will have a predominantly African authorship.

The programme has built capacity amongst clinical practitioners in all three countries through training and mentorship, and though other courses. Lablite has developed training and mentoring programmes and materials for primary healthcare workers delivering decentralized care for HIV in rural communities, including innovative video case-studies for use in mentoring and refresher training. These now in the process of being adopted for national training programmes in Malawi, Uganda and Zimbabwe. An element of the development of the video case-studies was training local individuals to film, script and edit the videos. This also builds the capacity of the research partners in Africa to communicate health messages.

Recommendations for future programmes
For implementation research there is a need for a critical mass of competent researchers across a range of disciplines, so building sustained capacity of local researchers is absolutely vital. In addition to technical research skills they require high level interpersonal, management and negotiation skills and the ability to communicate complex information to non-specialist audiences.

Output Title	Communication of new knowledge and data to relevant stakeholders, planners and policy makers.
Output number per LF		4	Output Score	A+
Risk:		High	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Targets	Progress
4.1 Number of a) papers b) policy briefs c)other publications produced	12 x papers / 4 x policy briefs / 3 x other publications / By March 2015	On track: 6 papers published, 1 submitted, 7 in development, 5 papers expected in 2015 / 3 policy briefs published, 1 in development / 14 associated other publications and 2 in development, 3 baseline reports published, 3 graphic novels
4.2 Policy Analysis study informs debates around policy and guidelines processes nationally and internationally	Policy analysis study reported by March 2015	Achieved: Data collected and initial results available and, disseminated nationally.
4.3 Lablite results feed into and encourage dialogue, internationally around decentralisation of ART and implementation of new WHO guidelines	Relationships built with key international stakeholders which will last beyond the life of Lablite by March 2015	Achieved well ahead of schedule: e.g. Lablite staff were involved in the HIV Modelling Consortium, carrying out modelling work commissioned by WHO to inform the guidelines
4.4 Local researchers and wider Lablite team engage with policy makers and influencers	Relationships built with key national stakeholders and policy makers which will last beyond the life of Lablite by March 2015	Achieved well ahead of schedule: Teams in all three countries have been involved with a range of different national policy makers.

Key Points
Expectations exceeded for this output. The team have a high standing internationally and have successfully communicated the results and lessons learned in a range of situations. Training packages and methodologies have been integrated within respective MoH programmes in all three countries. The University of Zimbabwe team negotiated changes to the standard operating procedures to enable nurse-led ART roll out and initiation and Lablite researchers are discussing the shortage of ART supplies in certain (remote) locations (currently managed by reducing the amount of drugs being given to each patient with time and other opportunity costs to the patient). In Malawi the team have been instrumental in training additional personal, to maintain a critical mass, within a high staff-turnover environment and advised MoH about possible changes to the ART regimen. In Uganda, close collaboration with MoH and training providers resulted in the development of training materials and processes to challenge the status quo, e.g. bringing training to the workplace reduces time away from clinic and resulting pressure on the rest of the teams and reduces the need for per-diem payments, a costly part of the training culture.

Summary of responses to issues raised in previous annual reviews (where relevant)
The results of the research will continue to be disseminated after the end of the programme, including at a number of International and National conferences. There are plans for a number of country-based dissemination and debriefing events. In-country teams will continue to be involved in Lablite-related activities, with MoH, and issues that the project raises, e.g. the ongoing training and decentralisation activities.

Recommendations for future programmes
The combination of robust methodologies and strong partnerships within an implementation research programme, has the potential to help address sensitive issues around health systems strengthening and service delivery, including management of procurement, staffing and absenteeism, training, arrangements for clinic layout patient confidentiality and efficiency of use of staff time and accountability to local communities.
## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
The key cost drivers are staff and staff-related costs and transportation. Other costs drivers are incidental costs for surveys, data collection, monitoring and training and supervision costs.

Exchange rate fluctuations were an important risk factor which were carefully managed during the programme.

The overall costs of the programme were very competitive because participation of Ministry of Health staff in each country were covered by the individual countries. To increase the likelihood of sustaining the interventions after external funding, the programme was deliberately designed so that each participating site had to operate within existing recurrent and staffing budgets.

VfM performance compared to the original VfM proposition in the business case

The programme has performed well. It was designed to improve value for money for the delivery of ART, increasing the number of patients treated for the same finite amount of money. The results of DART suggest up to 33% more people can be treated safely and effectively using the same funding envelope, if expensive and potentially unnecessary laboratory costs are removed.

The focus was on the economic and practical difficulties experienced by patients seeking to access HIV care. The work included studies with a focus on equity in Malawi, Zimbabwe, Central and Northern Uganda.

Assessment of whether the programme represented value for money

The programme represented value for money. It was designed to improve value for money for the delivery of ART, increasing the number of patients treated for the same finite amount of money. The programme has successfully decentralised ART initiation and treatment in the demonstration sites in all three countries. As is usual for research programmes, it will be some time before all of the data are analysed and reported and final results available.

Quality of financial management during programme
There were some delays with the invoicing at the start of the programme. This improved when the MRC CTU moved to University College London. The programme has carefully monitored cost-efficiency through close working between the programme administration, the university finance office and responsible staff in each of the three countries. Forecasting was accurate and the programme completed spending on track, by March 2015.

The programme came to an end in March 2015. The original agreement (with another UK Government Department) did not include an audit requirement. The current agreement requires final audited accounts by 31st July 2015.

Date of last narrative financial report	September 2014
Date of last audited annual statement	July 2015 (expected)

E: RISK (½ page)

Quality of risk management over the life of the programme

The team have monitored and managed risk effectively.

The programme has been high risk throughout, because of the innovative nature of the research. The teams worked together flexibly, to ensure that robust methodologies were used, combined with strong local partnerships to overcome the inevitable implementation blockages. External risks included the major challenges in the dissemination and uptake of the findings, the political changes in each of the countries and the continuing Global financial crisis and the effect that this has had on funding for ART provision.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

Lablite made good progress against the planned timeframe. They have produced high quality research results and have moderately exceeded expectations about the outcome of the programme. The workplan was ambitious and the teams have worked hard to achieve outputs over the time period. With the benefit of hindsight, an inception phase of one year, would have been appropriate for this innovative approach, to enable in country teams to negotiate the necessary policy changes in ART roll out in advance of implementation.

Performance of partnership (s)
This has been a significant strength of the Lablite programme, the country teams have worked well together and individually in each country have developed strong partnerships with MoH and other key stakeholders. As a result it has been possible to overcome implementation blockages that could have caused significant delays. In addition the Lablite in country teams are receiving requests from their respective Governments, to assist in the roll out of training for ART initiation at other sites.

Asset disposal and value obtained by DFID
There are no assets over £1000 to be disposed of, the majority of funding was for staff time and training activities.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
The international context for ART roll out has changed significantly over the period of the programme and particularly since UNAIDS announced its 90:90:90 strategy (90% of HIV positive people know their status, 90% of these are effectively treated on ART and 90% of these have adequate viral suppression). These targets are extremely ambitious and challenging for all countries. If adopted, the Lablite approach has the potential to be very influential but it will take time and considerable effort to persuade international agencies and Governments to adopt these effective low-cost approaches.

There is an early indication that low cost viral load testing may become available for use in low-resource settings in the medium term. If combined with the Lablite approach, this could make a major contribution to achieving the 90:90:90 targets.

Monitoring progress throughout the programme
Members of the Human Development team in Research and Evidence Division attended two Lablite partner meetings, in London and Uganda. In addition team members met with a number of the partners to discuss progress, financial, asset and risk management and annual meetings with Medical Research Council Clinical Trials Unit staff during the lifetime of the programme. In April 2015 two staff conducted a programme completion review including seven peripheral site visits in Malawi and Zimbabwe and final progress meetings with senior managers in Zomba, Harare and London.