Annual Review - Summary Sheet

Title: United Nations Relief and Works Agency (UNRWA): funding basic services and protection for Palestine refugees
Programme Value: Up to £137.5m. £107m was disbursed in 2011-15; up to £30m is allocated for 2015/16, with half linked to progress on results, and up to £0.5m for technical assistance.		Review Date: 29 May 2015
Programme Code: GB-1-202885	Start Date: March 2012	End Date: 31 March 2016

Summary of Programme Performance
Year	2012/13	2013/14	2014/15
Programme Score	A	A	A
Risk Rating	Medium	Medium	Medium/High

Summary of progress and lessons learnt since last review

This Annual Review covers the period from 1 April 2014 to 31 March 2015. It mainly draws on data for the calendar year of 2014 reported in UNRWA’s 2015 Harmonised Results Report.

During this period, UNRWA has continued to deliver assistance to a growing population of Palestinian refugees, despite facing some of its toughest challenges to date. While UNRWA has made progress on key human development indicators, the ongoing civil war in Syria and the latest outbreak of conflict in Gaza have enhanced poverty and vulnerability among parts of the population. UNRWA personnel have also been affected, with fourteen killed in Syria and eleven killed in Gaza in 2014. Ongoing issues such as movement and access restrictions in Gaza and the West Bank, forcible transfer from the West Bank and restrictions on Palestinians’ rights in Lebanon have raised protection concerns and caused continued dependency on UNRWA. While UNRWA is receiving a higher amount of donor funding than ever, the Agency is operating with a structural budget deficit: there is a projected General Fund shortfall of $107m in 2015. UNRWA’s Emergency Appeals are regularly under-funded and, despite austerity measures, the Agency still relies on exceptional end of year contributions from donors, and the deferral of payments to creditors, in order to pay salaries in the final quarter of each year. UNRWA’s Medium Term Strategy was endorsed at the November 2014 Advisory Commission meeting, however challenges remain for 2015.

UNRWA has made progress on a number of performance indicators since the 2014 Annual Review, including: percentage of children identified as having special needs; number of medical consultations; diabetic control rate; percentage of children aged under 18 months who have been vaccinated; number of Palestinians refugees receiving social transfers; and the percentage of new inscriptions meeting UNRWA standards. UNRWA’s progress, however, has been hindered in several areas including: number of students completing vocational training, percentage of schools using the Education Management Information System, and number of women attending at least 4 ante-natal care visits.

A key lesson learnt since last year’s annual review is that some of the indicators in the logframe are problematic and need revising. The details of which indicators require changing are in the detailed output scoring sections. At a higher level, another lesson from 2014 is the continued need to engage with UNRWA on their chronic financial deficit, with 2015 looking to be their most challenging year yet financially.

DFID’s business case for support to UNRWA was extended by one year in March 2014 as per the previous Annual Review’s recommendation, and updates were made to targets and indicators accordingly. Ahead of the next business case, DFID will work with UNRWA to develop a new Logical Framework (log frame), working closely with UNRWA and other donors to agree harmonised new targets and indicators that reflect the complex political and insecure context in which UNRWA operates and the reform measures required.

Summary of recommendations for the next year

DFID should:

- Work closely with UNRWA and the donor Harmonised Results Working Group to agree a new set of targets and indicators for 2016 onwards.
- Support UNRWA further to harmonise and streamline reporting to maximise efficiencies for both UNRWA and donors.
- Encourage UNRWA to strengthen their Department for Internal Oversight and to continue working on their risk management systems.
- Engage with UNRWA on reform and addressing their chronic financial deficit by facilitating the implementation of the Medium Term Strategy and providing technical assistance.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-202885/documents/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-202885/documents/

UNRWA provides protection and assistance for some five million Palestinian refugees in five fields of operation (the West Bank, Gaza, Jordan, Lebanon and Syria) pending a political resolution to the refugee issue as part of the Middle East Peace Process (MEPP). UNRWA implements services directly with a workforce of 30,000 staff and spends 57% of its budget on education, 18% on health, 13% on support services, 10% on relief and social services and 2% on infrastructure and camp improvement.[1]
[1] http://www.unrwa.org/how-you-can-help/how-we-spend-funds

DFID is a the third largest donor to UNRWA’s General Fund and during the reporting period the 2011-15 business case was extended until 31 March 2016. The key results to which DFID has contributed in 2014/15 are as follows:

- Results funding: 488,584 children provided with education; 70,924 pregnant women attending four ante-natal appointments; 299,038 individuals supported by cash-transfers;[2] and
  [2] These are total UNRWA results, rather than DFID attributions. DFID’s attribution for the General Fund in 2014 was 9.89%. Attributed figures for 2014/15 would be as follows: 48,320 children provided with education; 7,014 women attending at least four ante-natal appointments; and 29,574 individuals supported by cash transfers.
- Policy leverage: DFID has engaged closely with UNRWA on the development of their Medium Term Strategy for 2016-21, reforms to enhance efficiency, improvements to internal oversight and measures to address the Agency’s financial problems.

UNRWA works in a challenging and highly sensitive political environment. During 2014 particular challenges included the conflict in Gaza in July and August and the protracted crisis in Syria, which has also affected UNRWA’s operations in Jordan and Lebanon. Fourteen UNRWA staff were killed in Syria and eleven UNRWA personnel lost their lives in Gaza. In Gaza, the Agency had to shelter an unprecedented number of displaced people (approximately 300,000) in its schools. There were incidents in which UNRWA shelters were hit by the Israeli forces, causing loss of life, and separate incidents in which Palestinian militant groups hid weapons inside empty UNRWA schools. UNRWA launched a Flash Appeal to respond to increased needs in Gaza and continued to appeal for funds for the Syria appeal. The UK contributed £9m to UNRWA’s Gaza Flash Appeal in 2014/15 in addition to our ongoing project support, alongside £12.5m for the Syria emergency appeal. These contributions have been managed under separate business cases, however, and are not the focus of this Annual Review.[3]
[3] DFID contribution to UNRWA Gaza Flash Appeal at http://devtracker.dfid.gov.uk/projects/GB-1-204841/ ; project support to UNRWA Jobs Creation Programme in Gaza at http://devtracker.dfid.gov.uk/projects/GB-1-202375/ ; Syria response at http://devtracker.dfid.gov.uk/projects/GB-1-203216/

Although the West Bank is often perceived as one of the more stable of UNRWA’s operating environments, Palestinian refugees have continued to face protection challenges in the West Bank including demolitions, displacements and forcible transfer. Palestinian refugees in Lebanon have remained highly dependent on UNRWA due to their lack of rights, and Palestinian refugees from Syria attempting to flee into Lebanon and Jordan have been prevented from doing so since both countries closed their borders to Palestinian refugees in 2013/14.

Despite constructive dialogue with donors and host countries about reform and resource mobilisation, UNRWA’s financial challenges remained severe during the reporting period with a forecast end of year deficit for the General Fund in 2015 of $107m. UNRWA’s Emergency Appeals are also regularly under-funded (UNRWA has received pledges amounting to $175m from its $720m appeal for Gaza reconstruction, and the 2014 $417m appeal for Syria was only 50% funded). While UNRWA has implemented austerity measures (including limitations on recruitment, travel expenses, training, drawing down reserve, and not spending money on capital investments), the Agency still relies on exceptional end of year contributions from donors, and the deferral of payments to creditors, in order to pay salaries in the final quarter of each year. At UNRWA’s request, DFID brought forward half of the payment scheduled for November 2014 to September 2014 in order to address urgent cash flow problems. Given the breakdown in the latest round of peace talks in April 2014 and the growing Palestinian refugee population, continued conversations about UNRWA’s financial sustainability will be critical.
## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

The outcome statement from the UNRWA/DFID log frame is: “Basic services are sustainably provided and human rights are protected for Palestine refugees.” DFID’s assessment is that UNRWA has performed slightly below the expected milestones but that UNRWA has continued to make progress against most outcome indicators despite the increasingly difficult operating environment:

#	Indicator	Milestones 2014 (Jan to Dec)	Actual	Comment
1	Percentage of children under 5 years who are underweight (new cases).	Males 1% Female 1%[4]	1.6%	Indicator has been changed from children under 3 to children under 5 to align with international standards.
2	REFORM: Mean score obtained by students in Monitoring Learning Achievement Scores in Arabic and Maths (sex-disaggregated)	Data collected biannually	Data collected Biannually	No data was due to be collected in 2014.
3	Percentage of graduates employed or continuing their studies among active job seekers (female)	75% (68%)	72.3% male (60.6% female)	Employment rates for UNRWA TVET graduates have decreased at the Agency-wide level. The Agency-wide employment rate was 75% female for 2012 graduates, which decreased to 60.61% for 2013 graduates. For male 2012 graduates, the employment rate was 78%, which fell to 72.29% for 2013 graduates. The sharp decline in employment rates is an expected and understandable trend. The unstable situation and mobility restrictions in the West Bank have had a negative impact on the graduate employment rate for females. Political, social and economic constraints and instability in Gaza have also had a major impact.
4	Survival rate to the end of basic education male (female)	91.8% (95.5%) / (school year 2013/14)	90.9% (94.59) (school year 2013/14)	Pupil survival rates to Grade 9 Agency-wide slightly decreased for boys down 1.5% and for girls down 0.4%, but are higher than before the reform. The impact of Gaza data on the Agency-wide reporting needs to be noted, as it accounts for 48% of the data.
5	REFORM: Average daily medical consultations per doctor (across all services).	93	95.8	Despite variations throughout the fields, the Agency-wide average number of consultations per day has declined by 9% since 2013. A more modest target for Syria will be set in 2015, with the understanding that the data collected may not be completely accurate. The ongoing conflict affects patient behaviours, but perhaps more importantly, data collection is not totally accurate given the circumstances. A priority for the UNRWA Syria Field Office in 2015 is to improve the accuracy of data collection.
[4] Milestone reflects previous indicator of “percentage of children under 3 who are underweight”. UNRWA now reports on the percentage of children under 5 who are underweight so as to align with international standards.

Overall output score and description

The programme has scored an A overall.

	Output	Score
1	Provide high quality educational services	A
2	Provide high quality health services	A
3	Protect the vulnerable	A+
4	Ensure protection of human rights	A

Key lessons

DFID will continue to engage with UNRWA on the Agency’s ongoing financial crisis and the challenges of its operational context. DFID will work with UNRWA to establish a better risk management system and to strengthen UNRWA’s Department for Internal Oversight Services. A key lesson in 2014 has been the difficulties UNRWA has had in making progress on evaluations so further support will be provided to help UNRWA improve the quality of its evaluations overall as well as to fund evaluations of specific activities. DFID will also second a Social Development Adviser to help support the Agency’s reform process. 2014 has demonstrated that emergencies will continue to be a feature of UNRWA’s work so DFID will need to consider how best we can structure our multiyear business case to ensure we have the flexibility required to respond. We must also consider how to further streamline reporting and change indicators where they have proven to be problematic in the past, working with UNRWA to ensure targets are accurate and that our logframe reflects those targets accordingly.

Key actions

DFID should:

- Work closely with UNRWA and the donor Harmonised Results Working Group to agree a new set of targets and indicators for 2016 onwards.
- Support UNRWA further to harmonise and streamline reporting to maximise efficiencies for both UNRWA and donors.
- Encourage UNRWA to strengthen their Department for Internal Oversight and to continue working on their risk management systems.
- Engage with UNRWA on reform and addressing their chronic financial deficit by facilitating the implementation of the Medium Term Strategy and providing technical assistance.

Has the logframe been updated since the last review?

Yes. Output indicator 3.2 has been changed to be “Percentage of SSNP individuals who are abject poor” (see explanation in detailed output scoring section below) and the target for 2014 has been amended accordingly. A new logframe will be developed for the new multiyear business case for support from 2016, aligned with UNRWA’s new Common Monitoring Matrix and Medium Term Strategy for 2016-21.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Provide high quality educational services
Output number per LF		1	Output Score	A
Risk:		Medium	Impact weighting (%):	50%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
1.1 Number of children enrolled in UNRWA basic education schools (% girls)	491,641 (50% girls)	488,584 (49.8% girls) / Jordan - 118,546 / Lebanon - 33,257 / West Bank - 50,566 / Gaza - 240,413 / Syria - approx. 45,802
1.2 Percentage of all children identified as having disabilities (or Special Educational Needs)	1.5%	3.62%
1.3 Number of students completing vocational training courses (of which women)	3,458 (1,419 female)	3,316 (1,438 female)
1.4 REFORM: Pupil teacher ratio/class sizes in basic education	Gaza 38 Jordan 37 Lebanon 34 Syria 38.7 West Bank 35	Gaza 38 / Jordan 35 / Lebanon 31 / Syria 30 / West Bank 38
1.5 REFORM: Number of areas where all teachers have been trained through UNRWA school-based teacher development programme	14	15
1.6 REFORM: Percentage of schools using the school-based agency-wide Education Management Information System (EMIS) to report and plan	80%	0%

Key Points

Indicator 1.1: The number of students enrolled this year is slightly lower than the previous year, particularly in Syria where enrolment has dropped from 67,292 to 45,802. The security situation in Syria affected both children’s ability to enrol and attend school, and UNRWA’s ability to report data.

Indicator 1.2: This target has been exceeded, even though (as a relatively new indicator) the identification of disability is expected to increase gradually as teachers’ understanding of the issue is enhanced.

Indicator 1.3: The number of students completing vocational training is marginally lower than last year, however the number of women completing is higher.

Indicator 1.4: The average class sizes for all fields, except the West Bank, are lower than their targets and have therefore the target has been surpassed. The average class size in the West Bank has increased from 35 to 38, however classes in Jordan, Lebanon and Syria have decreased in size thus making this indicator exceed its target.

Indicator 1.5: The areas in each Field Office are now numbered and grouped differently than how they had been in the previous annual reviews. The total number of areas now stands at 22 and due to this restructuring the result for Academic year 2013/14 is actually 6 areas, and this has been altered in the logframe. Currently, in 2014-2015, 5676 teachers from 15 targeted areas are undergoing training and graduation will take place in June 2015, exceeding the target of 14 areas.

Indicator 1.6: As part of its education reform, UNRWA had set a target of 80% of schools using the school-based agency-wide EMIS by this year, however this has not been achieved. UNRWA has explained that the responsibility for the development and implementation of EMIS had been placed under a project manager in Gaza and the conflict led to that work being stalled. UNRWA will now be piloting the Agency-wide EMIS in Gaza in July 2015 and the system will be rolled out to the remaining fields in January 2016. Agreement to extend the timeline of this implementation was agreed with another bilateral donor funding it.

Summary of responses to issues raised in previous annual reviews (where relevant)

As per the recommendation in last year’s Annual Review, we have linked half of our 2015-16 funding (£15m) to results and reform, and are providing up to £0.5m for technical assistance to help drive forward reforms and address issues in UNRWA’s internal oversight.

Recommendations

DFID will:

(a) Encourage UNRWA to implement EMIS and revise the target for 2015 to reflect the challenges of the operational environment.

(b) Continue to support UNRWA to pursue reforms of TVET to enable it to become more sustainable, to have a better and more measurable impact on refugee employment and livelihoods, and to include more women and vulnerable refugees.

(c) Revise numerical targets for enrolment and vocational training in 2015/16 to maintain current achievement levels, taking account of the impact of the ongoing Syria crisis on service delivery.

Output Title	Provide high quality health services
Output number per LF		2	Output Score	A
Risk:		Low	Impact weighting (%):	25%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
2.1 Annual number of medical consultation	9,371,426	9,457,155 / Jordan - 1.72m / Lebanon - 1.3 m (262k PRS) / Syria - 9.83 m / West Bank - 1.3 m / Gaza - 4.2 m
2.2 Diabetic control rate (of which women)	32%	45.6%
2.3 Number/percentage of pregnant women attending at least 4 ante-natal care (ANC) visits	75,492 (90%)	70,870 (86.8%) / Jordan – 20,297 / Lebanon – 4,051 / West Bank – 34,789 / Gaza – 10,417 / Syria - 1,316
2.4 Percentage of children under 18 months who have received all EPI (Expanded Programme on Immunization) vaccinations according to host country requirements	99%	99.30%
2.5 REFORM: Number of clinics implementing the Family Health Team (FHT) approach (out of a total of 137 clinics)	100	99

Key Points

Indicator 2.1: The target medical consultations across the fields has been exceeded. UNRWA anticipates an increase in medical consultations each year due to population growth, but the Family Health Team (FHT) approach is designed to reduce the number of consultations required and improve data collection.

Indicator 2.2: The target for percentage of patients with controlled diabetes out of all diagnosed patients was exceeded. While the control rate is satisfactory, concerns relating to the continued presence of behavioural risk factors remain, which UNRWA is addressing by continued outreach and screening.

Indicator 2.3: There was a slight under-achievement in the number and percentage of pregnant women attending at least 4 ante-natal care visits. UNRWA is working to target the 10-15% of women who do not attend the minimum required and to understand their reasons, including whether they are receiving antenatal care elsewhere. UNRWA is developing a survey tool.

Indicator 2.4: The target for percentage of children under 18 months who have received all EPI vaccinations has been met. 2014 results continue to be satisfactory in West Bank (2,354 of 2,397), Gaza (3,048 of 3,064), Lebanon (374 of 376) and Jordan (2,354 of 2,397), though additional efforts in 2015 will focus on identifying the defaulters in each field.

Indicator 2.5: The result for clinics implementing the FHT approach met expectations. 99 of 115 UNRWA health centres (excluding Syria) have successfully implemented the FHT reform. FHT has been delayed in Syria due to the on-going conflict, but the transition is 86% complete. All 115 centres are on track to be implementing the health reform before the end of 2015. Douse

Summary of responses to issues raised in previous annual reviews (where relevant)

The 2014 Annual Review recommended reducing DFID’s 2015 target for ante-natal care visits from 95% to 90%, to bring it closer to UNRWA’s already-surpassed target while encouraging continued progress. This target was revised accordingly, however the target has been missed (86.8%) and the results showed a slight decrease from 2014 (88.8% / 74,486). As noted above, UNRWA will intensify its surveying and education outreach to address this.

Regarding issues with data collection in Syria, in early 2015, a task force visited each health center and health point to ensure proper data collection techniques were being implemented. These supervisory visits will continue. Since the start of the conflict in Syria, UNRWA’s focus has been on providing care, but this year, a refinement and emphasis is being put on proper data collection. However, it will likely continue to be less than 100% accurate, since the implementation of electronic records in Syria is still not feasible, due to security and logistics concerns.

Recommendations

DFID will:

(a) Encourage UNRWA to improve data collection capacity in Syria.

(b) Assess in the business case for support for UNRWA beyond 2016 whether additional support to health reforms at an operational level would be helpful, and if so, in which sectors. Consider whether earmarking of funds would be appropriate.

Output Title	Protect the vulnerable
Output number per LF		3	Output Score	A+
Risk:		Low	Impact weighting (%):	15%
Risk revised since last AR?		Yes – reduced from Medium	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
3.1 Annual number of Palestinian refugees receiving social transfers (food or cash) from UNRWA	291,757	299,038 / Jordan – 59,094 / Lebanon – 61,938 / West Bank – 36,156 / Gaza – 106,667 / Syria - 34,766
3.2 REFORM: Percentage of SSNP individuals who are abject poor.[5]	45.5%	55.30%
[5] Abject poverty is operationally defined by UNRWA as the minimum monetary cost of food, which satisfies the average nutritional needs in terms of daily required calories. In Lebanon Field, the term ‘extreme poor’ is used in lieu of ‘abject poor’.

Key Points

Indicator 3.1: The number of beneficiaries in UNRWA’s Social Safety Net Programme (SSNP) has been capped since 2013 but has been slightly increased in 2014 following contributions from donors in 2014. The SSNP is mainly funded through the General Fund with additional project funding from several donors. The SSNP served an average of 289,215 individuals each quarter in 2014: the level of need is greater than this but it is met via other funding streams. In 2013, UNRWA provided social transfers to 1,031,869 refugees through its Emergency Appeal, separate to the General Fund.

Indicator 3.2: In the 2012 report this indicator was changed to be “percentage of refugees identified (or estimated) to be poor who receive a social transfer. However, following consultations with donors, UNRWA have reverted to reporting on percentage of SSNP individuals who are abject poor. The donor Harmonised Results Working Group agreed that this indicator better demonstrates how well UNRWA targets the poorest and how many abject poor people are receiving assistance. We have therefore adjusted our log frame to reflect this change in reporting, and have used the 2015 target provided by UNRWA to be the milestone for this year. With these changes in mind, UNRWA have exceeded the target for this year. UNRWA monitors the value of social transfers provided through the SSNP (food and cash) on a quarterly basis based on the local market. This figure is compared to the abject poverty line, resulting in a percentage that reflects, on average, how far the social transfer went to covering families’ basic food consumption needs. The values below are for the last quarter of 2014:

Gaza: US$162/US$559 = 28.8%
West Bank: US$212/US$654 = 32.4%
Jordan: US$158/US$635 = 25.4%
Lebanon: US$148/US$909 = 16.3%
Not relevant to Syria given the crisis as they provide blanket coverage.

Summary of responses to issues raised in previous annual reviews (where relevant)

DFID has encouraged UNRWA to underpin the Medium Term Strategy for 2016-21 with a strong strategy to address poverty by helping to break the transmission of poverty from one generation to another.

Recommendations

DFID will:

(a) Work with UNRWA to determine whether the number of social transfers is the most relevant indicator to capture UNRWA’s protection / vulnerability work, given only a small proportion (299k out of 1.3m) of social transfers are covered by the General Fund.

(b) Encourage UNRWA to revise targets for 2015 for reform indicator 3.2 to reflect UNRWA’s quick pace of progress.

Output Title	Ensure protection of human rights
Output number per LF		4	Output Score	A
Risk:		Low	Impact weighting (%):	10%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
4.1 Percentage of new inscriptions meeting UNRWA standards	99%	90%
4.2 Percentage of education staff who successfully complete the Human Rights and Conflict Resolution training programme (of which women)	60%	76%
4.3 Number of gender-based violence (GBV) survivors detected	2,360	2,359

Key Points

Indicator 4.1: Three out of the five fields achieved their target, however the Syria Field Office was especially unable to reach its target due to the impact of the crisis, which prevents Palestinian refugees from obtaining the proper documentation and makes it difficult for them to reach UNRWA registration centres. The West Bank Field Office also narrowly missed its target. On balance DFID judges that UNRWA met expectations for this indicator in this context.

Indicator 4.2: 76% of education staff (17,884 people) completed the Human Rights and Conflict Resolution training programme, exceeding the target. Evaluation of the training was positive, with 93.75 per cent of the trainees stating that they felt better able to teach human rights.

Indicator 4.3: During 2014, the GBV referral system has continued to expand. Trainings to frontline staff and CBOs have continued. Of the 2,539 survivors detected, there were 3,061 services accessed (counselling, legal aid, medical care, and social support). The number of services accessed is greater than the number of survivors detected because of the multi-sectoral approach to GBV, which means that the same survivor could access multiple services depending on their needs. The integration of Palestinian refugees in Syria, Lebanon and Jordan into the referral system continued in 2014 and has resulted in the detection of 787 GBV survivors in Syria and more than 70 survivors in Lebanon and Jordan.

Summary of responses to issues raised in previous annual reviews (where relevant)

We increased our target for Human Rights and Conflict Resolution Training in 2014-15 from 40% to 60% to reflect UNRWA’s quicker-than-anticipated progress in this area. They have successfully exceeded this target, scoring 76%. We also added the indicator “number of gender-based violence (GBV) survivors detected following the 2014 annual review, which also met its target.

Recommendations

DFID will:

(a) To increase our target for Human Rights and Conflict Resolution Training in 2015-16 from 60% to 80% to reflect UNRWA’s progress in this area.

(b) To explore further which ways DFID can support the implementation of UNRWA’s gender mainstreaming strategy in the new business case for support beyond 2016.
## VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

The main cost driver for the General Fund is salaries for around 30,000 teachers, health professionals and other frontline service delivery staff. The unit cost of service delivery also depends on the population of Palestinian refugees. This is projected to increase by 22.5% from 5.27m to 6.46m between 2016 and 2021. UNRWA takes a universalist approach to providing services; all refugees are entitled, irrespective of whether they have the means to pay or not.

Making cost savings on salaries is difficult. UNRWA is often subject to union strike action affecting service provision. In the Medium Term Strategy (MTS), UNRWA reiterated their commitment to adhering strictly to the Agency’s Pay Policy which dictates that UNRWA will take into account the relationship between UNRWA compensation and that of the Government of the host country. DFID has maintained regular dialogue with UNRWA on this issue throughout 2014.

Cost savings could however be made by taking a targeted approach to service delivery, using means testing or targeting vulnerable groups. UNRWA has made some progress on this in implementing fee-paying technical and vocational training courses for non-refugee beneficiaries. DFID will continue to encourage UNRWA to do more in this area.

VfM performance compared to the original VfM proposition in the business case

The business case estimates an economic return based on the short-term fiscal stimulus and education benefit streams, there is a Net Present Value with benefits four times greater than costs over the course of the programme. This calculation was based on (i) the increase in GDP due to UNRWA’s demand for goods and services in the economy (a fiscal multiplier effect) and (ii) the increase in annual wages for each additional year of schooling (a stream of benefits from providing education). Given this is a somewhat academic exercise, which is appropriate for a Business Case, for the purpose of an Annual Review it makes more sense to compare actual VFM metrics with the baseline.

For the purpose of this Annual Review, we will examine UNRWA’s performance against some of the VFM metrics which were mentioned in the original business case.

Economy	Salaries / Drug prices	UNRWA teachers’ salaries were 75% higher than PA teachers in 2010 / In 2010, procurement costs of seven drugs were lower for UNRWA than the PA.	In 2012-14, UNRWA salaries are 15% higher than PA salaries
Efficiency	Cost per outpatient visit to primary healthcare clinic / Cost per child in primary education	In 2010, NIS36, compared to NIS41 in PA facilities. / NIS3098 per child for grades 1-9 for UNRWA. PA costs were NIS2702 in 2010. Using exchange rate for 2010 (NIS3.9 = $1), UNRWA’s unit cost was $794.	$934 (including Syria) in 2013 (source: UNRWA Harmonized Results Report 2014)

In 2012, the unit cost – both direct and indirect costs - for basic education was $913 per pupil, hence a 1.3% overall unit cost increase from 2012-2013, despite a 2.6% decline in enrolment across the board. The comparison with the baseline year is not easy because UNRWA now includes direct and indirect costs. It is more relevant to work out why there has been an increase in the unit cost since last year, when the methodology used was comparable to the one used now.

UNRWA intends to update the DFID-funded Health and Education Efficiency Study in 2015. This will be an opportunity to further interrogate the cost data, and refine the VFM metrics, whilst ensuring that UNRWA continue to report on the metrics which are selected for the UK to monitor this programme effectively.

Assessment of whether the programme continues to represent value for money

Yes. There are a number of benefits that were not quantified at the outset, but which continue to feature, such as a lower probability of outbreaks of violence in refugee camps and reduced social exclusion.

Improved fiscal sustainability was one of the expected benefits at the time of writing the Business Case. This has become a growing source of concern, and one that DFID needs to engage more concretely on. Agreement on efficiency savings, as part of sector reform strategies, would be a start.

Quality of financial management

Financial sustainability is the greatest risk to the UNRWA programme. It is also a challenge to the long-run VFM of UNRWA’s activities. Simply put, if UNRWA’s voluntary contributions dry up, or at best cannot keep up with need, there will be no salaries to pay teachers and health workers.

The latest UNRWA financial report and audited financial statements (for year ended 31 December 2013) was published in July 2014. The operating deficit and limited cash position of UNRWA remain key concerns. The report referred to UNRWA’s dependency on voluntary contributions - 96% of the income of the General Fund (GF) - and the fact that a lack of steady contributions puts a strain on programme activities. UNRWA briefed on the upcoming UNBOA audit at the November 2014 Advisory Commission meeting and March 2015 Sub-Committee meeting. The report will be published in July/August 2015 and DFID will follow-up its recommendations at the November 2015 Advisory Commission meeting.

Date of last narrative financial report	Monthly reports received by email – latest is March 2015
Date of last audited annual statement	July 2014 (covering year ended 31 December 2013)

E: RISK (½ page)

Overall risk rating: Low/Medium/High

Medium/High

Overview of programme risk
UNRWA’s continuing deficit poses a risk to service delivery and the external security situation has deteriorated over the life of the business case. Key risks / mitigation are as follows:

Financial risks / Medium Term Strategy: UNRWA is continuing to operate on a recurrent budget deficit – currently projected at $101m by the end of 2015. The UK has engaged closely with UNRWA, other donors and host countries on the development of a Medium Term Strategy for 2016-21 to help UNRWA address its deficit in order to provide more sustainable service delivery for Palestinian refugees. DFID is now working up a technical assistance package to help UNRWA implement reforms. DFID’s Fiduciary Risk Assessment of UNRWA in April 2012 reported that the overall levels of fiduciary risk had been reduced from medium to low following improvements in UNRWA’s systems. DFID will update this by conducting a Due Diligence Assessment in May 2015.

Security risks to staff and implementation: The regional security environment in which UNRWA operates has deteriorated over the life of the business case. The rise of ISIL marks a challenge to regional security. The conflict in Syria has continued unabated since early 2011, causing hardship both for Palestinian refugees who have stayed in the country and those who have fled or attempted to flee to neighbouring countries. Fourteen UNRWA staff have been killed in Syria. There have been two conflicts in Gaza in the business case period: one in late 2012 and one in July-August 2014. Eleven UNRWA personnel lost their lives in the latest conflict and the Agency had to shelter an unprecedented number of displaced people (approximately 300,000) in its schools. The Agency has adapted the way it delivers services, for instance by providing distance learning materials to pupils who are unable to travel to school due to the security situation, and it is adapting its schools to be more suitable to serve as shelters in future.

Respect for neutrality of UN premises: During the conflict in Gaza in 2014, UNRWA re-emphasised the importance of all sides respecting their neutrality and inviolability under International Law. Nevertheless, 118 UNRWA installations were damaged (including nine UK-funded schools). There were incidents in which Israeli strikes on or near UNRWA designated emergency shelters resulted in civilian fatalities. In separate instances, weapons components were hidden in UNRWA schools by militant groups. DFID is engaging with UNRWA on its follow up to the UN Secretary General’s investigations into these incidents.

Counter-terrorism: UNRWA has clear measures in place to prevent any funding or assistance to terrorism, in line with the UK’s counter-terrorism legislation. These are centred on application of the UN’s neutrality policy and legal framework. For instance, job application forms include questions about prior convictions and appointment letters refer to neutrality provisions. Swift disciplinary action is taken if there is evidence of the involvement of personnel in inappropriate political or military activities. Staff and beneficiaries are vetted against the UN’s 1267 Sanctions Committee list of terrorists and terrorist entities and there have been no matches. Lists of staff are shared with local governments. UNRWA facilities are monitored closely and there are strict no weapons policies. Assistance is provided to beneficiaries on the basis of humanitarian need.

Outstanding actions from risk assessment

- Revise existing risk register to align it with programme risks as laid out above.
- Continue to engage with UNRWA to address their chronic financial deficit and weaknesses in Internal Oversight systems.
- Monitor restrictions on Palestinian rights in Lebanon and Jordan for refugees fleeing Syria and engage with diplomatic and humanitarian partners in advocacy.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

2014 has been a particularly challenging year for UNRWA due to the ongoing crisis in Syria and the deteriorating situation for Palestinian refugees from Syria, and also due to the 50-day conflict in Gaza in the summer. The impact of these conflicts is reflected in a few indicators where UNRWA have not delivered against the planned timeframe, such as the lack of progress on percentage of schools using the school-based agency-wide Education Management Information System (EMIS). As described under Output 1.5, the lack of delivery is directly linked to the Gaza conflict as the responsibility for its development and implementation had been placed under a project manager in Gaza prior to the escalation of hostilities. Similarly, the percentage of new inscriptions meeting UNRWA standards has decreased from 99% to 90%, with the Syria Field Office reporting that it was unable to reach its target due to the impact of the current crisis and the prevailing political situation, which prevents Palestinian refugees from obtaining the proper documentation and makes it difficult for them to reach UNRWA registration centres.

However, despite these incredibly difficult operating conditions, UNRWA has successfully delivered outputs against the majority of planned timeframes, and has overachieved in several key areas as well. UNRWA have exceeded the target for annual number of medical consultations and exceeded the target for diabetic control rate by a sizeable 43%. 76% of education staff have now successfully completed the Human Rights and Conflict Resolution training programme, exceeding the target of 60%. Other key indicators where UNRWA have delivered against planned timeframes and met targets include percentage of children under 18 months who have received all EPI vaccinations and the number of clinics performing the Family Health Team approach.

Performance of partnership

DFID and UNRWA have continued to enjoy a strong partnership in 2014, with continued engagement on UNRWA’s reform and results, and building UNRWA’s capacity on evaluation. DFID has been supporting UNRWA through continued substantial core funding to the General Fund despite increasing budget pressures, a technical assistance package and political support. In turn, UNRWA have engaged the UK in their dialogue around the development of the Medium Term Strategy (MTS).

UNRWA’s Department of Internal Oversight (DIOS) 2013 report released in November 2014 identified a number of concerns that DFID has been working to address. Internal oversight is a priority for DFID, to ensure our funds are managed appropriately and for learning and accountability. The May 2015 Due Diligence Assessment of UNRWA will allow DFID to follow up on the fiduciary risk implications of these weaknesses and in addition to that we are providing up to £0.5m for technical assistance to help drive forward reforms in UNRWA’s internal oversight. Although a challenging issue, UNRWA has engaged with DFID on this matter and it was discussed with other donors at the March 2015 Sub-Committee meeting.

Asset monitoring and control

As DFID’s contribution is an un-earmarked contribution to UNRWA’s General Fund, we have not requested specific reporting on the management of programme assets, or carried out monitoring or spot checks. UNRWA briefs DFID on key risks e.g. lack of funds to maintain its vehicle fleet through the SubCom / AdCom process.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

An assessment of the partnership principles is not considered to be relevant for this programme.

DFID made 30% of its 2014/15 funding conditional on progress against reforms, however. The assessment of the 2014/15 Results Compact is attached at Annex A. The full funding was released to UNRWA. Key findings were that, while some further work was needed to build UNRWA’s evaluation capacity, there had been strong performance against the remainder of the Results Compact – including on the Medium Term Strategy. We noted that DFID will continue its engagement with UNRWA on all results and reform issues, especially on planning, evaluation and technical assistance, and draw up a Results Compact for the 2015/16 funding.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

DFID has been supporting UNRWA to build the capacity of its evaluation division within the Department for Internal Oversight. We allocated £300,000 of our £500,000 2011-15 monitoring and evaluation fund to support the implementation of UNRWA’s Evaluation Plan and convened meetings with key donors. Progress in this area has been gradual and challenging given a lack of resourcing in the evaluations division. However, in the reporting period DFID agreed to fund:

- A quality improvement project for evaluations across UNRWA.
- An UNRWA Human Development Study.
- Evaluations of UNRWA’s Resource Mobilisation Strategy, the eHealth programme, the Safety and Security programme, Jordan rehabilitation centres and the Jordan and West Bank educational science training centres.

These initiatives were still ongoing beyond the scope of the Annual Review period.

UNRWA is still working under the theory of change in the business case. However, the Medium Term Strategy for 2016-21 has re-ordered the Strategic Objectives to place protection of rights as the first and overarching objective.

OUTPUTS				OUTCOME		IMPACT
1	Provide high quality educational services	50%		Basic services are sustainably provided and human rights are protected for Palestine refugees		Long, healthy and dignified lives for Palestine refugees
2	Provide high quality health services	25%
3	Protect the vulnerable	15%
4	Ensure protection of human rights	10%

DFID is engaging with UNRWA on the development of its Common Monitoring Matrix, including by encouraging the Agency to enhance disaggregation of data by sex, age and location where appropriate.

Monitoring progress throughout the review period

DFID undertook several field visits to Gaza, the West Bank, Jordan and Lebanon in the reporting period. Field visits to Syria were not possible due to the security situation. DFID has encouraged UNRWA to develop its engagement with beneficiaries, a theme which now comes through strongly in the MTS.

This Annual Review was undertaken by the B2 Programme Officer with support from the B1d SRO, input from a range of A-grade advisors and sign off by the Head of Office. It was based on the 2015 Harmonised Results Report, reform reports and exchanges with UNRWA’s Department of Planning as well as input through the Harmonised Results Working Group.
Final Results Compact/ Performance Tranche Assessment for 2014/2015

Section 1: Delivery against key indicators, including on reform (50%)
Target	Achieved?
Overall score of A or higher in DFID’s Annual Review	Yes

Additional comments on progress

The Annual Review, completed in May 2014, scored an A. Results delivered in 2013 included the provision of basic education for 491,641 children, antenatal classes for 74,486 pregnant women and cash transfers for 291,757 individuals. The Review demonstrated that UNRWA has continued to implement its reform agenda, where funding has allowed.

Section 1 assessment – Achieved. Funding disbursed in October 2014.

Section 2: Progress on value for money (25%)
Target	Achieved?
Finalise and put into use by sharing with field and programme directors the data from the Activity-Based Costing (ABC) exercise	Yes
Provide an update on how UNRWA plans to revise baselines and projections from the April 2013 DFID-funded ‘Health and education efficiency in UNRWA’ study	Yes
Maintain firm adherence to Pay Policy in negotiations with staff unions	Yes

Additional comments on progress

UNRWA gave a presentation on the ABC exercise at the June 2014 Advisory Commission (AdCom) meeting. The ABC model has been completed and the outputs have been shared internally so that the model is now in use as a reference source for internal decision making. It has been used to develop the new efficiency and effectiveness indicators in the MTS for 2016-21. UNRWA has been clear that cost will not be the only decision-making factor, however; for example, it costs more for UNRWA to educate a child in Lebanon than in Syria due to local economic conditions, but this does not mean that UNRWA will reduce service delivery which is enshrined in its mandate. DFID is continuing its dialogue with UNRWA on efficiency and effectiveness and how the ABC model will be further developed to respond to requests for information and improve planning. / UNRWA has updated DFID on the use of the efficiency indicators from the ‘Health and education efficiency in UNRWA’ study. Some indicators have already been reported in the 2013 reform reports. The health indicators included costs per consultation, total health costs per capita, hospital admissions per capita and prescriptions per capita. The education indicators included the cost per pupil for basic education. However, four factors affected UNRWA’s ability to use the new indicators for baselines and projections. First, there was a comparability issue as the study included Syria data whereas subsequent reports have not because of the ongoing conflict. Second, UNRWA’s transition from one type of accounting methodology to another (UNSAS to IPSAS) resulted in a change to the way costs are reported. Third, there was a need for the ABC costings to be validated. Fourth, UNRWA is still rolling out better information systems via eHealth, the Education Management Information System and the Enterprise Resource Planning software which are needed to extract data. UNRWA will work fully to integrate the new indicators in the third quarter of 2015 to feed into 2016 baselines and 2021 projections, in line with the new monitoring matrix in the Medium Term Strategy (MTS) for 2016-21. / UNRWA has maintained adherence to the Pay Policy in negotiations with staff unions during the period from May-November 2014, including in ongoing talks with the West Bank union following their December 2013 strike. UNRWA briefed interested donors on application of the Pay Policy in the summer of 2014, and included a clear reference in the Medium Term Strategy for 2016-21 to control cost drivers via continued adherence.

Section 2 assessment – Achieved.

Section 3: Medium Term Strategy (MTS) (15%)
Target	Achieved?
Deliver a draft MTS by June 2014 and a final MTS (save for final formatting and minor adjustments) by November 2014, which: / Is underpinned by a strong strategy to address poverty by helping to break the transmission of poverty from one generation to the next through continued health provision alongside reforms to education and relief and social services to enable enhanced livelihoods opportunities. / Commits to producing an action plan to reform the TVET programme to make it more financially sustainable and to ensure that both the TVET and microfinance programmes have a better and more measurable impact on refugee employment and livelihoods. / Reflects that cash transfers are proven to be more effective than food transfers and are often the preferred modality by refugees, and sets out feasible options for how UNRWA could move from food to cash transfers where appropriate to the context. / Is ‘costed’, setting out what level of service delivery UNRWA can afford to deliver based on different funding scenarios. / Shows clearly how UNRWA intends to enhance its partnerships with others (including the private sector) to secure sustainable and more efficient service provision for Palestinian refugees, without impinging on UNRWA’s mandate. / Contains a strengthened monitoring framework, disaggregating indicators by poverty, disability and sex, wherever possible. / Demonstrates throughout due regard to the needs and impact of its programmes on women and girls.	Yes
Demonstrate achievement against agreed ToRs of the DFID-funded technical assistance on the MTS and beneficiary engagement	On track

Additional comments on progress

After a useful exchange of views in June 2014, UNRWA has delivered a strong final draft of the Medium Term Strategy (MTS) in advance of the November 2014 AdCom. The MTS includes poverty as an underpinning theme. It includes a commitment to reform the technical and vocational education and training (TVET) programme to make it more financially sustainable via opening up courses to fee-paying non-refugee students. It includes a commitment to make the microfinance programme independent. The MTS states that cash assistance is UNRWA’s preferred methodology wherever possible, with decision-making on how to undertake that transition delegated to the field-level Strategic Response Plans which will be finalised in June 2015. While the final draft MTS was not costed, UNRWA held a productive meeting with interested donors to establish expectations and timelines. DFID clarified that the costings chapter should give a clear sense of what direction will be given to fields within UNRWA’s financial reality; UNRWA agreed what content to include and set out a timeline for filling in the numbers once the Strategic Response Plans are complete. The final draft MTS includes stronger consideration of how UNRWA will enhance its partnerships. It includes a monitoring framework with better disaggregation, which DFID will engage with UNRWA on in the run up to June 2015. The MTS gives due regard to the needs and impact of its programmes on women and girls, paying particular attention to protection needs of women and girls given incidents of gender-based violence and early marriage in its fields of operation, and it commits UNRWA to improve the gender balance among its more senior staff. / DFID funded a planning officer from January to September 2014 to assist with the development of the MTS. The Director of Internal Oversight has confirmed that the post holder fulfilled her duties by organising MTS workshops, managing engagement with stakeholders, co-ordination of feedback and drafting, and mapping of community perceptions. She also provided the first draft template of the field level Strategic Response Plans and helped develop the guidance to fields. DFID and UNRWA agreed terms of reference for a beneficiary engagement post, but following an unsuccessful recruitment around, we are now pursuing a different option to second a DFID Social Development Adviser to UNRWA to take this issue forward. The MTS has given a clear priority to the issue of beneficiary engagement including via a commitment to produce an annual report to refugees. Due to an underspend against the budget allocated for technical assistance, UNRWA is also looking to take on additional TA in the form of a Partnerships Officer to take forward UNRWA’s work in this area.

Section 3 assessment – Achieved / on track.

Section 4: Transparency and evaluation (10%)
Target	Achieved?
Continue to provide monthly financial reports to donors	Yes
In accordance with the Evaluation Plan, build the capacity of the Evaluation Division according to milestones agreed with DFID and demonstrate clear improved links to programming and decision-making	Partially achieved with some challenges

Additional comments on progress on transparency and evaluation
UNRWA has continued to provide monthly financial reports to donors. It has also given presentations on its financial situation and resource mobilisation strategy at the April 2014 Sub-Committee meeting and the June 2014 AdCom meeting. / There has been some progress on evaluations. Following the agreement of an Evaluation Plan in late 2013, DFID allocated funding to support the evaluations work in the first half of 2014. DFID and UNRWA agreed a proposal to improve the quality of the Agency’s evaluations in order to ensure that project-level evaluations can be useful for decision making and to promote transparency by publishing evaluations online. We also agreed a proposal to co-finance an evaluation of UNRWA’s Resource Mobilisation Strategy. However, there have been challenges. The quality proposal was not agreed until October 2014 and a lack of funding has meant that many of the planned evaluations have been cancelled. UNRWA updated the donor Harmonised Results Working Group on this in September and October, and have now produced a revised evaluation plan which is aligned to the strategic objectives in the MTS. DFID has welcomed this, while flagging that the sustainability issue remains; the Evaluation Division does not have enough money allocated from the General Fund to undertake all these evaluations, and funding from donors is not assured. DFID will continue to work with UNRWA to improve its evaluation capacity in order to promote accountability and lesson-learning.

Section 4 assessment – Partially achieved.

FINAL COMMENTS AND ASSESSMENT

Half of the funding associated with this Results Compact has already been released in October 2014 based on the strong score of the Annual Review. / While some further work is needed to build UNRWA’s evaluation capacity, DFID judges that there has been strong performance against the remainder of the Results Compact – including, crucially, on the Medium Term Strategy. We therefore recommend the release of the remaining funding. Timely disbursal is required in order to help the Agency pay its teachers’ and doctors’ salaries on time, given the Agency’s end of year financial shortfalls. DFID will continue its engagement with UNRWA on all results and reform issues, especially on planning, evaluation and technical assistance.