Annual Review - Summary Sheet

Title: UK Post-Conflict Development Programme for Northern Uganda (PCDP)
Programme Value: £100,515,534		Review Date: 30 June 2015
Programme Code: 200250	Start Date: 15/06/2009	End Date: 31/12/2016

Summary of Programme Performance
Year	2013	2014	2015
Programme Score	B	A	A
Risk Rating	Medium	Medium	Medium

Summary of progress and lessons learnt since last review
Since the 2014 review progress on the remaining components of the programme has been broadly positive. In relation to achievement of the remaining targets and milestones, three of four outcome indicator milestones were met or were just short of being achieved, and one is assessed as having been overambitious. Of the output indicator milestones, nine have been met or surpassed, and two were not achieved. This is encouraging progress given the complexity of the programme and the significant reprogramming of a number of components that was required following the misappropriation of funds under this programme by the Office of the Prime Minister (OPM) in 2012/13.

There are some questions around the overall cohesion and aggregate contribution of the components to PCDP’s planned outcome as well as the Government of Uganda’s Peace, Recovery and Development Plan (PRDP) for Northern Uganda. PCDP was designed to contribute to PRDP alongside other Government of Uganda and other donor support for the plan. Support for and coordination and monitoring of the overall PRDP has inevitably been effected by the discovery of misappropriation of funds in OPM, which amongst other things resulted in the withdrawal of DFID’s technical assistance for OPM, the decision not to provide budget support for PRDP under PCDP, and the cessation of budget support for PRDP by a number of other donors. Additionally, the PCDP Steering Committee did not continue to function after this series of events. That said, the remaining components of the programme are delivering relatively well against their targets and milestones and having impact in their own right, in some cases delivering more direct results than when they were channelled through GoU institutions.

The next phase of PRDP is currently under design, and through PCDP DFID is providing strategic technical assistance to support this process and ensure the next phase learns critical lessons from PRDP 1, as well as drawing on the findings of the Economic Recovery Analysis (ERA) funded through PCDP.

The original programme period was 2009 – 2014, and whilst the overall programme timeframe has been extended to 2016, a number of the activies and components have ended prior to and during the period of this review. The complete picture of which components remain active and which have been closed over the programme’s lifespan is summaried below as they relate to the Output indicators in the log frame:

Output indicator	Financial Year when DFID support finished/finishes
2.1	2010-11
1.1, 1.2, 1.3, 2.2, 2.3	2013-14
3.1, 3.4, 4.1, 4.3	2014-15
2.4, 3.2, 3.3	2015-16
4.2	2016-17

In relation to reviewing and learning lessons from the activities where support has recently ended, an evaluation of the Northern Uganda Social Action Fund (NUSAF 2) is underway, and DFID contracted a consultant to review the Advisory Consortium on Conflict Sensitivity (ACCS). The conclusions of the ACCS review are included below. Review/evaluation plans for the other components are detailed throughout the review.

Summary of recommendations for the next year

Revisions will be required to the logframe, as per the recommendations throughout this review.

In the final year of PCDP, whilst reviews/evaluations are completed for the various components, it will be important to agree a method to review the overall impact and lessons learned from the programme. Whilst a full evaluation is not planned at this stage, it will be important to capture lessons around the model of PCDP as an umbrella programme and the challenges and complications that stem from such an arrangement, as well as the impact of the changes to the context and institutional arrangements over the programme period.

With the conclusion of the ACCS programme, DFID should consider its future bilateral engagement in the conflict and security sector in Uganda.

DFID should continue to ensure that strategic technical assistance and lessons from the Economic Recovery Analysis inform and help to shape the next phase of the PRDP.

.
A. Introduction and Context

DevTracker Link to Business Case:
DevTracker Link to Log frame:

Outline of the programme
The conflict in northern Uganda lasted 23 years and prevented the people of northern Uganda from enjoying the benefits of national stability and economic growth seen elsewhere in the country. Two million people were in camps for internally displaced persons from 1991-2011 and 22,000 children were abducted (an estimated 2,000 of whom have never returned) during the period of protracted armed conflict. As poverty steadily reduced across Uganda, levels in the north were 22% above the 2009 national average.

The UK’s Northern Uganda Post-Conflict Development Programme (PCDP) is providing just over £100 million to support recovery in post-conflict northern Uganda. This programme, now running over six years (2010-2016) was originally designed to build on the emerging peace in greater Northern Uganda following the Cessation of Hostility Agreement between the Lord’s Resistance Army (LRA) and the Government of Uganda (GoU) in 2006 and support the Government of Uganda’s Peace, Recovery and Development Plan. PCDP aimed to generate growth, development and opportunities and promote peace building in a region emerging from a period of conflict and neglect.

Following the suspension of financial aid to GoU in 2012 as a result of a corruption scandal in the Office of the Prime Minister (OPM) linked to PRDP, a number of the components under the PCDP were reprogrammed and funding was channelled through different delivery channels. DFID reprogrammed PCDP’s youth development programme which is now delivered through Volunteer Service Overseas (VSO) and Youth Business International (YBI) through its partnership with Enterprise Uganda (EUg), both of which are running well and are on track to surpass targets. Whilst it was originally intended that PCDP should provide budget support through OPM for the Government of Uganda’s PRDP, the fiduciary risks of doing so were judged to be too high. Additionally, support through the Private Sector Foundation Uganda (PSFU) was phased out, and technical assistance to OPM was ended.

At the time of writing this annual review, with 18 months remaining, the majority of PCDP’s components have finished and have been reviewed/evaluated or will be in due course. The components that continue on into the next reporting period are the support to the Democratic Governance Facility basket fund (DGF) under Rights, Justice and Peace, and the youth development work. From 1 January 2016, the DGF support will be the only live component.

The intended impact of PCDP is to build a peaceful, vibrant Northern Uganda, with increased opportunities for the people of the north and reduced poverty for all of Uganda.
The intended outcome of PCDP is to reduce poverty in Northern Uganda by improving service delivery, supporting the most vulnerable, helping 10,000 young people to find jobs and funding conflict resolution and peacebuilding activities.
The four outputs of the programme expect to or have achieved the following key results:
- 1. Local government capacity for equitable service delivery and management is strengthened. This output has funded the construction of 1738 homes for health workers and teachers, increased 21 target District sub-country governance conditions to a minimum standard, and installed community-level project Monitoring and Evaluation (M&E) tracking systems in 485 sub-counties.
- 2. The most vulnerable conflict-affected communities are rebuilt and empowered. This output has supported around 3,500 extremely vulnerable people through access to social services, shelter and livelihoods in Acholi and Lango. It also supported almost 24 million labour hours on food/cash for work projects in Karamoja and some 10,000 food transfers. Finally, it is developing an evidence base behind the use of results-based financing in healthcare, through financing 21 results-based health facilities and 10 input-based facilities across northern Uganda, targeting some 345,475 consultations and treatments.
- 3. The private sector is revitalised and accessible employment opportunities are created. This output seeks to contribute to the peaceful development of northern Uganda through encouraging economic growth. The Private Sector Foundation Uganda (PSFU) programme approved grants for 426 businesses (under the target). It was originally providing skills training through the Northern Uganda Youth Development Centre, this was ended in 2012. There is evidence of strong performance from the Youth Develpoment Programme (YDP) and Northern Uganda Youth Employment Programme (NUYEP) programmes in providing vocational skills and entrepreneurship training, which are both on track to surpass targets of 15,400 youth trained in vocational skills and 8,400 youth trained in business start-up. Surveys conducted by International Alert have returned higher-than-targeted responses on perceived access to economic opportunity.
- 4. Government, civil society and communities can engage actively in peace building and reconciliation. This output has exceeded expectations in influencing the GoU’s Peace, Recovery and Development Plan (PRDP) interventions to make them more conflict sensitive. Through the Democratic Governance Facility (DGF) legal aid services are being provided, and satisfaction with the role of traditional institutions in traditional justice processes is currently above the target, though there are indiciations that these figures are declining. This annual review is recommending that the logframe indicator be revised to specify legal aid services provided just in the PRDP region with revised milestones and targets for the DGF extension period.

## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment
PCDP aims to increase economic, social and political opportunities, thus improving the lives of people affected by conflict in northern Uganda. It was originally designed to support and contribute to the GoU’s PRDP across a range of sectors.

In relation to the overall impact of the GoU’s PRDP, the proportion of people living in poverty in northern Uganda has reduced in recent years, but only slightly - from 46.2% in 2009/10 to 41.8% in 2012/13. This is compared with the decline in the national average from 24.5% in 2009/2010 to 19.7% in 2012/13. Perceptions that the North is marginalised by the GoU persist, with the final Peace and Conflict Indicators Survey (PCI) showing only between 41.1% and 47.5% of respondents in affected areas reporting that post conflict development interventions in the North have helped bridge differences between the North and South. This is concerning and is down from 64.2% two years ago.

PCDP’s outcome indicators reflect the current components of the programme and span a range of sectors including healthcare service delivery, job creation, satisfaction among the targeted population with basic services and assessment by respondents of local governance responsiveness. Over the past year, progress towards the current outcome indicators has been mixed and the detail is shown below.

As discussed in the review summary, whilst the remaining components of the programme are delivering relatively well against their targets and milestones, there are questions around the overall cohesion and aggregate contribution of the components to PCDP’s planned outcome as well as to the PRDP. In the absence of a strong national coordination and monitoring mechanism for PRDP that draws in all support regardless of funding channels, there is a question as to how far it is possible to assess whether the impact of current support for northern Uganda, including through PCDP, has been greater than the sum of its parts.

This point around cohesion and contribution to an overall theory of change is also reflected to some extent in the management structrues of PCDP in DFID – many of the components were or are complicated in their own right, each have their own delivery chain and geographical focus and have warranted treatment and programme management as individual projects. This question will be explored further in the coming year and the final review to be scheduled for after programme completion.

Progress Against Outcome Indicators
Number of under-fives presented with fever that are tested for malaria and appropriately treated in the 31 Private not for Profit (PNFP) facilities (disaggregated by gender).
The annual milestone is 45,162 of which 32,965 are to be delivered by results-based financed (RBF) facilities and 12,197 for input-based financed (IBF). This has been greatly surpassed, with the RBF facilities reaching 43,660 and the IBF facilities reaching 17,332 (50% over-achievement).

Number of Youth Development Programme youth with decent jobs (employed or self-employed in the formal or informal economy) (attributable to DFID).
The final target for this is 11,000 - i.e. a decent job for 70% of the recipients of VSO supported training package. Evidence to date suggests that this will not be met as currently defined. The most recent data from VSO indicates that only 29% meet all three sub criteria for a ‘decent job’. The three criteria are: working more than 25 hours a week (revised down from 40 or more hours[1]); earning a minimum of the regional average wage; and either having been in work for 6 months, or expecting to be in employment for the next 6 months.
[1] Revised following receipt of survey data in March 2015 which broke down responses into ‘greater than 25 hours’ and ‘greater than 45 hours’. ‘Greater than 25 hours’ is closer in spirit to a ceiling of 40 hours than ‘greater than 45 hours’.

Broken down these figures are more positive than the small proportion who meet all three criteria:
51% were working 21 hours or more per week (of whom 22 percentage points were working over 45 hours).
- 35% were earning a minimum income of UGX. 141,000 per month. Also, the number reporting no income earned dropped from 66% at baseline, to 11% during follow up.
- 55.4% were employed for the last 6 months or expected to be in that employment for 6 months.

This is a clear underachievement on the indicator, but the recent annual review mission concluded that the original inidicator was over-ambitious (based as it is on an International Labour Organisaiton definition of ‘decent work’ that is very hard to meet in an informal agrarian economy) but that the actual results that are being acheived are substantial and significant.

In addition to VSO supported beneficairies, another project under PCDP run by Youth Business International and Enterprise Uganda, has trained an additional 7166 youth in its entrepreneurial course, and is reporting income increases averaging 183% per beneficiary. These results are not formally included in the outcome level indicator, and results require further validation, but indicate funds under PCDP are achieiving significant outcomes within the income and economic development area.

Level of satisfaction among target population with quality of basic socio-economic services.
The final target for this indicator was 90%. According to the 2013 Citizen Report Card, satisfaction fell just short of this, reaching 85% of those surveyed. The robustness of this data and methodology needs some further investigation.

Percentage of respondents assessing that local government is responsive to community needs.
The PCI survey was carried out three times over the course of the ACCS programme in order to create a time series dataset for use in monitoring the impact of the PRDP on peace and conflict in northern Uganda. It used both quantitative and qualitative approaches, covering 21 districts in nine regions of Uganda. The data collection methods included a perception survey, consensus panels and key informant interviews. The target for this particular indicator is: Acholi 59%; Lango 59%; West Nile 62% and Karamoja 57%. The actual results were Acholi 58.1%; Lango 51.4%; West Nile 55.3% and Karamoja 71.6%. This shows that this indicator was exceeded for Karamoja, and narrowly missed for the other regions. 4,197 respondents were questioned across northern Uganda, including 2,562 from Acholi, Lango, West Nile and Karamoja.

Overall score and description - A

Overall, the PCDP scores an A this year, reflecting the fact that each individual output has scored an A when assessed against current output indicators. Within outputs, performance has been variable, with highlights including the youth training under YDP and the low-cost yet high-impact technical assistance to Gulu Local Government. NU Health, which is pioneering the use of results-based financing in project implementation, is beginning to show positive signs of the impact of RBF. It is too early for the built-in impact evaluation to draw specific lessons, but we will continue to monitor this closely. Other programmes, including PSFU, which was closed early, have inevitably had weaker performance against their logframe targets.

Key lessons
This configuration of the PCDP – as one large umbrella programme with many distinct components and delivery partners – is challenging in terms of programme management as well as undertaking an overall review and measuring progress towards an outcome. As such, this annual review focuses on the PCDP-level logframe indicators, but is complemented and has been informed by detailed individual reviews and evaluations being carried out on each component.

PCDP was designed with a high level of flexibility to respond to changing contexts and assessments of risk. This proved to be very useful given the changes required following the misappropriation of PCDP and other PRDP funding discovered in 2012/13. However, the multiple changes to the programme mean that the original theory of change and plans to holistically support the PRDP have not come to fruition. Value for money has however been pursued through the impact and effectiveness of the individual components.

In programmes of this nature, the overall DFID Senior Responsible Owner in practice must rely on and be supported by ‘sub-SROs’ for each component who are closer to the day to day work, delivery chain, and decision making.

The impact of small components like the TA provided to Gulu and Lira local governments can be significant. DFID has recognised its impact and ensured that the Governance, Accountability, Participation and Performance programme (GAPP) incorporates this form of support. Further work is planned to understand the conditions that facilitated the impact of this TA.

Indications are that the results-based financing system under NU health may be gaining some traction and that the programme will generate some important evidence and learning. It is too early for this to be confirmed, but the ongoing process of feeding back emerging lessons on this will continue. There is further a lesson learning workshop scheduled for September 2015.

Demand for the training provided by VSO and Enterprise Uganda vastly outstrips the current supply through this project, and cost/benefit is likely to be positive. However, there is likely to be insufficient availability of funding within the community/country to meet this demand when the current project comes to an end. There may be enough availability of self-sponsorship to make the continuance of the VSO six months courses viable, although this will then exclude those unable to pay.

- The ACCS final review has been completed, drawing lessons which are of relevance for DFID’s own programming in Uganda, as well as in similar contexts. The key lessons were:
  - Integrating conflict sensitivity within large government programme is essentially a highly political endeavour (rather than a technical fix). NGOs can play an important role, however, concerted messaging, monitoring and buy-in to the approach amongst stakeholders and drivers of change is necessary, from the earliest design phases.
  - The need for a clear appreciation of the conceptual distinctions between conflict sensitivity, peacebuilding and integrated programming. This confusion was evident within the ACCS programme design and in implementation. Applying the principles of conflict sensitivity to an intervention or programme does not automatically mean that the programme will address conflict drivers or resolve conflict. This requires a more focused peacebuilding approach.
  - When functioning well, consortia can strengthen programme performance in a variety of ways. However, there are a number of key criteria for effective functioning of a consortium, which if absent, can undermine performance. These include: a shared understanding of the programme scope, foundational concepts, theories of change and benefits of consortium working amongst members; clear lines of accountability for performance and robust management structures (including financial management) and oversight.
  - The review also confirms DFID’s sense that although the PCI methodology was indeed thorough, it offered relatively poor Value for Money (VFM) and should have been accompanied by a more robust and targeted advocacy strategy (as should other ACCS products). DFID was right to seek to address land conflicts, but the 12 months that were given to Saferworld to do this were only enough to make a start – sustained work is needed, and a sensitivity to the political aspect of some of these conflicts is also required.

The output indicator for the number of decent jobs gained by beneficiaries of the youth training component was unrealistic in terms of its strict definition of a ‘decent job’. Based on our better understanding of the context of what type of jobs and income opportunities are available and could be feasibily achieved. This will now be amended so the successes of the programme in the remaining months can be more usefully monitored.

Key actions
The entire PCDP programme will be coming to an end in December 2016. Although all components are being reviewed or evaluated in some form, a review (rather than a full-scale evaluation) of PCDP is recommended, to bring together into one place all the lessons learned from components of PCDP and to make recommendations on future programming. The ToRs should be developed well in advance of the 2016 Annual Review of PCDP (Action: SRO – November).

DFID to take a decision on its future support in the areas of post-conflict work by December 2015, taking into account the recommendations of the ACCS final review (Action: Governance, Security and Humanitarian (GSH) Team Leader– September).

Has the logframe been updated since the last review?

Yes, the logframe was updated in line with the recommendations of the 2014 annual review. Corrections have also been made to the NUYDC component of the logframe. Several further amendments to the logframe will be required following the recommendations of this review.
## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Local government capacity for equitable service delivery and management is strengthened
Output number per LF		One	Output Score	A
Risk:		Medium	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Baseline, Milestones, Progress
1.1 Number of houses for health workers and teachers constructed by NUSAF2 (DFID attributable)	Baseline 2009 Milestone 2012 Milestone 2013 Target 2015 / Planned 0 500 1,000 1,738 / Achieved 75 Partially achieved, 944 1738
1.2 Number of sub-counties in target districts meeting minimum governance conditions	Baseline 2009 Milestone 2012 Milestone 2013 Target 2015 / Planned 4 12 17 21 / Achieved 15 21 No new data available
1.3 Percentage of sub-counties with operational community-level project M&E tracking systems	Baseline 2009 Milestone 2012 Milestone 2013 Target 2015 / Planned 0 30% 85% 100% / Achieved 100% 85% 100% (485/485)

Key Points
  1. Number of houses for health workers and teachers constructed by NUSAF2 (DFID attributable)
DFID provided £24m ($35m) to the World Bank (WB) NUSAF2 programme to cover the building of 1738 houses for teachers and health workers. Of this sum, £21m ($30,450,000) was allocated to building of houses; £2.2m ($3.5m) was to cover overhead costs of the project of which M&E is a component; and £0.8m ($1.25m) was allocated to the Inspectorate of Government (IG) to improve transparency, accountability and anti-corruption (TAAC) of NUSAF2. The purpose of DFID’s support to NUSAF2 was to increase access to basic social services in the education and health sectors by building houses for teachers and health workers in order to attract and retain staff. Lack of housing for teachers and health workers was identified as one of the priority constraints to improved service delivery in the education and health sectors in the North at the time of programme design. The impact of DFID’s contribution to NUSAF2 needs to be considered in the context of the overall NUSAF programme which, amongst other things, undertook a broad set of community driven and monitored infrastructure projects.
The original target of 1,000 units attributable to DFID was revised down to 869 units (each unit containing 2 houses). The project review was conducted in May 2015 and concluded that the target number of houses (1,738, as 869 two-house units), were completed within the £24 million allocated for this activity, albeit with a number of delays. So far, over 1,758 teachers i.e. M=1,054, F=704 and 844 health workers staff have so far been accommodated. In addition, 356 of 497 units funded by the World Bank under NUSAF 2 were completed and handed over.
The houses are equipped with solar panels, enabling teachers to do lesson planning, mark students’ homework, charge their phones and be in touch with district officials. The World Bank report that completed and ongoing engineering works for most of the houses and health centres visited and inspected have been observed as largely satisfactory. Adherence to sector standards has generally improved and was strengthened from the time of deployment of engineering assistants in April 2012. The engineering assistants provided guidance to contractors through correct technical interpretation of design drawings, bills of quantities and construction specifications. In addition, standards associated with the construction works such as iron sheet roof covering and painting finishes have been given due attention to ensure that they all fulfil approved technical specifications.
Community participation in construction supervision is reported to have strengthened adherence to sector designs and technical specifications, and ensured quality control. In Moyo district, for instance, members of beneficiary communities received basic information on the desired quality of materials intended for construction works, such as mix ratios for reinforced concrete. Community members then observed ongoing construction activities to ensure compliance with desired works quality recommendations, provided by supervision personnel. When works were deemed unsatisfactory by the community, they provided instant information to responsible subcounty and district technical personnel, who responded with appropriate action.
There is a report dated November 2013 called the Citizen Report Card for NUSAF 2 that covered 24 of the 55 districts where NUSAF 2 operates. The citizen report card is a tool that provides public agencies with systematic feedback from users of public services. The report states that 85% of the respondents were satisfied that NUSAF2 investments had improved their access to education, health and safe water. However, it is important to note that it is not possible to identify how far this can be attributed to increased numbers of houses for teachers and health workers. Furthermore, there isn’t more recent data, showing whether the levels of satisfaction has either increased, decreased or remained static over the last two years.
It should be noted that the operational costs (incurred by the project and the World Bank) rose over the programme period. The main reason for this was the decision to enhance the intensity of technical assistance on construction standards provided to the districts with a responsibility to oversee the building work. This resulted in a significant increase in costs, but due to exchange rate gains, the per-unit cost of the houses built has turned out the same (in £) as originally planned; and the units are extremely high-quality as a consequence of the technical assistance on construction standards – far better quality than much public infrastructure in Uganda, without being inappropriately over-specified.
This was a large investment by DFID but there is little evidence around the direct impact of the investment. What we know is that the houses were built to a high standard; they are extremely popular with the staff that benefit from them, who have anecdotally told DFID that they would previously have struggled to find local accommodation in many of the areas in which they have been built; they are popular with local communities, who see it as a positive measure of support to health workers and teachers who are – usually – respected by the local commnuities; they are very high-quality; and came in on-budget despite the increases in admin costs, due to the exchange rate fluctuations. We should however seek to corroborate this formally by commissioning a small evaluation to run alongside the impact evaluation planned by the World Bank.

The purpose of the Transparency, Accountability and Anti-Corruption (TAAC) component was to strengthen transparency and accountability in implementing the broader NUSAF programme, which in total is itself a $100 million operating across three components (livelihood investment support; community infrastructure rehabilitation; and and institutional development). TACC supports the creation of Social Accountability Committees (SACs) at sub-project level to monitor the implementation of projects and report corruption.

The IG trains team members, conducts awareness raising activities, whilst also investigating reported cases. By 2015:

- 625 SACs selected for formation, 567 trained and 84 followed up.
- 40,000 members of the community SACs at the sub-project level were trained.
- 12,000 spot messages and talk shows were channelled through 18 regional radio stations.
- 2000 NUSAF project-related cases of corruption were received via SMS, telephone calls and letters. Of these reports, 426 cases were deemed actionable, of which two have been taken forward for prosecution so far and are ongoing at the time of this review.

The Inspector General (IG)’s office has drawn on the SAC model and built on it for future monitoring work. It has labelled these new groups ‘community monitoring groups’, which are comprised of 9 people, of which 5 are direct beneficiaries from the community (the same as in the SACs) and 4 are (new) non-beneficiaries added to increase the impartiality of the group. The IG’s office has developed a curriculum on what should be taught to the community monitoring groups to enable them to carry out their duties, and developed training material and training aids to be used by the 37 trainees and 9 regional managers who will train the groups. The IG has also developed a remote monitoring tool which uses a mobile phone system. The trainees and regional managers feed into this system which also links with the Global Positioning Satellite system (GPS) to confirm that the training has been conducted.

The absence of detailed statistical analysis of the cases being dealt with (for example, how many cases were resolved? What actions were taken? How long did resolution take?) makes it hard to gain full assurance that TAAC is working effectively in addressing corruption in NUSAF. Requests for this type of analysis have been repeatedly made of the IG’s office but not yet addressed.

1.3 Percentage of sub-counties with operational community-level project M&E tracking systems
This target fits within the NUSAF component, and has been reached according to reports from NUSAF. As the programme draws to the end of its implementation however, there is an urgent need to provide accountability for results across the components and areas of implementation of the programme. In an effort to respond to this urgency, OPM has put in place mechanisms to strengthen the M&E function of the project. For instance, Extended Participatory Rural Appraisal Facilitators and Sub County Community Development Officers have been engaged in data collection at community level, data entry and reporting at district level.

Numerous communities with funded Community Infrastructure Rehabilitation projects were involved in procurement of works and management of construction works. NUSAF decided that during these critical project implementation stages, district and sub county technical personnel were required to provide the necessary technical support and it was necessary to amend the monitoring approach to rely less on community reporting and more on hired and paid-for independent experts, increasing the administrative costs. NUSAF reports inadequate operational funds for field-based activities, especially field monitoring and supervision (partly for the reasons just explained), and claims that as a result, the districts provided limited support to communities in which these activities were and are still ongoing. Nevertheless, they were able to reach all subcounties with the tracking systems, so the logframe target is recorded as having been met. Lessons can usefully be drawn on the cost and burden of the type of community monitoring originally envisaged under NUSAF.

1.2 Number of sub-counties in target districts meeting minimum governance conditions
Following the positive results found during the 2014 review, DFID continued with support to both the Lira and Gulu District Councils through technical assistance. This shorter review of the work undertaken reflects the assurance given by the depth of the previous review and the closure of this project in March 2015.

The support given to Gulu and Lira district councils consisted of the placement of two technical advisers within the councils to provide support to the technical administrative side (through the Chief Administrative officer) and the political side (through the Chair of the Council).

The work in Gulu continued to go from strength to strength with the appreciation of the work of the Technical Assistance (TA) evident in reports from the Chair and other staff, and the responsibility given to the TA. The diverse range of responsive assistance that he was able to provide cut across areas of governance and into new areas such as support for local revenue mobilisation (a plan for the Council was created), private sector development (work on the development of a Business Park was advanced through the TA) and service delivery monitoring (supporting Councillors to get into the field). The TA also provided support on pan-Acholi issues and to smaller district councils.

There is no doubt that the work of the Gulu TA helped the Gulu District Council attain the top spot in the Advocates Coalition for Development and Environment (ACODE) Local Government Scorecard, moving up one place from the previous year. In recognition of his effectiveness, and in response to demand, the Gulu TA’s contract was extended from September 2014 to March 2015. To ensure his continued support to the Acholi sub-region councils he was then recommended for and received a contract from April 2015 with the Governance, Accountability, Participation and Performance programme which DFID began to co-fund with USAID from December 2014. His role will enable him to continue to support Gulu District but also provide demand-driven support to all District councils in the Acholi sub-region. He will work alongside two other TAs providing similar support. For DFID this is a positive conclusion to a project we have continually assessed as high-performing.

The TA provided to Lira District council came to an end at the scheduled conclusion date in September 2014. Although he continued to be perceived as a valued resource for the Lira Council Chair, as reflected in a letter written to DFID asking for a contract renewal, DFID judged his performance to be disappointing. A failure to implement his duties over a number of months, combined with the submission of duplicate invoices showed carelessness in his work and even possible attempts to defraud. We assured the Lira Council Chair that we remained supportive of their work and would ensure GAPP provide them with support to achieve their goals- which they have been doing since late 2014. A visit to the Chair is planned with the next GAPP field trip to the Lango sub-region to assure him of our continued support in person, and listen to any concerns he has.

Our overall assessment of this limited scope TA programme is positive and it has provided an invaluable source of inspiration for the GAPP programme, especially the Gulu experience. DFID’s additional financial support plus the evidence from these two “pilots” convinced GAPP to recruit and post 3 TAs per sub-region to support district councils in a similar way to how the DFID TA project had been operating, spreading this model to cover 35 district councils, although at a somewhat lower level of intensity. Whilst this is a very welcome follow on to the project, we will need to reflect more critically on the reasons for Gulu recording greater success than Lira: including individual ability, broader context, or other issues.

In relation to the specific target of 21 sub-counties meeting minimum governance conditions, although this target was reached by last year’s PCDP annual review, no new data was available this year. It is likely that at least 21 would classify as having met the minimum conditions, but since it is not possible to confirm, this target has been judged as amber this year. The Accountability Adviser will obtain the final figures from the Government of Uganda.

Summary of responses to issues raised in previous annual reviews (where relevant)
The World Bank are planning an evaluation but it is unlikely to cover in sufficient detail the impact of DFID’s investment, especially as regards the construction of houses. As such, a separate small evaluation is recommended below.

The DFID investment in GAPP has taken place and takes into account lessons from the embedded TA approach. Extensions to the TAs were provided until September 2014 (Lira) and March 2015 (Gulu).

Recommendations
- DFID will need to engage with the WB/OPM Secretariat to ensure that an evaluation of the Community Infrastructure Rehabilitation component of NUSAF 2 takes place or – more likely – commission its own separate evaluation to explore this. The evaluation should look at value for money, usage and whether the presence of the houses has led to tangible benefits to the communities (Lead: MDG Team Leader)
- The IG’s office should undertake a proper analysis of its data on NUSAF-related complaints, providing information on how many cases have been resolved, by what method and in what time-frame, and a geographical analysis of complaints so “hot-spots” can be identified. Based on this assessment, the SRO should then consider if something along these lines should carried out under the new SUGAR project. The accountability adviser should conduct a visit to the IGG with the team responsible for TACC (Lead: MDG Team Leader and Accountability Adviser).
- It was not possible within the timeframe of this review to obtain updated data on the number of sub-counties meeting minimum governance conditions, so although it is highly likely the target has been met or exceeded, it remains amber in this review. We will obtain latest figures when these are available and add them to the logframe once known to confirm the status against the target (Lead: Accountability Adviser).
- We need to reflect more critically on the reasons for the Gulu TA recording greater success than the Lira TA to inform future similar interventions. Accountability Adviser to do this and submit to PRDP SRO by September 2015.

Output Title	The most vulnerable conflict-affected communities are rebuilt and empowered
Output number per LF		Two	Output Score	A
Risk:		Medium	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Baseline, Milestones, Progress
2.1 Numbers of Extremely Vulnerable Individuals/People with Specific Needs lacking access to social services, shelter & livelihoods in areas to which they return, resettle or reintegrate	Baseline 2009 Milestone 2010 Milestone 2011 Target / Planned 10,190 (total); 3,748 (M); 6,442 (F) 3,500 (Total); 2,205 (F); 1,295 (M) 0 0 / Achieved 3,500 (Total); 2,205 (F); 1,295 (M) 0 0
2.2 Number of labour hours worked on food/cash for work projects in Karamoja (attrib. to DFID)	Baseline 2009 Milestone 2012 Milestone 2013 Target / Planned 0 28m (14m F) 28m (14m F) 28m (14m F) / Achieved 23.9m 23.9m 23.9m
2.3 Conditional food transfers received by NUSAF2 participating households in Karamoja (metric tonnes, attributable to DFID)	Baseline 2009 Milestone 2012 Milestone 2013 Target / Planned 0 13,468 14,964 14,964 / Achieved 9,878 9,878 9,878
2.4 Number of Out-Patient Department (OPD) consultations and treatments in the 31 PNFP facilities per year (disaggregaged by male/female , and by age-group)	Baseline April 2011 to March 2012 Milestone I April 2012 to March 2013 Milestone II April 2013 to March 2014 Target March 2015 / Planned 21 RBF HF =210,708 10 IBF HF = 78,032 Total= 288,740 21 RBF HF =223,663 10 IBF HF =82,509 Total =306,172 21 RBF HF =237,714 10 IBF HF=87,322 Total =325,036 21 RBF HF=252,975 10 IBF HF=92,500 Total=345,475 / Achieved 20 RBF HF =186,851 (81,934 M, 104,917 F; 83,182 U5 and 103,669 Adults) ; 10 IBF HF =73,593 (28,416 M, 45,177 F; 22,220 U5 and 51,373 Adults). 335,854 20 RBF HF Male Female Total / U5 54,660 49,733 103,393 / Adult 52,433 97,093 149,526 / Total OPD 107,093 146,826 253,919 / 10 IBF HF Male Female Total / U5 10,732 10,448 21,180 / Adult 20,273 38,347 58,620 / Total OPD 31,005 48,795 79,800 / GD Total 138,098 195,621 333,719

Key Points
Outputs 2.1-2.3 relate to projects that are now closed so are fully covered in previous annual reviews. There is no additional detail to add in this review.

2.4 Number of OPD consultations and treatments in the 31 PNFP facilities per year (disaggregaged by male/female , and by age-group)
This component is on track to deliver expected results and learning. Previous annual reviews have identified the following achievements, and these persist:
- Separation of roles and responsibilities of purchaser, provider, and verifier of health services – this has improved accountability.
- There are some behavioural changes at PNFPs with some actively considering new ways to attract patients, including dissemination of information and reduction of user fees for key services; and
- The implementing partner has secured the buy-in of District Health Teams into the concept of results based financing and has trained them in verification methods.

In addition, the programme has delivered significant health services, contributing to health, wellbeing and poverty reduction in northern Uganda. Initial evidence gathered by the implementing partner (IP) suggests that the quality of health services provided by results-based facilities has improved, as documented – for example – by improved treatment of pneumonia. The project has improved the skills of district health offices to supervise and measure service delivery in a systematic way. The quality assessment tools have been gradually refined and improved over time. The IP has contributed important policy inputs to the debate taking place in Uganda about national health financing and results-based financing of health services, and the project has attracted international attention and is documented as a case study in DFID’s Payment by Results strategy. A lessons-learned workshop is planned for September 2015 at which the IP and the independent evaluation team will come together to share the impact evaluation findings alongside management lessons learned by the IP.

What are the key challenges of the programme?

There are many development partners working in health in Northern Uganda, making it hard to incentivise results-based funded health facilities to make the additional effort required to earn results-based funding, as they have access to significant resources from elsewhere that are not results-driven. This risks contaminating the experiment under this project and has required careful design of the impact evaluation to try and determine the attribution of the DFID funding to changes seen.

Although it is too soon to be definitive about the lesson and results of this pilot, there is a concern that the expense of managing and delivering the programme would not be realistic to consider at scale if national government leadership is required. Input-based funding may prove to be less effective than results based funding but also less costly to manage. Predicting the costs of managing results-based funding at scale is difficult due to concerns about capacity of the public sector to implement the rigorous approach needed, and further analysis of this question has been commissioned from the implementing partner and will be discussed at a national dissemination event scheduled for September 2015. This work involves the IP transparently evaluating and sharing the costs of managing the two different approaches in order for this assessment to be carried out.

There is a potential clash between DFID’s approach to fiduciary risk management and the results-based funded arm of the trial, where health facilities are paid on the basis of services delivered and not required to deliver a financial audit in return for funds received. The approach has not been changed for NU Health because to change the approach to managing one arm of the intervention in an impact evaluation would risk discrediting the impact evaluation sufficiently to mean that the investment to date in the evaluation (around £700,000) would go to waste. However, DFID’s Aid Effectiveness Team has committed to review how to reconcile the need for effective financial audit in payment by results, with the need to take a hands-off approach to recipients of funds, in line with the theory of results-based funding (where autonomy and discretion are given to implementing partners to enable them to develop innovative solutions to provide the services for which they are being reimbursed).

Staff turnover means a constant need to refresh understanding of how the facilities are reimbursed. In particular, poor financial skills lead to repeated non-compliance by facilities and they either lose funding or need to re-work and re-submit compliance inputs, taking up time and effort. In general, the financial and management capacity of facilities is weak and they can struggle to meet their expectations to provide financial audit.

Poor data collection by facilities continues to make the process of verification of results time-consuming and it is likely that facilities are delivering services for which they are eligible for compensation, but are unable to receive compensation because they have not recorded the service effectively.

Recommendations
Continue to monitor progress of the RBF mechanism here, gather lessons at the September lessons-learning exercise, and share these widely among the international community and with DFID. These lessons should include greater transparency and analysis of value for money questions, especially focused around the costs of managing the results-based financing component of the programme (Owner: MDG Team Leader)

Output Title	The private sector is revitalised and accessible employment opportunities are created
Output number per LF		Three	Output Score	A
Risk:		3.1 High, 3.2 Medium, 3.3 Low	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Baseline, Milestones, Progress
3.1 Number of applications for small grant scheme received and approved	Baseline 2009 Milestone 2011 Milestone 2012 Target 2015 / Planned 0 500 (received) 200 (approved) 1,200 (received) 800 (approved) 1,200 (received) 1,000 (approved) / Achieved 62 (received) 32 (approved) 363 (received) 273 (approved) 626 (received) / 426 (approved)
3.2 Number of YDP youth trained in a core vocational skill (s) relevant to local market opportunities	Baseline 2009 Milestone 2012 Milestone 2013 Target December 2015 / Planned 0 0 4,400 (35% female, 1,580) 15,400 (50% female) / Achieved 3,687 (49% female) 10,014 (49.4% female, 4.4% disability)
3.3 Youth trained in Business Enterprise Start up Tool (BEST)	Baseline 2009 Milestone 2014 Milestone March 2015 Target Dec 2015 / Planned 0 2,400 6,600 8,400 / Achieved 3556 7,167 Target date Dec
3.4 Percentage of respondents perceiving they have access to increased economic opportunity [disaggregated age/gender]	Baseline 2011 Milestone 2012 Milestone 2013 Milestone 2015 / Planned Acholi: 32% [M: 17%, F:15%]; Lango: 27% [M: 13%, F:14%]; West Nile: No data available; Karamoja: No data available. Acholi 42% Lango: 37% Baseline: West Nile; Karamoja Acholi 52% Lango 47% West Nile 34% Karamoja 29% Acholi 62% Lango 57% West Nile 44% Karamoja 39% / Achieved Acholi: 45% [M:24%, F:21%]; Lango: 41% [21%, 20%]; West Nile 24% [M:13%, F: 11%]; Karamoja: 19% [M:14%, F:5%] Partially achieved. Acholi 50%; Lango: 47%; West Nile: 26%; Karamoja: 33% Missed: / Acholi 38.4% Lango 38.8% West Nile 22.7% Karamoja 34.5%

Key Points

3.1 Number of applications for small grant scheme received and approved

The purpose of this £13m grant scheme programme was to support the creation and expansion of new businesses to drive job and income growth in Northern Uganda. Matching grants (requiring an equivalent 50% investment from the firm) were given to business enterprises to enable them pursue investment opportunities in a region recovering from conflict. The project and its funds were managed by the Office of the Prime Minister in partnership with PSFU.

The programme was suspended in November 2012 following the corruption scandal within the OPM. Activities were reactivated briefly under the direct management of PSFU in July 2013 to cover only outstanding commitments to beneficiaries, before final closure. £4,059,388 was disbursed in grants out of a planned total of £10.5million, and £986,706 was spent on management and administration costs. The final payment of £1,347,037 was approved in April 2014.The total cost of DFID’s contributions to PSFU was £5.046 million[2].
[2] This figure comprises a total disbursement of £6.996m, but of which PSFU returned 7.939 billion Uganda shillings due to early closure of the project. This returned amount was never re-converted into GBP but re-disbursed to other projects from DFID Uganda’s local Uganda shilling account. The GBP value of the retuned amount is calculated as £1.950m, based on the exchange rate of the days on which the returned monies were received.

The 2014 review noted PSFU had given grants to many businesses with insufficient assessment of their business expertise or the viability of the enterprise, and that monitoring and evaluation of had not yet produced strong evidence of efficacy or impact.

Subsequent to the 2014 Annual Review PSFU published an End of Project Report (Quest no: 4939970). It claims the project created 97,430 indirect jobs. However, the results figures are not credible as they rely only on estimates provided in grant applications by firms (see below for validation exercise during a field visit). Nine grants were described in the report, including three main case studies. The report noted the following lessons:

- Upfront financial contributions from beneficiaries improved commitment and success compared to those who made commitments in kind.
- Working through government (civil servants and politicians) threatened to derail the project.
- Conflict assessment was required to avoid precipitating conflict drivers.
- Business Development Services were important to build the capacity of enterprises to operate competitively.

The report also made some strong recommendations with regard to management of the suspension. These included the need for the implementing agencies reputation to be safeguarded in the event of suspension, for example, by including clauses in PSFU/grantee agreements with regard to the possibility and impact of suspension of funding.

The DFID Uganda Private Sector Adviser and Growth Team Deputy Programme Manager undertook a field visit in April 2015, in order to make some assessments of the impact of the grants made under PSFU. Beneficiaries were chosen on the basis of their location close to other field visits being undertaken at the same time in Gulu and Dokolo districts. They were then selected on the basis of those who returned phone calls. This provides a random element, although those willing to return calls and arrange visits are more likely to have had greater success.

From the limited review of these beneficiaries the following conclusions can be drawn:
- All five beneficiaries had somewhat credible business plans, and there was no evidence of misappropriation (although selection bias by those visited agreeing to meet would have applied) –equipment purchases were verified in place.
- Four out of five had suffered as a result of poor implementation and planning (both by themselves and by project implementers) – in respect of receiving delivery of equipment before other elements to operationalize it were in place (such as land title and electricity).
- Two out of the three which received equipment had not yet managed to operationalise it, indicating substantial risk of future benefit, and invalidating the ‘results’ reported based on their grant applications.

The numbers of jobs predicted by these businesses and reported by PSFU had not, therefore, materialised. One beneficiary visited had predicted 50 direct and 2000 indirect jobs, but the machinery had not yet been operationalised. A much lower figure had been given by a firm receiving technical assistance to install and sucessfully run existing machinery (15 direct and 50 indirect jobs), but field visit interviews indicated that these figures were also optimistic. There is also a question of attribution, and the scale of the benefit accruing to each beneficiary, many of whom would not have gained ‘jobs’ but merely an additional outlet in which to sell their produce. The real impact of the grants therefore remains unassessed. PSFU reported that the early closure of the project had prevented them from undertaking effective monitoring and evaluation activities. However, although results will not reach those reported by PSFU, the procurement of the stated equipment by the grantees visited indicate some positive current and future impact.

3.2 Number of YDP youth trained in a core vocational skillrelevant to local market opportunities
This component is delivered by Voluntary Services Overseas. Thekey indicator of progress for this project - the number of students trained in vocational skills is broadly on track. Indicator 3.2 is under target, but sufficient trainees are enrolled in current cohorts that this figure can be confidently assumed to meet the overall project target of 15,400 by the end of the project in December 2015.

A key issue is whether or not the skills provided are ‘market-relevant’. Overall, interviews with beneficiaries suggest that they are, and significant steps have been taken with Vocational Training Institutes to build their understanding of how to identify and respond to ‘market relevance’ in choice of course and curriculum, and in the delivery of ‘entrepreneurship’ skills. While outcome indicator 1 – Percentage of YDP youth with decent job – is not reaching its current target, this is due to an over ambitious and unrealistic target set at this level which wasn’t based on good evidence of what was achievable in this context. Even students who do not meet any of the three sub-criteria for this indicator may still have been equipped with ‘market relevant skills’. This should be examined in more detail in the final evaluation and project completion report.

The use of grants (worth an average of £750, or approximately 20 times the average monthly salary), provided to groups of around 15 graduates in the form of tools for vocations (woodworking or hairdressing tools for example) is not directly reflected in the output targets. Grants have been provided as planned but in many cases, the members of groups have fallen away, (as the number of tools provided could only adequately support one or two livelihoods) and the tools have been left to remaining members. This has proved a benefit in some respects, however, as the size of the livelihood opportunities represented by these tools may only be enough to support one to two graduates in many cases (though exceptional groups exist, and the tools in almost all cases appear sufficient and even necessary to support livelihoods). Given the non-sustainable and limited replicability of these grants, their utility relative to those who did not receive them should be properly examined in the evaluation and project completion reports.

3.3 Youth trained in Business Enterprise Start up Tool (BEST)
This component is delivered by Youth Business International and Enterprise Uganda. This indicator is clearly on track. The target of reaching 40% women is also on track – currently this is running at 45%. The target relating to youth involvement (6600 out of 8250 should be ‘youth’) has also been achieved (7167 youth beneficiaries have been included).

Beneficiaries met during recent field visits commended the quality and utility of the training, and corroborated the large numbers attending. DFID Uganda’s method of selecting beneficiaries at random from the training attendance lists also helped corroborate these figures (although only approximately 35% of randomly called beneficiaries were able to meet, this matched our initial expectation around those having their phones on them, answering them and being available).

Savings and investment clubs were reported on in detail during the recent quarter, and progress appears to be good with over UGX 150 million in savings (approximately £35,000) raised, and governance relatively sound. 11 clubs have managed to open accounts at financial institutions They benefit an estimated 350 people (around 5% of the total number of beneficiaries).

The highly positive initial estimates of the cost/benefit ratio of this activity require further examination but are likely to emerge following further analysis as positive.

3.4 Percentage of respondents perceiving they have access to increased economic opportunity

The final run of the Peace and Conflict Indicators under the ACCS programme revealed declines in the perception of access to increased economic opportunity across all districts except Karamoja, and results below target in all four regions. Although – as noted above – International Alert changed the groupings of regions in this iteration of the PCIs[3], they provided the data to us in the required format for reporting against the logframe targets for this review. The targets were Acholi 62%; Lango 57%; West Nile 44% and Karamoja 39%. The responses were Acholi 38.4%; Lango 38.8%; West Nile 22.7% and Karamoja 34.5% – lower across the board than the responses to a slightly different question on economic opportunities in the past two years in the PCI report itself. Several issues may be contributing to a perception that economic opportunities are decreasing, including the conflict in South Sudan which has hit both trade and remittances. In general, male respondents were between 7 and 10% more positive than female respondents in this indicator.
[3] The severely affected study areas comprise Acholi (Amuru, Gulu, Kitgum and Lamwo) and Karamoja (Abim, Kotido and Moroto). The sporadically affected study areas comprise Lango (Lira, Otuke) and West Nile (Adjumani, Arua, Yumbe and Zombo). The spillover study areas consist of Bukedi (Tororo), Bunyoro (Kiryandongo), Elgon (Mbale) and Teso (Amuria and Soroti). The control region comprises Kasese, Masaka and Mbarara districts.

A more detailed review of the ACCS programme has recently been conducted by a DFID-funded consultant. The review corroborates DFID concerns expressed throughout the programme’s lifespan that the methodology of data collection and reporting results in a very high-cost product in the PCIs. Compounded with the lack of a clear set of lessons drawn out of each iteration of the PCIs, or a broader advocacy and communication strategy, the assessment is that this area of the ACCS programme did not offergood VFM.

It is however important that any successor programme to PRDP should integrate a tracking and monitoring system for beneficiary perceptions of progress in peace, conflict, economic opportunites, government responsiveness and the North-South divide.

3.5 Other related interventions
Under PCDP DFID Uganda has worked with the Office of the Prime Minister on a major review of the Northern economy, establishing for the first time a set of economic accounts, modelling likely growth patterns, and recommending key intervention priorities. It was based on a widescale survey of business in the region. The final report, produced by Oxford Policy Management, was launched by the Prime Minister and First Lady at the bi-annual PCDP monitoring conference in April 2015. Its key findings are:
- The North remains highly disadvantaged in infrastructure, poverty prevalence, and in number of private businesses
- Northern businesses are typically isolated, trading within their own districts
- Northern Uganda would have to grow at over 10% a year for 25 years to catch up with the rest of Uganda.
- Northern Uganda does have key advantages in terms of land, geographic location to markets, and minerals, which represent significant economic potential
- Achiving the potential will require massive, coordinated and risky investments by government and private sector.

DFID has also supported the Office of the Prime Minister to develop the design of its PRDP 3 programme, with a renewed focus on employment and growth. Consultants from Delta Partnerships have produced a thus far well-received report, which is currently awaiting submission to cabinet.

Summary of responses to issues raised in previous annual reviews (where relevant)
A considerable amount of work has been done under output 3.2 to address issues raised in previous annual reviews. In summary:

An additional output has been included in the revised component log frame[4] to reflect the importance of achieiving sustained capacity improvements at the partner training institutions. Staff capacity has been built through monitoring visits, financial management support and project management meetings, and training in areas such as reporting and data managemententerprise development, and board governance).
[4] The component logframe does not have formal status under PCDP, but is used to govern and manage the project sub-component. No changes were required to the overall logframe.

- A gender toolkit was devised in July 2014, with an action plan for partners to work on and develop. Follow ups have been made to identify the actions arising and develop suitable indicators on that basis. Partners are now required to report against this on a monthly basis.
- Challenges remain to convince the partner staff that greater attention to gender related issues is required beyond provision of crèche and sanitation services.

Detailed market analysis has been tendered jointly through VSO and YBI (sister project).

Logframe reporting notes that 8 new courses in 5 institutions have been introduced in response to market demand. Enterprise managers are in place at all GWCs teaching youth how to make a business of the market relevant skills they’re learning. Enterprise training has also been delivered by Enterprise UG to instructors and key staff at YDP partner organizations.

The log frame has been revised in relation to literacy needs, and now provides a breakdown of the types of post training support. There are a number of synergy areas the three organizations are working on together, including the provision of training on entrepreneurship by Enterprise Uganda to key staff at YDP partner organizations.

On output 3.3, the previous annual review’s most substantive recommendations were to undertake improved market assessments, and improve targeting of youth and women. The first is reflected in a currently ongoing detailed market assessment survey study, and the second was undertaken in a variety of ways, and reflected in the achievement of youth and gender targets.

Recommendations

On output 3.1 (PSFU), DFID should consider further independent review of PSFU grantees(DFID owner: Private Sector Adviser – a decision to be made as PCDP overall evaluation planning is undertaken)

On output 3.2 (VSO vocational training) , and 3.3 (Enterprise Uganda entrepreneurial training), comparative, detailed and careful collection and interrogation of data, and a high quality evaluation are required to maximise lesson learning from the project in the remaining period..

On output 3.3 DFID staff should also make every effort to attend at least one or two days of the five day training in the final project period. Given the high apparent cost/benefit and effective delivery systems, consideration should be given to maximising results through a grant increase and/or extension (DFID owner: Private Sector Adviser)

In terms of output 3.4, although DFID should not consider continuing future funding of the PCIs, we should ensure through our advocacy around PRDP’s successor that a monitoring tool of some sort is incorporated – but not based on International Alert’s methodology due to the high costs (DFID owner: PCDP SRO).

Output Title	Government, civil society and communities can engage actively in peacebuilding and reconciliation
Output number per LF		Four	Output Score	A
Risk:		Medium	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y/N

Indicator(s)	Baseline, Milestones, Progress
4.1 Number of interventions and systems under PRDP modified to make them more conflict sensitive	Baseline 2009 Milestone 2013 Milestone 2014 Target 2015 / Planned 0 3 6 9 / Achieved 5 16
4.2 Number of men and women reached by legal aid service supported by DGF	Baseline 2010 Milestone 2011/12 (bridging period) Milestone 2013/14 Target 2016 / Planned 679273 women and men reached by the Legal Aid Basket Fund partners over a five year period (and an additional 3,002,000 reached by Platform for Labour Action's mediat outreach work). 220,000 women children and men reached. 1,500,000 women, children and men reached (and an additional 6,000,000 reached by PLA's media outreach work) 2,000,000 women, children and men reached (an additional 6,000,000 reached by PLA's media outreach work) / Achieved 1,419,548 Progress to date shows 95% of the annual target was reached in six months. Chances of reaching the annual target of 1,500,000 are high. Direct beneficiaries total up to 32,488 and indirect 1,387,060. 1,854,632 reached to date. Although no milestone was set for 2015, progress towards target indicates that strong progress. DGF is currently reviewing its logframe to include annual milestones.
4.3 % of Ugandan women and men satisfied with the role of traditional institutions. / 4.4 Proportion of respondents perceiving decrease in levels of competition and grievance between PRDP region and between north and south	Baseline 2013 Milestone 2012/13 Milestone 2013/14 Target 2016 / Planned Lango: 91%; Acholi: 97%; Teso: 41%; West Nile:50% 30,000 direct and indirect beneficiaries reached by DGF funded peace initiatives 100,000 direct and indirect beneficiaries reached by DGF funded peace initiatives Lango: 65%; Acholi: 72%; Teso: 40%; West Nile: 35% / Achieved N/A No target for 2015. Latest scores are: Lango 68%; Acholi 73%; West Nile 71%. / Baseline 2011 Baseline 2012 Milestone 2013 Target 2015 / Planned No data available Acholi:34% [M:18%, F:16%]; Lango 40% [M:22%, F:18%]; West Nile: 34% [M:19%; F:15%]; Karamoja: 30% [M:20%, F:10%] Acholi: 39%; Lango 45%; West Nile 39%; Karamoja 35% Acholi 45%; Lango 50%; West Nile 45%; Karamoja 40% / Achieved Acholi: 40%; Lango: 39%; West Nile:42%; Karamoja: 47%. Acholi 30%; Lango 29.9%; West Nile 39.5%; Karamoja 32.2%

Key Points

4.1 Number of interventions and systems under PRDP modified to make them more conflict sensitive
This indicator has been significantly exceeded. The influence of the programme on the ability of key stakeholders to address the four drivers of conflict (transitional justice (TJ), youth, gender and land) is most evident at the local level. ACCS has contributed to an understanding, responsiveness and engagement amongst district local governments and other key stakeholders in relation to the four key conflict drivers highlighted in the conflict analysis (land, youth, gender and transitional justice) and an increased understanding of the principles of conflict sensitivity – this includes both conflict sensitivity training provided to local governments in the early stage, and in the latter stage achievement and overachievement respectively of targets around advocacy products on conflict sensitivity and number of key stakeholders reporting increased ability to address land conflicts in a conflict-sensitive manner. Ongoing support will however be needed to sustain progress, further embed the approach and broaden engagement to a wider set of relevant stakeholders (including at sub-county level).

At a national level ACCS appears to have had some influence on the overall direction of PRDP, however this contribution was difficult to evidence. The external review of ACCS picks out their contribution through highlighting the importance of a focus on the ‘software’ of reconstruction and reconciliation as well as the ‘hardware’. In general, the Conflict Analysis was found to have been influential in framing a shared understanding and discourse on the key conflict issues (in particular the four key conflict drivers) amongst state, non-state and political actors at the national, district and community level. The PCIs also contributed to the evidence base of peace and conflict issues and trends in northern Uganda and their relationship to development interventions. ACCS was however undermined in the early years of the project by limited access and buy in from OPM to ACCS work and inefficiencies within the ACCS consortium leading to lateness in producing and engaging on important influencing products. During 2013, the lack of OPM coordinating structures undermined influence on PRDP.

ACCS engagement with national level policy frameworks and efforts to build linkages between national and local level stakeholders has during 2014 has gained some traction. ACCS contributed to an increased emphasis on youth and conflict within the National Youth Policy and a broader understanding of Transitional Justice issues within the TJ Policy. How far policies will translate into actual implementation and change remains unclear.

Engagement at a national level on land conflict issues has increased commitment to addressing local land issues in a conflict sensitive manner amongst a range of national level stakeholders (Uganda Wildlife Authority (UWA), Ministry of Land, key investors). Specifically, Saferworld has supported the ability of key stakeholders in Nwoya and Otuke to manage land issues in a conflict sensitive manner with some evident success in reducing tensions. Their accompaniment approach has been valued for being collaborative and pragmatic, placing local government in the lead and helping them build trust with communities and engage relevant stakeholders In Apaa, Saferworld’s intervention has shifted the attitudes and behaviour of a range of stakeholders, encouraging actors from both sides of the border to work together with a positive and consultative approach to border demarcation.

However, ultimately success has been limited. This was in part due to Saferworld’s inability to sustain support and monitor the situation as events unfolded (border demarcation) in order to build confidence amongst key communities. However, Saferworld also required a deeper understanding of the key drivers of conflict and dynamics among factors and key actors (including those entrenched political interests at a national level who use violence for political ends) and broad range of approaches to addressing these. A conflict sensitivity approach is not sufficient. Longer term engagement is required to bring about significant change on land issues and the time was too short to make a sustained difference. Any gains remain fragile.

The external review of ACCS found that progress in particular in the first two years of implementation was limited, not living up to its potential or expectations. This is largely attributed to delays in producing a foundational conflict analysis, insufficient traction gained with key stakeholders including OPM, and an unclear functional division of labour including a management model that did not include clear lines of accountability. The OPM case in 2012 further complicated the picture, with large changes in many PCDP interventions as a result of the aid suspension and suspension of many PRDP and PCDP projects. The external review also notes that in its initial phase, the ACCS partners International Alert, Refugee Law Project and Saferworld, did not hold a common understanding of the concept of conflict sensitivity, or indeed the theories of change behind the intended programme outcomes/impact.

DFID and an external reviewer provided the impetus behind a change in the programme’s focus towards the four conflict drivers identified in the ACCS Conflict Analysis (land, gender, youth and transitional justice), assigning a thematic lead from within the consortium for each one. This had a positive effect and was assessed by the external reviewer as increasing ACCS’s relevance, addressing more directly Strategic Objective four of the PRDP (peacebuilding and reconciliation), and directly and clearly focusing on conflict drivers emerging as a legacy of conflict (land, gender relations and youth). ACCS began to emerge as a true consortium in its final year, drawing on each other’s strengths when advantageous for example through access to each other’s networks or common platforms. This led to some stakeholders consulted in the external review describing the consortium as having a ‘strong collective voice.’

The partners have significant work to do in evidencing change, even if this is widely understood to be challenging in their areas of operation. Nonetheless, the use of theories of change, supported by a robust monitoring framework, would have made this significantly easier. With the possible exception of Saferworld, there was limited focus evident on outcome reporting. However, the programme remained dogged by challenging relationships, to varying degrees, with the Government of Uganda counterparts.

Research conducted by the consortium was in general of a fair quality, with one or two products, the Conflict Analysis in particular, being taken up and visibly influencing key stakeholders. However, many of the research products suffered from being overly long and analytical, without clear, implementable recommendations. This may explain inconsistency in and a disconnect between the research carried out and subsequent advocacy, which was in some areas (transitional justice) probably more effective, but in others (PCIs) less effective in influencing processes and stakeholders, especially at the national level.

4.2 Number of men and women reached by legal aid service supported by DGF
Indicators 4.2 and 4.3 are drawn from the the Rights, Justice and Peace (RJP) component of the Democratic Governance Facility (DGF). The DGF is a multi-donor basket fund with contributions from eight donors including the UK, Austria, European Union, Denmark, Ireland, Netherlands, Norway and Sweden. The purpose of the DGF is strengthened democratisation, protection of human rights, access to justice, peaceful co-existence and improved accountability in Uganda. Support to the RJP component under PCDP is £5.58 million from 2011-2016, which is aimed at supporting civil society organisations to engage in dialogue at local and national levels, on peace building, access to justice, human rights and transitional justice as well as to work with Government of Uganda on the development of policy and legislation.

In response to significant outstanding conflict issues hampering recovery in the Northern Uganda (lack of transitional justice, land conflicts, sexual and gender-based violence (SGBV)), RJP support is targeted at giving 40% of the people in Northern Uganda access to legal aid services, enable access to local decision making, human rights awareness and facilitating policy discussions between Ugandans and elected officials.

Each year, the DGF contracts an external review to cover progress against its logframe milestones and targets. This year’s DGF review notes that there is evidence that a number of changes in legal aid service delivery have occurred in 2014/15. The package of services to the poor is now more comprehensive; there is a clearer referral pathway between advice and dispute resolution; there is a closer working relationship between legal aid providers and justice and/or local government systems; there is increased visibility, validation and legitimacy for DGF Partners providing legal aid services; and the range of services provided to special interest groups has expanded.

During the reporting period, the DGF legal aid programme increased geographical coverage for legal aid services from 58 to 67 districts (of which 29 are in the PRDP region) providing a range of services including legal advice, representation, alternative dispute resolution (ADR), legal and human rights awareness and prison decongestion. There is evidence of provision of services to special interest groups - women, children, disabled and partner coordination and capacity development.

This year, a total of 59,976 (45,999 men and 13,977 women) accessed direct legal aid services in 67 districts. The Pro-bono Project of the Uganda Law Society enlisted and utilised the services of 1,053 registered advocates to the cause of the poor in the justice system. A total of 1,068 children were diverted out of the the formal criminal justice process (to serve alternate community service sentences) by the Legal Aid Clinic of the Law Development Centre.

Indirect beneficiaries of DGF partner programmes totaled 1,854,632 men, women and children, who benefitted through legal and human rights outreach programs in the communities; information, education and communications materials; radio programs and spot messages. Indirect beneficiaries (1,854,632) are calculated in line with the estimations made in the Legal Aid Basket Fund evaluation report done by the Law & Development Partnership (LDP) in September 2011 and Baseline Study carried out in July 2013, depending on the nature of the activity:
- Awareness, sensitisation – the actual number of people who attend the awareness/sensitisation session.
- SMS messages – actual number of people receiving the messages.
- Each radio/TV program or spot message reaches 100 people.
- Each booklet reaches 2 people.
- Each poster reaches 10 people.

4.3 Percentage of Ugandan women and men satisfied with the role of traditional institutions.
Progress against this indicator is measured by the DGF baseline survey and DGF partner reports, with progress in reaching the final target to be measured by the DGF endline survey. Although there is no formal milestone in 2015, progress has been measured by partner reports.

Reports have noted a decline in satisfaction with traditional institutions in Lango and Acholi, and an increase in the level of satisfaction with those in Teso and West Nile. The DGF attribute the decline in the level of satisfaction in Acholi and Lango to the internal clashes in the cultural institution cultural institution KerKwaro Acholi (KKA) and in the Lango Cultural Foundation (LCF). KKA has faced considerable criticism internally and from external stakeholders alleging mismanagement of funds (DGF has ended its partnership with them over this issue). The Lango Cultural Foundation is divided into two parallel factions, with two Paramount Chiefs claiming leadership. Internal troubles have reduced the credibility and respect for the respective institutions within their constituents. The declining satisfaction with the role of traditional institutions in the transitional justice process may be related to a declining trust in traditional institutions overall.

Beyond the formal reporting against logframe indicator 4.3, several other PCDP interventions are of relevance to output 4, as they work to promote efforts at peace and reconciliation. Under the RJP and ACCS component, the Outreach Team of RLP’s National Memory and Peace Documentation Centre (NMPDC) supported a joint memorial prayer with the victims and survivors of the Omot massacre, in Omot, where the LRA abducted and wounded and mutilated its victims. Significant progress was made in the ‘forgiveness in peace building research’ being conducted in collaboration with University of Notre Dame, USA. During the reporting period, 5 community outreaches, were also conducted by RLP under DGF support, reaching over 600 people, to promote local justice approaches and initiatives, especially on land justice, in collaboration with the Pawel and Patiko Clan Chiefs, which is increasingly embraced by the locals. ACCS also continued its critical work with groups of survivors of the conflict across northern Uganda, and organised a National Reconciliation Conference in Kampala, attended by some 350 people drawing on national and local government, cultural, religious and civil society leaders. ACCS also launched its Compendium of Conflicts: the first attempt in Uganda at a definitive compiliation of conflicts to inform the debate and healing process.

Under the DGF, the Centre for Women in Governance carried out monitoring activities for the implementation of the Uganda Action Plan on United Nations Security Council Resolution 1325, 1820 and Goma Declaration. As a result of the monitoring exercise, from a sample of 20 districts in Uganda, a report was produced which noted that despite Uganda having one of the most gender-sensitive constitutions in the world, cases of domestic violence have increased of 18.4% and defilement continues to lead in sex related crimes in 2012 and 2013. The report makes recommendations among others to intensify funding allocation and action to address SGBV.

There have been challenges reported associated with political pressure on CSOs especially those working on sensitive issues at national and district level, which in recent months has become more actutely clear with developments regarding the draft NGO bill. DGF-funded interventions should work more closely together to monitor any constraints in the operating environment and seek support from DGF and its donors where necessary.

The DGF logframe indicators (including indicator 4.3) are excessively reliant on the population level perceptions survey, and concerns are that improvements or deteriorations in these measures cannot be attributed to DGF and also rely on policy changes (such as adoption of the Transitional Justice policy) which are outside DGF’s influence. These concerns will be addressed in a review of the DGF logframe.

Summary of responses to issues raised in previous annual reviews (where relevant)
The 2014 annual review recommended that DFID focus ACCS’s activities to enable it to increase impact at local and national levels, to move on influencing the Youth Policy and Action Plan, and to take forward work on land and/or minerals.

In the 9 months between that review and the end of the ACCS programme, DFID invested significant time in redirecting and refocusing ACCS through considerably increased engagement with the consortium and by revising their workplans. The final review of ACCS concludes that they have had some progress on the Youth Policy and Action Plan, with the drafts before Cabinet containing (in some cases verbatim) recommendations from ACCS. DFID also agreed work with Saferworld on land conflict hotspots.

Saferworld has supported the ability of key stakeholders in Nwoya and Otuke to manage land issues in a conflict sensitive manner with some evident success in reducing tensions. Their accompaniment approach has been valued for being collaborative and pragmatic, placing local government in the lead and helping them build trust with communities and engage relevant stakeholders. In Apaa, Saferworld’s intervention has shifted the attitudes and behaviour of a range of stakeholders, encouraging actors from both sides of the border to work together with a positive and consultative approach to border demarcation.

However, ultimately success has been limited. This was in part due to Saferworld’s inability to sustain support and monitor the situation as events unfolded (border demarcation) thus building confidence amongst key communities. However, Saferworld also required a deeper understanding of the key drivers of conflict and dynamics among factors and key actors (including those entrenched political interests at a national level who use violence for political ends) and broad range of approaches to addressing these. A conflict sensitivity approach is not sufficient. Longer term engagement is required to bring about significant change on land issues and the time was too short to make a sustained difference.

Recommendations
DFID to consider future support to land conflict, as well as more broadly to bilateral support in the area of conflict. (DFID owner: GSH Team Leader)

Amend the PCDP Logframe to reflect updated changes of DGF Logframe (indicators, milestones, assumptions). (DFID owner: PCDP SRO)

Amend DGF logframe, In particular, align indicators with the post-Juba peace process outcomes. DFID DGF Steering Committee representative to propose this work be undertaken.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
The major costs drivers vary by component and include trainings, management fees, staff costs, office administration overheads, travel expenses, programme evaluation costs, conferences/workshops, office equipment, information and technology equipment, and building of houses.

Overall, the programme is delivering slightly under budget, with more details in the section below on financial performance. Cost drivers are monitored within the delivery of individual PCDP components and DFID staff working on these programmes ensure that any pre-agreed ceilings are not exceeded, as well as tracking any contextual shifts that could impact on the relative significance of the different cost drivers.

VfM performance compared to the original VfM proposition in the business case
There is regular monitoring of programme delivery by implementing partners and DFID to ensure that funds are used for intended purposes and as per approved work plans and budgets. Regular audits are conducted on the use of DFID funds by implementing partners in accordance with the funding arrangements in place. A range of partners are used across PCDP including multilateral financial institutions, national and international NGOs and commercial consultancy firms.

The original programme memorandum made the assumption that the total investment of £100m would deliver economic benefits worth 2.5 times the cost of the programme, based on the following assumptions:

1. Improvements to health and education outcomes due to construction of health workers and schoolteachers houses
2. Improvements to governance conditions (reduced leakage through corruption)
3. Jobs created through private sector grant scheme
4. Increased employability and opportunities for young people
5. Social support provided to the extremely vulnerable

Without revisiting the detailed cost benefit analysis it is clear that some of these assumptions have changed or have not been met, whilst others remain valid.

On A – improvements to health and education – this assumption still stands. The evidence collected to date on the construction of houses suggests that it has incentivised better attendance by the targeted beneficiaries, however this is anecdotal in nature, gained largely by DFID staff on field monitoring visits. This will be further investigated through an evaluation, most likely a focussed evaluation commissioned by DFID to work alongside the World Bank’s planned broader evaluation NUSAF2.

On B – improved governance conditions - it was envisaged that DFID would contribute to building capacity both of local government (through the Uganda Local Governments Association (ULGA)) and central government (through contributions to PRDP2 sector budget support). In 2013 the decision was taken not to provide sector budget support (due to the OPM corruption case) and technical assistance to OPM was withdrawn. The ULGA project also received a qualified audit.

Work on local govenance has proven more successful and DFID is now taking forward this work in partnership with USAID through the Governance, Accountability, Performance and Participation programme (GAPP) under follow on support to a separate programme. There is quantitative and qualitative evidence that the technical assistance DFID supported at local level (through ULGA and the TA to Gulu and Lira) has made a significant impact in improving governance, government performance and management of finances and did provide excellent value for money. This is most evident in Gulu reaching and retaining the top position in the Local Government scorecard. Nevertheless, the overall success to date on improving governance conditions is, for a programme the size of PCDP, relatively modest (albeit in a challenging context), and successes that have been recorded have been rather localised in their nature.

On C – jobs created and D – increased opportunities for young people - the original assumption in the programme memorandum was that the grant scheme would create 9,800 jobs over five years. The assessment earlier in this review questions the scale of job creation claimed by PSFU (either 58,000 or 97,000 jobs created), while not entirely discounting some success. Further assessment will be required to confirm the extent of job creation. YDC and NUYEP are both delivering well and look to meet the targets for numbers trained. Where it is less clear that they will be able to meet targets is around the number of youths ending up with a ‘decent job’ following training. As mentioned earlier, this indicator is will be amended to be based on something more evidence based and realistic. Evaluations are also planned to compare VfM across the two interventions and also attempt to benchmark across similar skills projects in Uganda, and potentially worldwide.

E – social support to the most vulnerable - this assumption, which relates to the work undertaken by the office of the UN High Commissioner for Refugees (UNHCR) to resettle extremely vulnerable individuals and persons with special needs from internally displaced persons (IDP_ camps back into their communities and improving access to income-generating opportunities to moderately insecure households in Karamoja, remains unchanged. Activities have been completed and original targets achieved.
Commercial Improvement and Value for Money
Overall, in 2014/15 DFID disbursed PCDP funds on the basis of approved and detailed costed work plans with clear results indicators and targets. Regular monitoring trips were also carried out to ensure that programme components continue to deliver the envisaged results at set costs.

DFID has followed open competition principles in all procurement processes within the PCDP. All contract opportunities under the WB NUSAF2 programme and youth development programmes were advertised, following which submitted bids were evaluated and contracts issued on competitive basis.

A number of implementing and downstream partners under the programme were chosen through competitive bidding. The procurement of goods and services under the various components of the programme was done through competitive bidding. Audits have identified action plans to strengthen procurement practices. In addition, DFID has held sessions with Implementing Partners to explain value for money and strengthening procurement processes.

Role of project partners

DFID Uganda: Oversees the delivery and implementation progress of the various components to ensure that the programme delivers intended results according to approved objectives and work plans. DFID’s oversight also ensures that emerging issues are promptly addressed.

WB Bank and TST/OPM: The WB receives and manages DFID funds for building houses for teachers and health workers and ensures that DFID funds under NUSAF2 are used for intended purposes. The WB conducts regular procurement audits, financial audits and project implementation supervision missions and regularly meets with DFID on progress. TST/OPM is the implementing agency for the project.

VSO manages DFID’s funds and contracts Gateway Centres that are used to implement the Northern Uganda Youth Development Programme (YDP). VSO provides financial and technical oversight of YDP delivery. In addition to training youth in vocational and life skills, Gateway Centres also manage sub-grantees in implementing the programme.

YBI/EUg. YBI holds management responsibility for the use of DFID funds while EUg operates as the implementing partner of the Youth Employment Programme.

ACCS: Conducts annual peace and conflict impact assessments, carry out conflict-sensitivity interventions and advocacy for consolidating peace in the north.

Technical Advisers: They provide technical assistance to the Chairs of Gulu and Lira LGs.

DGF: DGF is mult-donor, multi-component basket fund/facility that works through project partners to implement activities across a range of governance issues. The DGF team perform a range of tasks including assessing proposals, conducting due diligence on implementing partners, monitoring and evaluating progress, and audit of funds to implementing partners.
Health Partners International (HPI)/Montrose: The implementing partner of the Results based financing experiment with PNFPs. It provides a rigorous and high quality management function to the programme.
Liverpool Associate School of Tropical Medicine (LATH): They are conducting a fully independent impact evaluation of the Results-based financing of the NU Health programme.
Private Sector Foundation of Uganda: they have completed their contribution, comprising management of the business grant fund
Oxford Policy Management: contracted to deliver the Northern Uganda Economic Recovery Analysis
Delta Partnerships: Currently contracted to provide TA to support the PRDP 3 design and planning document for Office of the Prime Minister.

Assessment of whether the programme continues to represent value for money
It is challenging to assess the overall vfm of the overall programme, but this will be attempted as part of the final review. Attempts are however being made to ensure that individual components represent value for money in their own right. There are some concerns about the administrative/operational costs of some of the remaining or recently closed components particularly NUSAF and NU Health. The NUSAF costs will be looked into further, but in part relate to the heavy monitoring and assurance burden of the structures put in place to monitor fiduciary and corruption risks.

There is no doubt that the management and administration costs of the NU Health programme are high as a proportion of the overall costs of delivering the programme compared to other programmes. Previous annual reviews have said that “the double layers of management and budgeting by HPI and Montrose make it difficult to isolate the intervention’s cost from the support and management costs. The milestones could be revised to clearly distinguish between these costs which will help in undertaking the value-for-money analysis. The real question about VFM in this programme is whether results-based financing delivers good quality health services at a lower cost per service delivered (or even better, per health gain achieved) than input-based financing, but this will not be assessed until the evaluation survey final round is complete in September.

The NU Health team provides a very rigorous and high quality management function which was procured through a fully competivite market procurement and early indications are that the close attention paid to what the health facilities in the programme deliver has resulted in significant gains in quality and quantity of health services provided, and has encouraged innovations by those health facilities – for example, health facilities that are rewarded on the basis of the number of children they immunise are conducting immunisation outreach at local churches on Sundays. So the early indications are that the programme is very well managed and having an impact – ie, it is effective.

The efficiency with which services are provided will be assessed as part of the evaluation, as described above, and we have asked the NU Health team to collect data on facility sources of revenue and facility outputs broken down by facility type, for use by the evaluation team as part of their final evaluation report to be provided at the end of August. This assessment will look at the costs for facilities only and will compare input-based and results-based facilities. However, a further question is whether service provision is efficient once the costs of the management agent are factored in, and we will ask the evaluation team to conduct this assessment as well, using a rough rule of thumb about allocation of the costs of the management agent to input-based and results-based facilities.

We will have better information about equity when the evaluation has been completed.

The ACCS review goes into detail on the value for money achieved by that programme so it is possible in this review to say more about this component in this review. It found that both Saferworld and International Alert reported systems to ensure that programme related goods and services were competitively priced and to ensure budget compliance. Refugee Law Project did not. The fact that the programme came in slightly over budget overall with no prior agreement from DFID, suggests that, even where they existed, these systems were not optimal.

The review also found limited evidence of value for money considerations as a factor guiding overall decision making within the consortium. Efforts were made by DFID to mitigate the misuse of UK funds through undertaking regular spot checks of the three organisations. DFID also made efforts to scrutinise budgets to ensure expenditure was in line with needs and to rationalise requests leading to significant cost savings.

Factors undermining the programme’s efficiency and effectiveness limited the value for money of the ACCS programme during the first two years of the programme. From 2012/13 increased effectiveness and efficiently through enhanced strategic focus and working relations and resulted in the programme representing better value for money during the remaining years. In general, however the potential return on investment (in terms of influence) was undermined to an extent by inadequate attention to follow up of reports and products with consistent levels of targeted advocacy. The return on investment of certain activities during this period, e.g. Saferworld’s land work, will have been constrained by the fact they were unable to sustain their intervention.

Quality of financial management
PCDP, together with its reprogrammed and reoriented components is on track against its financial and results forecasts. The programme spend against forecast in 2014-15 was 75%. The shortfall was predominantly due to four budget lines where reimbursements to DFID were made during the year, represented as negative spend in the table below. Removing these reimbursements from the calculation, actual spend was 98.6% of forecast. Full details of how each component performed against its forecast are available in the table below:
Component	Forecast (£)2014/15?	Actual Spend (£)
NUSAF II World Bank - resource spend for administrative reform	0	-2,200,000.00
Advisory Consortium on Conflict Sensitivity - Accountable Grant	1,134,271.00	1,134,271.00
Uganda Local Governments Assocation - strengthening Gulu & Lira councils	19,647.11	17,989.73
Private Sector Foundation Uganda - Small Grants Scheme for Northern Uganda	0	-12,352.78
Peacebuilding and Reconciliation in Northern Uganda	1,210,000.00	1,210,000.00
Advisory support, research and evaluation for northern Uganda	82,210.59	66,979.20
Uganda Investment Authority - economic analysis in northern Uganda	21,324.71	21,278.64
Youth skills and employment in northern Uganda - on-budget spend	0	-358,704.18
Improving access to healthcare in northern Uganda	4,866,891.58	4,750,572.51
Direct procurement of goods for recovery in Northern Uganda	-22,987.28	0
Youth Development Programme - Voluntary Services Overseas	3,702,982.00	3,702,982.00
Response to the Nodding Syndrome outbreak in Northern Uganda	1	0
Impact evaluation of a DFID programme to improve access to healthcare in northern Uganda	80,000.00	-20
Northern Uganda Youth Entrepreneurship Programme (NUYEP)	838,902.00	838,902.00
Payment of Liabilities incurred by Private Sector Foundation Uganda prior funding freeze to the Office of the Prime Minister	0	-390,646.89
TOTAL	11,933,242.71	8,781,251.23

Date of last narrative financial report	Dates vary by PCDP component
Date of last audited annual statement	Dates vary by PCDP component

E: RISK

Overall risk rating: Medium

Overview of programme risk

The table below provides an overview of risks across the components of the programmes. Component-level risk matrices are contained within delivery plans for each component which were drafted in April-May 2015.

Risk	Status and mitigating action	Impact/Probability
The absence of final peace agreement between LRA and the GoU and the likely return of the LRA in Uganda	DFID monitors the attitudes of both LRA and GoU through ACCS and news media. ACCS conflict analysis concluded that it is highly unlikely that the LRA will return to Northern Uganda.	High/Low
Conflict emerges in Northern Uganda	While ACCS peace and conflict analyses identify some key conflict drivers in the north, the evidence suggests that a resumption of widespread conflict remains unlikely.	High/Low
The uncertain status of peace, security and stability in South Sudan/DRC and Kenya leading to unstable northern Uganda.	The break out of conflict in South Sudan has led to the influx of South Sudanese refugees in northern Uganda. However, this has not resulted into any large scale instability of Northern Uganda. There are however local level tensions between host communities and the arrivals from South Sudan. The political situation in South Sudan continues to evolve with GoU playing an important stabilising role. DFID continues to monitor the situation in both Kenya and South Sudan.	Medium/Medium
Lack of political will within central government to support local government institutions	The 2012 OPM corruption scandal and the suspension of financial aid to GoU by donors has resulted in GoU having less resources with which to support local government institutions. As a result, the credibility of central government has been undermined at LG levels that increasingly believe that OPM role under PRDP be limited to monitoring and not include implementation.	Medium/Medium
Supplementary resources from GoU are inadequate and OPM does not use DFID funds for intended purposes	Currently DFID does not provide support to Northern Uganda through GoU systems. Suspension of financial aid to GoU by donors has meant that GoU has fewer resources available to support post conflict recovery in Northern Uganda through PRDP grants to the districts.	High/Low
Failure of youth development programme to secure employment creates tensions and resentment	Given the broad satisfaction with this project from beneficiaries and communities, this risk is now considered low.	Low/Low
Private investors do not respond to grants scheme due to fear of socio-economic tension and instability / Private investments do not create the intended socio-economic outcome / Grants scheme is politicised	As a result of the 2013 Annual Review and the OPM corruption scandal, DFID suspended financial aid to GoU and closed this component of the programme. Currently, DFID has settled liabilities wth SMEs that arose from the implementation of the component prior to aid suspension through an Accountable Grant with PSFU. Over the course of the year, DFID received a substantial reimbursement from PSFU and this is now closed.	Low/Medium
Uganda Investment Authority (UIA) economic recovery analysis is inaccurate and misguides economic recovery	When the quality of the first phase of the economic recovery analysis was unsatisfactory, DFID terminated the contract with UIA in 2012. The second phase of the work has been contracted to Oxford Economics through competitive bid. The report has been presented to OPM and MoFPED and formally launched, to an extremely positive reception. There are already signs of the new ERA influencing the policy debate in this area.	Low/Low
Building of houses for teachers and health workers causes health and environmental damage	World Bank/NUSAF2 project hired environmental specialists who provide oversight and guidelines so that environmental and social safeguards are put in place for every sub-projects under the project.	Medium/Low
The physical progress on teachers and health workers houses do not reflect the level of funds disbursed from DFID	DFID contributions have finished, and the agreed number of houses have been constructed and handed over. DFID’s focus is now on accountabilities.	Medium/Low

Risk of funds not being used as intended

Following the 2012 corruption scandal in the Office of the Prime Minister involving funding meant for the PRDP and for PCDP, DFID indefinitely suspended all budget support to Uganda and reprogrammed most financial aid. This included reprogramming a number of the components under this programme. The risk that DFID’s funds could be misused still exists given the operating environment, however no funds under this programme are currently channelled through GoU systems and DFID has further increased its vigilance in monitoring, assurances, and scrutinising accountabilities and requests for payments. For all PCDP components, systems have been assessed and established to minimise the risk that funds will be misused or diverted. Some specific localised fraud cases have come about during the reporting period which have all been investigated and followed with DFID’s Counter Fraud and Whistle Blowing Unit.

Climate and Environment Risk
Of all the existing interventions under PCDP, NUSAF is the component that carried some environmental risks given the construction element of that component. The environmental impacts of the other interventions at community level are marginal and widely dispersed as they do not entail large economic activities or land acquisition; they also do not undertake significant civil works.

Under the NUSAF2 component, DFID funded the building of teachers’ and health workers’ houses. Construction of new housing can lead to poor sanitation if there are insufficient toilet facilities for the workers. Other environmental risks include land uptake; loss of vegetation; risk of soil erosion and runoff; management concerns over construction debris and poor restoration of material extraction sites; and risks associated with transportation of construction materials. NUSAF2 has environmental and social safeguard specialists who oversee the environmental sensitisation and assessments of the various sub-projects under the project.

DFID’s role in the environmental management of these components of the PCDP has been one of entering constructive dialogue with World Bank on the environmental impacts of interventions so that social and environmental safeguards are put in place. For NUSAF2 the matter is frequently raised during the WB project implementation supervisions and reflected in the Aide Memoire. Supervision has ensured that the requisite standards have been followed.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe
Delivery of PCDP’s planned outputs and outcomes is broadly proceeding according to the revised timeframe. However, in a programme of this size it is impossible for performance to be uniform. Where delivery has not been aligned with plans, this has usually been because DFID has chosen to end activities, for example with PSFU. Indeed, some components including NU Health are proceeding ahead of planned timeframe on achieving some output milestones.

It is also noted that for some components, not all partner disbursments were made as planned. For example, with ACCS, repeated late and poor reporting from the implementing partners resulted in quarterly advance payments by DFID sometimes being made 1-2 months late.

Performance of partnerships
A range of partners are being used to carry out PCDP’s activities. These include small Ugandan NGOs and CSOs, international NGOs and some commercial organisations. In some cases DFID is contracting these partners directly, but with most is doing so indirectly. Where any issues arise with partners, performance against particular outputs, more structured field/asset visits or reviews, these are addressed. In cases where performance reflects more serious challenges, budgets and activities are either redirected or – as in the case of PSFU – halted. While this review does not go into the detail of all partnerships, individual component reviews provide additional detail.

A reflective exercise was undertaken at the request of the DGF Board last year. They carried out a light touch assessment of all 83 DGF Partners including the 26 supported by PCDP. Of the 26, six were identified as performing excellently and plans have been made to intensify DGF’s engagement with them. 17 partners were identified as meeting expectations and three partners were found to not be meeting expectations. In response, DGF has increased its capacity development support to key partners and providing training to partners on financial management and reporting against results.

Summary of DGF light touch assessment results
	Excels	Meets expectations	Needs improvement
Rights, Justice & Peace	6	17	3
Total partners (RJP)	26

Asset monitoring and control
In line with DFID guidance, each PCDP component maintains an asset register and regularly monitors this through a combination of routine field visits and specific asset spot checks. Details of these are saved on Quest in the form of back to the office reports, and further details are also available in component-level reviews and delivery plans.

G: CONDITIONALITY

Update on partnership principles
Following the 2012 OPM corruption and the suspension of financial aid to GoU DFID stopped delivery of any component of the PCDP through GoU. Whilst no component of PCDP is being delivered through GoU, implementing partners are still required to demonstrate consistent strong financial management and accountability and the programme is still aligned against Government plans and targets. We continue to monitor the Partnership Principles in relation to this programme - particularly the trends in commitment to poverty reduction and human rights - and while there are some areas of concern, they do not have a direct impact upon PCDP activities. We will continue to monitor these trends in the next year and where necessary take actions to mitigate risks to achieving the programme’s objectives and where possible use programme activities to advocate for improvements in Partnership Principle commitments.

H: MONITORING & EVALUATION

Evidence and evaluation
## Evidence on conditions in the North: According to Uganda Bureau of Statistics (UBOS) National Household Surveys, poverty in northern Uganda has dropped from 60.7% in 2005/6 to 41.8% in 2012/13. However, the region continues to remain marginalised and is still the poorest part of Uganda as compared with the national poverty average of 19.5% (Year 2012/13). Because Northern Uganda is still marginalised and poor, programme interventions and the geographical focus of the programme still remains relevant.
## Evidence on PCDP delivery models: Following the 2012 OPM corruption scandal, DFID terminated funding to NUYDC and OPM. This led to the suspension of the PCDP Steering Committee which was chaired by PS OPM and a reprogramming of the youth development component of the programme. Following the 2012 Annual Review findings and suspension of funding to OPM, the grants scheme component was cancelled however DFID agreed to honour the outstanding liabilities incurred by the component through an Accountable Grant with Private Sector Foundation. Moreover, DFID restructured the PCDP so that monitoring and delivery of various components are undertaken through the three DFID programme teams. As the findings of this Annual Review shows, leadership on each component by the various lead advisers has led to improved performance of the individual components.

NU Health: The evaluation under NU Health is on track. The third and final survey is underway. A thorough independent peer review of the evaluation team’s midline report was completed and they have refined their approach accordingly, including adding more qualitative research so that we can understand not just the impact of different financing approaches on what health facilities deliver,but also the management choices they make in how they deliver. The team has also invested in handheld electronic devices with which to collect data from facilities and benefi ciaries for the final round of the evaluation. This is expected to reduce the time for data cleaning and entry significantly, therefore reducing costs and increasing the speed with which the endline report can be generated, due in September.

## NUSAF2: There is currently little evidence of the benefits resulting from the construction of the houses save from the Citizen Report Card that was carried out in 2013. Terms of Reference for an evaluation of the Community Infrastructure Rehabilitation component of NUSAF have been developed. However, it is unclear whether or when this evaluation will take place as the contracting process has started and no clear date has been set on when this will happen. A World Bank evaluation is being prepared, but as mentioned earlier in this report, DFID will consider commissioning its own separate evaluation to understand the impact of our investment.

ACCS: A final review has been carried out. The main lessons and conclusions are listed above under the outcome, output and VFM sections of this review. It was decided that a full evaluation was not necessary, but the review stands to draw out important lessons which we will share within the relevant DFID communities and with the implementing partners.

DGF: With the current phase of the DGF coming to a close end of 2016, development partners intend to extend their support to DGF I to 2017. The DGF extension phase will be used to:

- Evaluate the impact and effectiveness of DGF I (including RJP) and assess whether quality and quantity in terms of Theory of Change, programme structure and strategies, partnership portfolio and results achieved are satisfactory and adequately aligned to the political and governance realities prevalent in Uganda.
- Conduct political and programme analyses as well as a CSO diagnostic study.
- Drawing on insights of the Evaluation and lessons learned, design/formulate and appraise a new five year phase of the DGF II starting January 2018.

PFSU/Youth: An evaluation is planned to cover the two youth training initiatives of VSO and YBI/Enterprsie Uganda. This will interrogate the positive results reported so far, and seek to establish VfM benchmarks across the two projects in comparison to other youth training initiatives. Consideration will be given to further review of PSFU beneficiaries, with a decision to be taken as overall PCDP evaluation plans are finalised.

Monitoring progress throughout the review period
The individual DFID SROs and programme managers for individual components are responsible for setting out in Delivery plans their plans for monitoring progress of their components results and partners. They are overseen by the Senior Responsible Owner for the PCDP programme. The earlier section of this review outlines some of the monitoring approaches taken, but these broadly include a range of formal and informal monitoring from contact with stakeholders in Kampala, field visits during which stakeholders based outside are consulted, and progress towards achieving milestones and targets is verified. This includes physical verification, but also wherever possible, beneficiary feedback.

In the output score section for NUSAF, for example, the role of beneficiaries not only as providing feedback but also in playing a key oversight function is highlighted.

Beneficiary feedback is an intrinsic part of the review process for the ‘quality’ component of the results-based funding formula under NU Health. Patients who have received services from one of the health facilities being funded by the programme are sampled and then consulted to ensure that they received the services that the health facility has reported as provided, and asked their opinion about the quality of the service received: mainly, general satisfaction about the services and staff attitudes. This client satisfaction result has a weight of 2 points in the quarterly quality assurance score form. The feedback affects the level of payment to facilities receiving results-based funding. Other interaction between verifiers and clients also includes interviews of a sample of mothers checking how the weight of their U5 has been measured, fevers handled, and vaccinations carried out. The implementing partner also interviews clients by phone about their overall satisfaction with the health facility, potential complaints they might have and what were the user fees paid.

The independent evaluation team also seeks feedback about the experiences patients have at facilities, including the level of fees they are asked to pay. Because the programme focuses on the continuum of care in maternal, newborn, and child health, the evaluation surveys assess the following four target population groups, whose knowledge, practices, and access to health care are measured, as well as health-related household socioeconomic information. The evaluation also assesses households’ health seeking behaviour, to understand whether consultations have been effective in conveying public health messages. The final round survey of the evaluation is currently underway.

DGF is a large and complex programme working across a number of themes and with a very large number of partners. DGF’s Annual Review/Mid Term review recommended that the M&E system should be improved. DGF has worked considerably on the M&E system, as confirmed by a recent diagnostic assessment conducted by DFID. The DGF does collect biannual or quarterly reporting from partners, as well as mid-term and project completion reviews and evaluations. However, much partner reporting is activities-based, however, some reporting further along the results chain in partner reporting. There are variable capacities to monitor outcomes amongst partners, although some of the more established partners have their own well developed M&E systems independently of DGF, such as Action Aid International Uganda. DGF has conducted M&E capacity building for partners in November 2014. Nonetheless there is room for considerable improvement in the substance of the M&E system, building on the infrastructure in place and the lessons learned in this current phase of DGF. A balance needs to be struck between the monitoring activities that partners can be asked to supply, since the use of resources for M&E should be proportionate.

Both VSO and Enterprise Uganda skills programmes involve detailed collection of individual information on entry of participants to the programmes and then follow ups six months after project engagement. Beneficairy databses have enabled DFID staff to monitor and interview beneficiaries at random during their quarterly field visits on this project.

As we approach the end of PCDP, and reviews/evaluations are completed for the components as detailed above, it will be critical to agree a method of review for the PCDP overall. A full evaluation is not recommended at this stage, as sufficient evidence should be gathered by component-level reviews and evaluations. It will be important however to capture additionally lessons around the model of PCDP as an umbrella programme and the challenges and complications that stem from such an arrangement and the changes in context over the programme period.