Annual Review - Summary Sheet

Title: Creating Opportunities for Poor and Excluded people (COPE)
Programme Value: £24,200,000		Review Date: May 2015
Programme Code: 202958	Start Date: August 2013	End Date: December 2016

Summary of Programme Performance
Year	2014	2015
Programme Score	A+	A+
Risk Rating	Medium	Medium

Summary of progress and lessons learnt since last review

The Creating Opportunities for Poor and Excluded people (COPE) programme, implemented by the Manusher Jonno Foundation (MJF), has achieved all –and exceeded most– of its output indicators over the past year and is on track to achieve all its outcomes.

MJF continues to impress as its projects show strong working relationships between MJF, the 117 non-governmental organisations (NGOs) it supports, and the poor and marginalised communities the programme targets. They build effectively on long-standing NGO relationships with communities, activate community support and volunteerism, which enables the project to adapt to local context – something that is most apparent in the Chittagong Hill Tracts, where the programme integrates service delivery more closely with work on rights than it does elsewhere in the country.

MJF’s fund management capacity is clearly demonstrated, both through its robust systems and the quality of feedback received from COPE project partners. Its role in managing COPE extends beyond fund management alone. The review team saw evidence of MJF’s continuing strength in establishing effective links between grassroots work and national level policy processes – something that is rare in projects of this kind.

Summary of recommendations for the next year
Priority recommendations for MJF under this Annual Review focus on three main areas:
- MJF should commission case studies, drawing on the outcome attribution and impact monitoring data, on transformational change processes that MJF has been involved in over the last 12 years. by January 2016
- MJF should use the last 18 months of the current programme to pilot linkages between its different programmes. For example, could some partners in other components increase their work to Combat Violence against Women and Girls (CVAWG) or their use of the Right to Information Act (RTI), using good practice from other partners whose primary focus is in those areas?
- These two pieces of work should feed into the development of a strategy to feed into forward planning.- by March 2016

The review also makes recommendations on cash management, and suggested clarification of its approach in some areas, including access to markets for CHT income generating activities, work with marginalised communities, engagement of men in CVAWG work and changing social norms, response to human trafficking as lined to migration, advocacy around decentralisation. A full list of recommendations is below:

Recommendations for DFID focus on:
- Clarifying plans for future funding by December 2015; and
- Coordination with other DFID programmes (e.g. SGSP, CLP/EEP programmes) to ensure MJF is able to communicate effectively with other DFID partners in similar field (e.g. issues on land, garments worker etc)
- DFID to help MJF to reach out to other donors to reduce reliance on DFID funding.

Full list of recommendations
  1. MJF should expand its livelihood work to include a better linkage to markets in its CHT programme. In order to maximise the impact of activities and ensure sustainability, it would be useful to ensure that farmers are being able to sell their products at fair prices by supporting them to access markets. To support this, opportunities to link to other UK-funded projects such as EEP/CLP and Katalyst should be explored by DFID– by September 2015.
  2. MJF should explore opportunities for mainstreaming some of its other initiatives across its ROM work, including Violence against Women (see output 2) and Right to Information (see output 4), both in the current programme and in the design of any future programme.
  3. MJF should ensure that its short-term approaches to working with marginalised communities (e.g. dalits) are fully consistent with its long-term goals.

2.1.	For future programming, MJF should explore whether and how to engage more actively with men as part of its anti-Violence against Women work, and to link approaches to a long-term strategy for changing social norms on acceptable behaviour – by March 2016.
2.2.	MJF should look at whether its CVAWG work would be more effective as a cross-cutting issue across all programming rather than as a separate programme, and should pilot this approach during the remaining time available under COPE – by June 2016.
2.3	The wording of output indicator 2.3 should be amended, to clarify that what is being measured is the percentage of girls in project areas remaining unmarried until age of 18.

  1. In the light of recent evidence and reporting on the scale of human trafficking from Bangladesh, MJF should assess its current work on safe migration and identify whether there is more it can do – by October 2015.
  2. Overall the review team felt that MJF’s activities on workers’ rights had some real strengths, but emphasised breadth over depth of coverage in some areas. MJF and its project partners should develop a forward-looking strategy on MJF’s broader objectives in this space, how each of the projects is contributing to those objectives, and where and how it would be of most benefit for MJF to work in future – by December 2015.
  3. Indicator 3.1 should be re-worded to say “preparatory education” instead of “non-formal education”, because the type of education MJF supports is not non formal education as generally understood, but preparing children for school enrolment.

  1. MJF should continue its initiative to mainstream RTI across its other work using the existing community groups in other areas – a pilot initiated by August 2015.
  2. MJF should finalise a strategy and set of activities to complement its long-term decentralisation campaign goals with efforts to achieve more concrete short- and medium term changes in improving the local governance – by December 2015.
  3. Linked to the above, DFID and MJF should consider and actively seek for synergies among a range of other similar initiatives on local government. Most of these interventions have been ongoing for over a decade and future programming needs to be better informed on where DFID/MJF interventions are adding value. A mapping exercise to complement the strategy mentioned above should be undertaken by November 2015.
  4. MJF should revisit its strategy and current programmatic arrangement for Access to Justice component by September 2015. This work should be informed by DFID work with other donors and government on the shape of future support for reform in the justice sector, which will include a discussion of where NGOs can best support sustainable improvements in access to justice.
  5. MJF should consider piloting new & innovative social accountability tools in the remaining time under COPE, explore how it can act as an “importer” of international good practice for its partners, and seek complementarity with other existing projects such as the World Bank Global Partnership for Social Accountability by March 2016.

  1. DFID should clarify its plans for any future funding of MJF by March 2016 to ensure that MJF has adequate time to react appropriately (see also Recommendation C above). A future phase of funding should consider, among other aspects, the following questions:
- Is there an opportunity to have two separate streams of work: one for more mature partners and one for newer entrants who require more support to develop?
- Going forward should MJF’s approach be more focused and strategic to improve the prospects of transformational impact in a few key areas?
- How can projects leverage each other better and work more closely together?
- Can projects be given more flexibility to adjust once underway or scale up if successful?
- Is there a need for MJF to have a regional presence?
- What is the most effective way to link social and economic empowerment through the range of programmes supported by DFID?
  1. As part of the same process, MJF should invest in its own strategy development both to respond to and to guide DFID thinking and ensure its own vision of its role and future is taken into account. Once MJF has clarity on the likelihood and scale of DFID funding, MJF should develop and implement a programme strategy accordingly – by December 2015.
  2. In future, MJF should consider putting more resources into working with new/other partners and donors.

6.1.	DFID and MJF should commission case studies, to be completed by January 2016, drawing on the outcome attribution and impact monitoring data, on powerful change processes that MJF has been involved in over the last 12 years. This should include learning from failure.
6.2	MJF should review and prioritise its policy advocacy efforts in relation to the following two findings (among others) and should establish an advocacy strategy strategic document for the whole programme as well as for individual components. It should feed these recommendations into a broader strategic planning process – by September 2015:
  - Reduce number and range of issues covered in order to cover selected issues in greater depth based on clear value for money rationale.
  - Balance a high profile legislative advocacy agenda against ongoing advocacy for more effective implementation of existing legislation and policies.

A. Introduction and Context

DevTracker Link to Business Case:	4019077
DevTracker Link to Log frame:	4685174

Outline of the programme
The UK government is providing £24.2 million over 3.5 years (2013-2016) to Manusher Jonno Foundation (MJF) to implement the Creating Opportunities for Poor and Excluded people Programme (COPE). Australia’s Department of Foreign Affairs and Trade (DFAT) has provided AUD 6 million for 3 years between 2012-2013 to 2014-15.

 Bangladesh sustained growth over the past decade, and significant progress has been made against most of the Millennium Development Goal (MDG) targets. While the country has made substantial progress to reduce the poverty gap, there remains a high proportion of the population living below $1 a day. Inequality has improved but not by much in the past 10 years. Recent analysis has identified that there remain a number of obstacles in Bangladesh for inclusive growth, most notably power, skills and governance that depress new investment, jobs and growth. Lack of accountability at all levels, politicisation and misuse of power often impedes efforts to meet basic needs and provide basic services. Social inequalities are particularly acute for women, despite the opportunities that the country’s economic development have created for employment outside the home. Children from poor families engage in hazardous work and workers often experience harsh working environments. Marginalised groups, including the extreme poor, minorities, people with disability and groups such as sex workers, transgender people and “dalits”[1] are excluded from their entitlements to public services, facilities and resources.
[1] Dalit is the deprived population in Bangladesh and elsewhere in the world. The term is used in Bangladesh to refer to “low caste” Hindus but over time has come to be used for a range of socially excluded groups, usually traditionally involved in professions perceived as unhygienic such as toilet cleaning and pig rearing. The term is perceived as an insult, although it is currently also used by members of these social groups to refer to themselves.

MJF, through partner organisations, is building citizens’ awareness and capacity to raise their voices and claim their entitlements. MJF also works with the supply side to promote accountability of service providers and public institutions, and to respond to citizens’ demands. The objective is to generate enough public pressure to bring about changes in governance that will secure citizens’ rights and entitlements long-term. This complements other DFID programmes (e.g. Strengthening Government Social Protection System for the Poor Progroamme).

COPE follows the UK-funded Rights and Governance Challenge Fund (RGCF) programme (2008-13), also implemented by MJF, in providing funding, technical and organisational support, and access to national policy influence for non-governmental organisations (NGOs) and community based organisations (CBOs) selected through a competitive process. COPE currently supports 117 NGOs under the following pillars:

Programme Pillar	# Partners
Ensuring Rights of the Marginalized Population	31
Socioeconomic Development of Chittagong Hill Tracts	16
Combating Violence against Women	21
Protection of Working Children and Vulnerable Workers	20
Ensuring Responsiveness of Public Institutions	29
	117

MJF’s role also encompasses capacity building for its partners (Output 5) and national level policy advocacy work in each of the five programme areas and on cross-cutting issues that affect all programming (Output 6).
## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment
COPE outcome statement is: Marginalised and vulnerable people have better access to public goods, resources and services and the programme has 10 outcome-level indicators (see table below). With the exception of two (related) indicators (4.b and 4.d) on land access, all indicators have been achieved, and in most cases well exceeded, showing that the programme is on track to achieve its outcomes. Progress towards the outcome reflects both the results of proactive project-led initiatives, and changes brought about by government initiatives, some of which were influenced by advocacy campaigns supported by the programme. For example MJF reports that preparation of lists of eligible safety net recipients by project partners (linked to Indicator 1.a) was bolstered by government drives to distribute Vulnerable Group Feeding (VGF) cards, including among destitute women, and a 20% increase in the national budget allocation for safety nets.

Indicators 4.b and 4.d focus on khas[2] land distribution. While projects working in this area are doing high quality work, their progress has been set back by political instability, which limited interaction with government agencies and service providers, as well preventing organisation of demand-side gatherings and protests. It now looks unlikely that the cumulative target of khas land acreage for the programme will be achieved, so it is recommended that this target be adjusted in line with revised expectations. One or two of the other targets where the project is over-achieving could be increased to balance this out.
[2] Khas land is government/public land intended for redistribution to people who depend on agriculture for a living but own no or less than 10 decimals of land. (All the land records of the government under Register No. 8 and Khatian No. 1 represent Khas land)

The progress towards the outcome targets indicates that programme activities are on the right track. We have also reviewed the original programme assumptions and the theory of change, to confirm that they are still valid and that outputs can still be expected to lead to the programme’s outcome. While the political unrest earlier in 2015 may make the two outcome targets above unachievable, the overall theory of change for the programme looks robust.

	Indicators	Milestone, March 2015	Progress	Status
Outcome Indicator 1: Increased use of services (education, health, and social protection) by poor, marginalised, and vulnerable people
1.a	Number of poor, marginalised, and vulnerable households who gained access to government safety net services.	Cumulative: 64,500	85,667: / (29,983 men, / 55,684 women	Exceeded
1.b	Total amount (in £million) of social safety net support received by programme beneficiaries	Cumulative: 3.10	4.11	Exceeded
1.c	Number of boys and girls in project areas and communities who were supported & completed primary school.	Annual: 12000	15631	Exceeded
Outcome Indicator 2: Women and girls protected against violence
2.a	Number of women victims of violence receiving compensation, resolution or legal services.	Cumulative: 18500	19,368	Achieved
Outcome Indicator 3: Vulnerable and marginalised groups' participation and representation at the national and local political structures
3.a	Number of marginalised men and women elected to local bodies (union parishad)	No target for 2015 as elections are not due until 2016.
Outcome Indicator 4: Legal rights and access to resources realised in programme areas
4.a	Number of workers having annual pay increase through collective bargaining. (25% men 75% women.)	Cumulative: 30000	31,527	Achieved
4.b	Number of acres of additional khas land and water bodies leased to poor and marginalised people.	Cumulative: 4265	2,300	Not achieved
4.c	Number of women and men in programme areas having paid work and self-employment.	Annual: 13600	18,797	Exceeded
4.d	Total value (in million £) of government khas land and water bodies accessed by beneficiaries.	Cumulative: / 3,412	1,840	Not achieved
Outcome Indicator 5: Children protected from hazardous labour
5.a	Number of working children (aged 14-17) withdrawn and reassigned from non-hazardous work. 75% boys, 25% girls)
	Withdrawn	Cumulative: / 5000	5,076	Achieved
	Reassigned	4000	4,148

Overall output score and description

Output	Overall Score	Impact Weighting
1. Marginalised people are organised to claim their rights and fight discrimination	A+	30%
2. Women's groups equipped to challenge violence against women and girls	A+	20%
3. Rights of working children and vulnerable workers protected and strengthened	A++	20%
4. Capacity of citizens in project areas to monitor activities of government service delivery institutions	A+	10%
5. More sustainable civil society organisations	A+	10%
6. Evidence generated, synthesised, and used to advocate for changes in various social development policies	A++	10%
Cumulative Score	A+

COPE has achieved all –and exceed most– of its output indicators over the past year and is on track to achieve all its outcomes. MJF continues to impress as its projects show strong working relationships with –and understanding of- communities and their needs. They build effectively on long-standing relationships with communities and activate community support and volunteerism, and they link to local government even where it is not explicit in their mandates. The team also saw evidence of MJF’s adaptation of programmes to local context, for example in its integration of service delivery with rights education in the Chittagong Hill Tracts.

Following last year’s annual review, MJF has reviewed their data collection and management techniques. The dedicated Project Officer regularly reviews the field information and data provided by partner NGOs, in discussion with the organisation. MJF also cross-checks the information when they visit the programme activities (MJF staff visit each partner NGO twice a year). In addition, DFID is helping them through expert assistance in improving systems for monitoring and learning, including the capacity of their monitoring and evaluation team. The M&E Review Team has submitted an initial report with recommendations for MJF to consider. These will be followed up later in 2015.

MJF’s fund management capacity is clearly demonstrated, both through its robust systems and the quality of feedback received from COPE project partners. However its role in managing COPE clearly extends beyond “fund management”. The review team saw evidence of MJF’s continuing strength in establishing effective links between grassroots work and national level policy processes – something that is rare in projects of this kind, and a real strength of the MJF approach.

Key lessons
- Capacity development of service providers alone is not sufficient to ensure access to services for the marginalised group of population. Identifying structural problems and bridging relations with the targeted community need to work simultaneously to ensure the rights of the marginalised.
- Although Bangladesh has several legal provisions that ought to promote accountability, MJF’s support to partners is critical to ensure local communities are able to articulate their demands to public institutions.
- MJF places a huge emphasis on organisational and advocacy capacity building of COPE grant holding partners as an intrinsically valuable outcome of the programme. For this, the programme has established a robust ‘change model’ that supported NGO partners[3] to work on the ‘demand’ and ‘supply’ sides of accountability relationships, building	advocacy capacity while strengthening the capacity of policy implementation and service delivery. At the heart of this, MJF is an active interlocutor between the ‘micro’ and the ‘macro’, linking pro-poor policy level advocacy around an impressive range of policy areas with ground-level support to entitlement-claiming by a wide range of poor and excluded social groups. For example, MJF work with organisations representing workers in the garment and shrimp industries has informed the advice that MJF staff have provided to the drafting of laws and regulations such as the labour law, setting employment rights and minimum wages for the garment workers.
  [3] e.g. partners under 3 thematic areas: rights of the marginalised, responsive governance, the Chittagong Hill tracts and local governance

- There should be more sharing and replication amongst partners under COPE since partners vary in their capacity and could learn from each other and from each other’s successes.
- Projects should be more flexible: successes should be allowed to scale up within the life of the current project rather than waiting for a new round of funding.

Key actions

For MJF
  1. MJF should consider commissioning a study to assess the impact of MJF’s work on poverty alleviation. Some streams of work (such as khas land transfers, skills training of mothers of working children and adolescent children or socioeconomic empowerment in CHT) result in significant improvements in assets and incomes that are not currently being assessed in terms of the impact they are having on poverty reduction.
  2. MJF should commission case studies, drawing on the outcome attribution and impact monitoring data, on powerful change processes that MJF has been involved in over the last 12 years. This should be the programme’s priority in the next 6 months.
  3. Based on the recommendation from the on-going M&E review, MJF should amend the wording of two output indicators (Outputs 2 and 3 below) and consider adding additional indicators reflecting MJF’s contribution to policy changes..
For DFID:
  1. DFID should involve MJF and some of its partners in discussions on the future shape of its programming on social and economic empowerment, to inform both DFID’s own planning and that of MJF and its partners. This will need to happen between now and March 2016..

Has the logframe been updated since the last review?
Yes. The logframe has been revised in line with recommendations made in the 2014 Annual Review (AR). The following changes have been made:
- Rewording of outcome indicators 1.a, 1.c, 2.b and 4.a. No change in scoring.
- Removal of outcome indicator 2.a. and renumbering of 2.b. to 2.a.
- Rewording of output indicator 1.2, 1.6 and 2.2. No change in scoring.

A few recommended changes have not been made because they would undermine MJF’s reporting mechanisms for its partners but will be taken into account in the design of any programme in future. Others have not been made as they will be revisited during a Monitoring & Evaluation (M&E) review of COPE and of MJF’s approach to reporting qualitative changes, in line with the recommendations of the 2014 AR. The initial recommendation from that review is not to make major changes to the numerical indicators in the COPE logframe but the review does recommend amending the wording of one output indicator and adjusting targets and milestones against a few indicators. The emphasis for the next 18 months should be to put more effort into documenting the changes in systems and formal and informal rules that the project has contributed to.

## C: DETAILED OUTPUT SCORING

Output Title	Marginalised people are organised to claim their rights and fight discrimination
Output number per LF		1	Output Score	A+
Risk:		Medium	Impact weighting (%):	30%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone - March 2015	Progress	Score
1.1. Number of people supported by the project to practice their citizen rights and tradition	Annual: 150,000	169,093 / Man: 35,197 / Woman: 133,896	A+
1.2. Number of people from marginalised groups taking part in local government bodies and local forums / (70% women, 30% men)	Cumulative: 7500	8,489	A+
1.3. Number of children in project areas learning in mother tongue in their schools	Cumulative: 5000	5,557	A+
1.4. Number of children enrolled in primary schools	Cumulative: 46000	49,619	A+
1.5. Number of men and women received skill development training and entrepreneur assistance	Cumulative: 15000	15,952	A+
1.6 Number of poor and marginalised people in target communities in CHT who increase their monthly income by£9 through income generating activities.	Cumulative: 8000	8,129	A

Key Points
This output covers a range of MJF’s work:
- Indicators 1.1. and 1.2. gather evidence of mobilisation activities across all MJF’s work;
- Indicators 1.3, 1.4 and 1.5 report on work under the two pillars of Socioeconomic Development of Chittagong Hill Tracts and Ensuring Rights of the Marginalised Population
- Indicator 1.6 focuses exclusively on the Chittagong Hill Tracts (CHT).

All indicators have achieved or moderately exceeded milestones.

Activation of citizens to practice and claim their rights, whether through independent activity or through government committees and structures (indicators 1.1 and 1.2) lies is at the core of all of MJF’s work. This is clearly one of MJF’s strengths. COPE projects visited by the Annual Review team showed strong working relationships with –and understanding of- communities and their needs. They built effectively on long-standing relationships with communities and activated community support and volunteerism, and they linked to local government even where it was not explicit in their mandates.

The Rights of the Marginalised (ROM) programme has been central to MJF’s work since 2002. It works with people whose entitlements to basic resources and services are denied, whether due to negligence of service providers, lack of inclusive policies and programmes, lack of information about their rights and how to access them, or low social status. Through COPE, MJF works with people who are marginalised due to occupation (e.g. dalits, harijan[4], fisher-folk, sex-workers); minority identity (e.g. religion, caste, ethnicity); living in vulnerable or remote areas (e.g. Char, Haor or Hill areas); disability; disease status, biological identity or behavioural practices (e.g. homosexual, transgender). Over the past year, the Rights of the Marginalised (ROM) component has ensured that 4,195 poor and marginalised people (2371 males and 1824 females) received 1670 acres of khas land and water bodies. It also facilitated access to social safety nets for 19,488 people and to health services for 38,439 people, and helped 10,950 children enrol primary schools. These achievements give a sense of the reach of COPE despite the relatively small scale of many individual projects.
[4] Harijan population is one of the subsections of the Dalit community who are traditionally involved in sweeping and cleaning. This community was migrated from India by the British rulers to do the cleaning work in the cities and towns of what is now Bangladesh.

ROM activities focus on both empowering marginalised groups to claim their rights and making service providers aware of the needs of these groups and their obligations to provide services that meet those needs. This strategy is gradually paying off, with local level progress made on integrating communities and developing relationships with local officials, but it is equally clear that the changes in social norms required for integration of some groups will require sustained long-term investment, and also that central positions, policies and priorities can be highly influential. At the national level MJF’s achievements reflect the varied needs of its beneficiaries and include amendments to fisheries, land and anti-discrimination legislation, securing a land commission for indigenous groups, high level government interest in rights of dalits and introduction of some protective quotas such as guaranteed places for dalits at public universities. The review team had some concerns that MJF’s short-term advocacy for rights of the dalit community could undermine long-term mainstreaming efforts.

Another major theme in the ROM stream has been on the rights of the landless to khas lands. The review team visited Uttaran, an MJF partner in Satkhira working with landless people to help them access khas land, both as individuals and as farmer groups. Despite the scale of the challenge, including land grabbing, political economy issues and violence, significant progress has been made and numerous beneficiaries shared feedback on how their lives, livelihoods, security had been transformed by having access to land. As noted above, the knock-on effects of recent political unrest, including limited access to decision-makers in government, mean that at outcome level the project has been unable to secure rights to the acreage of khas land expected in the logframe, but this setback (hopefully temporary) does not lessen the importance of the work for the communities involved.

MJF has been working on Socioeconomic Development of the Chittagong Hill Tracts (CHT) since 2005 and under COPE it has 16 partners and 9 sub-partners working across the 3 Hill districts of Banadarban, Khagrachari and Rangamati. MJF’s work in CHT is unusual in that it integrates aspects of service delivery with rights education work and support for claiming entitlements to Government resources. The review team recognised that this was an appropriate adjustment of approach to accommodate the particularly disadvantaged and isolated status of many target communities.
Project initiatives include support for community-led collective income generation initiatives (e.g. organic agricultural production), where possible linked to accessing Government of Bangladesh resources, and initiatives to enhance food security such as rice banks and natural vegetable/fruit storage. Income generation activities have generated around £60,000 over the past year for some of the most disadvantaged and isolated communities in Bangladesh. MJF partners also work with 24,426 students in 337 schools, training teachers; activating School Management Committees, Parent Teacher Associations and Mothers Groups; helping schools set up income generation schemes (126 schools) and supporting community schools to register with the government (37 completed, 60 more underway). All CHT activities promote preservation of indigenous knowledge, tradition and cultural practices – in particular COPE partners emphasise provision of mother tongue based education for indigenous children and formation of local cultural groups, as well as publication of traditional land laws and family customary laws.

Summary of responses to issues raised in previous annual reviews (where relevant)
The 2014 AR focused on recommendations linked to indicators that are dealt with elsewhere.

Recommendations
  1. MJF should expand its livelihood work to include a better linkage to markets in its CHT programme. In order to maximise the impact of activities and ensure sustainability, it would be useful to ensure that farmers are being able to sell their products at fair prices by supporting them to access markets. To support this, opportunities to link to other UK-funded projects such as EEP/CLP[5] and Katalyst should be explored by DFID– by September 2015.
    [5] Support from other DFID programme also help some of the NGOs in the CHT area. For example, 2 NGOs: Eco Development and Green Hill receive funding from the DFID supported EEP programme. Evidence shows that experience of EEP was valuable for these 2 NGOs as it ensured creation of livelihood opportunity for project beneficiaries through crop diversification, organic farming and market linkage,
  2. MJF should explore opportunities for mainstreaming some of its other initiatives across its ROM work, including Violence against Women (see output 2) and Right to Information (see output 4), both in the current programme and in the design of any future programme.
  3. MJF should ensure that its short-term approaches to working with marginalised communities (e.g. dalits) are fully consistent with its long-term goals.
Output Title	Women's groups equipped to challenge violence against women and girls.
Output number per LF		2	Output Score	A+
Risk:		Low	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone March 2015	Progress	Score
2.1. Number of dowry-less marriages in programme areas	Cumulative: 6700	6446	A
2.2. Number of women victims of violence in project areas supported to have access to medical and /or legal assistance.	Cumulative: 25500	28302	A+
2.3. Number of early marriages (i.e. girls under 18 years) prevented in project areas. Programme works to prevent (outside beneficiary groups) and to actively stop people from marrying underage girls.	Cumulative: 6600	7693	A+

Key Points
Violence against women and girls is a huge challenge in Bangladesh, with around 65% of married women having experienced physical violence[6] and with wider impact on health, education and mobility. Combating Violence Against Women and Girls (CVAWG) is therefore an important, if challenging, area to make progress in. Despite the increased opportunities for education and formal employment that are available to women, there remains a widespread cultural/social tolerance for domestic violence, traditional patterns of early marriage and dowry, and ongoing vulnerability for women who remain economically dependent on men.
[6] Violence Against Women Survey 2011 by BBS

MJF’s CVAWG programme uses a strategic approach that considers “the 5Ps” - participation, prevention, protection, provision and policy advocacy. CVAWG aims to reduce violence in private and public domain through community activism and to increase institutional responsiveness to address needs of women and girls during any violence.

Output indicator 2.1. has been achieved, while output indicators 2.2. and 2.3 have been exceeded. These reflect progress on reducing incidence of dowry payments, on helping women who are victims of violence seek medical care and legal redress, and on stopping and preventing early/child marriage – a traditional practice associated with long-term negative impacts on the lives of girls.

On both dowry and child/early marriage, initiatives mix preventative measures (e.g. awareness raising, building women’s support groups and talking to families who may be considering marrying their daughters off early) and protective measures (e.g. collective community action to stop early marriage). For access to medical/legal services, COPE partners work with police stations to make the police force, lawyers and health service providers aware of the rights and needs of women who have been victims of violence and to insist upon prompt response to violence against women. Under CVAWG and also under MJF’s Access to Justice component of its Governance pillar (see output 4), projects also help improve the functioning of local salish (community-based alternative dispute resolution) and village courts, and collaborate with hospitals and health services to ensure appropriate treatment for victims of violence. The review team was impressed with the level of community engagement and participating women’s confidence to take collective action. Women’s groups were well connected to – and supported by – law enforcement in the areas visited, and could clearly explain their tactics for stopping and preventing early marriage.

MJF also advocates for policy changes at the national level, drawing on evidence generated by the partners at the grassroots. Its national level advocacy work on CVAWG has high visibility and therefore significant leverage. Among MJF’s current advocacy targets are for improved implementation of the Domestic Violence Act (2010), for compulsory registration under the Hindu Marriage Registration Act and gender sensitive microfinance rules and regulations. MJF is also actively involve with other national forums and CSO platforms to advocate with the government in formulation of the Child Marriage Act.

Summary of responses to issues raised in previous annual reviews (where relevant)
- In line with the 2014 AR recommendation to pay more attention to the changing dynamics and patterns associated with violence against women, dowry and early marriage, MJF has revised the reporting format and prepared a fact sheet on dowry and early marriage.
- A recommended lessons learned study to share what is working well with other civil society groups, and in particular the women’s movement and government agencies involved in the multi-stakeholder platform against CVAWG is at the final stage. It had been delayed due to political unrest. On the basis of the draft study, two dialogues have been organised with existing VAWG network members to explore feasibility of establishment of a new multi-stakeholder platform. MJF will undertake further consultation prior to making a final decision about this.

Recommendations
2.1.	For future programming, MJF should explore whether and how to engage more actively with men as part of its anti-Violence against Women work, and to link approaches to a long-term strategy for changing social norms on acceptable behaviour – by March 2016.
2.2.	MJF should look at whether its CVAWG work would be more effective as a cross-cutting issue across all programming rather than as a separate programme, and should pilot this approach during the remaining time available under COPE – by June 2016.
2.3	The wording of output indicator 2.3 should be amended, to clarify that what is being measured is the percentage of girls in project areas remaining unmarried until age of 18.

Output Title	Rights of working children and vulnerable workers protected and strengthened.
Output number per LF		3	Output Score	A++
Risk:		Medium	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone - March 2015	Progress	Score
3.1 Number of students received Non Formal Education (NFE) from child centres	Annual: 11,000	16,885	A++
3.2 Number of workers in decent working conditions supported by the programme (30% men, 70% women)	Cumulative: 25,000	Total: 35,235 / Men: 16,044 / Women: 19,191	A++
3.3 Number of migrant workers in project areas receiving training and support for safe and legal migration. (70% men, 30% women)	Cumulative: 3,200	Total: 3,490 / Men: 2,975 / Women: 515	A+

Key Points
Over the past year MJF has significantly surpassed all three of its milestone targets for this output. The three indicators link to two thematic streams: child protection and development (CPD) and workers’ rights (including migration).

MJF aligns its CPD stream in line with the Child Labour Elimination Policy and the Labour law. MJF focuses on both preventive and rehabilitative approaches in mitigating the problem of child labour. For this, MJF’s target is to work firstly to withdraw children from hazardous work and secondly, to provide non formal education to these children with the objective of enrolling younger children of 6 to 13 years of age into government schools. Under the Labour Law, children of 14 and over are allowed to work, but this component’s ultimate objective is to eliminate child labour completely through bringing back maximum number of children to formal education. Acknowledging the reality that due to economic hardship of their families, stopping work may not possible for some older children (14‑17), MJF has adopted a temporary arrangement for those children to move into less hazardous work environments.

A strong point about this project was that it uses the base of a “multi-purpose” community centre to offer flexible support to children based on their and their families’ needs. For example, while some children go to the centre for classes before or after work, others attend classes full time and children who have moved on to government schools are encouraged to return to the centre for support on homework. Parents and older children (particularly mothers) can also access vocational training (e.g. tailoring, block printing or cell phone repair) to help them provide alternative sources of income for the family and avoid sending their children out to work. Another positive aspect of this project, that came through on a visit to one of the centres during the Annual Review field visit, was how well connected this projects was to the local community, with many factories in the area sending their child workers to the centre and others even contributing financially to sponsor the work.

The second thematic stream that feeds into this output area is workers’ rights. These projects aim to simultaneously work on improving the awareness of workers on their rights, engaging with relevant stakeholders including Associations, Trade Unions, Employers and others while also creating a better legal environment for workers in the garments and shrimp processing sectors. Other projects also focus on potential migrant workers and agriculture workers, and COPE has a small pilot initiative with domestic workers.

Through this stream over the past year 35,235 people have been supported to have better working conditions (e.g. wage increase, 8 hour day, overtime pay, maternity leave, etc.) against a target of 25,000. A large part of this has come from the garments sector where MJF’s efforts have coincided with broader sectoral changes following the Rana Plaza building collapse that killed 1,100 people in 2013. In addition to its factory level work with workers’ organisations, MJF has played a valuable role in working with the government to develop the Rules that relate to the Labour Law. As part of the Annual Review, the team met with shrimp workers in Khulna and garments factory workers and mid-level managers in Dhaka through two different projects.

Safe and legal migration is an important issue in Bangladesh given the number of people who migrate annually (both within Bangladesh and overseas) and the risks involved. MJF partners have organised community level awareness-raising initiatives, training and community level dissemination events on safe and legal migration. In addition, the project has established 12 Safe migrant rights information centres to provide practical and authentic information at grassroots level. This stream of work is particularly important given the recent findings on the scale of illegal migration that is occurring from Bangladesh[7].
[7] It is estimated that in 2014, approximately 58,000 people migrated illegally to countries in South East Asia while the number of safe and legal migration was reported to be over 350,000. Source BMET and RMRRU

Summary of responses to issues raised in previous annual reviews
- The 2014 Annual Review recommended that work in the CPD stream should take advantage of the offer from the Campaign for Popular Education (CAMPE) to provide free training on Non-Formal Education (NFE) for partners over the next year. Both MJF and this review team thought this was a helpful offer, but was not best suited to the students the project is working with. Given that the multi-purpose centre’s “school” is very small and functions more like a half-way house between work and mainstream schooling, that it has a very diverse group of students in terms of age and literacy/numeracy levels, and that resources are very scarce, the full-fledged NFE curriculum is not appropriate. The education provided focuses more on improving basic literacy and numeracy while also working on social skills and confidence. The school teachers and management felt that the interactive methods used allowed the children to learn with greater ease and support. As such, the child-based, customised approach that the school has adopted seems to be appropriate.
- The 2014 AR recommended that the 2015 AR should assess the quality of preparatory education inputs. This is covered by the ongoing M&E review but as a proxy assessment the review team looked at the number of children who were transitioning to formal schools through this project. Of the 16,885 children that have been provided with non-formal education through the child centres over the last year, 5,076 have so far been integrated into the formal system. MJF provides tutorial support at their child centre to children who were enrolled in to the formal school, to help them prepare for their study properly. Through regular school follow-up and home visit, MJF track whether children are continuing with their formal schooling or dropping out. During the next academic year, which begins in January 2016, approximately 3,500 additional children will be supported to be enrolled. Given that the projects work with children of varying ages, from 5 to teenagers, only 50% of children are expected to enrol in formal schools.

Recommendations
  1. In the light of recent evidence and reporting on the scale of human trafficking from Bangladesh, MJF should assess its current work on safe migration and identify whether there is more it can do – by October 2015.
  2. Overall the review team felt that MJF’s activities on workers’ rights had some real strengths, but emphasised breadth over depth of coverage in some areas. MJF and its project partners should develop a forward-looking strategy on MJF’s broader objectives in this space, how each of the projects is contributing to those objectives, and where and how it would be of most benefit for MJF to work in future – by December 2015.
  3. Indicator 3.1 should be re-worded to say “preparatory education” instead of “non-formal education”, because the type of education MJF supports is not non formal education as generally understood, but preparing children for school enrolment.

Output Title	Capacity of citizens in project areas to monitor activities of government service delivery institutions
Output number per LF		4	Output Score	A+
Risk:		Medium	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone – March 2015	Progress	Score
4.1 Number of people involved in project areas to monitor health, agricultural extension, education, social protection, nutrition services available to the poor	Cumulative: 16,060	Cumulative: 17,469	A+
4.2 Number of Government institutions monitored by partner organisations using social accountability tools: / a) Agricultural Extension Offices / b) Health Facilities / c) Social safety net programmes / d) Schools	Cumulative: / a) Agricultural Extension Offices: 90 / b) Health Facilities: 180 / c) Social safety net programmes : 60 / d) Schools: 120	Cumulative: / a) Agricultural Extension Offices: 97 / b) Health Facilities: 285 / c) Social safety net programmes : 90 / d) Schools: 210	A+

Key Points
Over the past year MJF has surpassed both its milestone targets for this output. The indicators link to MJF’s governance programme on Responsive Public Institutions. The programme is a continuation of MJF’s previous UK-funded work under RGCF and involves a mix of new and old partners and geographic areas. Implementation of the Right to Information (RTI) Act (2009) and improving local legal services for the poor (particularly women) also constitute two important streams under the programme. While the current Access to Justice strategy emphasises improving access to local justice systems for the poor, the changes taking place (e.g. weekly village courts) due to MJF partners’ interventions will not be sustained without MJF support despite being mandated by law. This is primarily due to lack of capacity of the Union Parishads – a fundamental challenge also recognised by MJF. The stream is also closely linked to MJF’s work on combating violence against women (see output 2).

Output indicators capture only the grassroots demand side of MJF’s work in this space. MJF partners use a range of social accountability tools including community scorecards, public hearings and social audit as their key public monitoring tools. MJF also supports local government institutions in enhancing capacity of the elected representatives/local officials and activating participatory structures (e.g. Union Parishad Standing Committees, School Management Committees). At the national level MJF, along with other partners, is engaged with campaigning for decentralisation of resources and responsibilities to local government, but is also paying attention to shorter-term goals such as increasing local revenue base through negotiating shared resources with the central government (e.g. a percentage of land transfer fees). The ongoing M&E review is particularly important for work in this area, which depends on capturing system change as well as qualitative changes around service delivery and accountability relationships.
Summary of responses to issues raised in previous annual reviews (where relevant)
The 2014 AR recommended for MJF to put in place grievance and feedback mechanisms. MJF has undertaken consultations with its partners and local project participants and identified options for further review. A Grievance Mechanism in a more institutionalized form for selected social safety schemes is being piloted under the UK-funded Strengthening Government Social Protection Systems for the Poor (SGSP) project, which may offer a useful model for COPE.

Recommendations
  1. MJF should continue its initiative to mainstream RTI across its other work using the existing community groups in other areas – a pilot initiated by August 2015.
  2. MJF should finalise a strategy and set of activities to complement its long-term decentralisation campaign goals with efforts to achieve more concrete short- and medium term changes in improving the local governance – by December 2015.
  3. Linked to the above, DFID and MJF should consider and actively seek for synergies among a range of other similar initiatives on local government. Most of these interventions have been ongoing for over a decade and future programming needs to be better informed on where DFID/MJF interventions are adding value. A mapping exercise to complement the strategy mentioned above should be undertaken by November 2015.
  4. MJF should revisit its strategy and current programmatic arrangement for Access to Justice component by September 2015. This work should be informed by DFID work with other donors and government on the shape of future support for reform in the justice sector, which will include a discussion of where NGOs can best support sustainable improvements in access to justice.
  5. MJF should consider piloting new & innovative social accountability tools in the remaining time under COPE, explore how it can act as an “importer” of international good practice for its partners, and seek complementarity with other existing projects such as the World Bank Global Partnership for Social Accountability by March 2016.

Output Title	More sustainable civil society organisations
Output number per LF		5	Output Score	A+
Risk:		Medium	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress	Score
5.1 Number of small partners receiving financial support other than from MJF	Cumulative: 6	7 (116%)	A+
5.2 Percentage of MJF budget coming from sources other than DFID.	Annual: 23%	27% (117%)	A+

Key Points
This output reports against two indicators on the diversification of funding sources; the first for small MJF partners[8] and the second for MJF’s own fundraising achievements. Performance against both indicators moderately exceeded 2015 milestone targets.
[8] Under this output, a small partner is different from MJF’s regular partners and sub-partners. The “small partners” are those locally organised CBOs or people’s organizations that have been facing multiple challenges which are attributed due to lack of capacity in managing program, insufficient grant, poor project management, and weak financial management and governance mechanisms. These organizations applied to MJF for fund but failed to qualify due to their poor capacity. As a result, MJF’s Capacity Development Unit decided to support some of these organisations to develop their systems and strengthen programme implementation. Initially, they received training to develop their organisational capacity and then MJF provided approximately £5450 for one year to implement their respective project.

MJF works with a diverse range of partners; some that are very large and well established in their own right and others that are much smaller and more dependent on MJF both as a source of funding and for capacity building and guidance. To work with multiple partners, MJF has developed mainly a two pronged approach, working directly with some organisations as “partners” and indirectly with smaller organisations as “sub-partners” through their direct partners. Other than these two groups, MJF also provides capacity development support to a group of “small partners” who applied to MJF for funding but failed to qualify due to their poor capacity. The Annual Review team met with a broad range of these partners, sub-partners and small partners, who gave a lot of positive feedback about MJF, its staff, the support that has been provided. NGOs of all sizes consistently reported that being an MJF grantee resulted in an improvement of management and financial processes/systems, and that as a result they had been more successful bidding on other projects. Since the project’s inception, MJF strengthened the management and organisational capacity of 17 small partners out which 7 partners (41%) have been able to manage funding from other sources for new projects.
Diversifying its own sources of finance away from DFID is desirable for MJF’s future sustainability and growth. Indicator 5.2 reflects this objective. Over the past year, MJF received 27% of its funding from other sources and new projects were developed with the World Bank, European Union and Comic Relief UK
Despite this progress, sustainability remains an important issue for MJF, particularly given that 18 months remain in the current phase of programming and no decisions have yet been made on follow-up programming.

Summary of responses to issues raised in previous annual reviews (where relevant)
The 2014 Annual Review recommended that the M&E review should include measures of the strength and density of the interactions of partner civil society organisations. This is being followed up in the ongoing M&E review which will be completed by December 2015.
.

Recommendations
  1. DFID should clarify its plans for any future funding of MJF by March 2016 to ensure that MJF has adequate time to react appropriately (see also Recommendation C above). A future phase of funding should consider, among other aspects, the following questions:
1. Is there an opportunity to have two separate streams of work: one for more mature partners and one for newer entrants who require more support to develop?
2. Going forward should MJF’s approach be more focused and strategic to improve the prospects of transformational impact in a few key areas?
3. How can projects leverage each other better and work more closely together?
4. Can projects be given more flexibility to adjust once underway or scale up if successful?
5. Is there a need for MJF to have a regional presence?
6. What is the most effective way to link social and economic empowerment through the range of programmes supported by DFID?
  1. As part of the same process, MJF should invest in its own strategy development both to respond to and to guide DFID thinking and ensure its own vision of its role and future is taken into account. Once MJF has clarity on the likelihood and scale of DFID funding, MJF should develop and implement a programme strategy accordingly – by December 2015.
  2. In future, MJF should consider putting more resources into working with new/other partners and donors.

Output Title	Evidence generated, synthesised, and used to advocate for changes in various social development policies
Output number per LF		6	Output Score	A++
Risk:		Low	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress	Score
Number of policy advocacy campaigns on rights and governance	Cumulative: 3	Cumulative: 8	A++

Key Points
This indicator is intended to demonstrate how MJF’s role in managing COPE extends beyond fund management and in particular to reflect MJF’s upstream policy work. During the past 12 years, MJF has contributed to demonstrable successes in policy advocacy (e.g. RTI Act, Domestic Violence Act) and the review team saw clear evidence of MJF’s continuing strength in establishing effective links between grassroots work and national level policy processes. A recent example was special development allocations for disadvantaged groups including ‘dalits’ by the Government of Bangladesh following intensive awareness raising by MJF and partners. For example, allocation for dalit community is increased in the national budget for last two years: in 2013-14, the amount was £1,021,700 which was increased to £1,151,700 in 2014-15.

These achievements have been accompanied by profound learning on how best to support transformative governance processes in support of pro-poor change. However, as a result (in part) of a focus on numerical indicators in MJF’s monitoring, many of these changes and MJF’s contribution to them are not well written up, in ways that could inform and influence policy makers and practitioners who were not directly involved in the processes. It would be counterproductive and misleading to try to claim attribution (since none of these high level changes can be attributed to MJF’s work alone), but there is a compelling need for MJF to document and communicate the change processes and its contributions better.

The Annual Review team was also struck by the strong emphasis on advocacy for enactment of new laws in MJF’s advocacy portfolio, with relatively little on implementation of existing laws. The issue of depth vs breadth in specific advocacy areas particularly in the context of limited remaining time of the project needs to be looked at as well.

Summary of responses to issues raised in previous annual reviews (where relevant)
- MJF continues to invest in social media as recommended in the 2014 Annual Review, and initiated its “Equality through Dignity” campaign in September 2014 as planned. This campaign, which aims to change society's attitude towards women by highlighting their contribution (unpaid/paid) to the family, community and the state, expects to make a contribution in reducing discrimination and violence against women and girls. Since changing social attitudes does not happen overnight, the cumulative effect of campaigns like this as well as MJF’s on-going advocacy in other areas like VAWG, workers’ rights, child labour and land issue, has placed the organisation in an advantage position to convey the messages of the marginalised at the policy arena.
- As recommended in the 2014 AR, this output is a focus of the current M&E review. The review has suggested that as well as measuring the number of policy advocacy campaigns, MJF should also measure the numbers of laws influenced. This is a smarter indicator and reflects different types of advocacy activity. The review has suggested that this could be further divided into three sub-indicators measuring MJF’s contribution to the drafting of laws, the enactment of laws and the implementation of laws.
- The indicators will need accompanying narrative evidence of MJF’s contribution. This narrative is relevant to recommendation 6.1 below.

Recommendations
6.1.	DFID and MJF should commission case studies, to be completed by January 2016, drawing on the outcome attribution and impact monitoring data, on powerful change processes that MJF has been involved in over the last 12 years. This should include learning from failure.
6.2	MJF should review and prioritise its policy advocacy efforts in relation to the following two findings (among others) and should establish an advocacy strategy strategic document for the whole programme as well as for individual components. It should feed these recommendations into a broader strategic planning process – by September 2015:
  - Reduce number and range of issues covered in order to cover selected issues in greater depth based on clear value for money rationale.
  - Balance a high profile legislative advocacy agenda against ongoing advocacy for more effective implementation of existing legislation and policies.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key Cost Drivers and Performance
In the reporting periods, MJF has efficiently spent £8 million under the COPE program. Of the money spent, the major expenditure categories are: grants made to partner NGOs for different programme activities; programme management cost (e.g. project monitoring, partner’s capacity, personnel costs for programme management, staffs development) research, policy & advocacy related costs (workshop/conference, policy research, advocacy & campaign, communication and documentation); and administration costs. Approximately 79% of the total costs were incurred by partner organisations, 10% is spent for program operating costs, 9% on staff salaries-MJF admin and programme staff, and the remaining 2% for central supplies and procurement costs. COPE spent 90% of its projection for the year. Unit costs have remained fairly consistent, with some adjustment for inflation on the staff pay and overheads. Political instability had an impact on partner review planning process but only limited financial implications.

MJF has established an effective financial monitoring system to oversee the costs in relation to the prescribed financial policy and procedures. During budget negotiation with its NGO partners, the key component of the project cost is ascertained and on the basis of market rate, values are estimated. In the financial monitoring process and quarterly financial reports, costs are further evaluated and compared to the estimates. As well as a check on value for money, this review can also help to identify unauthorised or irregular expenditure by partners.

MJF has ascertained a good procurement system and the capital items of the projects are procured through competitive process. All partner organisations have a procurement policy and they comply with the central procurement procedure. Under the COPE program, MJF has established the process of unit cost analysis to guide its partners to obtain maximum inputs at the lowest possible costs. Programme and finance jointly reviews quarterly progress report and provide feedback to ensure recommendations are communicated to relevant partner NGOs.

VfM performance compared to the original VfM proposition in the business case
COPE adopts and uses Value for Money (VFM) systematically to demonstrate efficient spending of economic resources and producing maximum benefit for the wellbeing of the poor and disadvantaged people in the programme locations.

Based on the proposition of the business case, MJF has specified some core VFM indicators in the logical framework and developed measurement procedures. MJF has carried out rigorous processes to ensure cost efficiency of all spending. During the budget negotiation every activity is assessed, evaluated and rationalised by its costs.

The Business Case included a cost benefit analysis. The original VFM proposition in the Business Case estimated a benefit to cost ratio for the benefits that it was possible to quantify, and concluded that the programme was highly viable and offered opportunities for significant return. The internal rate of return (IRR) of the investment was estimated to be 20%. That analysis did not include some significant benefits which cannot be quantified otherwise the IRR and net present values (NPVs) would be higher. The review found no reason to revisit the assumptions underpinning the appraisal.

For the VFM measures in the logical framework, benefits estimates have been made across the three key programme components including: i) value of access to khas land and water bodies; ii) total amount of social safety net support received; and iii) earning increase monthly of marginalised people in CHT by £9. Performance against the VFM measures is on track, as follows:
- Value of khas land and water bodies received by the landless and marginalised at £1.84 million;
- An over-achievement of 33% on access gained to government safety net services and estimated value of £4.11 million;
- 8129 poor and marginalised people in target CHT communities have increased their monthly income by at least £9 through income generating activities;
- 8455 workers received £336,348 as maternity, termination, retrenchment and lay off benefits.

During the reporting period, most outputs and outcomes have overachieved against their indicators. Effective program implementation has ensured quality services for the poor and marginalised, particularly in the areas of inclusion in social safety net schemes, fixing minimum wage and increase annual payment of formal sectors workers, and government extension services. Moreover, skills development support to women for income generating activities helped them to ensure additional income and begin moving out of poverty traps.

Assessment of whether the programme continues to represent value for money
COPE has played a key role in supporting poor and marginalised people to enjoy a better quality of life as well as MJF’s evolution as a leading human rights based organization in Bangladesh. Overall VFM performance indicates that COPE continues to represent good value for money. Since the 2014 Annual Review, COPE has delivered good results at output and outcome levels and is offering value for money. The programme is overachieving against most of the milestones for the present reporting period despite spending less compared to previous year. It has driven down unit cost per beneficiary by introducing efficient unit cost tracking procedures, and has offered capacity building training using internal resources such as resource persons, venue and food at low cost. A part of the MJF office is used for training purposes, saving funds previously required for rental and transportation costs.

Quality of financial management
MJF has an integrated financial management system which includes sound internal control at each stage of fund transfer, financial monitoring, standard policies and procedures, secured accounting software, budgetary control, risk assessment, standard procurement, delegation of authority and internal and external audits. Finance staff members visit partner organisation twice annually to review fiduciary risk and controls. Feedback from the report is shared with the partner to ensure mitigating steps are taken to ensure effective financial stewardship. The quarterly financial reports and call forwards are also reviewed by the finance team and recommendations passed on before disbursement.

The activity-based financial reporting system enables tracking of all expenditures against each budget line. MJF has been conducting budget variance analysis yearly and estimates future cost through financial projections. To ensure financial accountability, every fiscal year MJF finance department prepares a risk assessment of all partner NGOs using a prescribed score sheet. The team also prioritises monitoring visits based on risk assessment and takes appropriate action as applicable. All funds are subject to regular audit internally and externally. In addition, DFID commissions external audits of a random sample of PNGOs on an annual basis. The last audit, FY-2014 did not raise any major observation. MJF have also prepared an appropriate action plan for the previous audit observations. The review looked at the process through which MJF and its partners reporting suspected fraud or corruption. As a result of this review, MJF has updated its fraud reporting system and process and is working with all its downstream partners to ensure they are aware of DFID’s policies on counter fraud and whistleblowing.

Date of last narrative financial report	7th May, 2015
Date of last audited annual statement	12th May, 2015

E: RISK

Overall Risk Rating: Medium

Overview of programme risk
COPE programme is managed through an accountable grant agreement. MJF is responsible for delivering the programme and for financial oversight of DFID funds. DFID has worked with MJF for over 13 years and during this period MJF has consistently delivered results. External financial audits and procurement reviews have found that MJF has the systems and policies in place to manage DFID funds.

The overall risk environment has changed recently owing to the political unrest in Bangladesh, particularly in the first part of 2015. MJF regularly assesses risks to programme implementation relating to this and has a number of mitigating strategies which they are employing to minimise the impact on their programmes. The most significant impact has been on MJF’s Governance projects, and in particular work with local government (output 4) but projects have also faced restrictions when reaching out to government officials, and work on sensitive issues such as access to land has been particularly hard hit.

The political unrest also affected DFID’s ability to visit branch offices and view MJF projects since January 2015, and restricted MJF’s own monitoring of its partners (although it didn’t prevent all monitoring: MJF staff were able to adjust the timing of their travel to work around the blockades). All blockades and hartals were lifted by the end of March and as of May 2015 movement is unrestricted and government officials are more accessible again.

Outstanding actions from risk assessment
- MJF and partners will continue to assess and mitigate the impact of any further political unrest in Bangladesh on MJF programmes;
- DFID is currently supporting MJF to update their Operating Procedures for fraud reporting and to improve and strengthen counter-fraud communications to staff across the organisation;
- In terms of management arrangement the 2014 AR noted the need to strengthen the M&E unit with closer oversight from MJF senior management to improve on results reporting and communications around advocacy work. The M&E review is ongoing and is expected to be completed by Dec 2015.

Recommendations
MJF should develop a strategic approach of managing large closing bank balances in its central operating accounts and within its partners to reduce cash management risk.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe
MJF is ahead of target across all output indicators and on track for delivery against the planned timeframe. Political unrest from January – March 2015 has generated some delays in implementation of project activities, particularly those requiring significant cross-country travel, and limitations to engagement with government but these have not caused significant delays overall.

Performance of partnership(s)
The partnership between DFID, DFAT and MJF is performing well, with good, regular communication. MJF has developed vibrant partnerships with its project implementation partners and it is clear that partners value their relationships with MJF (see Feedback from Beneficiaries on the next page for more details).

MJF and its partners recommend that DFID should be more hands on and link up better to other programmes it funds (e.g. RTI work by the British Council under the Transparency and Right to Information Programme).

Asset monitoring and control
MJF management and grantees are equally confident and satisfied with the uses of program fixed assets. The following procedures are in place for asset monitoring and control:
- Physical verification/spot checks are carried out on a quarterly basis;
- Fixed assets are registered with ID numbers;
- External audit reports confirm validation and existence of assets in an integrated asset register.

G: CONDITIONALITY

Update on partnership principles
The Partnership Principles do not directly affect DFID funding for the COPE programme, because no project funds pass through the government. The Principles include a commitment to strengthening domestic accountability that relates closely to the mandate of COPE. While there are concerns about ongoing political instability, and a contraction of the space for independent media and civil society, there are also some signs of Government of Bangladesh commitment to increasing accountability in some of the areas the project works on, ranging from active engagement with implementation of the RTI Act to efforts to improve regulation within the Garment industry.

H: MONITORING & EVALUATION

Direct feedback you have had from stakeholders, including beneficiaries
Throughout the annual review process, feedback was collected from a large range of beneficiaries including: large and small NGO partners, government counterparts, civil society groups and Community Based Organisations, media and direct beneficiaries of project initiatives. Across the board feedback was very positive about both MJF and its partners.

MJF’s partners organisations have system in place of receiving regular beneficiary feedback and response to exert maximum benefits of the project. For example, one MJF project partner has changed their staff working time to address beneficiaries’ need. Now their working time is afternoon to late evening and they meet the beneficiaries in the evening for meetings and training. The review team also received direct feedback from the beneficiaries. For instance, members of the dalit community in Jessore (implemented by NGO Paritran) spoke on how they were more accepted by other members of the community than in the past.

Some areas of improvement that were identified for MJF were:
- MJF should provide its partners with more technical knowledge: MJF can produce and/or access research, evidence and international good practice examples that would help its partners develop more sophisticated and up to date ways of working
- There should be more sharing and replication amongst partners under COPE: Partners vary in their capacity and could learn from each other and from each other’s successes.
- Projects should be more flexible: successes should be allowed to scale up within the life of the current project rather than waiting for a new round of funding.

Feedback on DFID was also sought as part of this process and the following issues were identified:
- Donor funding patterns are pushing NGOs toward becoming project subcontractors with very few opportunities for NGOs to specialise in their core competency areas. Future funding needs to be flexible enough to support NGOs’ own vision for change, as well as donor objectives.
- More funding should have been allocated to the work that MJF is doing: MJF and its partners do work that other organisations or structures are not able to take up. MJF’s unique selling point is that it is not only a channel for funding to a selection of small and medium-sized NGOs on issues of governance, rights and accountability, but also a partner in advocacy work, with a strong emphasis on building the capacity of its partners. For example, as well as working at a local level with NGOs on workers’ rights, MJF and its another NGO partner have also been closely involved in the drafting of Labour Law and the implementing rules for them. Similar policy level advocacy is on-going on land issue.
- DFID should ensure better linkages and dialogue between MJF and its partners and other relevant programmes (e.g. work on RTI that will be done under the Transparency and Right to Information Programme).

Evidence and evaluationAs discussed above, DFID and MJF are currently undertaking a Monitoring and Evaluation review for COPE specifically and MJF more broadly. While MJF already has in place systems to ensure accurate and consistent reporting against output indicators, this review will help ensure that MJF more consistently gathers evidence of its qualitative and transformative impact in future. For this, the review will develop a plan for MJF to strengthen its quantitative, qualitative monitoring system along with its internal M&E capacity. The review will also propose some indicative evaluation questions on which programme evaluation over the remaining period should focus on.

Monitoring progress throughout the review period
The Annual Review team comprised:
- DFIDB Governance Adviser (Team Leader)
- DFIDB Private Sector Adviser
- DFIDB Extreme Poverty Team Leader and Social Development Adviser
- DFIDB, Programme Manager, Extreme Poverty Team
- DFIDB, Financial Adviser

The process included 4 days of field visits including visits to projects run by the following organisations:
- Rights of the Marginalised: Paritran, Uttoran
- Combating Violence against Women: Banchte Shekha
- Protection of Working Children and Vulnerable Workers: SAFE, WAFWSD, AWAJ
- Ensuring Responsiveness of Public Institutions:JJS, MLAA, Rupantar

We also arranged a phone conversation with the following CHT partners: Hille Hilly; Green Hill; Taungya, CIPD, ASHIKA.

The team was accompanied on the field visits by the DFIDB Lead Adviser and Programme Manager for COPE, the MJF M&E Advisor and the relevant MJF programme managers.