## Logframe
PROJECT NAME | Libya Security, Justice and Defence Phase 2 Delta (while programme remains out of Libya)
IMPACT | Impact Indicator 1 |  | Baseline 2014 | Target to Sep 2015 | Not Applicable | Not Applicable | Not Applicable
Progress towards a political settlement and contribute towards the prevention of further conflict and decline, at the national and local level. (extract from Oct 14 NSC strategy for Libya) | Extent of progress towards a political settlement | Planned | Minimal Progress (2) | No Agreement Negotiations Continue (3)
Achieved
Source
UNSMIL reports and HMG DipTels used by Post Board to expertly assess the extent of progress towards a political settlement using the following scoring: 1=Breakdown of UNSMIL Lead Talks, 2= Minimal Progress, 3 = No Agreement Negotiations Continue, 4 = Substantial Progress, 5 = Political settlement Achieved.
| Impact Indicator 2 |  | Baseline 2014 | Target to Sep 2015 | Not Applicable | Not Applicable | Not Applicable
| Degree of conflict and decline at a national and local level. | Planned | Low level civil war | 0 -No further decline
Achieved
Source
UNSMIL reports and HMG DipTels used by Post Board to expertly assess the situation in Libya using the following scoring mechanism: -2= Significant Deterioration (hence minus number) (high intensity conflict and sugnificant increase in body count ), -1= Slight Deterioration (upward trend in violence, increasing body count and geopraphic spread of conflict), 0 = No Further Decline (currently assessed as low level civil war - ongoing instability and sporadic outbreaks of violence), +1 = Slight Improvement (hence positive number) (reduced trend in violence, decreased body count and geographical spread of conflict) (reduced violence), 5 = Significant Improvement (ceasefire largely holding)
OUTCOME | Outcome Indicator 1 |  | Baseline 2014 | Target to Sep 2015 | Not Applicable | Not Applicable | Not Applicable | Assumptions
Security, Justice and Defence (SJD) support to political settlement. Prevention of further conflict and decline at 8 key locations. | Usefulness of support to UNSMIL and the International Community on the SJD aspects of a political settlement produced by Cardno at Output 1 below. | Planned | Some Use (2) | Good Use (3) |  |  |  | (1) The UNSMIL political settlement negotiations continue to focus on a Government of National Unity, with political, military/militia and civil society tracks. (2) There are no further drivers of conflict applied to these locations such as an expansion of the ISIL influence or a spread of the low level civil war.
Achieved
Source
UNSMIL, International Community and Cross Whitehall feedback and expert assessment by Post Board against the following criteria (1) No Use (2) Some Use (3) Good Use (4) Very Useful (5) Exceptionally Useful. Useful = any or all of speeding up, better focussing, better informing, or improving the chance of success of the political settlement negotiations.
| Outcome Indicator 2 |  | Baseline 2014 | Target to Sep 2015 | Not Applicable | Not Applicable | Not Applicable
| Perceptions of Social Peace at 8 key locations (Sabha (DDG) , Nalut, Taji, Murzuq, Aubari, Suq-al-Juma (Tripoli district), Bani Walid, Al Sahel (PCi)) covered at Output 2 and 3 below. | Planned | Average score 2.75 | Average Score 2.75
Achieved
Source
Quarterly reports from Danish Demining Group and Peaceful Change Initiative and results of the final PCi Social Peace Survey (which rates each location against a number of criteria from 1= Bad, 2= Fairly Bad, 3= Neutral, 4= Fairly Good, 5 = Good - (TBC PCi can also measure Sabha) with independent expert assessment by the Libya Post Board.
| Outcome Indicator 3 |  | Baseline 2014 | Target to Sep 2015 | Not Applicable | Not Applicable | Not Applicable
Planned
Achieved
|  |  | Source |  |  |  |  | RISK RATING
High
INPUTS (£) | CSSF (£) |  | Govt (£) | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
£1.22M
INPUTS (HR) | CSSF (FTEs)
1
OUTPUT 1 | Output Indicator 1.1 |  | Baseline 2014 | Target to Sep 2015 | Not Applicable | Not Applicable | Not Applicable | Assumption
SJD analysis in support of the political settlement. | Timely and quality delivery of national population surveys | Planned | 1 | An additional 2 |  |  |  | (1) Cardno Emerging Market Ltd deliverables on contract by week commencing 15th Jun 15. (2) Internationals continue to be barred from travelling to Libya but local Libyan staff can continue to work including leaving the country to meet internationals overseas. Note this work is on the DFID baseline.
Achieved
Source
Receipt of Cardno report to satisfactory quality (as assessed by Head of SJD and DFID project manager) and as per timelines defined in contract.
| Output Indicator 1.2 |  | Baseline 2014 | Target to Sep 2015 | Not Applicable | Not Applicable | Not Applicable
| Timely and quality delivery of media monitoring reports | Planned | 2 | An additional 2
Achieved
Source
Receipt of Cardno report to satisfactory quality (as assessed by Head of SJD and DFID project manager) and as per timelines defined in contract.
| Output Indicator 1.3 |  | Baseline 2014 | Target to Sep 2015 | Not Applicable | Not Applicable | Not Applicable
| Timely and quality delivery of conflict dynamics reports | Planned | 1 | An additional 3
Achieved
Source
Receipt of Cardno report to satisfactory quality (as assessed by Head of SJD and DFID project manager) and as per timelines defined in contract.
IMPACT WEIGHTING (%) | Output Indicator 1.4 |  | Baseline 2014 | Target to Sep 2015 | Not Applicable | Not Applicable | Not Applicable
30% | Timely and quality delivery of civil society mapping | Planned | 0 | 1
Achieved
|  | Source | [5 empty] | RISK RATING
|  | Receipt of report to satisfactory quality (as assessed by Head of SJD and DFID project manager) and as per timelines defined in contract. | [5 empty] | High
INPUTS (£) | CSSF (£) |  | Govt (£) | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
£385K
INPUTS (HR) | CSSF (FTEs)
0.3 + 0.5 DFID Conflict Advisor
OUTPUT 2 | Output Indicator 2.1 |  | Baseline 2014 | Target to Sep 2015 | Not Applicable | Not Applicable | Not Applicable | Assumptions
Capable tier 2 National Leadership Group (NLG). ‘Partnerships’ between local government and community leaders. | NLG conflict management actions undertaken in accordance with agreed Charter. | Planned | 0 | 1 |  |  |  | Note 4 SPLD locations are Zuwarah, Benghazi, Tobruk and Al Bayda. 7 current locations are Nalut, Taji, Murzuq, Aubari, Suq-al-Juma (Tripoli district), Bani Walid and Al Sahel . Assumption - Internationals continue to be barred from travelling to Libya but local Libyan staff can continue to work including leaving the country to meet internationals overseas. Note this work is on the FCO baseline.
Achieved
Source
Expert assessment by Libya Post Board of account of 1 conflict management action against agreed Charter - account to be provided by PCi in quarterly reports.
| Output Indicator 2.2 |  | Baseline 2014 | Target to Sep 2015 | Not Applicable | Not Applicable | Not Applicable
| Number of locations Social Peace and Local Development (SPLD) programme have been rolled out to. | Planned | 7 | 11 (4 additional)
Achieved
Source
Quarterly reports from PCi and independent testiment from Libyan locations where available.
| Output Indicator 2.3 |  | Baseline 2014 | Target to Sep 2015 | Not Applicable | Not Applicable | Not Applicable
Planned
Achieved
Source
IMPACT WEIGHTING (%) | Output Indicator 2.4 |  | Baseline 2014 | Target to Sep 2015 | Not Applicable | Not Applicable | Not Applicable
35% |  | Planned
Achieved
|  | Source | [5 empty] | RISK RATING
High
INPUTS (£) | CSSF (£) |  | Govt (£) | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
£310K
INPUTS (HR) | CSSF (FTEs)
0.35
OUTPUT 3 | Output Indicator 3.1 |  | Baseline 2014 | Target to Sep 2015 | Not Applicable | Not Applicable | Not Applicable | Assumptions
Increased safety and security in Sabha. | Number of people including percentage of women reached with mine risk education messages to International Mine Action Standards (IMAS) standards through community and schools visits. | Planned | No data available | 3000 people at least 40% of which (1200) are women. |  |  |  | Internationals continue to be barred from travelling to Libya but local Libyan staff can continue to work including leaving the country to meet internationals overseas. Note this work is on the FCO baseline.
Achieved
Source
Quarterly and final reports from DDG and results of DDG internal Quality Assurance assessmentsto IMAS standards.
| Output Indicator 3.2 |  | Baseline 2014 | Target to Sep 2015 | Not Applicable | Not Applicable | Not Applicable
| Extent of ERW (non-technical) survey and marking of threats to IMAS Expolosive Ordinance Disposal (EOD) level 2 with reports entered into Information Management System Mine Action (IMSMA) database. | Planned | Partially complete - comprehensive data not available. | Fully complete for all contaminated areas in Sabha (but not the surrounding area).
Achieved
Source
Quarterly reports and final report from Danish Demining Group on surveys and marking and confirmation from UNMAS that non-technical survey reports have been entered into the IMSMA database managed by UN Mine Action Service (UNMAS) and Libyan Mine Action Centre (LibMAC) - the Libyan technical authority.
| Output Indicator 3.3 |  | Baseline 2014 | Target to Sep 2015 | Not Applicable | Not Applicable | Not Applicable
Planned
Achieved
Source
IMPACT WEIGHTING (%) | Output Indicator 3.4 |  | Baseline 2014 | Target to Sep 2015 | Not Applicable | Not Applicable | Not Applicable
30% |  | Planned
Achieved
|  | Source | [5 empty] | RISK RATING
High
INPUTS (£) | CSSF (£) |  | Govt (£) | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
£500K
INPUTS (HR) | CSSF (FTEs)
0.3
OUTPUT 4 | Output Indicator 4.1 |  | Baseline 2014 | Target to Sep 2015 | Not Applicable | Not Applicable | Not Applicable | Assumptions
Planned
Achieved
Source
| Output Indicator 4.2 |  | Baseline 2014 | Target to Sep 2015 | Not Applicable | Not Applicable | Not Applicable
Planned
Achieved
Source
| Output Indicator 4.3 |  | Baseline 2014 | Target to Sep 2015 | Not Applicable | Not Applicable | Not Applicable
Planned
Achieved
Source
IMPACT WEIGHTING (%) | Output Indicator 4.4 |  | Baseline 2014 | Target to Sep 2015 | Not Applicable | Not Applicable | Not Applicable
Planned
Achieved
|  | Source | [5 empty] | RISK RATING
INPUTS (£) | DFID (£) |  | Govt (£) | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 5 | Output Indicator 5.1 |  | Baseline 2014 | Target to Sep 2015 | Not Applicable | Not Applicable | Not Applicable | Assumptions
Planned
Achieved
Source
| Output Indicator 5.2 |  | Baseline 2014 | Target to Sep 2015 | Not Applicable | Not Applicable | Not Applicable
Planned
Achieved
Source
| Output Indicator 5.3 |  | Baseline 2014 | Target to Sep 2015 | Not Applicable | Not Applicable | Not Applicable
Planned
Achieved
Source
IMPACT WEIGHTING (%) | Output Indicator 5.4 |  | Baseline 2014 | Target to Sep 2015 | Not Applicable | Not Applicable | Not Applicable
Planned
Achieved
|  | Source | [5 empty] | RISK RATING
INPUTS (£) | DFID (£) |  | Govt (£) | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)

## Results Chain
Libya Security, Justice and Defence Phase 2 Delta (while programme remains out of Libya)
OUTPUTS |  |  | OUTCOME | IMPACT
1 | SJD analysis in support of the political settlement. | 30% | Security, Justice and Defence (SJD) support to political settlement. Prevention of further conflict and decline at 8 key locations. | Progress towards a political settlement and contribute towards the prevention of further conflict and decline, at the national and local level. (extract from Oct 14 NSC strategy for Libya)
2 | Capable tier 2 National Leadership Group (NLG). ‘Partnerships’ between local government and community leaders. | 35%
3 | Increased safety and security in Sabha. | 30%
4 | 0 | 0%
5 | 0 | 0%

## Logframe Summary
Libya Security, Justice and Defence Phase 2 Delta (while programme remains out of Libya)
Results Chain |  |  | Indicators | Baseline 2014 | Not Applicable | Source
IMPACT | Progress towards a political settlement and contribute towards the prevention of further conflict and decline, at the national and local level. (extract from Oct 14 NSC strategy for Libya) |  | Extent of progress towards a political settlement | Minimal Progress (2) | 0 | 0
|  |  | Degree of conflict and decline at a national and local level. | Low level civil war | 0 | 0
OUTCOME | Security, Justice and Defence (SJD) support to political settlement. Prevention of further conflict and decline at 8 key locations. |  | Usefulness of support to UNSMIL and the International Community on the SJD aspects of a political settlement produced by Cardno at Output 1 below. | Some Use (2) | 0 | 0
|  |  | Perceptions of Social Peace at 8 key locations (Sabha (DDG) , Nalut, Taji, Murzuq, Aubari, Suq-al-Juma (Tripoli district), Bani Walid, Al Sahel (PCi)) covered at Output 2 and 3 below. | Average score 2.75 | 0 | 0
|  |  | 0 | 0 | 0 | 0
OUTPUTS | SJD analysis in support of the political settlement. | 30% | Timely and quality delivery of national population surveys | 1 | 0 | Receipt of Cardno report to satisfactory quality (as assessed by Head of SJD and DFID project manager) and as per timelines defined in contract.
|  |  | Timely and quality delivery of media monitoring reports | 2 | 0 | Receipt of Cardno report to satisfactory quality (as assessed by Head of SJD and DFID project manager) and as per timelines defined in contract.
|  |  | Timely and quality delivery of conflict dynamics reports | 1 | 0 | Receipt of Cardno report to satisfactory quality (as assessed by Head of SJD and DFID project manager) and as per timelines defined in contract.
|  |  | Timely and quality delivery of civil society mapping | 0 | 0 | Receipt of report to satisfactory quality (as assessed by Head of SJD and DFID project manager) and as per timelines defined in contract.
| Capable tier 2 National Leadership Group (NLG). ‘Partnerships’ between local government and community leaders. | 35% | NLG conflict management actions undertaken in accordance with agreed Charter. | 0 | 0 | Expert assessment by Libya Post Board of account of 1 conflict management action against agreed Charter - account to be provided by PCi in quarterly reports.
|  |  | Number of locations Social Peace and Local Development (SPLD) programme have been rolled out to. | 7 | 0 | Quarterly reports from PCi and independent testiment from Libyan locations where available.
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
| Increased safety and security in Sabha. | 30% | Number of people including percentage of women reached with mine risk education messages to International Mine Action Standards (IMAS) standards through community and schools visits. | No data available | 0 | Quarterly and final reports from DDG and results of DDG internal Quality Assurance assessmentsto IMAS standards.
|  |  | Extent of ERW (non-technical) survey and marking of threats to IMAS Expolosive Ordinance Disposal (EOD) level 2 with reports entered into Information Management System Mine Action (IMSMA) database. | Partially complete - comprehensive data not available. | 0 | Quarterly reports and final report from Danish Demining Group on surveys and marking and confirmation from UNMAS that non-technical survey reports have been entered into the IMSMA database managed by UN Mine Action Service (UNMAS) and Libyan Mine Action Centre (LibMAC) - the Libyan technical authority.
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
| 0 | 0% | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
| 0 | 0% | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0

## Annual Review
Libya Security, Justice and Defence Phase 2 Delta (while programme remains out of Libya)
Results Chain |  |  | Indicators | Planned | Achieved | Score |  | Risk | Planned | Achieved | Score |  | Risk | Planned | Achieved | Score |  | Risk | Planned | Achieved | Score |  | Risk
|  |  |  | 2015 |  | 2015 |  | 2015 | able |  | able |  | able | able |  | able |  | able | Not Applicable |  | able |  | able
IMPACT | Progress towards a political settlement and contribute towards the prevention of further conflict and decline, at the national and local level. (extract from Oct 14 NSC strategy for Libya) |  | Extent of progress towards a political settlement | No Agreement Negotiations Continue (3) | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
|  |  | Degree of conflict and decline at a national and local level. | 0 -No further decline | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
OUTCOME | Security, Justice and Defence (SJD) support to political settlement. Prevention of further conflict and decline at 8 key locations. |  | Usefulness of support to UNSMIL and the International Community on the SJD aspects of a political settlement produced by Cardno at Output 1 below. | Good Use (3) | 0 | n/a | 0% |  | 0 | 0 | n/a | 0% |  | 0 | 0 | n/a | 0% |  | 0 | 0 | n/a | 0%
|  |  | Perceptions of Social Peace at 8 key locations (Sabha (DDG) , Nalut, Taji, Murzuq, Aubari, Suq-al-Juma (Tripoli district), Bani Walid, Al Sahel (PCi)) covered at Output 2 and 3 below. | Good Use (3) | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
|  |  | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
OUTPUTS | SJD analysis in support of the political settlement. | 30% | Timely and quality delivery of national population surveys | An additional 2 | 0 | n/a | 0% |  | 0 | 0 | n/a | 0% |  | 0 | 0 | n/a | 0% |  | 0 | 0 | n/a | 0%
|  |  | Timely and quality delivery of media monitoring reports | An additional 2 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
|  |  | Timely and quality delivery of conflict dynamics reports | An additional 3 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
|  |  | Timely and quality delivery of civil society mapping | 1 | 1 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
| Capable tier 2 National Leadership Group (NLG). ‘Partnerships’ between local government and community leaders. | 35% | NLG conflict management actions undertaken in accordance with agreed Charter. | 1 | 0 | n/a | 0% |  | 0 | 0 | n/a | 0% |  | 0 | 0 | n/a | 0% |  | 0 | 0 | n/a | 0%
|  |  | Number of locations Social Peace and Local Development (SPLD) programme have been rolled out to. | 11 (4 additional) | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
|  |  | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
|  |  | 0 | 1 | 1 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
| Increased safety and security in Sabha. | 30% | Number of people including percentage of women reached with mine risk education messages to International Mine Action Standards (IMAS) standards through community and schools visits. | 3000 people at least 40% of which (1200) are women. | 1 | n/a | 0% |  | 0 | 0 | n/a | 0% |  | 0 | 0 | n/a | 0% |  | 0 | 0 | n/a | 0%
|  |  | Extent of ERW (non-technical) survey and marking of threats to IMAS Expolosive Ordinance Disposal (EOD) level 2 with reports entered into Information Management System Mine Action (IMSMA) database. | Fully complete for all contaminated areas in Sabha (but not the surrounding area). | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
|  |  | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
|  |  | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
| 0 | 0% | 0 | 0 | 0 | n/a | 0% |  | 0 | 0 | n/a | 0% |  | 0 | 0 | n/a | 0% |  | 0 | 0 | n/a | 0%
|  |  | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
|  |  | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
|  |  | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
| 0 | 0% | 0 | 0 | 0 | n/a | 0% |  | 0 | 0 | n/a | 0% |  | 0 | 0 | n/a | 0% |  | 0 | 0 | n/a | 0%
|  |  | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
|  |  | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
|  |  | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
OVERALL OUTPUT SCORE |  | 95% |  |  |  | n/a | 0% |  |  |  | n/a | 0% |  |  |  | n/a | 0% |  |  |  | n/a | 0%
| Value | Threshold
A++ | 150% | 137.5% | Outputs substantially exceeded expectation
A+ | 125% | 112.5% | Outputs moderately exceeded expectation
A | 100% | 87.5% | Outputs met expectation
B | 75% | 62.5% | Outputs moderately did not meet expectations
C | 50% |  | Outputs substantially did not meet expectations
n/a | 0%
Risk
Low | 1
Medium | 2
High | 3