## Logframe
PLEASE NOTE - NON RED TABS ON THIS WORKBOOK ARE SELF POPULATING FROM THE RED TABS. PLEASE POPULATE THE RED TABS.
PROJECT NAME | Support to UNICEF for Syria Crisis
IMPACT | Impact Indicator 1 |  | Baseline 2015 | June 2015 | Target 2015
Lives saved, suffering reduced, dignity maintained and resilience promoted | N/A as one year humanitarian programme | Planned
Achieved
Source
| Impact Indicator 2 |  | Baseline 2015 | June 2015 | Target 2015
Planned
Achieved
Source
OUTCOME | Outcome Indicator 1 |  | Baseline 2015 | June 2015 | Target 2015 | Assumptions
Critical humanitarian needs alleviated amongst conflict affected persons | Extent to which UNICEF has adopted a whole of Syria approach measured on scale of 0 to 25 | Planned | tbc | tbc | tbc
Achieved
Source
DFID Whole of Syria approach assessment
| Outcome Indicator 2 |  | Baseline 2015 | June 2015 | Target 2015
| CHASE Annual Review score on reform priorities | Planned | N/A | N/A | A
Achieved
Source
CHASE assessment from Annual Review
| Outcome Indicator 3 |  | Baseline 2015 | June 2015 | Target 2015
Planned
Achieved
|  |  | Source |  |  | RISK RATING
| DFID (£) |  | Govt (£) | Other (£) | Total (£)
INPUTS (HR) | DFID (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline 2015 | June 2015 | Target 2015 | Assumption
Emergency assistance in WASH, Health, Nutrition, Education, Protection and Basic Needs provided within Syria | Food:-Number of supplementary food interventions (packages, hot meals, vouchers, cash) provided to individuals. | Planned | 0 | 55640 | 111280
Achieved
Source
Appeal document
| Output Indicator 1.2 |  | Baseline 2015 | June 2015 | Target 2015
| WASH - Number of beneficiaries provided with drinking water | Planned | 0 | 660000 | 1320000
Achieved
Source
Appeal document
| Output Indicator 1.3 |  | Baseline 2015 | June 2015 | Target 2015
| Health - Number of vaccinations provided | Planned | 0 | 224000 | 448000
Achieved
Source
| Output Indicator 1.4 |  | Baseline 2015 | June 2015 | Target 2015
| Protection - Number of child visits (daily sign-ins) to child/adolescent friendly spaces | Planned | 0 | 15400 | 30800
Achieved
|  | Source |  |  |  | RISK RATING
Appeal document
IMPACT WEIGHTING (%) | Output Indicator 1.5 |  | Baseline 2015 | June 2015 | Target 2015
45% | Education - Number of pupils provided with access to non-formal education | Planned | 0 | 64000 | 128000
Achieved
Source
Appeal document
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£)
INPUTS (HR) | DFID (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline 2014 | Milestone 2015 | Target 2015 | Assumptions
Emergency assistance in WASH, Health, Nutrition, Education, Protection and Basic Needs provided within Lebanon | WASH - Number of beneficiaries provided with drinking water | Planned | 0 | 8584 | 17168
Achieved
Source
Appeal document
| Output Indicator 2.2 |  | Baseline 2014 | Milestone 2015 | Target 2015
| Education - Number of beneficiaries of teaching and learning materials provided | Planned | 0 | 4205 | 8410
Achieved
Source
| Output Indicator 2.3 |  | Baseline 2015 | June 2015 | Target 2015
| Protection - Number of child visits (daily sign-ins) to child/adolescent friendly spaces | Planned | 0 | 2755 | 5510
Achieved
Source
Appeal document
IMPACT WEIGHTING (%) | Output Indicator 2.4 |  | Baseline 2015 | June 2015 | Target 2015
30% |  | Planned
Achieved
|  | Source |  |  |  | RISK RATING
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£)
INPUTS (HR) | DFID (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline 2015 | June 2015 | Target 2015 | Assumptions
Emergency assistance in WASH, Health, Nutrition, Education, Protection and Basic Needs provided within Jordan | WASH - Number of beneficiaries provided with drinking water | Planned | 0 | 57656.5 | 115313
Achieved
Source
Appeal document
| Output Indicator 3.2 |  | Baseline 2015 | June 2015 | Target 2015
| Education - Number of beneficiaries of teaching and learning materials provided | Planned | 0 | 357 | 714
Achieved
Source
Appeal document
| Output Indicator 3.3 |  | Baseline 2015 | June 2015 | Target 2015
| Protection - Number of child visits (daily sign-ins) to child/adolescent friendly spaces | Planned | 0 | 6039 | 12078
Achieved
Source
Appeal document
IMPACT WEIGHTING (%) | Output Indicator 3.4 |  | Baseline 2015 | June 2015 | Target 2015
25% |  | Planned
Achieved
|  | Source |  |  |  | RISK RATING
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£)
INPUTS (HR) | DFID (FTEs)
OUTPUT 4 | Output Indicator 4.1 |  | Baseline 2014 | Milestone 2015 | Target 2015 | Assumptions
Planned
Achieved
Source
| Output Indicator 4.2 |  | Baseline 2014 | Milestone 2015 | Target 2015
Planned
Achieved
Source
| Output Indicator 4.3 |  | Baseline 2014 | Milestone 2015 | Target 2016
Planned
Achieved
Source
IMPACT WEIGHTING (%) | Output Indicator 4.4 |  | Baseline 2014 | Milestone 2015 | Target 2016
Planned
Achieved
Source
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£)
INPUTS (HR) | DFID (FTEs)
OUTPUT 5 | Output Indicator 5.1 |  | Baseline 2014 | Milestone 2015 | Target 2016 | Assumptions
Planned
Achieved
Source
| Output Indicator 5.2 |  | Baseline 2014 | Milestone 2015 | Target 2016
Planned
Achieved
Source
| Output Indicator 5.3 |  | Baseline 2015 | June 2015 | Target 2015
Planned
Achieved
Source
IMPACT WEIGHTING (%) | Output Indicator 5.4 |  | Baseline 2015 | June 2015 | Target 2015
Planned
Achieved
|  | Source |  |  |  | RISK RATING
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£)
INPUTS (HR) | DFID (FTEs)

## Results Chain
Support to UNICEF for Syria Crisis
OUTPUTS |  | WEIGHTING | OUTCOME | IMPACT
1 | Essential services provided in Syria | 45% | Critical humanitarian needs alleviated amongst conflict affected persons | Lives saved, suffering reduced, dignity maintained and resilience promoted
2 | Essential services provided in Lebanon | 30%
3 | Essential services provided in Jordan | 25%
4 | 0 | 0%
5 | 0 | 0%
100%

## Logframe Summary
Results Chain |  | Weighting | Country | Indicator | Baseline 2015 | Target 2015
IMPACT | Lives saved, suffering reduced, dignity maintained and resilience promoted |  |  | N/A as one year humanitarian programme | 0 | 0
|  |  |  | 0 | 0 | 0
OUTCOME | Critical humanitarian needs alleviated amongst conflict affected persons |  |  | Extent to which UNICEF has adopted a whole of Syria approach measured on scale of 0 to 25 | tbc | tbc
|  |  |  | CHASE Annual Review score on reform priorities | N/A | A
|  |  |  | 0 | 0 | 0
OUTPUTS | Emergency assistance in WASH, Health, Nutrition, Education, Protection and Basic Needs provided within Syria | 45% | Syria | Food:-Number of supplementary food interventions (packages, hot meals, vouchers, cash) provided to individuals. | 0 | 111280
|  |  |  | WASH - Number of beneficiaries provided with drinking water | 0 | 1320000
|  |  |  | Health - Number of vaccinations provided | 0 | 448000
|  |  |  | Protection - Number of child visits (daily sign-ins) to child/adolescent friendly spaces | 0 | 30800
|  |  |  | Education - Number of pupils provided with access to non-formal education |  | 128000
| Emergency assistance in WASH, Health, Nutrition, Education, Protection and Basic Needs provided within Lebanon | 30% | Lebanon | WASH - Number of beneficiaries provided with drinking water | 0 | 17168
|  |  |  | Education - Number of beneficiaries of teaching and learning materials provided | 0 | 8410
|  |  |  | Protection - Number of child visits (daily sign-ins) to child/adolescent friendly spaces | 0 | 5510
|  |  |  | 0 | 0 | 0
| Emergency assistance in WASH, Health, Nutrition, Education, Protection and Basic Needs provided within Jordan | 25% | Jordan | WASH - Number of beneficiaries provided with drinking water | 0 | 115313
|  |  |  | Education - Number of beneficiaries of teaching and learning materials provided | 0 | 714
|  |  |  | Protection - Number of child visits (daily sign-ins) to child/adolescent friendly spaces | 0 | 12078
|  |  |  | 0 | 0 | 0
| 0 | 0% |  |  | 0 | 0
[5 empty] | 0 | 0
|  |  |  | 0 | 0 | 0
|  |  |  | 0 | 0 | 0
| 0 | 0% |  | 0 | 0 | 0
|  |  |  | 0 | 0 | 0
|  |  |  | 0 | 0 | 0
|  |  |  | 0 | 0 | 0

## Annual Review
Support to UNICEF for Syria Crisis
Results Chain |  | Weighting | Indicators | Planned | Achieved | Score |  | Risk | Planned | Achieved | Score |  | Risk
|  |  |  | June 2015 |  | 2015 |  | 2015 | 2015 |  | 2015 |  | 2015
IMPACT | Lives saved, suffering reduced, dignity maintained and resilience promoted |  | N/A as one year humanitarian programme | 0 | 0 |  |  |  | 0 | 0
|  |  | 0 | 0 | 0 |  |  |  | 0 | 0
OUTCOME | Critical humanitarian needs alleviated amongst conflict affected persons |  | Extent to which UNICEF has adopted a whole of Syria approach measured on scale of 0 to 25 | tbc | 0 | n/a | 0% |  | tbc | 0 | n/a | 0%
|  |  | CHASE Annual Review score on reform priorities | N/A | 0 |  |  |  | A | 0
|  |  | 0 | 0 | 0 |  |  |  | 0 | 0
OUTPUTS | Emergency assistance in WASH, Health, Nutrition, Education, Protection and Basic Needs provided within Syria | 45% | Food:-Number of supplementary food interventions (packages, hot meals, vouchers, cash) provided to individuals. | 55640 | 0 | n/a | 0% |  | 111280 | 0 | n/a | 0%
|  |  | WASH - Number of beneficiaries provided with drinking water | 660000 | 0 |  |  |  | 1320000 | 0
|  |  | Health - Number of vaccinations provided | 224000 | 0 |  |  |  | 448000 | 0
|  |  | Protection - Number of child visits (daily sign-ins) to child/adolescent friendly spaces | 15400 | 0 |  |  |  | 30800 | 0
|  |  | Education - Number of pupils provided with access to non-formal education | 64000 | 0 |  |  |  | 128000 | 0
| Emergency assistance in WASH, Health, Nutrition, Education, Protection and Basic Needs provided within Lebanon | 30% | WASH - Number of beneficiaries provided with drinking water | 8584 | 0 | n/a | 0% |  | 17168 | 0 | n/a | 0%
|  |  | Education - Number of beneficiaries of teaching and learning materials provided | 4205 | 0 |  |  |  | 8410 | 0
|  |  | Protection - Number of child visits (daily sign-ins) to child/adolescent friendly spaces | 2755 | 0 |  |  |  | 5510 | 0
|  |  | 0 | 0 | 0 |  |  |  | 0 | 0
| Emergency assistance in WASH, Health, Nutrition, Education, Protection and Basic Needs provided within Jordan | 25% | WASH - Number of beneficiaries provided with drinking water | 57656.5 | 0 | n/a | 0% |  | 115313 | 0 | n/a | 0%
|  |  | Education - Number of beneficiaries of teaching and learning materials provided | 357 | 0 |  |  |  | 714 | 0
|  |  | Protection - Number of child visits (daily sign-ins) to child/adolescent friendly spaces | 6039 | 0 |  |  |  | 12078 | 0
|  |  | 0 | 0 | 0 |  |  |  | 0 | 0
| 0 | 0% |  | 0 | 0 | n/a | 0% |  | 0 | 0 | n/a | 0%
|  |  |  | 0 | 0 |  |  |  | 0 | 0
|  |  | 0 | 0 | 0 |  |  |  | 0 | 0
|  |  | 0 | 0 | 0 |  |  |  | 0 | 0
| 0 | 0% | 0 | 0 | 0 | n/a | 0% |  | 0 | 0 | n/a | 0%
|  |  | 0 | 0 | 0 |  |  |  | 0 | 0
|  |  | 0 | 0 | 0 |  |  |  | 0 | 0
|  |  | 0 | 0 | 0 |  |  |  | 0 | 0
OVERALL OUTPUT SCORE |  | 100% |  |  |  | n/a | 0% |  |  |  | n/a | 0%
| Value | Threshold
A++ | 150% | 137.5% | Outputs substantially exceeded expectation
A+ | 125% | 112.5% | Outputs moderately exceeded expectation
A | 100% | 87.5% | Outputs met expectation
B | 75% | 62.5% | Outputs moderately did not meet expectations
C | 50% |  | Outputs substantially did not meet expectations
n/a | 0%
Risk
Low | 1
Medium | 2
High | 3

## Risk
No | Potential Risk | Gross Risk | [5 empty] | Mitigation actions by partner | Net Risk | Any additional mitigation actions by DFID
|  | Likelihood | Likelihood value | Impact |  | Risk Factor
|  |  | #N/A |  | #N/A | #N/A | #N/A
|  |  | #N/A |  | #N/A | #N/A | #N/A
|  |  | #N/A |  | #N/A | #N/A | #N/A
|  |  | #N/A |  | #N/A | #N/A | #N/A
|  |  | #N/A |  | #N/A | #N/A | #N/A
|  |  | #N/A |  | #N/A | #N/A | #N/A
|  |  | #N/A |  | #N/A | #N/A | #N/A
|  |  | #N/A |  | #N/A | #N/A | #N/A
|  |  | #N/A |  | #N/A | #N/A | #N/A
|  |  | #N/A |  | #N/A | #N/A | #N/A
|  |  | #N/A |  | #N/A | #N/A | #N/A
|  |  | #N/A |  | #N/A | #N/A | #N/A
|  |  | #N/A |  | #N/A | #N/A | #N/A
|  |  | #N/A |  | #N/A | #N/A | #N/A
|  |  | #N/A |  | #N/A | #N/A | #N/A
|  |  | #N/A |  | #N/A | #N/A | #N/A
|  |  | #N/A |  | #N/A | #N/A | #N/A
|  |  | #N/A |  | #N/A | #N/A | #N/A
|  |  | #N/A |  | #N/A | #N/A | #N/A
|  |  | #N/A |  | #N/A | #N/A | #N/A
|  |  | #N/A |  | #N/A | #N/A | #N/A
|  |  | #N/A |  | #N/A | #N/A | #N/A
|  |  | #N/A |  | #N/A | #N/A | #N/A
|  |  | #N/A |  | #N/A | #N/A | #N/A
|  |  | #N/A |  | #N/A | #N/A | #N/A
|  |  | #N/A |  | #N/A | #N/A | #N/A
|  |  | #N/A |  | #N/A | #N/A | #N/A
|  |  | #N/A |  | #N/A | #N/A | #N/A
|  |  | #N/A |  | #N/A | #N/A | #N/A
|  |  | #N/A |  | #N/A | #N/A | #N/A
|  |  | #N/A |  | #N/A | #N/A | #N/A
|  |  | #N/A |  | #N/A | #N/A | #N/A
|  |  | #N/A |  | #N/A | #N/A | #N/A
|  |  | #N/A |  | #N/A | #N/A | #N/A
|  |  | #N/A |  | #N/A | #N/A | #N/A
|  |  | #N/A |  | #N/A | #N/A | #N/A
|  |  | #N/A |  | #N/A | #N/A | #N/A
|  |  | #N/A |  | #N/A | #N/A | #N/A
|  |  | #N/A |  | #N/A | #N/A | #N/A
|  |  | #N/A |  | #N/A | #N/A | #N/A
|  |  | #N/A |  | #N/A | #N/A | #N/A
|  |  | #N/A |  | #N/A | #N/A | #N/A
|  |  | #N/A |  | #N/A | #N/A | #N/A
|  |  | #N/A |  | #N/A | #N/A | #N/A
|  |  | #N/A |  | #N/A | #N/A | #N/A
|  |  | #N/A |  | #N/A | #N/A | #N/A
|  |  | #N/A |  | #N/A | #N/A | #N/A
#N/A

## Delivery Plan
Delivery Plan |  |  | Last updated (date):
A. BASIC PROJECT INFORMATION
Project Title:
ARIES Project Number:
Component code:
Country:
Sector:
Total Value (£):
Start/End Date:
Implementing partner:
Partner contact details: |  | Name:
Job Title:
E-mail:
Telephone:
Latest Annual Review Score:
B.1 SYRIA TEAM PROJECT LEADS
Senior Responsible Owner:
DPM/Project Officer:
Lead Humanitarian Adviser:
Other Advisers (country):
B.2 SRO OBJECTIVES FOR THE PROJECT
1
2
3
4
5
6
C. KEY PROJECT DOCUMENTATION
Document |  |  | Quest Number |  | Last updated (date)
Business Case:
Grant Agreement:
Due Diligence Assessment:
Logframe:
Annual Review (last, include score):
Field Monitoring Report (provide details in section H)
Project Completion Review:
Performance Improvement Plan:
D. SUMMARY OF PROJECT PROGRESS AND KEY ISSUES SINCE LAST MEETING WITH SRO
E. CHECKLIST FOR KEY SYRIA TEAM AND DFID SMART RULES KEY REQUIREMENTS
Action | [6 empty] | Completed? (Yes, No, Partial, Exempt, N/A) | Date
Before project approval | A new project has been set up in ARIES with each country taking a separate component code
A PROJAs has been completed in ARIES ensuring the prepipeline amounts are correct
DPM has read the Syria M&E paper and understands responsabilities/steps that must be followed for reporting and annual reviews
Reporting guidance has been shared with partner and partner has agreed to comply
Project logframe has been approved by the Syria team M&E lead
For multilaterals the logframe has been sent to the DFID institutional lead for their review (ensuring it reflects MAR reforms)
After project approval (within first week) | Project has been approved by Lindy/Matthew in ARIES
Partner has been informed that the project has been approved
For more significant/larger grants a letter has been sent from the Secretary of State to the partner
All relevant project documents (e.g. Business Case, IRS, Proposal, Logframe) have been quested
Partner has confirmed if they are content to be named publically
International Engagement Team have been informed of project financial details for SoS announcements
Financial project details have been recorded in the regional allocation spreadsheet (update each year)
In ARIES a single PO for the grant with separate lines for each FY of each country (and linking to the component code) has been set up
If cost extension under the umbrella BC the appropriate amounts have been PROJMed from the dumping component and profiled by FY
Project details have been recorded in the database
Logframe data has been recorded in the database (update each year)
Reporting calendar has been recorded in the database
Financial assets have been recorded in the database
Due Diligence Assessment has been sent to Risk and Control
Before signing the MoU/GA | UK aid branding letter and guidelines have been sent to the partner and partner has agreed to comply
Counter terrorism legislation has been discussed with partner and partner is aware of their responsibilities
Obligations expected of partners and their downstream partners under the UK Bribery Act 2010 have been discussed and agreed with partner
Partner has been consulted if they would like advanced or arrears quarterly payments (only applicable to NGOs)
If funding covers retroactive results (backdating the grant) this has been approved by the SOR or FCPD
When drafting the MoU or GA | Does MoU/GA include paragraph on contingency of year 2 funding where multiyear?
Does MoU/GA include paragraph on sanctions for AGs?
Does MoU/GA include paragraph on branding?
Does MoU/GA include paragraph detailing reporting dates and deliverables?
Does MoU/GA include paragraph on proactively notifying DFID of loss/fraud/damage to supplies/operations?
Does MoU/GA include paragraph on proactively notifying DFID of issues affecting registration for agencies on XB?
Does MoU/GA include paragrah on Counter Terrorism legislation?
When finalising the MoU or GA | Has the MoU been signed by Matthew Wyatt (or Anna Morris in his absence)
Have you printed, had signed and couriered 3 copies to the agency? Of which:
One copy is to be retained by the agency
One copy is to be sent to DFID accounts payable with the RFF
Onecopy is to be stored in the agreement hardcopies folder
Has the formal MoU/GA with 2 signatures been quested?
After MoU/GA has been signed | For projects using UK aid branding, digital elements (e.g. websites) have been reviewed by the DFID’s Digital Service Team
Partner’s Annual Audited Accounts have been quested (update each year)
F. RECORD OF KEY ACTIONS TO BE TAKEN BY THE SYRIA TEAM OR PARTNER (INCLUDING ISSUES TO BE ADDRESSED FROM BUSINESS CASE, DUE DILIGENCE ASSESSMENT, ANNUAL REVIEW, PERFORMANCE IMPROVEMENT PLAN AND FIELD MONITORING REPORTS)
Action to be taken by |  | Source |  | Details of the action |  |  |  | By when (date)? | Key Quest doc no. | Notes/Completed? (Y, N, Partial)
G. RECORD OF QUARTERLY MEETINGS/COMMUNICATIONS WITH PARTNER (this table should also be completed at the planning stage with the quarterly meetings expected to happen with partners)
Who (DPM/Adviser) |  | Where (London HQ, country) |  | Date | Meeting notes Quest no. | Issues/areas discussed
H. FIELD MONITORING (this table should completed with details of the planned field monitoring, in general this should be at least once per year in each country, except Syria)
Who (DPM/Adviser) |  | Where (London HQ, country) |  | Date | Meeting notes Quest no. | Issues/areas discussed
I. LOGFRAME CHANGES (if needed record any changes to the logframe in the seciton below)
Version No. | Date | Author | Approved by | Summary of changes |  |  |  | Quest references
I. PERFORMANCE IMPROVEMENT PLAN (if needed, key actions are already included as below)
Action to be taken by |  | Source |  | Details of the action |  |  |  | By when (date)? | Key Quest doc no. | Notes/Completed? (Y, N, Partial)
SRO |  |  |  | Formal letter to partner explaining PIP
SRO |  |  |  | Formal response from partner with key actions
DPM |  |  |  | Monthly field level meetings on finance, performance against logframe and risk mitigation measures
DPM |  |  |  | Monthly/quarterly HQ meetings

## Indicators
Sector
NOTES
Food
Food | 1.1 | Number of monthly full food packages/vouchers/cash provided to individuals | Min 1500 Kcal
Food | 1.2 | Number of supplementary food interventions (packages, hot meals, vouchers, cash) distributed
Wash
Water | 2.1 | Number of beneficiaries provided with drinking water
Sanitation | 2.2 | Number of beneficiaries reached with sanitation activities
Hygiene | 2.3 | Number of beneficiaries reached with hygiene activities
Health
Health | 3.1 | Number of trauma consultations
Health | 3.2 | Number of primary health care consultations
Health | 3.3 | Number of health workers trained
Health | 3.4 | Number of vaccinations provided
Health | 3.5 | Number of facilities benefitting from medical supplies
Shelter/NFIs
Shelter | 4.1 | Number of people supported through shelter interventions
NFIs | 4.2 | Number of relief packages distributed
NFIs | 4.3 | Number of individuals benefiting from relief packages
NFIs | 4.4 | Number of cash grants, intended to purchase relief items, distributed
Agriculture/ Livelihoods
Agriculture | 5.1 | Number of people supported through agricultural interventions
Livelihoods | 5.2 | Number of people supported through livelihood interventions
Protection
Protection | 6.1 | Number of people benefitting from SGBV services
Protection | 6.2 | Number of children supported by psycho-social interventions
Protection | 6.3 | Number of adults supported by psycho-social interventions
Protection | 6.4 | Number of people trained in MHPSS and GBV services provided
| 6.5 | Number of child/adolescent friendly places/child psychosocial service centres
Education
Education | 7.1 | Number of pupils per month provided with formal education
Education | 7.2 | Number of pupils per month provided with informal education
Education | 7.3 | Number of school supplies provided
Education | 7.3a | Number of pupils provided with school supplies
Education | 7.4 | Number of improved school facilities
Enabling activities
Enabling activities | 8.1 | Number of high quality needs assessments undertaken | High quality defined as: relevant topic, good use of analysis, objective, clear recommendations targeted at policy makers
Enabling activities | 8.2 | Number of people targeted with humanitarian information campaigns

## Background
Risk Rating
Gross Risk
Likelihood of occurrence |  | Impact |  | Combined Risk Factor |  | Combined risk factor
Almost certain | 5 | Severe | 5 | Severe | >15 | 20 | Severe | 5 | 5 | 10 | 15 | 20 | 25
Likely | 4 | Major | 4 | Major | 8 to 14 | 19 | Severe | 4 | 4 | 8 | 12 | 16 | 20
Possible | 3 | Moderate | 3 | Moderate | 5 to7 | 18 | Severe | 3 | 3 | 6 | 9 | 12 | 15
Unlikely | 2 | Minor | 2 | Minor | 1 to 4 | 17 | Severe | 2 | 2 | 4 | 6 | 8 | 10
Rare | 1 | Insignificant | 1 |  |  | 16 | Severe | 1 | 1 | 2 | 3 | 4 | 5
[6 empty] | 15 | Severe |  | 1 | 2 | 3 | 4 | 5
[6 empty] | 14 | Major
[6 empty] | 13 | Major
[6 empty] | 12 | Major
[6 empty] | 11 | Major
[6 empty] | 10 | Major
[6 empty] | 9 | Major
[6 empty] | 8 | Major
[6 empty] | 7 | Moderate
[6 empty] | 6 | Moderate
[6 empty] | 5 | Moderate
[6 empty] | 4 | Minor
[6 empty] | 3 | Minor
[6 empty] | 2 | Minor
[6 empty] | 1 | Minor