Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Business in the Community: Private Sector Engagement Programme
Programme Value: £755,000		Review Date: 15 July 2014
Programme Code: 203417	Start Date: 15 July 2013	End Date: 15 June 2018

Summary of Programme Performance
Year	2014	2015
Programme Score	A	A+
Risk Rating	Low	Low

Summary of progress and lessons learnt since last review

After two years of the programme there is increasing awareness and interest among businesses, especially BITC member companies, to engage on international disaster response (IDR). The programme has helped to strengthen the engagement of these companies, and to inspire others to find out more. The programme has, and should continue to, add value in supporting strategic level business engagement in relevant global policy fora to influence the direction of business engagement in the sector, for example via the World Economic Forum and World Humanitarian Summit.

Summary of recommendations for the next year

1. DFID and BITC to agree a joint plan to promote the 2016 Award through relevant networks.
  1. BITC to target business projects to enter the 2016 IDR Award which aligns with DFID policy priorities including disaster preparedness, response, and resilience including if possible, conflict related emergencies.
  2. DFID to promote the IDR Award to its network including DFID strategic partner companies and to encourage humanitarian agencies and NGOs to promote the IDR Award to their corporate partners.

Acknowledging that the number of companies working in complex conflict affected locations and willing to profile their work is limited, working with DFID, BITC could explore and seek to identify case studies and Award entries from private sector engagement in conflict affected countries, particularly middle income countries such as Turkey or Jordan ahead of the WHS summit.

DFID/BITC to update logframe to ensure necessary support to any major disaster response (such as Nepal in 2015) is captured.

DFID/BITC to refine terminology “International Disaster Relief”, for example to “International Disaster Relief and Disaster Management”, to better reflect the contribution BITC is making to the whole humanitarian programme cycle rather than only immediate response.

BITC to define specific focus and format of the “Matching Tool” as soon as possible so that development process can begin, and so that complementarity with existing tools can be ensured.

DFID to facilitate inputs from relevant teams across DFID including Private Sector Department/CHASE operational response teams and Policy and Partnership Group.

BITC to work with UN OCHA to identify and disseminate appropriate materials and capacity building support to help business understand and engage effectively in humanitarian coordination structures.

BITC to encourage member network to use the INFORM Risk Index and to identify high risk countries to prioritise for mapping of business contributions as part of the “Matching Tool” process.

BITC to consider responding to expressions of interest to run disaster simulation exercises for individual organisations with both business and humanitarian partners, based on costs to be covered by requesting organisations.

Following the World Humanitarian Summit October synthesis report, DFID and BITC should agree a strategy on how BITC might continue to engage with WHS and build this into BITC’s 2016 workplan and logframe. BITC and DFID should seek clarification from UN OCHA on the mechanism for direct business engagement with the Summit itself, and the role that BITC could play in identifying companies to attend.

DFID to share information with existing networks within the humanitarian sector in the UK (for example START network, BOND, DEC) to facilitate opportunities for dialogue between business and humanitarian agencies, where BITC’s added value will be to convene and work with business, its core target audience.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-203417/documents/
DevTracker Link to Log frame:

Outline of the programme

The UK will provide up to £755,000 over a 5 year period to Business in the Community to help improve the coordination and effectiveness of the UK private sector when they respond to humanitarian emergencies.

The intended impact of the programme is the private sector is better harnessed to reduce human suffering in humanitarian disasters

The intended outcome of the programme is the private sector operating in the UK is better prepared to respond quickly, effectively and appropriately to humanitarian crises

Specific outputs include:

Increased insight and understanding for business on how they can best assist during humanitarian emergencies. This will involve the development and delivery of annual BITC International Disaster Relief Award (Award) as part of the BITC International Disaster Relief programme (IDRP), and the production and dissemination of best practice guidelines, case studies and insight reports.

Partnerships between NGOs and businesses are created. This will be done through forums for collaboration and development of a “Matching Tool” to identify and link businesses’ actual, and potential, contributions and engagement on this agenda with non-government organisations (NGOs).

Raised awareness amongst business and NGOs of the importance and effectiveness of the private sector in humanitarian response. This will be achieved through capacity building for business to identify their unique contribution and evidenced in the number of businesses showcasing their International Disaster Relief programme in their corporate communications.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment A+

DFID assesses that the BITC programme has moderately exceeded expectations
The BITC Private Sector Engagement Programme has moderately exceeded expectations in year two. The programme delivered on its core business – engaging business on the humanitarian agenda and developing best practice case studies, but also adapted quickly to big emergencies (Ebola and Nepal for example) where BITC facilited business contributions. The response of the private sector, operating in the UK, to major crises has been encouraging, in terms of both the scale and sophistication of the contributions increasingly moving beyond philanthropy. Notably, BITC also responded rapidly to DFID’s request to host a UK business consultation to contribute to the World Humanitarian Summit process capitalising on a time sensitive opportunity to influence the debate.

Overall output score and description

DFID assesses that overall the output score is A+. BITC moderately exceeded expecations.

In year two, BITC delivered on all programme outputs, and exceeded some, despite demanding challenges emerging including several major emergencies, staffing turnover in both DFID and BITC and increased policy attention at the global level as the World Humanitarian Summit nears.

BITC has ensured business participation in key programme activities has been good, including the disaster simulation exercise and the London World Humanitarian Summit business consultation. Entries to the 2015 IDR Award also doubled in year two demonstrating progressive awareness raising.

Key lessons

Preparations for the World Humanitarian Summit benefited from BITC’s engagement this year. BITC also hold a place on the Private Sector Working Group advising the Secretariat. The advisory group is well placed to advise on the best format and mechanisms to engage business and create meaningful dialogue at the WHS sessions in Istanbul.

In May 2015, ICAI published a review of DFID’s engagement with the private sector in development. Although the review didn’t examine this programme specifically, DFID should draw upon the review to guide best practice.

A number of opportunities have been provided for exposure to business leaders for DFID humanitarian staff who have attended simulation exercises, contributed to consultations and assisted in judging panels for example. This secondary outcome is welcome and could be more systematically expanded within the DFID humanitarian cadre.

Not all businesses can see the link between disaster relief programmes and business benefits, particularly in countries where they do not have direct operations. It remains vital to build and communicate a strong business case for business engagement, particularly in difficult contexts.

BITC has identified a lack of opportunities for engagement and dialogue between business and operational humanitarian teams rather than fundraisers. Where this has happened, there is demand for more of these types of opportunities. Business is also interested in better understanding humanitarian coordination structures and requested BITC to support.

Business engagement is increasingly well recognised and, for the leading companies, includes sophisticated approaches going beyond simply cash donations. There is however, still a strong focus on immediate response and on natural disasters. Relatively few companies are engaging extensively in disaster preparedness, resilience and risk mitigation, and in conflict related emergencies. In addition to response, there is an appetite for guidance on preparedness and resilience in particular. There is also an appetite from business to identify opportunities for strategic engagement in these areas.

In line with the findings of the research, Business Unique Contribution- International Disaster Relief conducted by BITC, there is increasing recognition that business has an important contribution to make beyond cash, including products, skills, services, expertise and capabilities. There is a need for more effective mapping and matching of these broader capacities, recognising that matching in these areas requires more long term relationships and building understanding among all partners involved. The “Matching Tool” will help the agenda move beyond a longstanding circular challenge of business not knowing what to offer and humanitarian agencies not knowing what to ask for, by mapping the whole range of business contributions in different contexts. The INFORM risk register has been identified as a means by which to identify the high risk countries to focus on initially.

There is willingness amongst business to collaborate, not only with humanitarian partners but also with other businesses, to maximise the value of their contribution to IDR. There is limited infrastructure for business to business collaboration in disasters, and BITC could play a valuable role here, including working with business directly and potentially working with some existing structures such as chambers of commerce and industry and trade bodies.

Lastly, the term, International Disaster Relief, which is used to describe this work and which was agreed by BITC and DFID at the start of the programme, refers to disaster preparedness, response, recovery and risk mitigation. Given, however, how the humanitarian sector has moved during the five years since the programme discussions began, there is a question on whether this term remains appropriate and effectively communicates the whole spectrum of BITC’s contribution to the agenda. There would be a risk in changing the terminology at this point, given the branding of the programme and the work to date in raising awareness among business, but it is an issue worth considering. Given how the business market has begun to buy into the concept of IDR, there could now be an opportunity to develop the phrase used to describe our work, for example “IDR and disaster management”.

Has the logframe been updated since the last review?

Yes, a revised version of the logframe was agreed in April 2015 to include the delivery of a UK consultation with private sector to contribute to the World Humanitarian Summit consultations.
## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Increased insight and understanding for business on how they can best assist during humanitarian emergencies
Output number per LF		1	Output Score	A
Risk:		Low	Impact weighting (%):	30
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Development and delivery of annual BITC International Disaster Relief Award (Award) as part of the BITC International Disaster Relief programme (IDRP).	Workshop for business on engagement in programme and award application process: January 2015 / IDR award winners announced and profiled in July 2015 (following support to applicants, webinars, assessment and judging panel) / IDR Award to be held annually 2014-2018	Completed / Completed / 2015 Award completed
Numbers of best practice case studies identified	Second set of case studies published: June 2015 (10 new)	7 award case studies published / [supplemented by 34 mini case studies from Vanuatu and Nepal responses published]
Insight papers articulating the business case for business engagement in disaster relief.	First Insight Paper produced December 2015	On track
Online guidance for business on engagement with humanitarian community on BITC website (also relates to Output 3).	Develop new IDRP web pages and add revised guidance material: May 2015 / Refresh and populate BITC website with Award winners and case studies annually	Guidance posted for Typhoon Haiyan, Nepal Earthquake and Vanuatu Cyclone. / Completed

Key Points

DFID assesses BITC to have met expectations for this output

The second year of the IDR Award has been successful, with almost double the number of entries in 2015 compared to the previous year. The standard of the entries was high this year, with four strong contenders for the overall winner. Given the programme focuses on the whole spectrum of preparedness, response, recovery and risk mitigation, it was particularly encouraging that one of the finalists focussed specifically on disaster preparedness and resilience, and it is hoped that this case study will inspire other companies to consider contributing beyond immediate response.

A BITC IDR Working Group has been established, comprising BITC International Leadership Team and member companies with a particular interest and expertise in this topic. The Group will meet regularly to provide guidance and support to BITC’s work in IDR.

Summary of responses to issues raised in previous annual reviews (where relevant)

Recommendation from 2014 AR: DFID and BITC to look to strengthen the best practice case studies from next year’s Award by starting to target businesses early and using cross DFID knowledge to encourage firms already involved in humanitarian response to apply and share their experiences.

Update: Companies in BITC’s network were actively targeted from January 2015 and encouraged to apply. DFID provided support through a blog by Dylan Winder highlighting the Award. In 2016, it would be helpful for DFID to proactively reach out to companies it works with to encourage entries, and to agree a joint plan for promoting the Award.

Recommendation from 2014 AR: DFID and BITC to review logframe to ensure the programme addresses the emerging challenges businesses face engaging with the humanitarian community.

Update: Logframe revised in April 2015 with the inclusion of an indicator to deliver a UK consultation with business for the World Humanitarian Summit which took place in May 2015.

Recommendations

1. DFID and BITC to agree a joint plan to promote the 2016 Award through relevant networks.
  1. a.BITC to target business projects to enter the 2016 IDR Award which aligns with DFID policy priorities including disaster preparedness, response, and resilience including if possible, conflict related emergencies.
  2. b.DFID to promote the IDR Award to its network including DFID strategic partner companies and to encourage humanitarian agencies and NGOs to promote the IDR Award to their corporate partners.

Acknowledging that the number of companies working in complex conflict affected locations and willing to profile their work is limited, working with DFID, BITC could explore and seek to identify case studies and Award entries from private sector engagement in conflict affected countries, particularly middle income countries such as Turkey or Jordan ahead of the WHS summit.

DFID/BITC to update logframe to ensure necessary support to any major disaster response (such as Nepal in 2015) is captured.

DFID/BITC to refine terminology “International Disaster Relief”, for example to “International Disaster Relief and Disaster Management”, to better reflect the contribution BITC is making to the whole humanitarian programme cycle rather than only immediate response.

Output Title	Formal partnerships between NGOs and businesses are created
Output number per LF		2	Output Score	A+
Risk:		Low	Impact weighting (%):	40
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of new partnerships between NGOs and business established supported by the "Matching Tool"	"Matching Tool" concept drafted by June 2015	On track. Concept paper developed and shared with stakeholders for consultation
Number of forums and increase in dialogue around importance of engagement and partnerships between NGOs and business. Milestones 2 and 3 to be repeated annually.	4 meetings with NGOs on engaging with business held by December 2015.	On track. 2 meetings completed by June 2015

Key Points

DFID assesses that BITC has moderately exceeded expectations on this output.

Development of the ‘matching tool’ has been delayed in consultation with DFID. The logframe will be updated with a new target completion date of October 2015 for the completion of the “Matching Tool” concept

During Year 2 of the programme, BITC has proactively provided support in several major disaster responses including the Ebola crisis, Tropical Cyclone Pam in Vanuatu and the Nepal Earthquake. This has included encouraging business to contribute, providing support and guidance on how to do so, and matching business offers with NGO requests. For the Ebola crisis, BITC reached out to members for support based on a request for assistance from DFID. An insight and summary report was provided. This work is not specifically included as a formal activity in the logframe, but has taken considerable time from BITC staff and, in dialogue with DFID, delayed delivery of the “Matching Tool”. This was the most appropriate prioritisation given the context and demonstrated immediate value to the overall purpose of the programme in raising awareness and understanding. In addition, DFID requested BITC at short notice to run a UK World Humanitarian Summit business consultation in May 2015 to capitalise on a policy influencing opportunity. This took up a considerable amount of the BITC team capacity but was delivered rapidly, creatively and on schedule to meet the obejective [see output 3 for more detail].

Despite these other demands, the ‘matching tool’ scoping exercise was completed, mapping existing platforms and services for brokering business-humanitarian collaboration. Meetings are ongoing with the best known of these including International Health Partners (IHP)and Global Hand. The views of business have been canvassed through the BITC disaster simulation event in April 2015, the World Humanitarian Summit business consultation and the IDR Working Group. Consultation meetings have been held with NGOs to seek their views on the “Matching Tool”. BITC has developed a concept paper summarising the main issues and ideas emerging from these consultations and during the next quarter will be working to build on this to develop a final concept for the “Matching Tool” which can be piloted.

A great deal of learning has been generated on the matching process through BITC’s experience in supporting business engagement in recent disaster responses, including the Ebola Crisis, the Vanuatu Cyclone and the Nepal Earthquake. This learning is feeding into the development process for the “Matching Tool”. Specific matches, both business-humanitarian and business-business, have been achieved in the Vanuatu and Nepal responses.

Summary of responses to issues raised in previous annual reviews (where relevant)

Recommendation from 2014 AR: BITC and DFID should investigate opportunities to align development of its “Matching Tool” with OCHA’s work in the same area.

Update: BITC has discussed several times with UN OCHA about the un.business.org tool, and has also sought feedback from other stakeholders. The tool does not appear to be widely used, particularly beyond the UN, a fact that is informally recognised by UN OCHA. BITC is continuing, through the “Matching Tool” consultation process, to understand more about the pros and cons of the UN OCHA tool and other existing platforms for business-humanitarian matching, to ensure lessons are learned and inform the development of the BITC “Matching Tool”. UN OCHA has expressed support for the work of BITC in this area.

Recommendations

BITC to define specific focus and format of the “Matching Tool” as soon as possible so that development process can begin, and so that complementarity with existing tools can be ensured.

DFID to facilitate inputs from relevant teams across DFID including Private Sector Department/CHASE operational response teams and Policy and Partnership Group.

BITC to work with UN OCHA to identify and disseminate appropriate materials and capacity building support to help business understand and engage effectively in humanitarian coordination structures.

BITC to encourage member network to use the INFORM Risk Index and to identify high risk countries to prioritise for mapping of business contributions as part of the “Matching Tool” process.

Output Title	Raised awareness amongst business and NGOs of the importance and effectiveness of the private sector in humanitarian response
Output number per LF		3	Output Score	A++
Risk:		Low	Impact weighting (%):	30
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Capacity building for business to identify their unique contribution and better understand how it can be used.	Disaster simulation exercise April 2015	Completed
Number of face to face meetings with business targets	50 Meetings: May 2015	Completed. 56 meetings with business and 23 meetings with humanitarian agencies held by June 2015
Recommendations on role of business in disaster relief put forward to DFID to inform World Humanitarian Summit 2016 preparations [New indicator added in 2015]	UK WHS consultation with business held in May 2015 / Paper submitted to DFID and UN OCHA with recommendations for WHS agenda planning meeting by end June 2015.	Completed / Completed
Number of businesses showcasing their International Disaster Relief programme in their corporate communications. Milestone 1 will be repeated annually	Baseline established on number of BITC members showcasing IDR in corporate communications in 2014, by June 2015.	Completed

Key Points

DFID assesses that BITC has substantially exceeded expectation against this output

At the request of UN OCHA and DFID, BITC organised a World Humanitarian Summit business consultation event in London in May 2015. This was outside the original programme plan, and BITC was able to plan and deliver the event in a very short timescale without additional funding. The consultation was attended by over 50 people including participants from multiple business sectors including hospitality, pharmaceuticals, construction, legal, professional services, food and beverages, and telecommunications. The event was opened by the Minister of State Rt Hon Desmond Swayne. BITC submitted a report with findings and recommendations from the event to UN OCHA and DFID in June 2015. It is not yet clear from the UN what opportunities exist for business to directly engage in, and participate at, the Summit itself in 2016. BITC is on the WHS Private Sector Advisory Group and will offer to present their research, insight and findings at the Summit, and could add value in identifying relevant companies to attend.

A successful IDR simulation exercise was held in April 2015 as part of Responsible Business Week. The event was attended by business representatives from across different sectors and humanitarian experts, and focussed on a fictional cyclone hitting Mumbai. Businesses identified what their contribution would be in this scenario, and how they could collaborate with other businesses and humanitarian agencies to add value to the humanitarian response.

BITC has been actively engaging with businesses throughout the year to raise awareness of IDR and the ways that business can contribute. The target for meetings with businesses has been exceeded in Year 2, and meetings have also been held with a range of humanitarian organisations. A baseline survey has also been completed on the number of companies featuring IDR in their annual company and sustainability reports. This baseline will be used to track progress in the sector in subsequent years of the project.

Summary of responses to issues raised in previous annual reviews (where relevant)

Recommendation in 2014 AR: DFID to continue to work with BITC, their business partners and NGOs/UN agencies to raise awareness amongst business and NGOs of the importance and effectiveness of the private sector in humanitarian response.

Update: BITC has worked hard on this agenda and there is growing awareness of the importance of the role of business in international disaster relief, and increasing appetite from companies for guidance on how to put their contribution into practice.

Recommendations

BITC to consider responding to expressions of interest to run disaster simulation exercises for individual organisations with both business and humanitarian partners, based on costs to be covered by requesting organisations.

Following the World Humanitarian Summit October synthesis report, DFID and BITC should agree a strategy on how BITC might continue to engage with WHS and build this into BITC’s 2016 workplan and logframe. BITC and DFID should seek clarification from UN OCHA on the mechanism for direct business engagement with the Summit itself, and the role that BITC could play in identifying companies to attend.

DFID to share information with existing networks within the humanitarian sector in the UK (for example START network, BOND, DEC) to facilitate opportunities for dialogue between business and humanitarian agencies, where BITC’s added value will be to convene and work with business, its core target audience.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

The main cost driver is salary costs. Charge out rates and levels of engagement were agreed with partners in advance.

VfM performance compared to the original VfM proposition in the business case

In terms of costs and timeliness, BITC represent good value for money. BITC has also leveraged its existing business network to reduce costs for DFID. During this year of the programme, BITC member companies have hosted several events free of charge at their offices and venues, meaning programme funds have not been spent on event hosting. These have included the IDR report launch, IDR simulation event, World Humanitarian Summit business consultation, IDR Award judging day, IDR Working Group meeting. BITC members have also contributed time and expertise for free to the programme, for example pro-bono support from BT to develop the IDR simulation.

Assessment of whether the programme continues to represent value for money

This programme continues to offer value for money, as it capitalises on BITC’s strategic position as a hub for the private sector on responsible business and a central source of advice and guidance for the private sector and their existing experience of partnering with the public sector to leverage business to address social challenges.

BITC has delivered all products required against the revised logframe to date. In addition, BITC has also been able to deliver additional activities not included in the original logframe, within the original budget, demonstrating excellent value for money. This has included the planning and delivery of the World Humanitarian Summit business consultation, and actively reaching out to business to support engagement, matching and coordination in major disasters including the Ebola crisis, Vanuatu cyclone and the Nepal earthquake. These activities have added value to the overall programme and have generated additional learning to feed into the core outputs.

Quality of financial management

A revised budget forecast was agreed in February 2015, based on the revised logframe. Claims have been in line with the budget forecasts.

A narrative and financial reporting schedule has been agreed and is being adhered to.

E: RISK (½ page)

Overall risk rating: Low

Overview of programme risk

Risks identified at the outset of the project remain valid.

The risk is low that there will be insufficient interest and commitment among business and humanitarian agencies to pursue this agenda. Evidence from the first two years of the programme is that there is a strong desire amongst business and NGOs to pursue this agenda, and that business is willing to contribute to the disaster responses that have occurred since the programme started.

DFID engagement in key events including Ministerial and senior management participation in the International Disaster Relief Award and the World Humanitarian Summit business consultation has assisted in engaging key stakeholders and all signs point to little difficulty in further engaging the private sector.

The risk that there will be insufficient international disasters to warrant business engagement is also low. During the last year of the programme, business have contributed to several disasters including the Ebola Crisis, Nepal Earthquake and Vanuatu Cyclone.

Outstanding actions from risk assessment

There are no outstanding actions.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

All relevant timeframes have been met. Due to additional support and advice the BITC International Team gave business in the wake of the Ebola crisis, the staff changes at both BITC and DFID, and also the initial feedback on the “Matching Tool” concept, there has been some changes to the timeframe for the development of the “Matching Tool”. In the revised logframe, this is now included as a more iterative process to allow for more consultation and piloting. This will not affect the programme meeting its overall timeframe.

Performance of partnership (s)
There have been several staff changes within programme teams at DFID and one at BITC. Despite this, good relationships have been developed and there is common agreement on the direction of the programme and ways of working.
BITC has notably demonstrated a high level of flexibility and commitment to the partnership in their willingness to organise and deliver the World Humanitarian Summit business consultation at short notice.

Asset monitoring and control

None

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

Not applicable.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

A baseline survey was developed in the first year of the programme, and a monitoring plan is being developed to track key metrics at relevant stages throughout the programme.

A baseline survey was completed during Year 2, capturing data on which companies are featuring IDR in their corporate communications, in the form of websites, company annual reports and sustainability reports. The survey looked at a 10% sample of BITC members as a proxy measure of the wider private sector operating in the UK. This baseline will allow BITC to track changes in the level of business engagement in IDR each year during the remainder of the programme.

Monitoring progress throughout the review period

Reporting and monitoring arrangements are included in the Accountable Grant arrangements. BITC has provided four quarterly reports during this year of the programme. BITC and DFID hold regular meetings (approximately once per month) to track progress of the programme. One visit to BITC offices was undertaken by the SRO and programme manager for the production of this review.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessment
Key points
Summary of response to programme issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process