Annual Review - Summary Sheet

Title: ACCESS TO FAMILY PLANING COMMODTIES IN NIGERIA
Programme Value: £18 Million / (Over 6 years 2011/12- 2016/17)		Review Date: 15 March 2015
Programme Code: / 202668-101	Start Date: / Oct 2011	End Date: / March 2017

Summary of Programme Performance
Year	2011	2012	2013	2014
Programme Score	N/A	N/A	B	A
Risk Rating	N/A	N/A	Medium	Medium

Summary of progress and lessons learnt since last review
The project provided 1.19 million couple years of protection (CYP), which is about one fifth above its target of 1 million CYP for the year, and increased access to a mix of quality contraceptives. The procurement of additional long acting reversible contraceptives (LARC) contributed to a more efficient mix of contraceptives, achieving a higher CYP at lower costs. Stock outs of contraceptives diminished by half since last year. The condition of the Central Contraceptive Warehouse (CCW) was satisfactory. Channel software developed and installed by UNFPA for supply chain management is in operation and has potential for support to integrated supply chain management for all medical supplies including contraceptives.
In 2014, the total supply of 3.1 million CYP through the basket fund for family planning (FP) commodities, including the support by Department for International Development (DFID), has had substantial catalytic effects on FP supply chain management at state and lower levels and on the further uptake of FP services. The fact that FP commodities were brought in the country resulted in a policy on free FP services in Nigeria, Government commitments on FP for the first time, an increasing number of partners joining, FP logistics management and software triggering and contributing to integrated supply chain management of essential medicines and contraceptives, and also review/re-supply (RRS) meetings in the whole country, improved coordination, capacity building and awareness of family planning. The number of new FP acceptors more than doubled.
At outcome level, results from the Nigerian Demographic Health Survey (NDHS) in 2013 do not signal much progress. Outcome indicators requiring survey data, like the Contraceptive Prevalence Rate (CPR), were not measured in 2014.
The main cost driver of the project is procurement of contraceptive commodities and delivery to the Central Contraceptive Warehouse (CCW) in Lagos, at a value of £3 million per year. This is covered by Output 1. The review assigns a scoring weight of 70% to this output.
All other activities that attribute to an efficiently managed national contraceptive supplies and logistical management system (Output 2) are funded by the United Nations Population Fund (UNFPA), the Government of Nigeria (GoN) and other Development Partners (DP). These interventions mainly concern ‘last mile’ distribution efforts between States and Service Delivery Points (SDPs). The review assigned a scoring weight of 30% to output 2.
Variations in FP supply chain management at state and lower levels remain, and it is likely to continue until Government institutionalise integrated supply management. Similarly, stakeholder coordination and supply chain management at federal level (Procurement Supply Management Sub-Committee (PSM) and UNFPA) serves its purpose for the short term, but requires a pertinent role of the Federal Ministry of health (FMoH) in the near future. UNFPA is exploring possibilities with states and Development Partners (DPs) on last mile distribution models that are integrated, government driven and likely more sustainable.

Summary of recommendations for the next year
1. DFID and UNFPA with other development partners should explore the window of opportunity offered by the passage of the National Health Bill, using the platform of the Development Partners Group (DPG) to ensure: (i) the new administration honour the National Health Bill commitment to allocate at least 1% of the budget to primary health care, including funding for family planning commodities, (ii) integrated essential health commodities supply management that include family planning commodities.
2. Given the current political transition in the country and the uncertainty in the fulfilment of government’s financial obligation to Reproductive Health (RH), UNFPA, through its role in the Reproductive Health Commodity Supply Technical Working Group (RHCS TWG) should ensure that a risk management plan is developed that establishes mitigation measures should GoN funds not be forthcoming in 2015. This is a high priority activity that requires immediate technical assistance to the RHCS TWG. The plan needs to be ready by July 2015.
3. Since the country experienced a 7 times increase of contraceptive procurement with the onset of the Free Contraceptives Commodity Distribution Policy, UNFPA should take pro-active measures to ensure sufficient storage of commodities for attainment of 36% CPR in 2018, recognizing the expected increase in commodities.
4. To prevent leakage to the private sector and ensure that the costs of commodities do not become a barrier to women, UNFPA should ensure that all contraceptives procured for the public sector are branded and marked as ‘for free’ and ‘not for sale’, starting immediately. The FMoH through the Central Contraceptive Warehouse using the Channel software, should monitor and report to the RHCS TWG on any non branded or marked commodity entering the country.
5. UNFPA should advocate for support to scale up use of Channel Software in all the 36 States in Nigeria and build the capacity of personnel to manage and use the software accordingly. The software is key to development of the supply chain management and integration and definite funds need to be set aside. A phased approach can guide the start in 2015. Savings from efficient procurement (from the basket fund) can be used and/or extra support from donors (or government) need to be sought.
6. To meet the short term needs UNFPA should intensify current advocacy and dialogue with state governments to make states take ownership of contraceptive distribution in the last mile and disburse funds in time - adapting the approach to the local environment, like the stop-gap measures in Lagos State, or government counterpart funding and FP budget line in Cross River State, etc. As part of the extended use of Channel software and supply chain management, UNFPA should provide technical and managerial support to selected state governments (start with 3 states in 2015) for development of standard operational procedures (SOP) in areas of monitoring and reporting of FP commodities as part of supply chain management.
7. UNFPA and FGoN should continue efforts to support states to initiate and provide government led integrated public health supply chains for essential medicines, including contraceptives that are feasible and sustainable.
8. UNFPA will need to use the next Multiple Indicators Cluster Survey (MICS) and the midterm Demographic Health Survey in 2016 to measure the programme impact and outcome level indicators. If the above two does not provide the required information UNFPA will need to design a sample survey that measures impact and outcome level indicators.
9. The catalytic effect of the “Channel” software is significant. UNFPA will need to document and share lessons learnt to Government at all levels, development partners and the Reproductive Health Commodity Security Technical Working Group (RHCS TWG).

A. Introduction and Context (1 page)

DevTracker Link to Business Case:
DevTracker Link to Log frame:

Outline of the programme
The Access to Family Planning Commodities in Nigeria project is providing annually £3 million to centrally procure FP commodities over 6 years (2011/12 – 2016/17). The expectation is that with this project at least 1 million Nigerian couples are provided with modern family planning each year. The project is funded by Department for International Development (DFID) and implemented by United Nations Population Fund (UNFPA).
Complementary, UNFPA uses own funds and pools funds from the Government of Nigeria (GoN) and Development Partners (DP) for implementation of a coordinated approach to forecasting, decisions on method mix, procurement, storage, distribution and transportation, management and monitoring, enhancing access to reproductive health commodities to public health facilities. In addition, other donors (UNFPA and Foreign Affairs, Trade and Development Canada (DFATD[1]) contribute to the total of $9.3 million in 2014 for the purchase of contraceptive commodities.
[1] Previously named CIDA
The procurement takes advantage of current centralized pooled procurement through UNFPA and supply using pre-qualified vendors which therefore ensure that manufacturers of the pharmaceutical items and contraceptive commodities maintain the highest quality standards. This pooled procurement mechanism also enables price advantages through bulk purchases internationally.
The project goal is to contribute to improved maternal and child health in Nigeria. As per the Business Case (BC) the intervention is expected to avert an estimated 1,251,336 unintended pregnancies and 7,531 maternal deaths by 2017.
The logical framework has been adapted upon the Annual Review 2013. According to this logframe the purpose (outcome) is to ensure that ‘women and men have access to a mix of quality contraceptives and use them’, while the outputs are:
1. adequate quantities of appropriate mix of quality contraceptives procured and distributed;
2. efficiently managed national contraceptive supplies and logistical management system.

Context
In 2010, the Government of Nigeria (GoN) established the new National Reproductive Health Policy with an ambitious goal to increase CPR by 2% annually, reaching a target of 30% by 2015[2]. To help achieve this, the GoN announced the removal of user fees for contraceptives in public health facilities and established lines for reproductive health (RH) in their national budget for the first time, committing $3 million to contraceptive procurement, and signing a Memorandum of Understanding with UNFPA to procure contraceptive products on their behalf. In addition, through UNFPA’s Global Programme to Enhance Reproductive Health Commodity Security (GPRHCS), Nigeria is receiving multi-year support from UNFPA for Reproductive Health Commodity Security (RHCS). However, the commitments of GoN and UNFPA were still far short of the estimated $11 to $16 million required each year to meet contraceptive procurement needs[3]. DFATD and DFID agreed in 2011 to provide additional funding for the procurement of contraceptive commodities. A basket fund, administered by UNFPA and including both donor and GoN funding, was created.
[2] National Reproductive Health Policy and Strategy to Achieve Quality Reproductive and Sexual Health for All Nigerians. FMOH, Abuja, Nigeria May 2011.
[3] Source: USAID DELIVER project assessment
In order to guide the procurement and distribution of reproductive health commodities, the Federal Ministry of Health (FMoH) established a sub-committee of the Reproductive Health Commodity Security Technical Working Group (RHCS TWG) which was mandated to provide guidelines on contraceptive forecasting, procurement and distribution to and within states. In January 2012 the TWG inaugurated the Procurement Supply Management (PSM) Sub-Committee to monitor and track procurement of contraceptives from the basket fund.
In addition to direct funding for the procurement of contraceptive commodities, technical assistance for procurement, supply chain management, service delivery and demand generation is provided by UNFPA and the USAID funded DELIVER project, both of which are members of the PSM and RHCS TWG.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment
Impact Indicatorsa	Baseline (2008)	NDHS (2013)	Target (2017)
1. Maternal Mortality Ratio (per 1,000 live births)	545/100,000	576/100,000	250/100,000
2. Infant mortality (per 1,000 live births)	75/1,000	69/1,000	40/1,000
Outcome Indicatorsb	Baseline (2008)	Milestone (2014)	Progress
1. Contraceptive Prevalence (modern) (% of married women currently using modern contraceptives).	9.7	13.7	10.3 (2013)c
2. Number of states with a CPR of less than 15% (modern).	24	20	19 (2013) c
3. Adolescent birth rate (Births – girls age 15 to 19) per 1000 births (or Teenage fertility) or % of adolescents who are already mothers or currently pregnant.	121/1,000	100/1,000	122/1,000 (2013)c

Notes:
1. Source for Impact Indicators - NDHS 2008, NDHS 2013, updated Logical Framework (2014)
2. Source for Outcome Indicators - NDHS 2008, NDHS 2013 updated Logical Framework (2014)
3. Source of data NDHS 2013

The impact indicators have national targets, are not specific to the project and are measured with national surveys. NDHS (2013) results do not indicate progress for maternal health and only modest progress for infant mortality. It is not likely that the national targets - set at half of the current rate, will be achieved by the country in 2017.
The outcome indicators are also measured with national surveys. An update for 2014 is not available; slow (indicator 1) or no progress (indicator 3) in 2013 since baseline (2008) indicate that milestones in 2014 likely have not been achieved. For outcome indicator 2 in 2013 the milestone for 2014 had been achieved, meaning that since 2008 in 5 extra states the CPR has reached a level above 15%.

Overall output score and description: A
With an overachievement in CYP by almost one fifth, while conserving an appropriate mix of contraceptives delivered at the Central Contraceptives Warehouse (CCW), the project moderately exceeds the expectations for 2014. Many interventions complement the result. The CCW has been renovated, and is well managed using contraceptives supply chain software that is now being considered for supporting the integrated approach on medical supply chain logistics in Nigeria.
Other interventions by UNFPA and others have helped to distribute the commodities from federal to state and make the contraceptive supply chain operational in 34 States and Federal Capital Territory down to service delivery point (SDP), including the continuation of review-resupply (RRS) meetings for clusters of SDPs. Improvements in terms of reduction of stock out at SDPs when compared with 2013 were observed. In addition in 13 States + FCT UNFPA supported demand creation activities. Furthermore, FP Stakeholder meetings at national and sub national levels convened with support from UNFPA put State and Federal Ministries of Health in the heart of the discussions on FP.
Training and support on LARC was provided to 335 SDPs in 2014 in 6 states and supported supervision by UNFPA and FMoH was conducted in 13 states. Further capacity building took place in pre-service education on LARC at all 98 midwifery schools in Nigeria, resulting in a threefold increase in LARC distributed and issued to lower levels in states.
Overall, access to FP commodities by clients has been increased. The number of new users of modern contraceptives is 3,5 million in 2014 based on findings of 2014 GPRHCS Survey and more than double the 2013 result. About 90% of public SDPs in states currently providing FP services are providing at least 3 modern contraceptive methods.
Despite these successes, making the system more sustainable remains a challenges. Although there are signs of sustained engagement of states to assume ownership of the last mile distribution of commodities to LGAs and SDPs for example – Lagos State at intervals undertakes responsibility while Cross River has legislated on counterpart funding. States vary in assuming responsibility (financial, logistics, coordination) and most do not have an adequate response yet. In addition, the inadequate number of skilled providers for FP services in states result in a limited number of SDPs that provide FP services to clients.

Key lessons
1. Use of local NGOs in states experiencing insurgency accelerated implementation of activities
2. Sustained partnership with religious and traditional leaders as entry points in programming contexts with restrictive religious and cultural systems helped to enhance the acceptance of family planning in the states especially in the North, through creating an enabling environment that allow open discussions on family planning.
3. Collective advocacy with other donors and partners are required to ensure Government honours pledges and commitments.

Key actions
Improving supply chain management for health commodities including contraceptives is a flagship activity for the next 3 years. It would include capacity building, retooling and strengthening warehouse management in the Central Medical Stores Oshodi and State warehouses to ensure that health commodities are distributed to end users. UNFPA has been engaging with States to devise strategies for effective distribution and monitoring of provision of public health commodities and essential medicines including contraceptives to service delivery points (SDPs). The focus is on supply chain integration project investments and supply chain strengthening in the states for improved synergy and efficiency in the distribution chain.
In a bid to improve port clearance and reducing lead time for procurements, UNFPA engages with the FMoH and the Ministry of Foreign Affairs to explore ways of addressing the usual bottle-necks in the clearing of contraceptive shipments at the ports. Actions include the prompt processing of Form CC1 to expedite clearing processes, exploring the use of pre-release conditions at ports and engagement of NAFDAC (National Food and Drug Administration and Control) to ensure inclusion in clearing process issues especially processing of waivers.
UNFPA will need to use the next Multiple Indicators Cluster Survey (MICS) or the midterm Demographic Health survey planned in 2016 to inform the programme evaluation at the end of 2017. If information from the above two national surveys are not available UNFPA should design a sample survey.
Has the logframe been updated since the last review?
The logical framework that was attached to the BC appeared not to be in full harmony with the BC. The BC had no strategic approach that justified the vertical and horizontal logic within the logframe, and the logframe had attribution and validity problems. The 2013 Annual Review recommended to revise the logical framework. Outputs in the revised logframe are:
- Output 1: Adequate quantities of appropriate mix of quality contraceptives procured and distributed
- Output 2: Efficiently managed national contraceptive supplies and logistical management system
The revised logframe is regarded an improvement, but still does not fully address attribution and validity issues. Output 1 targets the core of the intervention, but ‘distribution’ is not defined. The first output indicator (1.1 on page 6) measures ‘procurement and distribution to public health facility’. In fact, central level data on procurement are used and distribution is to the CCW only. Other Output 1 indicators (1.2, 1.3 and 1.4 on page 6) measure results based on performance on ‘last mile’ distribution and supply chain management up to facility level and FP service use, and rather belong to Output 2.
Therefore, to mitigate the problems of attribution and validity the review team advises that 3 indicators (1.2, 1.3 and 1.4) are being moved to output 2, and that an indicator is added to Output 1 measuring timeliness of procurement and storage, defined as “Procurement and delivery of contraceptives to National Store on timely basis in line with the Annual Procurement Plan for the year as determined by the PSM Sub Committee”

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Output 1: Adequate quantities of appropriate mix of quality contraceptives procured and distributed
Output number per LF		1	Output Score	A
Risk:		Medium	Impact weighting (%):	70%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones (end of 2014)	Progress in 2014
1.1 Couple Years of Protection (CYP) of family planning commodities procured using DFID funds and distributed to public health facilities1	1 million CYP	1.193,696 CYP / Outputs moderately exceeded expectation
1.2. % of public service delivery points in states currently providing FP services providing at least 3 modern contraceptive methods	90%	89% / Outputs met expectation
1.3. # of new acceptors of FP / (currently married women using FP services who are new acceptors of FP)	1,400,0003)	3,513,956 in 20142) / Outputs substantially exceeded expectation
1.4. # of Health Facilities supported to provide LARC	250	335 / Outputs moderately exceeded expectation

Notes: 1) figures are based on distribution up to federal level; procurement data used for calculation; 2) GPRHCS Survey estimates; 3) Milestone set after first measurement in 2013 (1,424,399 new FP acceptors)

Key Points
The project moderately exceeded its target for 2014 in the procurement of a mix of contraceptives for 1 million couple years of protection (CYP) by 19%. The overachievement can partly be ascribed to the procurement of more Long Acting Reversible Contraceptives (LARC) within the mix. FP commodities have not been branded ‘for free’ and ‘not for sale’ to prevent leakage to the private sector and ensure that the cost of commodities does not become a barrier for women as outlined in the Business Case.
The condition of the Central Contraceptive Warehouse (CCW) is satisfactory and was achieved with the collaboration of stakeholders engaged in public health commodity distribution. Channel software for supply chain management of contraceptives (developed by UNFPA) has been installed and is operational in the national and 6 states’ medical stores. Actions for the integration of data management of contraceptives and other public health commodities are being implemented at CCW through the collaborative efforts of development partners (DP). The Federal Ministry of Health (FMoH) and DPs perceive Channel software as the most robust but also flexible package to support the integration.

Summary of responses to issues raised in previous annual reviews (where relevant)
[AR 2014 Recommendation 4:] A risk management plan that mitigates risks related to GoN funds not forthcoming for procurement has been raised in the RHCS TWG and discussions on the design of the plan are ongoing in the PSM Sub Committee.
[AR 2014 Recommendation 3:] Following intervention coordination by the RHCS TWG, scaling up from the 6 states in 2013, in 2014, 7 states were assisted to train Nurses Midwives on LARC. In addition, CHEWs training on injectables was rolled out in 15 States in 2014. Also 180 Nurse Tutors from all the 98 midwifery schools in Nigeria were trained on LARC.
[AR 2014 Recommendation 2: ] The logframe has been revised (see page 5).
[AR recommendation 5:] In July 2014 UNFPA commenced the implementation of the Costed Implementation Plans (CIP), which target Behaviour Change Communication materials to increase demand more equitably, with 9 States (out of 15) submitting a formal request. For 3 States (Kaduna, Lagos and Cross Rivers) the Situation Analysis (in-depth analysis of the 2005, 2008 and 2013 DHS surveys to profile women who take up family planning and those who do not) has been finalised. The next step is the validation by stakeholders before commencing the costed plan (takes 1-2 months). The remaining 6 states will commence the situation analysis in April 2015.

Recommendations
1. Given the current political transition in the country and the uncertainty in the fulfilment of government’s financial obligation to RH, UNFPA, through its role in the RHCS TWG should develop the risk management plan that establishes mitigation measures should GoN funds not be forthcoming in 2015. This is a high priority activity that requires immediate technical assistance funded supported by development partners to the RHCS TWG. The plan needs to be ready by July 2015.
2. Since the Country experienced a 7 times increase of contraceptive procurement with the onset of the Free Contraceptives Commodity Distribution Policy, UNFPA should take pro-active measures to ensure sufficient storage of commodities at state and local level in the risk mitigation plan for attainment of 36% CPR in 2018, recognizing the expected increase in commodities.
3. To prevent leakage to the private sector and ensure that the costs of commodities do not become a barrier to women, UNFPA should ensure that all contraceptives procured for the public sector are branded and marked as ‘for free’ and ‘not for sale’, starting immediately. The FMoH through the Central Contraceptive Warehouse using the Channel software, should monitor and report to the RHCS TWG on any non branded or marked commodity entering the country.
4. The catalytic effect of the “Channel” software is significant. UNFPA will need to document and share lessons learnt to Government at all levels, development partners and the Reproductive Health Commodity Security Technical Working Group are necessary.
5. UNFPA Should support the installation of Channel Software in all the 36 States in Nigeria and build the capacity of personnel to manage and use the software accordingly. The software is key to development of the supply chain management and integration and definite funds need to be set aside. A phased approach can guide the start in 2015. Savings from efficient procurement (from the basket fund) can be used and/or extra support from donors (or government) need to be sought.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Output 2: Efficiently managed national contraceptive supplies and logistical management system
Output number per LF		2		Output Score		A
Risk:		Medium		Impact weighting (%):		30%
Risk revised since last AR?		N		Impact weighting % revised since last AR?		Y

Indicator(s)			Milestones		Progress
2.1. % of service delivery points in states reporting no stock outs of contraceptives in the last 3-6 months			75%		78%1) / Output met expectation
2.2. % of CYP of States with requests for contraceptives resupplied (fill rate) within the reporting year			86%		73% / Output moderately did not meet expectation

Notes: 1) GPRHCS Survey estimates for last 3 months;

Key Points
Achievements on Output 2 concern the ‘last mile’ distribution from states to service delivery points (SDP). They can mainly be attributed to interventions by DPs, NGOs, Local and State Government entities (see partnership section in section F), coordinated and supported by UNFPA and steered by the RHCS TWG chaired by FMoH.
Increasingly contraceptives supply chain challenges in the states are being met. The efforts of UNFPA to support last mile distribution and capacity building of service providers on logistics management in 34 states as well as coordination with the PSM Sub Committee on tracking distribution to states and SDPs in the last 3 years has led to 7 fold increase in CYP of commodities issued to lower levels and 5 fold increase in CYP of commodities issued to users at service delivery points[4].
[4] reported by UNFPA Nigeria
In 2014, the rate of no stock-outs in the last 3-6 months and the rate of SDPs at least providing 3 modern contraceptives both meet the milestone, the number of SDPs supported to provide LARCs exceeded the target by 34%[5], and the milestone (set last year) for new acceptors of family planning was more than doubled (150% increase above target). Review and re-supply (RRS) meetings sustained in 34 states, and regular distribution of commodities, funded by UNFPA , ensured their availability in LGAs and SDPs.
[5] 335 HFs supported with 2,000 units of IUD and Implant Removal kits funded by DFID (US$ 1.2 mil) and training costs covered by UNFPA and RMNCH Grant (US$1.5 mil)
Despite these successes, challenges related to making the system more sustainable remain resistant. Although there are signs of sustained engagement of states to assume ownership of the last mile distribution of commodities to LGAs and SDPs for example Lagos State at intervals undertakes responsibility while Cross River has legislated on counterpart funding. States vary in assuming responsibility (financial, logistics, coordination) and most do not have an adequate response yet. In addition, the inadequate number of skilled providers for FP services in states result in a limited number of SDPs that provide FP services to clients.
Other related challenges identified include: UNFPA is increasingly having difficulties in funding the RRS meetings thereby limiting the number of SDPs that could be incorporated into the distribution network and the frequency of the meetings. In addition, the distribution of commodities was held up due to late release of UNFPA funds for review/re-supply meetings at the beginning of the year. Contraceptives resupplied (fill rate) within the reporting year showed a slight decline due to increased service uptake at SDP level, which was not forecasted requesting FP commodities. And lastly, stakeholders are relatively slow in their reaction to expand training of Community Health Extension Worker (CHEWS) on injectables and other FP methods in order to rapidly scale up services in SDPs across the country.

Summary of responses to issues raised in previous annual reviews (where relevant)
[AR 2014 Recommendation 1:] Efforts are on going for integrated distribution of public health commodities at state level using the Direct Delivery and Information Capture last mile distribution model (DDIC) tested by USAID DELIVER Project, using government and donor funding. In addition, UNFPA is collaborating in the Global Fund Supply Chain Integration Project.

Recommendations
2. DFID and UNFPA with other DPs should explore the window of opportunity offered by the passage of the National Health Bill, using the platform of the Development Partners Group (DPG) to liaise with the government in providing guidelines through which states could draw funding from the PHC fund for the last mile distribution of public health commodities, using costed packages of the different health commodities including contraceptives.
3. DFID and UNFPA with other Development Partners should also use the passing of the National Health bill to advocate for integrated essential health commodities supply management that include contraceptives.
4. As part of the extended use of Channel software and supply chain management, UNFPA provides technical and managerial support to the state government (start with 3 states in 2015) for development of standard operational procedures (SOP) in areas of monitoring and reporting of FP commodities as part of supply chain management.
5. UNFPA and FGoN should continue efforts to support states to initiate and provide government led integrated public health supply chains for essential medicines that are feasible and sustainable.
6. DFID and UNFPA with other development partners should provide technical support to Federal and State Government levels for institutionalising integrated health services that include family planning.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)
Key cost drivers and performance
In 2014, as in previous years, the main cost driver is the cost of commodities, which is determined by the mix of commodities procured together with the unit costs of the commodities.
UNFPA uses the pooled procurement system through their Procurement Service Branch (PSB) in Copenhagen. Centralised UNFPA procurement procedures using pre-qualified vendors, generally help to ensure that manufacturers of pharmaceutical items and contraceptive commodities maintain the highest quality standards and lowest cost. This mechanism enables price advantages through bulk purchases internationally. UNFPA is consistently achieving equivalent or better prices for quality assured products[6] than the two internationally recognised price data sources: USAID’s listed prices and the Management Sciences for Health’s International Drug Price Indicator Guide.
[6] See e.g. Differential Pricing UNFPA’s Experience With Contraceptives Christian Saunders, Chief, Procurement Services, United Nations Population Fund. https://www.wto.org/ENGLISH/tratop_e/trips_e/.../17saunders_e.ppt; accessed 21 March 2015

VfM performance compared to the original VfM proposition in the business case
There appears to be no evidence to suggest that VfM performance on the part of UNFPA’s procurement practices has deteriorated. The efficient procurement processes of pooled procurement by UNFPA Copenhagen and the vast experience gathered over the years, together with the quantum of contraceptives procured for countries all over the world, places UNFPA in a strong position to handle these procurements of contraceptives on behalf of DFID.

Assessment of whether the programme continues to represent value for money
Family planning commodity procurement by UNFPA is likely to maintain its value for money in terms of economy, efficiency and effectiveness.
In economic terms, funds were saved by reduced clearing and freight costs as well as negotiated prices for contraceptives procured. Prices dropped by about 68% for implants and costs negotiated for other methods such as female condoms, pills and injectables have remained stable due to volume discounts. The costs attributable to customs clearing were lower due to prompt clearing and negotiated rates with Government recommended clearing agents (70% reduction in clearing costs from 2010 compared to 2012). In for the years 2012 and 2013 an analysis done by the USAID DELIVER project resulted in annual savings of 20 – 25% of the expected cost of procurement of contraceptives for all funds in the basket. A similar analysis for 2014 DFID funds only, would generate average annual savings of 19% (2011-2014) and 39% in 2014.
In terms of efficiency, the procurement of LARC contributed to a more effective mix of contraceptives, thus achieving a higher CYP at lower costs. This is because of the lower unit costs per CYP for LARC as compared to other methods[7].
[7] In fact, these savings can be used as an argument to allow inclusion of consumable (cotton wool, gauze, zylocain etc.) costs into LARC procurements.
In terms of effectiveness, this resulted in a CYP that exceeded the milestone with 19% in 2014, and extra new FP acceptors 150% above the set target in 2014. The procurement of FP commodities by DFID and others that was initiated to have a direct effect on the CYP, turned out to become an important catalyst for actions down the supply chain. The fact that FP commodities were brought in the country resulted in a policy on free FP services in Nigeria, Government commitments on FP for the first time, an increasing numbers of partners joining, FP logistics management and software triggering and contributing to integrated supply chain management of essential medicines and contraceptives, and also RRS meetings in the whole country, improved coordination, capacity building and awareness of family planning.
In terms of equity, the free services generate increased access for women and lower social classes. However, NHDS (2013) still indicates that demand for and access to contraceptives suffer from gender, rural/urban, social, economic and cultural inequities.

Quality of financial management
The UNFPA Nigeria country office has been having 2 separate routine audits in 2014. The UNFPA financial system aims at transparency, and therefore, audit results are made public and available to other donors. In addition, financial statements are being shared with DFID after the Board ratifies annually by June. IPSAS[8] may cause the impression of low implementation rates, because IPSAS requires that until goods are received in the country the supplier cannot be paid and thus expenses are not recorded for the time being, showing unnecessary underreporting for that point in time.
[8] UNFPA has adopted the International Public Sector Accounting Standards (IPSAS), introducing standards of expense recognition as it applies to the delivery of goods and services, to improve accountability and results-based management.

Date of last narrative financial report	June 2014
Date of last audited annual statement	June 2014

E: RISK (½ page)
Overall risk rating: Medium
Overview of programme risk
The following table presents the programme business case risk matrix with comments following the AR.
Risks	Impact on results	Likelihood	Comments
Government / other key stakeholders resist scaling up family planning in Nigeria.	High	Low	DFID, USAID and UNFPA all have programmes that are specifically working on ensuring that traditional, religious and political leaders are kept engaged in debates around family planning.
Health services are too weak at the primary and community level to deliver family planning services	Medium	Low/ / Medium	Health services are still weak at the primary and community level. However, some FP methods do not require high skills and can be delivered. Other methods (LARC) need skilled attendance. Particularly for LARCs the capacity at lower levels of the system is a risk, if skilled workers are not structurally (re)deployed by the government and remain clustered in central higher level locations.
Logistics management system fails to ensure commodities are moved from port to facilities at the right time in the right amounts	Medium	Medium	Logistics management systems in Nigeria for commodities from States to SDPs has been challenging with little or no Government funding devoted to it. The support has been largely from donors, but increasing visibility of logistics issues and advocacy has been getting Government’s attention recently.
The incorrect method mix is procured leading to stock outs of some commodities and for other going to waste.	Low	Low	The monthly PSM Sub Committee meetings enable responsive discussions about method mix, although the review-resupply meetings (for SDP clusters at local level) have in most states not been conducted regularly yet. FP commodities have a long shelf life; there is no evidence that even where they have been over procured, they have not gone to waste. The channel data management system also helps monitor stock at different levels preventing waste.

Added risk (medium impact/high likelihood): The non release of pledged counterpart funding may jeopardise the programme being financed by the basket fund from DPs for family planning. Non released government funds amount US$19.9 million pledged for 2013 and 2014. This results in government actual contributions from 2011-2014 to be 20% of the basket funds versus the expected of 44%.

Outstanding actions from risk assessment
The need for developing a risk management and mitigation plan, including the risk of non release of Government counterpart funding, is critical. Discussions are on going in the PSM Sub Committee on the design of such a plan.

F: COMMERCIAL CONSIDERATIONS (½ page)
Delivery against planned timeframe
The expected quantities of contraceptives were procured and delivered to the federal Government Warehouse in a timely manner in 2014.

Performance of partnership (s)
Partnerships are regarded key to the success of this program: partnerships for advocacy with Government at all levels, for ensuring last mile distribution, and for the contributions to the basket funding for procurement of contraceptives. The PSM Sub Committee is the prime platform for collaboration, including joint review and planning. Key partners are:
- The Gates Foundation run an Urban Family Planning Programme in 5 Nigeria cities (Ibadan, Ilorin, Abuja, Zaria and Benin City). This programme public and private facilities to strengthen service delivery, promote demand creation activities and conduct advocacy with governments to leverage support for family planning.
- USAID works with Government and UNFPA on quantification and supply planning (JSI Deliver). USAID has not procured any contraceptives for the public sector. USAID is working with the private sector and social marketing of contraceptive commodities.
- DFATD has a $21 million 5 year maternal and child health programme, working with UNFPA, UNICEF and WHO under the auspices of the UNH4. This involves Canadian $9 million for a variety of drugs, commodities and equipment for maternal and child health including contraceptives.
- UNFPA also has resources committed to work alongside this initiative – and has support from UNFPA at the highest level .
- Marie Stopes is a relative newcomer in family planning in Nigeria, present since 2009 but only active at scale from 2011, and were not mentioned in the original Business Case for this programme. They are involved in the private sector market in southern states, but also conduct outreach in public health facilities and are involved in training healthcare workers in the public sector on LARC through UNFPA and USAID funding.
- Association for Reproductive and Family Health (ARFH) currently implements the capacity building project funded by UNFPA to scale up access to injectable contraceptives through task shifting to CHEWS.
- Clinton Health Access Initiative (CHAI) has also been active in supporting quantification and supply planning validation.
- Planned Parenthood Federation of Nigeria (PPFN), Axios Foundation and National Primary Health Care Development Agency (NPHCDA) support the last mile distribution. Previously CHAI was also a supporting partner for the last mile distribution. However, monitoring expenses were not in balance with the requested activities and UNFPA suspended working with CHAI on this activity.
- Federal Ministry of Health (FMoH) is the main recipient of this technical support and contraceptives supply. It has the main responsibility for coordinating the implementation efforts for supply of the contraceptives to States.

Asset monitoring and control
This is done by the FMoH with technical support from UNFPA and John Snow Inc. including stock status reporting and monitoring supplies to states based on requisitions. The results are shared at the PSM meeting for concurrence.

G: CONDITIONALITY (½ page)
Update on partnership principles (if relevant)

The Partnership Principles were not considered within the project business case. In Sept 2014 DFID Nigeria conducted an assessment of the FGN commitment to the Partnership Principles which reconfirmed the UK’s declared policy that no UK aid money should go directly to the Government of Nigeria: as an anti-corruption measure and to avoid substituting for the country’s own resources. The Access to Family Planning Commodities programme is consistent with this policy. DFID funding is provided directly to UNFPA for the procurement of family planning commodities. No funding is passed through government channels and as such the Partnership Principles are not relevant for the direct management and monitoring of this project.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
The BC Theory of Change remains valid with project inputs resulting in increased CYP. There is no evidence yet to demonstrate that this is resulting in an improvement in health status. National surveys like DHS and MISC are regularly planned. No project evaluation is currently planned.

Monitoring progress throughout the review period
The DFID Annual Review of the project for 2013 highlighted the need to revise the logframe in order to demonstrate results and extent of contribution of UNFPA to the project. The logframe revision exercise however raised attribution and measurement validity issues with regard to the original purpose as laid down in the MOU between UNFPA and DFID.[9]
[9] MOU between DFID and UNFPA states: ‘The Contribution will be used exclusively for the following purposes: To support the Reproductive Health Programme of the Federal Ministry of Health to centrally procure Family Planning Commodities through UNFPA to provide 1 million Couple Years Protection (CYP) annually for the next 6 years (2011 – 2017) in Nigeria as laid out in the attached Business Case dated 25 July 2011.’
The Programme Performance Matrix and monitoring framework that have been indicated in the BC could not be referred to. Instead UNFPA performance documents were used. Instead of quarterly reports from UNFPA to DFID semi-annual reports are handed over.
Tracking of procurements and shipments from UNFPA Copenhagen is monitored and disseminated at monthly PSM meetings and a dashboard for monitoring completion of procurement is also done by UNFPA using the OTS Tracker by PSB and locally using the PSM Tracking Tool.
In addition, the annual survey on availability of essential medicines is conducted in Nigeria by FMoH with technical and financial support from UNFPA and technical support from John Snow Inc. and National Population Commission to assess the stock out and other service delivery issues.
Also tracking of fund release is done by UNFPA and this is compared to the forecast and quantification of needs by John Snow Inc. It is expected that the installation of Channel software in national and state medical stores will further enhancing tracking of commodities along the distribution chain.

Annual review process: Stakeholders – MoH at Federal, State and LGA levels, DPs, NGOs, and other partners were very supportive of the project and also voiced constructive comments about aspects of its implementation. UNFPA provided a briefing to the team in Abuja, after which the team visited Lagos and Crosss River States. Government officials and project, warehouse and clinic staff were met, including the Deputy Governor in Cross River State and State Ministers of Health. Not all stakeholders could be interviewed during the review process and only few ultimate beneficiaries, patients, were consulted during the review.
The review was conducted through analysis of secondary data and information provided by DFID and UNFPA including survey and routine data. This was supplemented by key informant interviews amongst stakeholders at all levels and field visits to the Government Warehouses and primary health care facilities.
The review was conducted by Ronald Horstman (Team Leader, International Consultant ) and Prof. Christian Ibeh (National Consultant) in Abuja, Lagos State and Cross River State over the period 9th – 16th March 2015.

DFID engagement in the future: As part of the assignment DFID has asked the consultant team to develop three options for future engagement of DFID. There will be included in a separate report.