ADDENDUM TO BUSINESS CASE ON SUPPORT TO INTERNATIONAL AGRICULTURAL RESEARCH CENTRES

FOR BRIDGE FUNDING AND SCALE-UP COST EXTENSION

SUMMARY INFORMATION
Project Name	Support to International Agricultural Research Centres (Aries code 202748)
Country or region targeted	Africa and South Asia
Type of cost extension	Bridge Funding to a High performing programme which can be scaled up to increase results
Original project budget	£40,093,717 (£30m + £10m + £93,717 for an external evaluation)
Original project start and end dates	01/04/2012 to 30/08/2015
Cost extension value	£10.2m
New project end date	30/08/2016
Business Case Quest Document No.	3323090

INFORMATION

What is the project’s purpose?
The intended impact of the approved programme is agricultural growth that contributes to poverty reduction and improvements in nutritional status. Under the existing programme, DFID has scaled up its support to high performing international agricultural research centres, linking funding to delivery in order to improve performance, particularly around scaling up and robust systems for impact measurement. Currently DFID has commissioned an external evaluation of the performance management funding mechanism. This evaluation is due to be completed by July 2015.

This costed extension will provide an additional year of performance related funding to the four international agricultural research centres, the World Vegetable Centre (AVRDC), CABI, icipe and ICIMOD to scale up results. The objectives are to deliver:

- new technologies, products and knowledge to address agriculture yield gaps, hunger and malnutrition;
- technologies, products and knowledge put into use at scale; and
- a step-change in systems to measure impact.

What is the objective of the cost extension?

This programme uses a performance management funding mechanism (PMFM), explicitly linking funding to performance to maximise influence and impact. The extension will enable us to further scale up work on stimulating agricultural innovation, with a strong emphasis on novel partnerships with the private sector, an area of strong Ministerial interest. An external evaluation is currently underway of this performance management funding mechanism. This will be finalised in July 2015, and will feed directly into the design of a new PMFM for international agricultural research centres from 2016 onwards.

In addition to scaling up results, the additional year of funding will allow a continuation of multi-year predictable funding to these centres, whilst DFID reviews the evaluation findings and considers the benefits of and approach to a new phase of support. This is aligned with the principles of the funding approach, which aims to provide stability and predictability of funding whilst linking payments to results within the PMFM.

This addendum meets the 4 key SMART Rules principles for a costed extension:

1. Each centre has demonstrated a clear need for continued funding, in line with corporate objectives around economic development, agricultural growth and innovation. Each centre has set out the extra outcomes and results that will be achieved in the additional year. Stability and predictability of funding has been a core principle in the current Business Case, and we wish to ensure continuity of funds, whilst allowing time for the design of a modified PMFM .
2. Each centre is performing well and delivering the results which they set out at the outset of the existing Business Case. CABI has received a performance bonus in each year of the current Business Case. AVRDC, icipe and ICIMOD continue to generate a good set of results and demonstrate overall value for money for DFID. Overall there is a high level of confidence in their ability to deliver the expected results.
3. Each centre has demonstrated that they are implementing the recommendations from the performance review last year. The project team has identified delivery risks for each of the centres and has set out in the Project Delivery Plan how we will mitigate them. Overall the Business Case is rated as low risk. The programme demonstrated good performance in the last Annual Review (scoring an A – outputs met expectations).
4. This extension would take the cumulative value of the total commitment to the programme over £40m (adding to the original Business Case of £30m and the additional £10m funds provided in 2012). The programme is low risk, with proven partners. Given the low risks attached, and one year extension of an existing programme which is performing well, this does not require a review by the Quality Assurance Unit. Quality assurance, however, will continue to be made at the formal performance review points (in mid-2015 and mid-2016). This process will involve external reviewers from other parts of DFID and at least one Senior Research Fellow from Research and Evidence Division.

What is the additional and total support the UK will provide?

The 2015/16 allocation to each centre is based on the annual allocation to each centre in the 2014/15 financial year, and based on an analysis of the centre’s financial needs for 2015/16. For the purposes of approving the total budget envelope, it is assumed that all programmes are awarded a performance bonus, although previous experience suggests that it is unlikely to be the case.

What are the expected results?

Each centre has provided details of anticipated results and milestones for the additional year. Summary of the main deliverables:

The World Vegetable Centre (AVRDC):
- Additional vegetable lines and national releases of improved vegetable seeds.
- Extension of home gardening model to an additional 3 countries.

Further development of vegetable grafting technology, including more stable resistance to soil-borne diseases, for salinity tolerance, and enhanced nutritional and/or taste traits.

CABI:
1. Continue the process of scaling up and pushing towards sustainability in 34 countries for Plantwise; testing suitable business models to support long term sustainability of Plantwise and mobile activities.
2. Develop more detailed analysis of the challenges for women in accessing plant health information, together with action plans/studies to increase the involvement in and access to Plantwise by women and youth.
3. Extend the scope of Plantwise and mobile and digital services to include invasive weeds. These have significant impact on food security through competition for arable and pasture land.
4. Assess the gendered impact of at least one major project/programme.

International Centre for Insect Science and Ecology (icipe):
- Further extension of “push-pull” striga technology in two countries (Malawi, Zambia); and fruit fly control technologies in Uganda, including partnership with private sector to commercialise production of bait.
- Evaluation and validation in on-farm field trials of new bio-acaricides on-host and off-host tick populations in zero-grazing settings in at least two action sites representing different agro-ecological zones of Kenya.
- Curriculum development with 5 universities on insect sciences; professional development curriculum introduced to post-graduate scheme and 3 additional post-Doctoral fellowships.

International Centre for Integrated Mountain Development (ICIMOD):
- Additional new knowledge on changes in climate and glacier/snow cover in the Himalayas and their impact on agriculture; ‘Regional Flood Information Outlook’ in Koshi Basin which will be used by national partners for flood risk management and reducing impact on agriculture sector.
- Innovations on water and agriculture related adaptation; laying out a framework for work on nutrition; climate and weather information system linking on droughts and cropping patterns using remote sensing applied at sub-national, national and regional scales as adaptation strategies; Innovative technologies like solar water pump for irrigation and to enhance agriculture productivity.
- Expand the use of more rigorous impact evaluations, including improving the effectiveness of mountain agriculture extension services. Rigorous impact evaluation studies on solar pumps and climate smart villages will be designed and implemented.

What is the approach to implementation?

Each centre was asked in January 2015 to demonstrate the financial needs for 2015-2016, a statement of progress against the 2014 performance review recommendations and to set out a revised results offer for the additional year of funding. These were reviewed by and adjusted in the light of discussions with the DFID team. In communicating a one year extension, DFID will emphasise that centres should not assume they will continue to receive funding under any new phase and that those unable to demonstrate a robust response to recommendations from the 2014 annual performance review will be at particular risk. Centres should also be aware that funding levels may change as well as the performance management system in the light of the external evaluation.

Describe any key changes to the original business case

A summary of the evolution of support to the different centres is included in the section below. Under this one year costed extension, we will continue with the PMFM that has been used to date.

We are piloting a new approach to looking at quality of research, alongside the existing quantitative metrics. This will require each centre to provide for the mid 2015 and mid 2016 (final) performance reviews:

- Best 3 - 7 research publications (depending on size of research centre) judged by them to represent high quality research and development relevance.
- 2 Impact Case studies which demonstrate the impact of research the centre has conducted with funds drawn wholly or partially by DFID and in areas in which the centre is still active.

These outputs will be peer reviewed as part of the annual performance review, and the results fed into the overall assessment. This will be introduced in mid-2015 and repeated at the final performance review. This will enable the system to be refined for any future phase of funding.

Compliance on Gender Equality

A recent evidence paper by DFID on agriculture and women identified a number of issues that highlight the need for a strong gender analysis in undertaking agricultural research and the role of technologies[1]. For example the evidence suggests that:
[1] Agriculture and Women, L Hlanze and M McWhirter, DFID Agriculture and Growth Evidence Paper Series, 2014.
- Women make up a significant part of the agricultural labour force;
- Agricultural transformation and male outmigration are creating new wage employment opportunities for women;
- Women’s activities in agriculture is gendered and context specific.

Gender is incorporated into the PMFM in two ways. There is an indicator on gender in Human Resource and organisational strategies which is tracked through the annual performance review, and there is an indicator on gender analytical research outputs. Together these provide a solid entry point for engagement on gender issues with the international agricultural research centres, and an incentive for centres to continue to strengthen their approach on gender within research. This is a proportionate commitment under the International Development (Gender Equality) Act 2014.

Additional background information on the programme changes and the performance funding management mechanism

The original programme approval was for £30m. An extension was approved taking the programme total to £40m over four years from 2011-2015. The intended impact of this programme is agricultural growth that contributes to poverty reduction and improvements in nutritional status. Under this funding, DFID planned to scale up its support to high performing international agricultural research centres, linking funding to delivery in order to improve performance, particularly around scaling up and robust systems for impact measurement.

The programme adapted the value for money assessment framework used in the DFID Multilateral Aid Review (MAR) in order to prioritise research centres and to structure the deliverables against which each centre is measured. The methodology used to prioritise centres uses a set of rigorous criteria reflecting both cost and value for money, results focus, performance, accountability and transparency, gender and environmental considerations and research excellence. Based on these assessments, core funding was initially allocated to 3 research centres, representing an increase in levels of funding to these centres:
- CABI
- World Vegetable Centre (AVRDC)
- International Centre of Insect Physiology and Ecology (icipe).

Funding of another centre, the Global Forum on Agricultural Research (GFAR), was also continued, but at a reduced level[2].
[2] An early decision was taken not to continue funding one centre, Crops for the Future (CFF), formerly the International Centre for Underutilised Crops (ICUC). However, funding was phased out, allowing CFF time to seek other donors. It received 0.75% of the total programme budget.

During 2012, based on an additional value for money assessment, using the same methodology, funding of a fifth centre commenced:
International Centre for Integrated Mountain Development (ICIMOD)

In November 2012, additional funding of £10m was made to two centres, CABI and icipe, taking the total programme from £30m to £40m. This additional funding was made in response to the inaugural performance review, which had demonstrated evidence of excellent research quality with development impact and value for money for DFID. These centres also showed that they could scale up their work to meet strong Ministerial interest in the use of science and innovation in tackling poverty and in new forms of partnership with the private sector to deliver development outcomes.

A key feature of the programme is a commitment to multi-year funding, as well as to an increased level of DFID funding to most centres. This phase of support represented a shift in approach for DFID, away from the previous funding to these centres, which involved ad hoc annual core funding allocations, with limited partnership dialogue and engagement. This had the intention of enabling centres to plan strategically and maximise use of DFID resources. Greater security of baseline funding would - enable centres to maximise and commit staff resource and map out individual and programme budgeted work plans over a longer timespan than would otherwise have been possible.

The performance funding mechanism involves the following features:

- Multi-year funding: to enable improved planning of resources by centres, resulting prospectively in more effective use of DFID resources.
- Performance related element: scaling up funding to high performing centres. Funding to comprise of a guaranteed minimum core contribution plus an additional element. The additional element to be allocated on the basis of performance against 3-5 high level deliverables for each centre.
- Value for Money: based on a systematic approach to assessing value for money and organisational behaviours across each centre. Funding would be linked to specific conditions related to organisational behaviour (including gender responsive organisations, climate smart behaviour and results focus) and maximising delivery and influence.
- Strategic: it would enable DFID to use our funding to improve results and to direct additional resources to emerging DFID research priorities.

The implicit theory of change in implementing this new approach has been that longer term funding, a tighter set of agreed deliverables, a mechanism for regular dialogue and partnership, and a performance bonus will improve performance of the individual centres in specified areas, and lead to results more closely aligned to DFID priorities.

Within this programme, DFID has adopted a distinctive approach to performance reviews. Each centre is assessed annually against 3 or 4 key objectives (using metrics which the centres themselves proposed) and a set of organisational behaviours. The centres write an annual performance report which is followed by a presentation to and questioning from the performance review team of DFID staff supported by peer reviewers. The review team share their findings and produce agreed assessments. Centres are afforded the opportunity to respond formally after each review.