Business Case

Summary Sheet

Title: UK RESPONSE TO THE EBOLA CRISIS IN SIERRA LEONE AND THE REGION
Project Purpose: CONTROL THE SPREAD OF EBOLA IN SIERRA LEONE AND THE REGION, LEAVING A LEGACY OF STRONGER HEALTH SYSTEMS
Programme Value: UP TO 416.13 MILLION		Country/Region: SIERRA LEONE/WEST AFRICA
Project Code	Project Title		Budget Allocation	Start Date	Senior / Responsible Owner
204838	Emergency support to respond to the Ebola Virus Disease in Sierra Leone 2014 (Urgent Needs)		£52.50m	Jul-14	Ed Davis
204876	Sierra Leone Kerry Town Ebola Treatment Facility		£53.54m	Sep-14	Claire Vallings
204890	Ebola Treatment Centres in Sierra Leone		£113.60m	Oct-14	Claire Vallings
204893	Reducing transmission of Ebola in Sierra Leone through changing behaviours and practices		£12.50m	Oct-14	Ed Davis
204896	Ebola Care Units in Sierra Leone		£68.50m	Oct-14	Claire Vallings
204900	UK Response to Ebola crisis through support for UNMEER and the wider UN System		£24.05m	Oct-14	Jo Scott-Nicholls
204902	UK Support to Ebola Crisis through support for the Joint Inter Agency Task Force (JIATF)		£36.44m	Oct-14	Jennie Barugh
204904	UK response to Ebola crisis through establishing laboratories		£15.00m	Nov-14	Claire Vallings
204917	Ebola Central Health Care Supply Chain Platform		£5.00m	Nov-14	John McGhie
204919	Match Funding for Ebola Response		£10.00m	Dec-14	David Bailey
204929	UK support for regional preparedness to prevent the spread of Ebola		£25.00m	Jan-15	Anne Philpott
	QUEST Number: Various

Intervention Summary (2 Pages)

What support will the UK provide?

DFID has approved plans in place to the value of £416.13 million to control the spread of Ebola in Sierra Leone and the region. There is a substantial direct delivery component, including by HMG military personnel and National Health Service volunteers, in addition to funding through implementing partners. This collective support is focused on the immediate response. The early recovery and longer term development efforts will be reflected in separate business cases.

What are the main programme activities?

Our efforts are focused on containing the outbreak in Sierra Leone and getting to zero cases, through the provision of safe isolation and treatment beds, laboratories to increase diagnostic capacity, ensuring safe and dignified burials, and social mobilisation to change behaviours as the most effective ways to prevent transmission, and supporting protection for vulnerable individuals and those affected by quarantine measures. This is underpinned by the deployment of civilian and military personnel and assets to strengthen command and control, through the provision of enabling infrastructure, and through support for the UN Mission for Ebola Emergency Response (UNMEER) and the UN system. The main activities are:

Building, running and staffing six Ebola treatment centres (ETCs) in Kerry Town, Port Loko, Hastings, Makeni, Goderich and Moyamba.
Funding the set up and running of safe isolation beds where people who suspect they might be suffering from the disease can seek swift and accurate diagnosis and appropriate care.
Building, running and staffing three new laboratories, doubling the number of tests that can be carried out every day.
Supporting over 100 burial teams nationally, and funding partners to work with people to agree practices which will allow them to honour their friends and relatives, while ensuring bodies are safely buried.
Procurement of essential medical supplies and personal protective equipment (PPE) for treatment and safe isolation facilities.
Support to surveillance teams, support for national and district alert call centres, and support for Ebola response fleet management including ambulances.
Supporting observational interim care centres (OICCs) for unaccompanied children to safely complete the 21 day quarantine period.
Supporting command and control capability at national and district level through military and civilian expert teams.
Contributing aid match funds for the Disasters Emergency Committee (DEC) appeal on the Ebola outbreak, and the appeal for donations to UNICEF’s Ebola fund.
Funding for multilaterals and international partners in Sierra Leone and to strengthen regional preparedness to manage the risk of Ebola spreading beyond the borders of the current epidemic.

Why is UK support required?

An Ebola outbreak was declared in Guinea on 22 March 2014 and confirmed in Sierra Leone on 24 May. Since then the spread through West Africa has been unprecedented, with the outbreak dwarfing all previous Ebola outbreaks combined. The hardest hit countries have been Liberia, Sierra Leone and Guinea. Tackling the disease requires significant and urgent support.

Recovering from a decade long conflict, Sierra Leone had been making good progress but from a very low base. The UK has a pre-existing cross-Government footprint in country, being the country’s largest bilateral donor, which includes support to the health sector. The UK is also one of the few nations that can mount a response of the nature required. It has global humanitarian expertise, significant rapid deployable capacity, including military assets, and the cultural and political ties that make it a natural partner for Sierra Leone.

How does the project fit with the country programme or department’s strategic objectives set out in the Operational Plan?

This urgent response was not anticipated in the Operational Plan, however the Ebola response programme (consisting of a number of distinct yet related projects) is wholly consistent with the priority DFID gives to humanitarian crisis intervention and is aligned to DFID’s strategy for tacking Ebola. In order to control the spread of Ebola in Sierra Leone and the region there are two strategic aims: 1) reduce the transmission rate to less than 1 initially and then to zero; and 2) prevent the spread to the wider region. An illustration of the fit between this programme and our strategic objectives is included in the strategic section of this business case.

What are the expected results?

Sierra Leone	Reducing transmission rate to less than 1 initially and then to zero / Providing 700 treatment beds and trained staff to work in treatment facilities / Providing safe isolation beds where they are most needed to reduce transmission at community level / Providing laboratories to double diagnostic capacity and provide 24 hour turnaround / Ensuring that all reported deaths are buried safely and in a dignified manner within 24 hours of reporting / Increasing public understanding of how Ebola is transmitted / Supporting quarantined households through food and decontamination
Region	Preventing spread to the wider region / Low manageable transmission rate / Strong preparedness in countries at risk / International response mechanisms in place

What are the key risks to the success of the programme?

Strategic	Planned UK efforts insufficient or too slow / Security situation impedes delivery / Domestic Sierra Leonean and International Community doesn’t respond at an adequate scale and speed
Delivery	Insufficient global supplies including personal protective equipment / Insufficient number of health care workers to work in treatment and safe isolation facilities / Insufficient delivery partners with expertise to deliver at necessary scale and speed / Safe isolation and treatment facilities becomes source of cross infection / transmission
Coordination	Lack of Government and International Community leadership and coordination capacity / Competition for key supplies drives supplies away from UK and Sierra Leone priorities
Fiduciary	Heightened risk through use of new partners / Possibility of waste through procuring more than is needed / Large scale procurement with opportunity for loss of assets / Scale of response and nature of work reduces UK ability to monitor implementation

Strategic Case

An outbreak of the Ebola virus disease was declared in Guinea on 22 March 2014 and since then the spread through West Africa has been unprecedented. Unless checked, the disease could have spread well beyond the region with catastrophic consequences. In September, the Centre for Disease Control and Prevention (CDC) stated that “without additional interventions or changes in community behavior, CDC estimates that by January 20, 2015, there will be a total of approximately 550,000 Ebola cases in Liberia and Sierra Leone or 1.4 million if corrections for underreporting are made”[1].
[1] Meltzer, M.I. et al, ‘Estimating the Future Number of Cases in the Ebola Epidemic — Liberia and Sierra Leone, 2014–2015’, 26 September 2014. (http://www.cdc.gov/mmwr/preview/mmwrhtml/su6303a1.htm?s_cid=su6303a1_w)

The hardest hit countries so far have been Liberia, Sierra Leone and Guinea. Although some cases of Ebola have been recorded in other countries such as Mali, Nigeria and Ghana this has been prevented from becoming a wider outbreak in the region. Isolated cases have also been recorded in the US and Spain.

In the hardest hit countries the disease has spread through a combination of weak health systems and the inability of the state to isolate cases successfully, trace those who have been in contact with infectious cases, protect health workers adequately and facilitate safe burials. To date there have been over 22,000 cases and more than 8,800 deaths in nine countries since the outbreak began. Of this, there have been over 10,500 cases in Sierra Leone with more than 3,200 deaths.

At the request of the Government of Sierra Leone and the UN, HMG decided to lead the international mission in Sierra Leone to control, contain and ultimately defeat Ebola (in Liberia the US is the lead and the French in Guinea).

In September UK Ministers agreed to a stepped up response to the Ebola outbreak in West Africa, with the UK playing a leadership role focused on bringing the Ebola outbreak under control in Sierra Leone. Key aspects of the UK offer were:

To set up a Joint Inter-Agency Task Force (JIATF) led by the UK Department for International Development, and including the Ministry of Defence, and Foreign and Commonwealth Office to provide the backbone of planning, infrastructure, training and management needed to scale up the response, working with the Government of Sierra Leone to provide coordination at national and district level, and support for the UN to tackle systemic issues.

To scale up the number of available treatment beds. This includes establishing physical infrastructure for additional beds using military oversight and local contractors; ensuring management and staff are available to deliver effective treatment; and ensuring supplies are available.

To pilot and prepare to take to scale Community Care Centres (Safe Isolation Beds) – community level care centres where individuals can present with early symptoms for early isolation, testing and referral.

To establish laboratories to speed up diagnosis of the disease and so make the system work more effectively.

To support prevention and infection control services such as social mobilisation, contact tracing and safe burial services to reduce the number of people needing treatment.

To prevent spread to the wider region through support for regional preparedness and ensuring robust contingency planning.

The overarching aim underpinning this offer is to control the spread of Ebola in Sierra Leone and the region, by reducing transmission rates to less than 1 initially (and the to zero). Once the transmission rate is less than 1, the disease will effectively be coming under control – fewer people will be contracting it than have it, which logically leads, eventually, to no new cases. A second imperative is to do this as quickly as possible to minimise loss of life.

Illustration of UK strategy
Through the following projects / To achieve this end state… / Our Strategic Aims are.. / Urgent Needs & Support for Appeals / Kerry Town Treatment Centre / 5 Ebola Treatment Centres and staffing / Reduce transmission rate of Ebola to less than 1 in Sierra Leone initially then to zero / Safe Isolation Beds / Laboratories / Control the spread of Ebola in Sierra Leone and the region, leaving a legacy of stronger health systems / Supply Chain Platform / Safe Burials and Social Mobilisation / Joint Inter-Agency Task Force (JIATF) / Support to UNMEER and UN system / Prevent spread to the wider region / Regional preparedness initiative / Stimulate global public goods to tackle this and future epidemics / Accelerated clinical trials and rollout of candidate Ebola vaccine / Delivering existing portfolio / Tackle wider consequences of Ebola in Sierra Leone / New initiatives to tackle immediate negative impacts

An assumption has been made that there would be little prospect of the disease being contained without UK intervention. Government systems alone were not sufficient to contain the outbreak and lack of a UK intervention would have almost certainly led to thousands of extra lives lost and the potential for region wide spread. It could also have led to complete breakdown of law and order and economic activity in Sierra Leone.

The response is sufficiently flexible to respond to needs as they arise and be driven by the epidemiological data. Parts of the response will be scaled up or down in different geographical areas as hotspots arise or the disease is brought under control. This will ensure that best use is made of resources, directing them to where they are most needed.

Compliance with the Gender Equality Act 2014
Although available data show both sexes infected and dying in roughly equal measure in the Ebola outbreak, women are particularly vulnerable due to their traditional caring roles and pre-existing gender inequalities in the society. In addition, the secondary impacts of Ebola on women and girls in particular are likely to be significant. DFID has developed a Protection Strategy covering the entire response to address gender-related vulnerabilities and mitigate the extensive secondary impacts on women and girls by: mainstreaming gender across the response; tailoring interventions to address the particular needs and vulnerabilities of men and women; and addressing the related secondary impacts on women through programme design. The response is therefore compliant with the Gender Equality Act.
## Appraisal Case

As mentioned in the Strategic Case above, it is reasonable to assume that an out of control epidemic risks mass fatalities, and possible regional contagion as evidenced by the limited spread to Mali and Nigeria. It also threatens an eventual wider spread. In addition to the CDC estimate in September that there could be as many as 1.4 million Ebola cases in Liberia and Sierra Leone by January 2015 the World Bank reported in early October that in the “Low Ebola” scenario, lost GDP for West Africa as a whole was estimated at $2.2 billion in 2014 and $1.6 billion in 2015. In the case of “High Ebola”, estimates suggested $7.4 billion in lost GDP for 2014 and $25.2 billion in 2015, with both cases assuming at least some spread to other countries.[2] Thus the cost of failing to respond outweighs the cost of the intervention.
[2] World Bank. 2014. The economic impact of the 2014 Ebola epidemic : short and medium term estimates for West Africa. Washington, DC : World Bank Group. http://documents.worldbank.org/curated/en/2014/10/20270083/economic-impact-2014-ebola-epidemic-short-medium-term-estimates-west-africa

In September UK Ministers agreed, at the request of the Government of Sierra Leone and the UN, that the UK would provide leadership for the effort to control, contain and ultimately defeat Ebola. Not responding positively would have been difficult to justify given the UK is Sierra Leone’s largest bilateral donor partner and the recent historical ties between the UK and Sierra Leone. No other international partner was able to intervene at the required scale and speed.

A comprehensive and multi-faceted response

The urgency of the situation and range of interventions needed to enable a full, coordinated response, made it necessary to maximise the effectiveness and efficiency of existing capacity, but this on its own was not considered sufficient. New capacity had to be brought on line as quickly as possible and at a dramatically increased scale. This meant using capacity within Sierra Leone, and from outside the country. In effect, a strategy of numerous interventions that collectively tackle all stages of the transmission cycle simultaneously made sense within the boundaries of management capacity and risk thresholds.

The key to success thus far has been the mobilisation of a far greater response than had previously been in place, ensuring the provision of services got ahead of the epidemiology and the number of cases. This meant working through a mix of partners to deliver the following:

- Increased awareness of how Ebola is transmitted
- Reduced transmission in treatment facilities
- Reduced transmission through safe burials
- Reduced transmission in communities in Sierra Leone

In addition, there was a need to improve planning and coordination of efforts, to tackle the wider consequences of Ebola in Sierra Leone and to prevent spread to the wider region. In September 2014 DFID commissioned analysis which highlighted that the countries at the highest risk of Ebola importation were Cote d’Ivoire, Mali, Guinea-Bissau, and Senegal, in large part due to their shared and largely porous borders with Sierra Leone, Guinea, and Liberia.[1] DFID has refined this to produce a dynamic risk index that highlights the continued risk of the spread to Nigeria and Ghana (“INFORM” Ebola).
[1] Ebola in West Africa, Ebola Risk Report 10th October 2014. Maplecroft Risk Analytics.

The mix of modalities, capacities, and partners used includes:

- DFID direct delivery: through direct procurement of goods and services, and the deployment of civil service and contracted expertise.
- UK MOD: a mixture of military personnel and assets, as part of a Joint Inter Agency Task Force.
- NHS personnel: advising and staffing key facilities
- UN: through support to the UN mission, UNMEER, and funding for UN delivery agencies, in particular UNICEF.
- Red Cross: through support to the Sierra Leone Red Cross Federation safe burial teams
- Non-Government Organisations: to deliver a wide range of priority initiatives.
- Government: support for the National and District level emergency response structures, in particular through planning inputs.

Evidence base

Given the unprecedented nature of the outbreak, the evidence base for what interventions are most effective is limited. An Ebola outbreak of this scale has never occurred before and public health emergencies of a disease with such a high mortality rate are also rare. As such, innovative thinking and approaches have been based on an understanding of the modes of transmission of the disease, the potential epidemiological curve, and the geographical region in which is occurring, including the capacity of state institutions and cultural context.

The response was based on the best available evidence for the epidemic to date and evidence from previous smaller epidemics. There was also investment in Ebola research, such as epidemiology and anthropology, which was drawn on to inform the ongoing response. Advice from DFID’s Chief Scientist, informed by a visit to Sierra Leone in October, also shaped the response.

In order to reduce the number of cases, interventions needed to be put in place that stopped the epidemic spreading. This included: 1) required cases to be isolated at an early stage in the disease (when their infectivity is low); 2) infected dead bodies to be prepared and buried safely; and 3) adoption of safe behaviours to reduce spread between people.

WHO and CDC modelling suggested that approximately 70% of cases needed be isolated at an early stage of the disease when their infectivity is low. The only previous evidence on early isolation of cases was through treatment facilities, however it was unlikely that it would be possible to sufficiently to scale up the number of beds in treatment facilities quickly enough, and therefore alternative solutions needed to be explored. One community based option (proposed by WHO) was community care centres (CCCs) to isolate cases. An alternative option of providing home based care (with distribution of personal protective equipment) was discounted as it had been trialled by UNICEF/USAID with some poor preliminary reports. It was also critical to ensure that there was rapid laboratory testing for these facilities, that people presented early to these facilities when unwell, that staff were trained to work in these facilities, and that health staff were protected from being infected.

In order to get infected dead bodies to be prepared and buried safely, this required burial teams to be trained to safely carry out sensitive safe burials. It also required social mobilisation to ensure the population were reporting deaths appropriately. Social mobilisation has underlain all the interventions, ensuring that the population were aware of Ebola, that they were adopting appropriate behaviours (such as hand washing) to stop cross infection, that they were presenting themselves early if developing symptoms, and that they followed appropriate burial practices.

In order to determine whether interventions were going to be effective, there were a number of models of the epidemic established by centres such as Imperial College, CDC and LSHTM. There were a wide variety of potential outcomes within each of the models, and between the models. The models confirmed that the outbreak was following an exponential growth as expected, The models suggested that if sufficient cases were isolated at an early stage, (as well as social mobilisation and safe burials), this would be sufficient to “turn the curve” and start to control the epidemic. The planned scale up in treatment facility beds was inputted into the models, which was used to suggest the likelihood that this would be sufficient to control the epidemic.

The graph below is the model developed in September (based on the CDC modelling) which showed the most likely scenario (in dark red) with upper and lower confidence intervals of the potential scenarios. The actual cases to date were shown in blue, and planned scale up in beds shown with a black dotted line. This model showed that under the most likely scenarios, the scale up in beds (accompanied with safe burials and social mobilisation) would be sufficient to control the epidemic and reduce the reproduction number to below 1.

Theory of Change

Based on this evidence, UK funding has been directed to treatment facilities in locations determined by the epidemiology as areas of high transmission, that are lacking in existing facilities and agreed with Government and communities. These are places that those suspected or confirmed as has having Ebola can go to be both safely isolated and to receive a certain standard of treatment. To encourage health care workers to volunteer, one of the facilities includes a wing for health care workers where they know they can be treated should they become a suspected or confirmed case.

The speed and geographical spread of the virus, along with the time taken to construct treatment facilities, dictated that smaller scale isolation facilities that could be set up rapidly in communities were also required. These reduce the risk of transmission by being located widely throughout the country, providing a triage service so that those who need health care but do not have Ebola do not need to go to treatment facilities.

Safe isolation and treatment facilities alone though would be insufficient. People have to accept and be willing to use them. Part of the solution to this is that they provide a certain standard of care and they are not perceived as likely sources of transmission or simply places where people die without their family around them. Social mobilisation has increased awareness and understanding of the disease, including on the symptoms of Ebola and how it is transmitted[2]. With this knowledge it could be expected that a greater proportion of people would present at isolation or treatment facilities earlier when they recognised they had potential symptoms. It could not be guaranteed, however, that even with information and understanding that behaviour would change. Messaging that chances of survival are greater when people seek treatment early was, and continues to be, vital. But denial must be addressed to avoid people remaining in their communities once they are infectious. This is particularly important in Sierra Leone where traditional beliefs are prominent around causes and treatment of disease.
[2] Study on Public Knowledge, Attitudes and Practices Related to EVD in Sierra Leone: KAP3. Focus 1000, CDC, UNICEF. January 2015.

Given that the symptoms of Ebola, especially those in the early stage, are similar to those of many other diseases, accurate diagnosis is another area of intervention that is required. Laboratory testing for Ebola in Sierra Leone was extremely limited as were staff with equipment and knowledge to run tests. Provision of laboratories and staff to work in them was therefore required.

Those identified as potentially or definitely having Ebola would most likely have had contact with a number of other people. To limit the spread, identification of those individuals through case investigation, contact tracing, and surveillance has been necessary. Monitoring of their condition, and in cases, isolation of them through quarantining of areas or households has occurred. To assist people under quarantine to observe the quarantine and not move out of these areas and risk infecting others, basic supplies of food and drink and other essential non-food items have been provided.

Together these interventions should reduce the number of people who stay in their communities and behave in a way that risks infecting others and should increase the number of people who present early for isolation and treatment. The highly deadly nature of the disease will, however, mean that many of those who contract the disease will not survive. Corpses are especially infectious. Burial practices in Sierra Leone can often include contact with the corpse and so burials are a potential source of widespread infection. Safe burials that ensure people do not make contact with the corpse have been vital. These must, however, be conducted in a dignified manner that respects the religious views and beliefs of the deceased and their family. Any other approach would simply drive reporting of deaths and unsafe burial practices underground. Interventions that provide burials in a safe and dignified manner and social mobilisation that explains the infectious nature of corpses and the respectful approach of burial teams has been important.

There was a similar risk that Ebola could spread more widely through high-risk countries in the region and therefore we have pushed key partners (WHO, EU, and bilateral partners) to ensure preparedness gets the attention it needs. UK funding has been directed to a new START programme, which will mobilise community organisations to prevent the spread of Ebola in neighbouring countries to reduce the risk of cross-border transmissions. This will focus on community engagement and community-based activities, such as training and awareness-raising, including through local health actors, and will focus on at-risk areas, such as border areas.

This suite of interventions combines to make an end-to-end system that people are more likely to engage with and safely isolates more people, reducing the rate of infection than if no interventions were made. These interventions have been underpinned by enabling infrastructure and personnel. The treatment facility at Kerry Town for health care workers and medevac provision enabled a greater number of health care workers to respond, and the provision of helicopters has allowed key activities to happen in a short timeframe. Civilian and military personnel embedded into District Ebola Response Centres along with equipment and supplies allowed greater coordination in the response. These elements combined to reduce the transmission rate below 1, to control the epidemic and so save lives.

- No further disasters occur during response / - Needs assessment accurate / - Behaviours change / OUTPUTS / Create more treatment beds / Create more safe isolation beds / Ensure safe burials / - Improved effectiveness of overall response / - Life saving assistance provided / - Transmission rate reduced to below 1 initially then to zero / Reduce transmission through social mobilisation / Strengthen coordination, command and control / ASSUMPTIONS / Provide enabling infrastructure for international health workers / - Funding for projects / - Technical expertise / - Military assets / - Contribute to appeals / Lives saved and suffering reduced / OUTCOME / IMPACT / INPUTS / Epidemic Controlled

Costs and benefits

The estimated overall cost of the UK intervention will be up to £416.13 million, though budgets are regularly reviewed and are committed to implementing partners only as needed. This budget is split across a range of projects, which is set out in the following financial case, to deliver the results outlined above. Based on the premise that Sierra Leone did not have capacity to respond and that the UK was best placed to do so, delivering the interventions detailed previously, there is little value in a full cost-benefit analysis of the overall response. There was a humanitarian imperative to act, to act at scale and at speed. The costs of any other course of action far outweigh the costs of action.

Value for money

The estimated cost has been set out above and in the Financial Case below. The financial cost of response is driven by the epidemiology and so costs could deviate from this amount. The budget required is assessed throughout the response to determine the budget required in line with the context.

The appropriateness of the overall multi-faceted intervention is based on the need for the UK to intervene in a range of areas. The other vital factor is timeliness. The projected epidemiological curve, depicting cases against time, shows that the longer the outbreak is left unchecked, the faster the virus is likely to spread. To achieve the strategic aim of reducing the reproductive rate below 1 and bringing the outbreak under control, the imperative is to implement all appropriate activities as quickly as possible. The longer the reproductive rate remains above 1, the greater the scale of the intervention required to bring the disease under control. Earlier action will cost less and save more lives.

A rapid, multi-faceted approach was therefore required across the piece. Unless the system of prevention, social mobilisation, safe isolation, diagnosis, treatment and safe burials is all up and running, the disease cannot be brought under control. An approach of procuring goods and services early, rapidly, and at scale to ensure the outbreak does not remain and get further out of control, does have the associated risk that some individual projects within the overall response may not deliver as good value for money as would be possible if there were time for greater analysis. However, given the inherent uncertainty in the epidemiology, waiting for more analysis would have resulted in slower action. This risk of incurring excess costs is tolerable given the risk of the alternative of doing too little and remaining behind the curve, which would ultimately lead to a higher cost overall. We have been monitoring the epidemiology regularly and have scaled up or down as appropriate, ensuring costs are not borne where they are not needed or committed.

To enable such rapid action and therefore value for money, there are a number of activities the UK is undertaking. The first is a cross Government effort with the UK bringing the full weight of expertise in its civil service to bear. Humanitarian, health, and programme management experience within DFID will be deployed to understand the details of interventions required and implement them effectively. This includes contributions to multilaterals and NGOs to implement interventions, but also includes deployment of NHS volunteers to staff facilities and military personnel to oversee construction of facilities and support command and control structures to ensure the parts of the system all function in a coordinated manner. The rapid deployment of staff from across the UK Government is vital.

Rapid funding mechanisms that allow implementing partners to adapt their response to changing needs as they emerge has been crucial. DFID has followed the Smart Rules and the humanitarian guidance within this to provide funding quickly to delivery partners best placed to deliver the activities needed. This includes pre-financing and rapid procurement mechanisms.

DFID has also procured and delivered the necessary assets and equipment at pace and at scale. This capacity has been used to fully equip treatment and safe isolation facilities for an initial period of their operations. This has prevented implementing partners competing against each other for limited supplies which would drive up prices. It also ensures a reliable pipeline of equipment.

Within this overarching framework of operating at scale and speed to generate effective delivery and value for money, suppliers for individual interventions are also assessed for value for money to ensure costs are reasonable at the individual intervention level. This is in the context of a limited pool of partners with expertise and willingness to mobilise in the timescale required. This has involved humanitarian and health advisors assessing the quality of proposed interventions, allayed with programme managers scrutinising costs. Such analysis has been rapid to avoid unnecessary delays and acknowledge the risk premium of hazardous interventions being delivered at speed and the additional costs this brings. This approach to programme management will strike a balance of speed, appropriateness and minimising costs.

As the context has changed, DFID has kept in contact with implementing partners, ensuring that forecast budget costs that are no longer needed are not incurred. This includes ensuring treatment and safe isolation facilities are of an appropriate size for the case numbers in a geographical area. Additionally suppliers are challenged to adapt their approach to make the best use of the budgets available – learning from what has proven effective and where an approach needs to change to deliver results in different areas.

Commercial Case

Given the need for rapid delivery, quick identification of partners was vital, especially in the initial stages. As the earlier diagram shows, in the initial phases each passing week represented an ever increasing number of cases. Fast identification and agreement with partners was therefore of paramount importance.

Very few potential delivery partners had the necessary experience or were in country to deliver at scale as the outbreak escalated. It was therefore necessary for DFID to build the market. This included setting out the HMG offer which included construction oversight of ETCs, procurement and delivery of assets and consumables to be used by operating partners and the construction and running of the unit at Kerry Town for health care workers as well as medevac provision. This built an understanding amongst potential partners of the enabling factors and share of risk the UK could offer and what requirement they could fulfil.

Market engagement events such as the call for proposals helped generate interest in a range of interventions including running ETCs and support for quarantined households. Engagement with potential partners at all levels of HMG also helped explain the offer and partnership that would deliver the strategy.

Both direct and indirect procurement were used to select appropriate partners as set out below.

Direct procurement:

Supply of assets and consumables including vehicles, PPE, and medical supplies for treatment and safe isolation facilities

DFID has adopted an approach to procurement to ensure adequate levels of supplies have been provided to partners to allow them to operate without any break in delivery. Given the large number and value of assets to be procured, these will be included on partners asset registers. For vehicles provided to the Government for operational purposes, most notably to district level response centres, an MoU will be put in place with Government, specifying that these remain DFID assets and that they are to be used only for the purposes of the Ebola response.

Direct procurement by DFID has ensured partners do not have to compete against each other for supplies, which could have driven up prices unnecessarily. This ensured an ongoing supply chain from international sources to Sierra Leone and mitigated the risk of stock-outs. Also, holding stock allows DFID to look at needs across projects and be flexible in releasing assets and consumables to partners as their need arises.

From September to December supplies were procured directly through CHASE OT, who are contracted by DFID specifically to provide staff and procure supplies in emergencies. Given this pre-contracted resource and the need for rapid mobilisation, organising a competitive procurement process was not necessary. Assets and consumables required for treatment centres and facilities providing safe isolation beds have been defined by implementing partners, and then approved by DFID before being passed to CHASE OT to source, ship and deliver to Sierra Leone. A CHASE OT team has been deployed in Sierra Leone and embedded in the Freetown office.

Given the competing needs for CHASE OT’s services, this has been a time-bound arrangement so a tender went out to source an external supplier to provide ongoing supplies from December onwards. A joint venture between Crown Agents and International Procurement Agency (CAIPA) was selected to provide a Central Supply Chain Platform. Assurance of CAIPA’s financial processes and operational capacity was provided as part of the tender process which was assessed on both the technical and commercial ability to deliver the terms of reference.

DFID has also undertaken some direct procurement locally, where goods are available to avoid time lags associated with shipping of goods internationally, often providing goods at lower prices. This has applied particularly to safe isolation bed facilities where more basic equipment such as sheets and buckets can easily be sourced in Sierra Leone.

Transportation of internationally procured assets and supplies

The majority of internationally procured assets and supplies for the response have been transported to Sierra Leone by air. Sea freight was not a viable option due to the length of the journey which would have delayed the opening of treatment and care centres, along with the fact that various commercial ships are avoiding docking in Freetown.

While DFID uses commercial air freight wherever possible, the high volumes of equipment and supplies required means that a large number of charter flights has been necessary. These flights are procured using the DFID Air Charter framework agreement, which exists to secure charter flights at the best possible market price. All flights have been loaded and unloaded by DFID procurement agents and Ministry of Defence colleagues to ensure security of assets.

DFID will apply to the European Union Civil Protection Mechanism for co-funding of up to 55% of the cost of transporting supplies. DFID is also making use of offers from Norway and the Netherlands for the transport of equipment via their air and sea assets.

Local construction of treatment facilities

DFID has directly procured the services of local construction companies to build treatment facilities under the oversight of the UK MOD Royal Engineers. This is lower in cost than construction by the Royal Engineers directly or by a UK sub-contractor, but retains quality standards and understands the local construction market and challenges, and a readily available work force to begin construction quickly.

Construction suppliers were identified through a rapid tender process, with tenders being assessed by a multi-disciplinary DFID team on their technical and commercial capability to deliver. As it is not possible to anticipate all the requirements of the treatment facility sites, where work needs to be completed beyond the initial scope and budget, this has been agreed by DFID though variation orders. This ensures that any faults or changes to the design deemed necessary can be made quickly.

Facilities management of Kerry Town treatment centre

The NGO partner operating the Kerry Town treatment centre initially had difficulty taking on facility management of the centre. As a consequence of this DFID directly procured the services of a facility management agent to provide catering, transport and security at the site, enabling the treatment centre to open in the required timeframe. This contractual arrangement was for a fixed period only and responsibility for facility management has transitioned to the NGO partner.

Indirect procurement:

Ministry of Defence (MOD)

The MOD is DFID’s main partner delivering the UK response to the Ebola crisis. The significant contribution they are making is covered by an overarching MOU framework agreement, supplemented by an exchange of letters between the Secretary of State and the Armed Forces Minister confirming the ceiling cap for MOD costs.

MOD personnel, including Royal Engineers, medics, and planning specialists have supported a number of initiatives, notably the establishment of treatment centres (including running part of the Kerry Town facility) and the setting up of the Joint Inter Agency Task Force. Military personnel have worked jointly with civilians to support coordination of the response at the national and district level. The MOD has also sourced and procured additional Air Transport Isolators (ATIs) to enable medevac, and deployed RFA Argus and three Merlin helicopters in support of the overall effort. In addition, during October and November the MOD provided training in the UK for health workers prior to deployment, and established and ran an Ebola training academy in Freetown, delivering WHO-standard infection prevention control training to Sierra Leonean volunteers and foreign medical teams.

NGOs

International and local NGOs are being supported by the UK to deliver a wide range of initiatives in response to the Ebola crisis. In Sierra Leone, DFID is funding NGOs to run and manage treatment centres, provide training for health care workers working in treatment and care facilities, to assist with social mobilisation, contact tracing and surveillance, safe burial services, and support to those in quarantined homes. In the UK, DFID is funding NGOs to provide training for health care workers prior to deployment, and to provide psychological support to health care workers before, during and after their deployment (which is integrated with the support systems provided by host NGOs for health care staff working in the facilities they manage).

NGO partners are selected based on a range of criteria including: track record in country; ability to scale up and deliver; reputation; geographical coverage; value for money; and evidence that they are working closely within the formal response architecture. Where possible, NGOs have formed consortia in order to achieve as wide a geographical coverage as possible, take advantage of NGOs’ niche capabilities, achieve economies of scale, and minimise transaction costs for DFID.

All NGO partnerships are governed by Accountable Grants. All Accountable Grants include standard text on use of DFID funds, zero-tolerance of fraud and corruption and monitoring arrangements so DFID can scrutinise expenditure and delivery. Given the time-critical nature of the response, DFID has provided some up front funding to allow implementing partners to commence activities quickly and avoid cash flow issues. The amounts provided have been on the basis of budget forecasts from partners that demonstrate need, with disbursements generally being made on a quarterly basis. In compliance with DFID’s zero tolerance policy for fraud and corruption, we will follow up with agencies where we have reason to believe that DFID-funded operations or supplies have been lost, damaged or unaccounted for.

National Health Service (NHS)

DFID is working with UK-Med to manage the supply of NHS staff to work in UK-supported facilities through the International Emergency Medical Register. Volunteers are deployed for a period of eight weeks, during which time NHS Trusts are reimbursed for the costs of locum cover during their deployment. NHS staff are hosted by the NGOs operating ETCs and safe isolation bed facilities, and their welfare and safety is overseen by the UK Med Quality Assurance Unit in country. The Unit, funded through an Accountable Grant, is responsible for reviewing and monitoring the safe operation of clinical protocols in the UK-run ETCs.

Public Health England (PHE)

DFID has entered into an MOU agreement with PHE to staff and run thee diagnostic laboratory facilities in Sierra Leone. The MOU covers the reimbursement costs associated with the deployment of PHE staff. PHE are also, in consultation with DFID and with the necessary ethical approval, conducting trials as part of developing enhanced diagnostic testing methods.

UNMEER, wider UN system and other multilateral

DFID contributed £20 million to a UN Multi Partner Trust Fund administrated by the United Nations Development Programme (UNDP) and agreed through an MOU between DFID and UNDP. These funds are earmarked to activities in Sierra Leone and the UK has a seat on the Advisory Board to the Trust Fund, enabling review of specific activities before disbursement. The Trust Fund is crucial to leveraging support from other donors and should assist in coordination of the response.

Additionally, the UK is funding technical assistance to the UN system through the established standby partnership. This will ensure that staff with expertise can be deployed rapidly to UN agencies and to districts to support the response at all levels. Funds have also been provided to UNICEF to provide protection services to vulnerable groups and procurement of medical supplies.

DFID has also provided funding to the International Federation of the Red Cross and Red Crescent in Sierra Leone through the British Red Cross appeal to support safe and dignified burials and treatment activities.

Other Governments

DFID has entered into agreements with a number of other country governments including Denmark, Norway, South Korea, and Australia to provide a supply of clinical staff to work in treatment facilities on a rolling basis. These agreements, which do not involve funding, are based on MoUs.

## Financial Case

As mentioned in the value for money part of the appraisal section, the financial picture cannot be certain due not only to the indeterminate nature of the epidemiology, both in terms of scale and duration, but also in terms of the scope of support, including financial support, from other international partners. The risk of this uncertainty is minimised to an extent through daily tracking of the epidemiology and regular discussions with other donors to understand the level and type of HMG support required.

DFID has plans in place to the value of £416.13 million if needed. This budget was approved on the basis of a series of submissions to the Secretary of State (not on the basis of this business case). The funding is split across the projects established to deliver the response as shown in the table below. Given the scale of the response projects have been set up under a new Ebola Crisis Response budget centre – PO438 and PO439 – to enable financial management.

Projects	Total Planned Budgets (£m)
204838: Urgent Needs	52.50
204876: Kerry Town Treatment Centre	53.54
204890: Additional Treatment Centres & Human Resources	113.60
204893: Safe Burials & Social Mobilisation	12.50
204896: Safe Isolation Beds	68.50
204900: Support to UNMEER & the wider UN system	24.05
204902: Joint Inter Agency Task Force (JIATF)	36.44
204904: Laboratories	15.00
204917: CAIPA Supply Chain Platform	5.00
204919: Match Funding for the Ebola Response	10.00
204929: Regional Preparedness	25.00
	416.13

The exact total required both by project and overall cannot be provided definitively at time of writing as the future trajectory of Ebola cases and the precise scale and scope of interventions needed to best address these cannot be guaranteed. If case numbers fall dramatically it may be that the full funding is not required. DFID will monitor this and scrutinise requests for funding from partners. It may also be that funding needs to be shifted between projects and components and within projects to ensure the flexibility required in moving resources to respond to need. These changes will be sought through submissions to Deputy Directors, explaining the rationale and ensuring the overall approved budget is not exceeded. If funding needs increase this will be sought through a submission to Ministers with an addendum attached to this business case.

Funding Partners

To deliver these projects, funding is provided to a range of partners as set out in the table below. Partners have been chosen by DFID based on their ability to deliver specific parts of the response at pace. This includes multilateral organisations and funding to appeals, funding to NGOs and local contractors, as well as transfers to UK government Ministries and Agencies delivering parts of the response. The table also shows the funding agreements used and amounts allocated to date.

		Indicative Commitment
Urgent Needs (204838)
UN Standby partnership	Memorandum of Understanding	£1,000,000
British Red Cross Appeal	Memorandum of Understanding	£5,100,000
MSF Belgium	Accountable Grant	£750,000
UNICEF	Memorandum of Understanding	£7,100,000
International Rescue Committee (on behalf of ERC Consortium)	Accountable Grant	£9,700,000
GOAL	Accountable Grant	£7,500,000
EMERGENCY	Accountable Grant	£950,000
International Rescue Committee	Accountable Grant	£738,052
Riders for Health	Accountable Grant	£50,000
MAP Action	Accountable Grant	£52,000
Norwegian Refugee Council/ACAPS	Accountable Grant	£548,107
World Vision	Accountable Grant	£8,597,169
UNICEF	Memorandum of Understanding	£2,558,520
Plan International UK	Accountable Grant	£5,120,742
Kerry Town Treatment Centre (204876)
Procurement and Logistics (by a number of suppliers)	Contracts	£25,962,000
Construction (by a number of suppliers)	Contracts	£3,000,000
Save the Children	Accountable Grant	£12,205,811
Ministry of Defence	Memorandum of Understanding	£7,342,000
Oxford Policy Management	Contract	£38,985
Kellogg Brown & Root (KBR)	Contract	£1,857,809
Additional Treatment Centres & Human Resources (204890)
Construction (by a number of suppliers)	Contracts	£10,420,000
Procurement and Logistics (by a number of suppliers)	Contracts	£46,148,727
IMC (Makeni ETC)	Accountable Grant	£6,546,727
GOAL (Port Loko ETC)	Accountable Grant	£10,386,522
Medicines du Monde (Moyamba ETC)	Accountable Grant	£7,648,760
EMERGENCY (Goderich ETC)	Accountable Grant	£5,417,991
Ministry of Defence	Memorandum of Understanding	£2,208,960
Sierra Leone Diaspora	Accountable Grant	£20,850
RedR	Accountable Grant	£886,436
UK Med	Accountable Grant	£346,587
UK Med	Accountable Grant	£1,696,000
International Organisation for Migration (IOM)	Accountable Grant	£4,187,240
WHO	Memorandum of Understanding	£188,167
International Humanitarian Partnership	Accountable Grant	£748,721
Maudsley NHS Trust	Accountable Grant	£241,328
Safe Burials & Social Mobilisation (204893)
IFRC (British Red Cross)	Memorandum of Understanding	£8,426,435
GOAL	Accountable Grant	£3,123,628
Safe Isolation Beds (204896)
Procurement and Construction (by a number of suppliers)	Contracts	£17,388,453
Partners In Health	Accountable Grant	£10,476,283
International Rescue Committee	Accountable Grant	£6,009,545
OXFAM	Accountable Grant	£8,486,459
UNICEF	Memorandum of Understanding	£20,603,393
UNMEER & wider UN system (204900)
Ministry of Defence	Memorandum of Understanding	£2,132,000
UN Multi-Partner Trust Fund	Memorandum of Understanding	£20,000,000
UK Joint Inter Agency Task Force (204902)
Ministry of Defence	Memorandum of Understanding	£20,062,000
CHASE OT and Stabilisation Unit deployments (by Crown Agents)	Contracts	£2,200,000
Laboratories (204904)
Construction (by a number of suppliers)	Contracts	£3,000,000
Ministry of Defence	Memorandum of Understanding	£2,600,000
Public Health England	Memorandum of Understanding	£4,200,000
CAIPA Supply Chain platform (204917)
Crown Agents/IPA	Contract	£5,000,000
Match Funding for the Ebola Response (204919)
Disasters Emergency Committee Appeal	Memorandum of Understanding	£5,000,000
UNICEF Appeal	Memorandum of Understanding	£1,000,000
Band Aid 30	Memorandum of Understanding	£1,000,000
Regional Preparedness (204929)
START Network	Memorandum of Understanding	£7,265,278

Financial risk and fraud is mitigated through a number of measures. Many of the partners are either established NGOs that DFID has funded before (though not necessarily in Sierra Leone) or parts of UK Government. As such, DFID will conduct country level due diligence on all NGO and multilateral partners we have not funded in Sierra Leone in the previous three years. Given the speed of response necessary, due diligence assessments have been prioritised, with those covered by central assessments and established partners being a lower priority than for new partners. Central assessments, including the rapid response facility will also be drawn on to establish potential risks.

Country level assessments focus primarily on ability to deliver in country – to scale up personnel and systems to deliver in areas they may not have delivered in Sierra Leone before. They also focus on partners’ ability to manage downstream partners, checking that processes are in place and operationalised to mitigate against misappropriation of funds. Key risks identified in due diligence assessments will be discussed with partners and incorporated into delivery plans to ensure they are acted upon.

Management Case

Leadership

A dedicated Ebola Crisis Team has been established to lead and manage the overall Ebola response. The team is led by a Director based in the UK. Another Director is based in Sierra Leone and heads the Joint Inter Agency Task Force (JIATF), made up of civilian and military expertise. The Ebola Crisis Team comprises the DFID office in Freetown, where the majority of the increased staffing capacity is focused on the response, and UK-based surge capacity to lead on cross-Whitehall and international coordination, wider/regional Ebola preparedness, and support operational delivery.

Ebola Crisis Team Senior Leadership
DEPUTY DIRECTOR / OPERATIONAL DELIVERY / DIRECTOR / JOINT INTER AGENCY TASK FORCE (JIATF) / DIRECTOR / EBOLA RESPONSE / Command Group / (DFID*, FCO, MOD) / DEPUTY DIRECTOR / DFID SIERRA LEONE / DEPUTY DIRECTOR / X-WHITEHALL, REGIONAL PREPAREDNESS & OPERATIONAL DELIVERY SUPPORT

* Deputy Director DFID Sierra Leone is DFID representative in JIATF Command Group

The Government of Sierra Leone has set up a National Ebola Response Centre (NERC) to lead and coordinate the overall Ebola response. The NERC consists of a pillar structure covering the key elements including case management, safe burials and social mobilisation. District Ebola Response Centres (DERCs) have also been established, with significant support from the UK, in each of the districts to coordinate the response at the district level.

The JIATF coordinates the UK’s response through daily interaction with NERC, including with personnel embedded in it. Through JIATF, the UK will second military and civilian personnel to support the command and control structures in districts to coordinate the alert system and deployment of teams such as ambulance, burial and contact tracing teams, to ensure the component parts of the system work together as a whole.

Programme Management

There are currently 11 distinct projects contributing to the strategic aims governing this programme (as per the illustration in the financial section above).

Operational Delivery Teams in Sierra Leone are responsible for the delivery of seven of the projects. The remaining four (support to UNMEER, JIATF, Match Funding Appeals, and Regional Preparedness) are led by programme management support in London.

Senior Responsible Owners (SROs) have been assigned to each project. The SROs utilise advisory and programme management capacity in their teams. These delivery teams are supported by a cross-cutting procurement and logistics team that lead on procurement of assets and consumables needed, such as PPE, medical supplies, vehicles and other assets.

Projects	SRO
204838: Urgent Needs	Ed Davis
204876: Kerry Town Treatment Centre	Claire Vallings
204890: Additional Treatment Centres & Human Resources	Claire Vallings
204893: Safe Burials & Social Mobilisation	Ed Davis
204896: Safe Isolation Beds	Claire Vallings
204900: Support to UNMEER & wider UN system	Jo Scott-Nicholls
204902: Joint Inter Agency Task Force (JIATF)	Jennie Barugh
204904: Laboratories	Claire Vallings
204917: CAIPA Supply Chain Platform	John McGhie
204919: Match Funding for the Ebola Response	David Bailey
204929: Regional Preparedness	Anne Philpott

Many of the projects consist of several components which are delivered by a range of partners including multilaterals, Non-governmental Organisations (NGOs), UK Government Departments and Non-Departmental Public Bodies such as the Ministry of Defence and Public Health England, and local construction companies.

As described above, due diligence assessments are carried out on all partners outside Government that DFID have not funded previously in the last three years in Sierra Leone. These assessments identify potential areas of risk which are incorporated, along with mitigating actions into delivery plans. These plans act as programme management tools for delivery teams to track results, risks and finances and are monitored by teams, with risk mitigations being escalated up the command chain as needed to ensure the results needed to achieve the strategic aims are delivered to time. Delivery plans will be updated regularly, informed by discussions with delivery partners and emerging needs.

Monitoring

Situation Reporting

There are four main mechanisms to monitor and communicate the situation and response of the Ebola crisis in Sierra Leone to senior levels. There is the daily Commander’s Update Brief (CUB) which reports to the JIATF Command Group; a situation report which is circulated three times a week; and a weekly operational brief. In addition to this, Ministerial and Official level COBR meetings also discuss the situation and appropriate response. All are focused on tracking the transmission rate and monitoring the epidemiology of the outbreak, using data generated from multiple sources; and tracking progress in the UK’s response. Key monitoring indicators include suspected, probable and confirmed cases and deaths by district; percentage of reported deaths that are buried safely; operational beds available; staff trained / available. Data is gathered from a range of sources, including the IFRC (Sierra Leone Red Cross), the National Ebola Response Centre (NERC), UNMEER, WHO and DFID / MOD reporting.

Programme-level monitoring

At programme level there is an Ebola Response Tracker with key performance indicators: This has been agreed between the Whitehall departments engaged in the response. The underlying purpose of the tracker is to report on indicators across the areas of UK-funded response intervention, for both the specific UK response and the overall national response, to track the situation in real time, and also to allow attribution to UK spend. Information is collected from DFID-managed facilities and partner agencies, including the WHO. There are also regular stocktake meetings between SROs and the Permanent Secretary and Senior Leadership in the Ebola Crisis Team to discuss UK projects, especially on progress and risks.

Project-level monitoring

In addition to delivery plans, projects have logframes. These draw on individual logframes with partners and aggregate results to track the overall outputs of each project. Asset registers are also established for partners so DFID can track the location and use of assets procured using UK funds, which delivery teams will monitor through spot checks.

Logframes and asset registers, combined with delivery plans, give delivery teams the key information needed to monitor the use of UK funds to deliver the results required to bring the outbreak under control. Monitoring of partners will be more intense than in most programmes due to the time-sensitive nature of the response. Discussions have at times been held on a daily basis with partners to identify bottlenecks to delivery, to evaluate where the response needs to be adapted or scaled up or down and identify who is best placed to take the necessary action. Also occurring throughout are regular field trips by DFID staff to ensure delivery is responding to need, of sufficient quality and coordinated.

Evaluation

Potential areas for evaluation will be identified to help inform future public health and humanitarian responses.

Risks and mitigating actions

The risk matrix below is incorporated into the programme delivery slide pack produced for SRO stocktake meetings and reviewed regularly.

Risks	Mitigation
Strategic Risks
Planned efforts insufficient / Security situation impedes delivery / Government, UNMEER, and wider international community is unable to respond at scale and speed required	Deliver as much as is feasible, push with all partners (NGOs, private sector, military) to generate capacity required / Review set of triggers on security situation weekly; enhance security protocols for UK team as necessary and community engagement. (BHC/ISAT) / Escalate any major concerns over UN scale up in Accra and NYC. Continued targeted lobbying including EU Council and EU conference / Public statements that risk of inaction is greater.
Delivery Risks
Insufficient supplies / Lack of partners and health workers – nervous to carry out high risk, unprecedented work / Quarantine measures and travel restrictions limit number of international staff volunteering in Sierra Leone / Partners do not sign final deals due to / changes in quarantine in home countries or lack of non-Ebola care / Health worker becomes infected in UK facility / Treatment or isolation facilities becomes source of cross-infection / transmission	Establish supply chain to deliver at scale quickly / Stimulate supply through forward contracts / High level engagement with partners including in-country. / Flexibility in programming and “the ask” of partners / Clear UK offer for international health care workers – Kerry Town bed and medevac mechanism / Targeted lobbying (by FCO) on selected home countries’ approach to quarantine. / Clinical protocols adhere to NHS minimum standards in facilities with NHS workers / Monitoring system for UK facilities (UK Med) / On-going monitoring of isolation and treatment facilities / Standard Operating Procedures agreed by the NERC
Coordination Risks
Lack of leadership and coordination capacity. / Competition for key supplies drives supplies away from UK priorities.	JIATF focus on NERC and DERC – structural changes already made / JIATF stepping into bolster command and control including at district level. / Engagement with UNICEF on global procurement needs and coordination.
Fiduciary Risk
Heightened risk through use of new partners. / Possibility of waste through procuring more than is needed	Prioritised due diligence and complete due diligence as soon as possible / Asset registers with spot checks, regular monitoring of financial expenditure. / Regular communications with partners by DFID Demand Manager to ascertain re-supply needs.

References