Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Monitoring, Evaluation and Learning Programme (formerly the ‘Results, Evidence and Knowledge Programme)
Programme Value: £12.72 million		Review Date: 1 August 2015
Programme Code: / 203516	Start Date: / 1 August 2014	End Date: / 1 August 2018

Summary of Programme Performance
Year	2014/5
Programme Score	A
Risk Rating	Low

Summary of progress and lessons learnt

Over the past twelve months the ICF Monitoring, Evaluation and Learning programme has delivered a range of useful, timely and relevant outputs. These include a web-based Knowledge Platform that is supporting the collection of ICF programme results and knowledge, a cross-government Monitoring, Evaluation and Learning strategy. DFID has also procured a comprehensive and complex monitoring, evaluation and learning contract that will strengthen collection of results, generate robust evaluative evidence and share lessons learned within HMG and to strategically important external partners.

Activities over the past year have led to the development of valuable plans and outputs that are a strong foundation for the four year programme. Positive feedback about the quality, timeliness and relevance of outputs has been provided by staff at DFID, DECC and Defra.

 Key lessons learned from the programme include:

1. Effective cross-government collaboration is crucial to ensuring that the complex programme successfully meets the needs of HMG, external stakeholders and delivers the highest quality outputs.
2. Building successful relationships and collaborating across different organisations takes time and may impact on the speed at which a programme can deliver results.
3. Sufficient Technical Adviser and Programme Management staff, time and skills across HMG is central to delivering a successful and complex programme of work. It is important that senior managers in all HMG Departments regularly review the availability of internal expertise and staff resources, and take appropriate action where necessary, to ensure delivery of a successful programme.

Summary of recommendations for the next year

1. Continue to work collaboratively across HMG to develop robust plans and quality assure outputs in accordance with international best practice.
2. Undertake research to understand why some ICF programmes do not report results through the Knowledge Platform. Subsequently, develop a strategy to incentivise reporting of results.
3. Ensure that monitoring, evaluation and learning activities are complementary and harmonized
4. Proactively engage international partners including the GCF, GEF, CIFs and EuropeAid to share good practice, lessons learned and to harmonize monitoring, evaluation and learning strategies.
5. Based on the findings from the Inception Report of Output 2, prepare a cost and/or time extension for the main Monitoring, Evaluation and Learning contract that reflects any additional VAT costs, needs for additional work and costs related to the timeframe of the ICF.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	N/A
DevTracker Link to Log frame:	N/A

Outline of the programme
The UK is providing £12.72 million over 4 years (2014/15-2017/18) through the ICF Monitoring, Evaluation and Learning Programme. This programme will enable HMG to understand and communicate results, evidence and lessons learned from the £3.9 billion International Climate Fund. This will allow the UK to influence major international partners, including the United Nations Framework Convention on Climate Change (UNFCCC), the World Bank and the Green Climate Fund and encourage other donors to take UK pilots to scale.

The programme will build global knowledge and evidence that low carbon, climate resilient development, supports growth and reduces poverty. Equally, the information gathered through this programme will supplement internal processes to strengthen public accountability and value for money from the ICF by supporting transparency and results-based performance management. The direct cost to DFID is £7.885 million (62%). DECC and DEFRA will provide £4.39 million (34.5%) and £445,000 (3.5%) of the funding respectively, in line with their percentage shares of the ICF budget.

The programme has four outputs:

Output 1: Provision of robust and appropriate tools and data to track core results across all relevant programmes (building on and supporting current ICF KPIs and programme monitoring).

Output 2: Generation of evidence and knowledge that address key strategic questions through fund level evaluations and synthesis work (building on programme-level evaluations), including whether and how the ICF has achieved transformation, and what the most effective delivery routes are and approaches for mobilising public and private climate finance.

Output 3: Knowledge Platform to enable the collection, aggregation, management and sharing of data and evidence across the ICF portfolio and among a wide range of users.
Output 4: Effective dissemination and promotion of learning across development partners and stakeholders to: encourage the use and application of the tools, lessons, knowledge and evidence generated through the ICF, support alignment of monitoring and evaluation activities and systems going forward, and help raise awareness and drive greater public and political support for assisting developing countries to manage the threats and opportunities from climate change.

Three of the four outputs (1, 2 and 4) for this programme will be delivered through a main contract that is in the final stages of being procured. Two sub-components of output 1 are delivered through separate arrangements set up by DFID:

- an Accountable Grant with the International Forestry Resources and Institutions (IFRI) to deliver a methodology for the forest dependent people Key Performance Indicator and associated data collection; and
- a Memorandum of Understanding with the World Health Organisation (WHO) / United Nations Development Programme (UNDP) to develop baseline data on the health benefits of clean energy (change in mortality / morbidity as a result of indoor air pollution from solid fuel use).

Output 3 is being delivered through a separate contract that has been procured through the Cabinet Office managed G-Cloud arrangement. DFID has led the programme management and procurement of all outputs, with DECC and DEFRA providing ongoing engagement through involvement in procurement processes, technical assurance of all processes and outputs and participation in a cross-Whitehall management team.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

The outcome defined in the log frame is an increase in evidence-based policy programming and delivery of climate change interventions. The Annual review has found that this outcome is on track to be achieved by the programme and there is a high level of positive feedback about need for the programme and quality of the outputs delivered to date from staff at DFID, DECC and Defra.

Over the past 12 months, DFID has procured the main monitoring, evaluation and learning contract that will create a comprehensive portfolio of evidence, demonstrate the results of the investments and understand how, when, why and in which circumstances different types of climate change programmes deliver results. A Cross-Government monitoring, evaluation and learning strategy has been developed that will further support the achievement of the four outputs. In addition, the Knowledge Platform an integrated web-based platform that is collecting and sharing ICF Results across all programmes, has been developed and is successfully capturing results.

Evidence collected and analysed for this review shows that the first year of the programme has developed valuable plans and outputs that are a strong foundation for the four year programme and have led to greater engagement in learning, collection of aggregate results and take up of evidence already. Positive feedback about the quality, timeliness, relevance of outputs and the value that is provided through the programme has been provided by staff at DFID, DECC and Defra.

The scores of the four outputs are as follows:

Output 1: Provision of robust and appropriate tools and data Score: A

Output 2: Generation of evidence and knowledge that address key strategic questions	Score: A
Output 3: Knowledge platform. Score: A
Output 4: Effective dissemination and promotion of learning. Score: A
Annual outcome assessment
The annual assessment of the programme is ‘A : Met expectations’. This assessment is based on a review of the four outputs scores and the logframe for the programme.

Key lessons learned

1. Continued harmonization and cross-government collaboration on all four outputs is crucial to ensuring that the programme develops to successfully meet the needs of HMG, external stakeholders and delivers the highest quality outputs. It is important to recognise that building successful relationships and collaborating across different organisations takes time and may impact on the speed at which a programme can deliver results.
2. There is high added value in engagement of external experts to ensuring that the strategy and activities are aligned with best international practice and deliver the highest quality outputs for HMG.
3. At the present time not all ICF programmes report their results through the KPIs and Knowledge Platform. It is important to understand why some programmes do not fully report and share their results and to subsequently develop an appropriate strategy to better incentivise reporting results.
4. It is important to have an integrated approach to monitoring, evaluation and learning to maximise the extent to which monitoring and evaluation are reflective learning tools that can be used to support programmes to adapt, maximise results and to inform decisions about future investments.
5. The importance of senior managers in all HMG Departments regularly reviewing the availability of internal expertise and staff resources and taking appropriate action to ensure delivery of a successful programme.

Key actions

1. HMG should work collaboratively across government to move forward with all monitoring, evaluation and learning programmes. Funding decisions and decisions about the future direction of the programme should be agreed by all Departments involved in the ICF.
2. Continued engagement with international agencies and advisers working in HMG about the MEL programme of work is essential to ensuring that results, evidence and lessons learned are shared, discussed and inform decision-making.
3. Research why not all programmes are reporting results and develop an appropriate strategy to incentivise more comprehensive reporting of results
4. Develop systems to collect regular feedback about the MEL programme from HMG stakeholders
5. Ensure a harmonized approach to monitoring, evaluation and learning that clearly identifies key audiences, ensures the needs and learning styles of key stakeholders are understood and prioritises effective and engaging ways of communicating evidence and learning.
6. Senior Managers at DFID, DECC and Defra will regularly review staff resources and skills in relation to those agreed by the ICF Sub-committee in 2014 and in relation to programme needs.
7. Based on findings from the inception report that will be delivered in February 2016, it may be necessary to extend the timeframe and cost of the main Monitoring, Evaluation and Learning programme contract (Output 2) to 2020. This would enable the programme of work to evaluate and analyse the lifetime of existing projects and enable synthesis to include ex-post evaluations of projects.

Has the logframe been updated since the last review? Yes.

The log frame has been updated to reflect the development of plans for each of the outputs.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Provision of robust and appropriate tools and data to track core results across all relevant programmes.
Output number per LF		1	Output Score	A
Risk:		Low	Impact weighting (%):	30%
Risk revised since last AR?		Y/N	Impact weighting % revised since last AR?	Y/N

Indicator(s)	Milestones	Progress
Updated baseline data on the Health benefits of clean energy	MoU signed with WHO/UNDP. Data collection to assess progress in period 2008-2013 undertaken.	Achieved

Supported methodologies developed and supporting KPI data collection	8 KPI methodologies developed	Achieved
Proportion of relevant ICF programmes reporting against at least 1 KPI	70%	Achieved
Number of useable KPIS developed and used by ICF programmes	12	Achieved

Key Points
The WHO project has taken slightly longer to start than planned, to ensure the right expertise and contacts are in place. The WHO is now undertaking the first phase of the project which involves completing a scoping and gap analysis of existing data collection efforts at the national and international levels including by governments, civil society and international agencies.

To date good progress has been made on some indicators (e.g. on heating and lighting fuels and technologies, disaggregated by sex), but further work is needed on both health and livelihoods indicators that take full account of gender relations and norms.

A review of the UK ICF forest related interventions across the 5 priority countries selected has been carried out detailing for each project all relevant and available documentation summarizing: project timeline; goals and activities (commenced and planned); spatial extent and configuration; participation selection processes; stated outcomes, outputs, expected results, and indicators; available datasets; and key contacts.

This preliminary analysis has revealed the significant delays in implementation for some ICF programmes which will have an impact on the delivery of some milestones under this project. IFRI has therefore formally requested a no-cost extension of one year taking project end to July 2019. Even with the extension, it will not be possible to provide actual impact data for some of the projects that have started late, but all projects will have a baseline and a process in place to continue tracking and assessing results.

Livelihood Impact data collection across 5,760 households (using tablets) for Nepal is completed. Over 30 enumerators, male and female, have been trained in social survey methods with local implementing partner organisations and MSFP staff. The final stages of work were cut short by the Nepal earthquake. The IFRI comprehensive data set gathered immediately before the earthquake could potentially be of wider significance longer term to track how households have coped in the face of exogenous shocks.

A draft paper has been produced and is currently undergoing review, on defining forest dependence and attempting to quantify it. Given the centrality of “forest dependent people” to the ICF KPI3, this comprehensive review has revealed the diversity of understanding and interpretation around the use of this term further complicating estimations of the effects of forest sector investments on people’s livelihoods. The paper will be published by November 2015. It will be important for DFID, DECC and DEFRA to come to an agreed working definition for future use based on the findings of this paper.

Recommendations:

1. Approve a request for a no-cost extension for the IFRI grant (although this will take the project beyond the lifetime of the overarching MEL programme) and adjust the logframe targets accordingly.
2. Ensure appropriate arrangements are in place to enable IFRI to coordinate with the MEL contract and ensure synergies with other forest KPI development work.
3. Agree across ICF a working definition/common understanding for ‘forest dependent people’
4. CED will work with relevant DFID country offices to support  IFRI’s work in locations where there are country offices with forest programmes that are managed centrally, such as Ghana and Ethiopia.

Output Title 2	Generation of evidence and knowledge that address key strategic questions
Output number per LF		2	Output Score	A
Risk:		Medium	Impact weighting (%):	40%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Perceived usefulness of ICF funded evaluations and evidence strategy	Positive qualitative feedback from international partners and HMG Departments	Achieved

Key Points
Terms of Reference (ToRs) for the Monitoring, Evaluation and Learning contract have been finalised. This will enable HMG to understand impacts and lessons learned from different climate change investments. Capturing and sharing this evidence is critical to demonstrating the feasibility and desirability of low carbon, climate resilient development. The ToRs were approved by two independent peer reviewers and by senior analysts at DFID, DECC and Defra. They have been approved by senior managers that represent DFID, DECC, Defra, the FCO and HMT through the ICF sub-committee.

Procuring the Monitoring, Evaluation and Learning contract started in December 2014 and concluded in June 2014. The procurement process used a two stage process and OJEU to identify a suitable supplier. Representatives from DFID, DECC and Defra were involved in procuring the contract. We have identified a preferred supplier and work will begin in August 2015. The inception phase of the contract will take place between August 2015 and February 2016.

Stakeholders interviewed from all three government Departments involved in the ICF reported that there have been very good cross-government working relationships and co-ordination throughout the procurement process.

An independent advisory group has been established that includes five international experts in monitoring, evaluation and learning. The group will provide strategic advice about the programme of work and support HMG to quality assure outputs.

A high level monitoring, evaluation and learning strategy has been developed and approved by all five departments that are involved in the ICF. The strategy and high level principles are ensuring that there are synergies between monitoring, evaluation and learning activities, co-ordination and harmonisation across all government departments and that plans reflect international best practice.

Monitoring and Evaluation Advisers at DFID and DECC have engaged Evaluation Advisers at the CIFs, GCF, GEF EuropeAid, and European Member States in discussions about the MEL programme of work. The Terms of Reference reflect the wider need for evidence by the international community. There is a high level of interest and engagement in the MEL programme by international stakeholders. This is supporting alignment of monitoring, evaluation strategies to deliver robust, appropriate and internationally agreed monitoring and evaluation frameworks for climate investments to support the most effective use of funds and value for money.

Recommendations

1. HMG needs to continue liaising with key stakeholders including the GCF, GEF and CIFs to ensure that i) The MEL contract reflects international best practice and ii) the need for evidence by the international community, as well as HMG.
2. HMG should work closely with the expert advisory group to ensure international expertise informs all stages of the programme of work and to ensure the highest possible quality and relevance of outputs.
3. The contract manager needs to engage and work closely with policy advisers with responsibility for designing future HMG climate investments to ensure that learning and evidence from contract informs funding decisions and strategic plans.
4. Sufficient technical adviser time and programme management support, as approved by the ICF sub-committee, should be allocated to this programme to ensure it is able to successfully deliver this output. Senior Managers at DFID, DECC and Defra should regularly review the availability of staff resources and take appropriate action as and when required.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Development of Knowledge Management and Results Platform
Output number per LF		3	Output Score	A
Risk:		Low	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Delivery of shared web portfolio for climate results between ICF partners	Knowledgebase scoping completed, with advice and buy-in from DECC and at least three DFID country offices.	Achieved
ICF generated evidenced is used by stakeholders with HMG and the International Community	Knowledgebase is accessed by all ICF country offices	Achieved

Key Points

Development of the ICF Knowledge Platform was procured through the G-Cloud in January 2015 and ICF results were collected for the first time through the online platform in March 2015.

Country Offices and ICF programmes have reported that the system is more user friendly than the previous system of collecting results. In addition, it was perceived to support efforts to report results, understand achievements and share learning with other country programmes

The results that have been recorded through the Knowledge Platform have been presented to the ICF sub-committee and have informed decision making.

The Knowledge Platform was piloted and tested with the DFID Kenya Country Office and other ICF programmes prior to the March 2015 round of results data collection. Lessons learned and feedback during this piloting phase has informed development of the platform. McAlpine and Gaiasoft continue to refine and amend the platform based on feedback from users about accessibility and added value of the platform.

A cross-government advisory group has been established to provide strategic oversight to the project and quality assure the outputs. Representatives from DECC, Defra, the Government Digital Service and DFID are engaged in the advisory group.

DECC and Defra have reported that the Knowledge Platform is a professional system that is accessible, user friendly and has improved the presentation and ability of HMG to report ICF results. There is some scope for improvement in the search function within the platform.

Recommendations

1. HMG needs to work with the contractor to ensure greater integration and use of the Knowledge Platform by ICF programmes. To be successful, the Platform needs to be a useful day-to-day tool and be able to provide detailed and tailored analysis on demand.
2. Further work needs to be completed by HMG and the MEL programme contractors to understand how to incentivise programmes to report results and how to quality assure results that are reported through the online platform
3. When the first two recommendations have been achieved, the contractor should review how evaluative evidence from programme level evaluations and key lessons learned by programmes can be captured by the Platform.
4. HMG needs to work closely with the Knowledge Platform contractors to ensure that the main MEL contract and the Knowledge Platform are aligned and harmonized.
5. The contractors should work with HMG to explore options for improving systems to quality assure data that is submitted by programmes. This should include referring to and learning from existing software such as Excel.

DETAILED OUTPUT SCORING (1 page per output)

Output Title	Sharing and communicating knowledge and learning
Output number per LF		4	Output Score	A
Risk:		Low	Impact weighting (%):	20%
Risk revised since last AR?		Y/N	Impact weighting % revised since last AR?	Y/N

Indicator(s)	Milestones	Progress
Number of international partners and Governments informed by ICF Knowledge and Plans	25	Achieved : A
Number of Governments and IFIs co-operating and sharing lessons from climate change programmes and aligning M&E approaches	5	Achieved: A

Key Points

Over the past 12 months a participatory Learning Dialogue with key internal and external partners has been completed to understand, engage and increase the skills and capacity of stakeholders managing and delivering ICF investments. This included southern partners, consultants and HMG programme managers. The Learning Dialogue focused on understanding how high quality learning for change actions can impact on results.

DFID has proactively engaged and shared monitoring, evaluation and learning plans and learning with the CIFs, the GCF, the GEF and EuropeAid. As a result of these meetings, monitoring, evaluation and learning strategies are becoming increasingly aligned and based on shared best practice. There is also a high level of interest and engagement in the MEL programme as it moves forward.

We have conducted a series of interviews and ran a workshop to gather feedback from the FCO, Defra, DECC and DFID. The Feedback was analysed and synthesised into a set of insights and actions that HMG is being applied to improve communications across the ICF, to foster improved learning from ICF programmes and the integration of climate considerations across programmes. Through this programme of work with ICF stakeholders across HMG, we have developed 10 high level Learning Principles that will inform all our integrated evidence and learning activities. These are already informing and will continue to maximise the impact of our evidence and results initiatives.

The work has successfully informed the Terms of Reference , selection of consultants for the main MEL contract (output 2). It has also strengthened DFID, DECC and Defra’s understanding learning for impact , and has resulted in a stronger learning strategy for the ICF.

Interviewees from DECC, Defra and DFID reported greater awareness of learning and communication of evidence within the ICF and within the wider Departments’ activities as a result of this work.

The Learning Dialogue is an exemplar for engaging stakeholders in learning about climate change across the ICF. It has successfully provided a basis and foundation for the ICF learning strategy ( currently in progress). It has also had significant influence across DFID, specifically with the Task and Response Group to ICAI and has informed the wider DFID Learning Strategy .

Feedback from DECC and Defra shows that using practical examples of how learning can inform and improve decisions is an effective way of engaging internal stakeholders in learning activities.

Recommendations

1. It is important to ensure that DECC and Defra are fully engaged in the Learning programme of work and that activities are relevant to the learning styles and needs of DECC’s programme managers. Future activities should engage and work closely with DECC and Defra from an early stage of development.
2. Complete the ICF Learning Strategy, based on the ICF Learning Dialogue and the 10 high level principles of Learning, in the next six months.
3. Continue to effectively engage external partners including the CIFs, the GCF and NGOs to ensure learning plans are shared, engage and enthuse key stakeholder groups

Summary of responses to issues raised in previous annual reviews (where relevant) N/A

D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
The key costs drivers for the programme are the cost of external expertise and resources through four contracts that will support the collection, analysis and communication of results, evidence and lessons learned from the ICF. This programme of work is necessary to understand and demonstrate results and lessons learned that will provide an evidence base for future climate investments by HMG and our international partners. It is also crucial to demonstrating accountability to the public in relation to a significant investment of public funds.

There are no changes to cost drivers that were identified in the Business Case.

VfM performance compared to the original VfM proposition in the business case
Economy: The suppliers for the Knowledge Platform and the main Monitoring, Evaluation and Learning contract were procured through an open competitive process to ensure international competition and value for money from a wide variety of suppliers. In addition, procuring the majority of services through one main contract is judged to provide good value for money because it will avoid significant staff resource spent managing a variety of smaller contracts, thus reducing staff time and administration costs.

Efficiency: The Evaluation Advisers and Economists interviewed at DECC and Defra were satisfied with the time frame for the various contractors delivering services in relation to the quality and relevance of services expected. DFID Advisers have proactively managed the number of people and days involved in delivering each output.

Effectiveness: Advisers interviewed for the Annual Review confirmed that the IFRI, WHO and Knowledge Platform contracts are highly relevant to ICF programmes and the capacity of HMG to report results and demonstrate the impacts of the ICF. The services provided by the suppliers have been thorough, useful and completed to a high standard.

Assessment of whether the programme continues to represent value for money

The programme is assessed to continue to represent value for money. This assessment is based on discussions with key stakeholders at DFID, DECC and Defra and an assessment of economy, efficiency and effectiveness of the four outputs

Quality of financial management

Date of last narrative financial report	N/A
Date of last audited annual statement	N/A

E: RISK (½ page)

Overall risk rating: Medium

Overview of programme risk

The key risks that are related to the programme include:

- Limited capacity of HMG staff with relevant skills and time to engage in this programme of work
- Low take up of ICF KPIs due to the perceived complexity and time involved in reporting
- Low engagement and interest from internal and external partners to take up knowledge and evidence,
- Challenge of gathering robust evidence from a highly complex and diverse portfolio of programmes that have high levels of autonomy and partnerships
- A limited pool of consultants with skills to deliver a successful programme of work.

Key actions undertaken in the past 12 month to mitigate risks include:

- The Change Team Leader has adopted a proactive approach to monitoring staff capacity and skills within the team to deliver the contract against staffing levels agreed with the ICF Sub-committee in May 2013
- The HMG team has worked closely with programme managers to support country programmes to report results, and to communicate the value and benefit of the KPIs and wider evidence and knowledge programme of work.
- A proactive approach to communicating and consulting with key internal and external stakeholders including the GCF, CIFs, GEF, the European Union and ICF programme managers.
- Recruitment of a CED Statistics Adviser in January 2015

Outstanding actions from risk assessment

HMG will need to continue to monitor and undertake actions to mitigate these risks.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
Outputs 1, 3 and 4 are on track to deliver against the planned timeline. Delays caused by finalisation and approval of the Terms of Reference for the MEL programme of work by the five Government Departments involved in the ICF, will mean that all of the Output 2 activities will now complete in March 2019, rather than March 2018. However, we expect significant progress and delivery of major outputs in relation to Output 2 to be achieved by March 2018.

Performance of partnership (s)
DFID has developed good professional working relationships with the WHO, IFRI, Alpine and LEAD during the past year. Advisers at DFID, DECC and Defra are satisfied with the quality, relevance and timeliness of outputs delivered by these organisations to date.

A key challenge in the next 12 months will be to ensure complementarity and shared learning between the partners and HMG.

Asset monitoring and control
NOT APPLICABLE

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

Not applicable

H: MONITORING & EVALUATION (½ page)

Monitoring and evaluation arrangements are considered sufficient for this programme.

Alpine/GaiaSoft, IFRI and the WHO produce regular quarterly reports with performance and financial updates that are reviewed by the Programme Managers and relevant policy advisers at DFID. In addition, the contract manager of the Knowledge Platform is seeking regular feedback from ICF programme managers about the use and accessibility of the Knowledge Platform. This feedback is informing the development of the Knowledge Platform.

There are biweekly meetings with Evaluation Advisers at DFID, DECC and Defra to monitor and assess progress towards Output 2 and harmonization between all outputs and streams of work. This has ensured a co-ordinated cross departmental approach to managing progress and performance toward to procuring the main Monitoring, Evaluation and Learning contract. This approach to monitoring will continue as we move to award the contract. Monthly meetings and quality assurance reviews of all outputs by analysts at DFID, DECC and Defra will play a key role in monitoring and evaluating the main Monitoring, Evaluation and Learning contract. When the main Monitoring, Evaluation and Learning contract has been awarded, there will be periodic site visits and consultation with country offices to evaluate progress and a timetable for collecting feedback from ICF programme managers will be developed. In addition, an independent expert advisory group has been established to support HMG’s capacity to evaluate the quality of the deliverables of the programme and ensure that they are aligned with international best practice.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessment
Key points
Summary of response to iprogrammessues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process