Programme Completion Report - Top Sheet

This Top Sheet captures the headlines on the programme performances performance over the course of its lifetime. Teams should attach summary sheets from each annual review over the life of the programme.

Review Date:	March 2015

Title: / African Risk Capacity (ARC) – Establishing a Pan-African Disaster Risk Pool for Food Security
Programme Code: 201578	Start Date: 8 December 2010	End Date: 31 December 2014

Summary of Programme Performance

Year	Dec 2011	Dec 2012	Jan 2014	March 2015
Programme Score	2	A	A+	A
Risk Rating	High	Medium	Medium	High

Financial Position

	Value in GBP
Original Programme Value	£2.5 million
No-cost extension to 31 December 2013	£0
Costed-extension in August 2013 to 31 December 2014	£1.3 million
Log-frame revisions (with dates) / April 2012 (move to new DFID Logframe format) / May 2013 adding output 3.4 and targets for December 2014 as agreed in costed extension
Total programme spend	£3.8 million

Follow up actions required following closure
None.

A. Introduction and Context

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-201578/documents/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-201578/documents/

Outline of programme and what it has achieved

DFID provided a grant of £3.8 million, as well as technical assistance, over four years to support the the African Risk Capacity Specialised Agency of the African Union (ARC Agency) to design and establish a pan-African mechanism for pooling risk and providing insurance for member countries against extreme climate events. ARC Agency also received support from the Swedish International Development Cooperation Agency (SIDA), Swiss Agency for Development and Cooperation (SDC), the Rockefeller Foundation, WFP's Saudi Innovation Fund, the International Fund for Agricultural Development (IFAD) and World Bank’s Global Facility for Disaster Reduction and Recovery (GFDRR).

The Programme has achieved its intended outcomes - a fully regulated mutual Insurance Company was established in early 2014 (ARC Insurance Company Ltd.), which offers affordable insurance to African countries that have approved contingency plans to use ARC finance for early responses to insured disasters. Four African countries (Mauritania, Senegal, Niger and Kenya) purchased insurance from ARC Ltd in 2014 for five growing seasons, and three of these countries (Mauritania, Senegal and Niger) received payouts totalling $26.5m after droughts. In future years, insurance cover is expected to be extended to more countries and other hazards, such as tropical cyclones and floods.

ARC was a very ambitious concept and an innovative initiative. Meeting the project’s intended outcomes is an impressive achievement, reflecting the significant efforts of the ARC team and member countries.

## B: PERFORMANCE AND CONCLUSIONS

Overall Outcome Assessment: A – Met Expectations

The project met its intended outcome: the establishment and operation of an African-owned insurance mechanism and disaster risk pool for sub-Saharan Africa. Key Achievements as of 31 December 2014 included:
- The African Union Treaty establishing ARC signed by 25 African Countries, and ratified by one country (Mauritania).
- 10 African countries developing or have finalised contingency plans, five of which were approved in March 2014, with a further five under consideration for Pool 2 in 2015.
- The ARC Insurance Company (ARC Ltd) established in November 2013, and capitalised in March 2014 by DFID and Germany’s KfW, with a strong control framework and sustainable financing structure.
- 4 African countries (Mauritania, Senegal, Niger and Kenya) purchased insurance from ARC Ltd in 2014 for five growing seasons
- AfricaRiskView (ARV) performed well, accurately assessing drought and harvest failure in three countries (Mauritania, Senegal and Niger) in 2014.
- ARC Agency supported three countries to produce Final Implementation Plans, which were supported by payouts of $26.5m from ARC Ltd.
- Demonstrated commitment to transparency and increasing public awareness of ARC.
- Generally positive feedback from stakeholders, with appetite for additional insurance coverage

There have also been some challenges, with the following recommendations for ARC:
More intensive support for members to produce stronger Contingency Plans (CPs) and Final Implementation Plans (FIPs) for drought responses with a strong development impact.
- Review the skills, grading and composition of the ARC Agency team in light of the operational objectives and priorities now that ARC is up and running. In particular, consider strengthening broad delivery mechanism expertise including social protection, humanitarian assistance, resilience, gender, socially inclusive beneficiary targeting, monitoring and evaluation.
- Examine how donor finance is flowing to member and prospective member countries and proactively discuss appropriate aid delivery mechanisms with a broad range of in-country stakeholders (including Governments, NGOs and donors). ARC should use this knowledge to strengthen its upstream guidance on the contingency and final implementation plans, including fiduciary and other risk assessments to ensure responses will have the best chance of achieving development impact.
- Continue to strengthen support given to the ARV country customisation process and planning, including by including additional sources of information and a broader range of stakeholders.
- Concentrate on encouraging Conference of Plenipotentiaries (COP) members to purchase insurance and become ARC Ltd. members, and contribute to the sustainable management of ARC by ratifying its Treaty and contributing towards the costs of its services.
- Consider de-linking membership fees from ratification in order to remove a potential disincentive to ratification
- Seek indicative approval of ARC Agency budget, including multi-year pledges of support, from donors, in advance of the COP’s approval of the work programme and budget.
- Consider ways to improve communication with donors on its delivery of services to countries.
- Document and share the best practice that has been enshrined within ARC’s management, governance and operational frameworks.
- Remain open to lessons that could strengthen ARC and its development impact.
- Work with ARC Ltd members, ARC Agency COP and donors to develop a long term vision for the two institutions that will clarify the roles and responsibilities as well as the decision making structures and lines of accountability. This should look at long term sustainability and affordability of the Agency work as much as at ARC Ltd’s work.
At the time of this review, ARC Ltd and ARC Agency have already started to respond to some of these recommendations, which is to be applauded.

Outcome Indicator	Target for December 2014	Progress
No. of risk pool participation requests received by project from national governments	10 countries have signed pre-participation agreements with ARC Agency, and at least 4 more are requesting PPAs in 2015.	Exceeded expectations: As at December 2014, ARC had signed pre-participation agreements with 13 countries. Four countries (Senegal, Mauritania, Kenya and Niger) purchased insurance with ARC Ltd. in Pool 1, with another five countries interested in joining Pool 2.
No. of countries with developed drought response contingency plans linked to regional contingent funds	6 country response contingency plans approved by the ARC Agency Board Peer Review Mechanism	Moderately did not meet expectations: Five countries were awarded Certificates of Good Standing (CGS) by the ARC Agency Governing Board in 2014. Four of these countries (Senegal, Mauritania, Kenya and Niger) went on to purchase insurance in 2014.
Percentage of funds pledged against ARC donor appeal	100% of required funding envelope to establish ARC is obtained. / USD 250 million was targeted to be achieved by November 2014 to support regional contingency funds to make ARC sustainable.	Met expectations: 100% of the funding required to establish ARC was achieved (although this was less than $250m as the size of the capital base required depends on the number of countries and amount of risk covered and ARC started with small pool). DFID and KfW paid in just under $100m, with further tranches available based on performance and need.

Overall Impact Assessment
The establishment of ARC Agency and ARC Ltd - only the second such mechanism in the world to pool sovereign weather risk – is a notable achievement. The institutions set up by this project enabled the capital investment by DFID and KfW and the first drought insurance purchases and payouts in 2014. The ARC team remain keen to strengthen ARC as it moves forward, and DFID will support them in this.

The project’s expected impact was that Sub-Saharan countries would be better able to manage extreme climate risk and improve timeliness of response through insurance payouts to affected countries. Four countries purchased insurance in the first year, more are interested to join in 2015, and there has been good progress in building capacity to understand climate risk financing and management. In late 2014, the first ARC payouts were triggered after poor rains in the Sahel ($16.5m to Senegal, $6.5m to Mauritania $6.5m and $3.5m to Niger). This is a good first test of ARC and its impact. The FIPs were of mixed quality, with all having to be strengthened before they could be approved. The quality of the responses in-country will now be monitored closely through an independent procedural audit and beneficiary spot checks. The anticipated value of ARC has been highlighted by the speed of the payouts which, despite delays, all arrived well before any other donor support for drought response.

## C: DETAILED OUTPUT SCORING

Output Title	Capacity and understanding built for African governments to take a fully informed decision on participating in the ARC pool
Output number per LF		1	Output Score	A+ / Outputs moderately exceeded expectations
Risk:		Medium	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Target / December 2014	Progress
No. of countries that are or have been in dialogue with ARC and actively considering ARC participation	18 countries	Exceeded: 41 AU member countries attended the CoP in 2012 to consider participating in ARC. By December 2014, 25 African Governments had signed the ARC Agency Establishment Treaty, 13 countries had signed pre-participation agreements and 4 countries had joined Pool 1. / While this demonstrates a strong willingness to participate, only one country (Mauritania) has also ratified the ARC establishment treaty. Until 10 ratifications are complete, ARC Agency’s operations will be reliant on donor finance and it will be unable to establish its own organisational structures.
No. of Africa RiskView and ARC training workshops held for stakeholders, including government and their partners, and regional body representatives	20 workshops and 400 people	Exceeded: 24 workshops have been held, reaching approximately 700 people. / Frequent country level multi-stakeholder meetings – combined with regional events for cross learning – continue to be required, as the quality of CP and FIPs is still not strong enough.
Economic rationale for ARC participation established and plan for monitoring benefits of participation developed	M&E frameworks developed to monitor the impact and benefits of contingency funding provided by ARC	Partially met: ARC Agency commissioned a cost benefit analysis of potential ARC benefits that was used to generate interest in countries to participate. This will be updated in 2015 using actual figures from the first year’s plans. / In establishing its systems, after an independent review of the CP process, ARC has committed to boost its internal capacity on M&E, and develop a mechanism for independent monitoring of countries’ delivery of response plans and the development impacts – including process audits and beneficiary spot checks. Work is underway on these as urgent priorities in 2015. / DFID has also encouraged ARC to establish feedback mechanisms that will help it to improve the responsiveness of the technical assistance service it provides to participating countries.

Summary of responses to issues raised in previous annual reviews (where relevant)
Relevant recommendations on this Output from previous annual reviews include:
1. ARC should put in place and independently review a monitoring system – tracking disbursement and effectiveness of targeting approaches and the contingency plans at country level.
2. ARC should ensure evaluation is built into ARC processes, in terms of the operation of ARC Agency and ARC financial affiliate and also disbursement at the country level. Robust evaluation of the Governance for ARC Agency will be required, including an independent Fiduciary Risk Assessment to ensure appropriate standards of due diligence.
3. ARC should evaluate national-level customization of AfricaRiskView and should consider developing a plan for technical development of AfricaRiskView (ARV) to potentially include additional sources of information.
ARC provided a full response on these issues in December 2012 and has made some progress in all areas. However, several of the recommendations still remain relevant today, in particular the need to strengthen monitoring and evaluation systems and staff capacity in these areas, due diligence by ARC on fiduciary and other risk assessments to ensure operations plans are best practice and deliver the expected results and the use of multi-stakeholder approaches and evidence for ARV customisation and planning in-country.

Lessons learnt and Recommendations for future programmes

The development impact of ARC is where its value lies. Strong targeting, evidence, monitoring and evaluation, with a multi-stakeholder approach to ARV customisation and contingency and response planning, is crucial to consolidating its effectiveness.

Slow ratification of the ARC Treaty Agreement limits the sustainability of the ARC mechanism. Without ratification, the Agency is unable to raise finance from membership fees to fund its work programme and country services and will require continued (ad hoc) donor finance. While donor finance is required, ARC Agency should ensure that donors are comfortable with the Agency’s programme of work and budget before it is approved by the Conference of Parties. It should also ensure it communicates with donors effectively on the capacity-building support it is providing to countries.

It is recommended that ARC:
Strengthens in-house capacity and advice to members on M&E.

1. Examines how donor finance is flowing to member and prospective member countries and proactively discuss appropriate delivery mechanisms with a broad range of in-country stakeholders (including Governments, NGOs and donors). ARC should use this knowledge to strengthen its upstream guidance on the CPs and FIPs while they are being developed, including fiduciary and other risk assessments to ensure responses have the best chance of achieving development impact.
2. Strengthens its support for customisation of AfricaRiskView and planning by including additional sources of information and a broader range of stakeholders.
3. Considers de-linking membership fees from ratification in order to remove a potential disincentive to ratification

Seeks indicative approval of its budget, including multi-year pledges of support if possible from donors, in advance of COP’s approval of the work programme and budget.

Output Title	Detailed design study for a feasible ARC risk pool architecture approved and agreed on by key stakeholders
Output number per LF		2	Output Score	A: / Met Expectations
Risk:		Low	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Target / December 2014	Progress
ARC financing strategy and institutional structure defined	Governance structure in place and operating for ARC Ltd	Met: ARC Agency assessed possible financial and institutional structures for operationalising the Insurance Risk Pool. These were presented to donors and the final structure for ARC Ltd and its financing and management structure agreed, including ARC Ltd.’s bye-laws and founding policies. An independent Board of Directors is in place, providing strong oversight. / The institutional relationships between ARC Agency and ARC Ltd rely on good personal relationships rather than a clear oversight structure, This could be a weak area in the future if staff change.
ARC participation, operation and M&E guidelines developed	Review conducted of contingency planning guidelines	Met: The Conference of the Parties (COP) took several decisions to guide the operationalization of the new Agency including on the structure of ARC country contingency planning standards and the sanctions policy. In March 2014, ARC commissioned Kimetrica to carry out an independent review of its contingency planning. The ARC Agency Governing Board has adopted all of the review’s findings, including: / new CP and FIP templates that clearly set out the operating procedures that each country will implement during a response / use of process audits and beneficiary spot checks to monitor adherence to approved operating procedures. / ARC Agency has incorporated a budget for process audits in 2015 to ensure that delivery of the first pay-outs is monitored effectively. However, more work is needed to provide clear guidelines that outline good practice, entrench improved country level monitoring into contingency plans and to develop a feedback system to ensure lessons are learnt and guidelines and templates updated appropriately.
No. of independent reviews of discrete technical portions of the ARC Project e.g. Africa RiskView, dynamic finance analysis, institutional structure, M&E, climate change stress tests	14	Partially met: 13 technical reviews have been conducted, mainly by countries as part of ARV customisation. / Dynamic financial analysis completed and positive review by GAD. Independent review of CP procedures completed in late 2014 – all recommendations agreed but not yet complete.
Development of products for risks other than drought	Flood modelling under development	Met: ARC Secretariat secured funding from Switzerland for development of the flood cover, and is on track to offer flood insurance in May 2016. A contract for tropical cyclone product development will be signed soon (probably funded by Germany), with insurance cover planned to be available in May 2016.

Summary of responses to issues raised in previous annual reviews
Relevant recommendations on this Output from previous annual reviews include:
1. ARC should put in place and independently review a monitoring system – tracking disbursement and effectiveness of targeting approaches and the contingency plans at country level.
2. ARC should ensure evaluation is built into ARC processes, in terms of the operation of ARC Agency and ARC Financial Affiliate and also disbursement at the country level. Robust evaluation of the Governance for ARC Agency will be required, including an independent fiduciary risk assessment to ensure appropriate standards of due diligence.
3. ARC needs to build on the economic case to make a robust case for capitalisation
4. Ensure that all remaining evidence required to make the case is in place, including the risk profile reports.
ARC provided a full response on these issues in December 2012 and has made some progress in all areas. However, as set out above, more work is needed on the monitoring and evaluation systems and staff capacity, ARC’s fiduciary and other risk assessments to ensure operations plans are best practice and deliver the expected results, and building the evidence base. ARC Agency should also ensure it communicates with donors effectively on the work it is doing to support countries on planning and M&E.

Lessons Learnt and Recommendations

Countries need more support to develop their contingency plans and final implementation plans. The Pool 1 contingency plans were initially weak, and a technical review process to strengthen them was introduced at donors’ request. In 2014, ARC Agency also undertook an independent review of its contingency planning process (see http:/www.africanriskcapacity.org/issues/contingency-planning), which will be updated annually. Following on from this, and the roll out of planning templates and Standard Operating Procedures (SOPs), Kimetrica is working in Senegal to pilot a process audit to monitor effectiveness of responses. Country level monitoring of contingency planning needs to be further strengthened, as does ARC Agency’s in-house capacity to support the development of effective plans and monitor their delivery. A monitoring framework, that uniformly captures programme delivery data – beyond the information obtained through spot checks and process audits is required, and needs entrenching in the ARC Agency mechanism.

Work is underway to expand the number of climate hazards insured by the ARC mechanism. This is rightly a long term vision for ARC and a diverse risk pool. However, the ARC mechanism is still in its infancy, and must also maintain sufficient focus on proving the concept of ARC, and strengthening country contingency and final implementation plans and monitoring to ensure that the ARC mechanism delivers the development impact intended.

It is recommended that ARC :
1. Increases the expertise and support it offers to countries in social protection, humanitarian assistance, resilience, gender, socially inclusive beneficiary targeting, monitoring and evaluation capability, in order to support countries to develop well targeted and responsive contingency plans.
2. Considers ways to improve communication to donors on its delivery of services to countries.
3. Focuses on proving the concept of ARC through excellent drought cover and responses before expanding to new risks.

Output Title	Consultation and political engagement carried out
Output number per LF		3	Output Score	A: / Met Expectations
Risk:		Low	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Target / December 2014	Progress
No. of consultations (bilateral meetings, presentations, seminars) held with representatives from countries, RECs, donors, NGOs, IOs, private sector and leading thinkers consulted on ARC concept	125	Substantially Exceeded: Over 200 consultations have been held.
No. of different actors financially supporting, or have pledged to support, the ARC initiative (donors, private sector, Member States etc.)	8	Met: 8 donors have supported ARC (DFID, KfW, the Rockefeller Foundation, SIDA, SDC, WFP's Saudi Innovation Fund, IFAD, World Bank GFDRR), in addition to 4 premium paying member countries.
Positive mention of ARC in national, regional, AU strategy papers, indicating its potential use as a risk management tool by governments	25	Exceeded: at least 33 positive mentions of ARC in peer–reviewed research, policy and dialogue papers, including: / 1. Post-2015 Hyogo Framework for Action, Africa Regional Strategy / 2. Africa Progress Panel 2015 APR / 3. Cabinet papers, budget and policy documents in Malawi, Kenya, Gambia and Mozambique.
Number of countries that have joined ARC CoP	30	Not Met: As of December 2014, 25 countries had signed the ARC Establishment Treaty. 1 country has ratified.

Summary of responses to issues raised in previous annual reviews:
Relevant recommendations on this Output from previous annual reviews include:
1. ARC should support the African Union to ensure that the ARC Specialised Agency meets the needs of participating countries and potential donors. These needs may be aligned, differ by degrees or in some cases be contradictory. This will include the need for appropriate and acceptable transparency, due diligence, reliability with a clear governance structure.
2. ARC needs to build on the economic case to make a robust case for capitalisation
3. Ensure that all remaining evidence required to make the case is in place, including the risk profile reports.
ARC provided a full response on these issues in December 2012 and has made good progress on outreach, but more support and evidence is needed to encourage in more donors to ARC Agency.

Lessons Learnt and Recommendations for future programmes:
ARC has done very well to raise its profile and build its membership base. It needs now to:
- Build the evidence base and encourage more donors to support ARC, and COP members to purchase insurance, with payments on time, and become ARC Ltd. members
- Move towards a more sustainable financial footing by the sustainable management of ARC by encouraging COP members to ratify the Treaty and contribute towards the costs of its services.

Output Title	Plan for the creation of the legal and organizational structure of ARC entity fully defined
Output number per LF		4	Output Score	A: / Met Expectations
Risk:		Medium	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Target December 2014	Progress
Legal structure of ARC defined, and vetted by the AU, donors, potential Member States, and legal experts	Legal structure established and in operation by Dec 2014	Met: The ARC Specialized Agency Establishment Treaty was adopted in November 2012, and has been signed by 25 countries. However, progress to ratify the Treaty has been slow (1 to date), which delays the Agency’s ability to establish its own structures and sustainable financing. / The legal structure for the Insurance Mechanism was agreed in November 2013. ARC Agency secured legal advice from Appleby LLP to manage the proper establishment of the ARC Mutual Insurance Company, and ensure the legal validity of the ARC’s bespoke company bye-laws. The legal framework and company bye-laws for the ARC Insurance Company were finalised in March 2014. / The lack of clear lines of accountability and control between ARC Agency and ARC Ltd are a weakness. A long term vision needs to be developed that is less reliant on the camaraderie and personal relationships between those working in both institutions.
Process for establishment of the ARC facility defined	ARC structures established and operational	Met: ARC Agency and ARC Ltd are both operational and offering insurance as anticipated. ARC Ltd was created in Bermuda in 2013 becoming operational March 2014. / As above, the governance mechanisms for ARC are complex and lines of accountability are unclear. A long term vision to align incentives and clarify roles is still needed.

Summary of responses to issues raised in previous annual reviews:
Relevant recommendations on this Output from previous annual reviews include:
1. ARC should support the African Union to ensure that the ARC Specialised Agency meet the needs of participating countries and potential donors. These needs may be aligned, differ by degrees or in some cases be contradictory. This will include the need for appropriate and acceptable transparency, due diligence, reliability with a clear governance structure.
2. ARC needs to ensure a clean transition between design and implementation. The ARC Project Team needs to start the process of ceding responsibility to the ARC Specialised Agency. Project Team staff have spent a lot of time in the last couple of years on ARC – however ownership now needs to broaden and this will require continued good management of the process.
3. ARC needs to ensure that all remaining evidence required to make the case is in place, including the risk profile reports.
ARC provided a full response on these issues in December 2012 and has made excellent progress with all the ARC structures up and running.

Lessons Learnt and Recommendations for future programmes:
The creation and operationalisation of ARC has been a major achievement – it is highly innovative and can offer many lessons to other public/private and development partnerships. ARC remains a young organisation, with room for improvement as it matures. Now that it is up and running, ARC Agency should consider a review of staffing (grades and skills) to ensure it has the right skills mix for this next phase of consolidation and expansion, and that there is a clear set of working protocols between ARC Agency and ARC Ltd.

It is recommended that ARC:
1. Documents and shares the best practice that has been enshrined within ARC’s management, governance and operational frameworks.
2. Remains open to lessons that could strengthen ARC and its development impact.
3. Works with ARC Ltd members, ARC Agency COP and donors to develop a long term vision for the two institutions that will clarify the roles and responsibilities as well as the decision making structures and lines of accountability. This should look at long term sustainability and affordability of the Agency work as much as at ARC Ltd’s work.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance
Key cost drivers for the project remain as anticipated - staff salaries and consultancy inputs and advice, as well as travel associated with supporting country participation in ARC, raising awareness, supporting the ARC Agency Governing Board and ARC Ltd Board of Directors. The consultants and staff are high calibre, extremely engaged and hard-working. However, the Standard Position Costs charged by WFP (coupled with an administrative overhead) are high. These costs are determined centrally by WFP who provide the Secretariat services under an Administrative Services Agreement (ASA) with ARC Agency. Such high costs may prove unsustainable for contributors to ARC Agency (both donors and Member States), and ARC Agency should assess (especially prior to renegotiations and renewals) the Administrative Services Arrangements to ensure that it provides the best value for money.

Pan-African working has allowed multi-country workshops (Francophone and Anglophone) for savings on training and customisation. Pooling risk from countries across Africa also decreases the cost of insurance by about 50%.

The design work supported in this project resulted in ARC Ltd being established in a way that offers good value for money to DFID, for example, the capital provided should be returned to the UK after 20 years and there was strong market interest in providing reinsurance for ARC Ltd.’s Pool 1, with very competitive pricing secured.

VfM performance compared to the original VfM proposition in the business case – did the Programme represent value for money?
There was no business case for this start-up support (agreed December 2010), and hence no formal VfM metrics agreed at the start. However, considering the project’s achievements - the establishment and operation of the first pan-African risk pool and insurance mechanism – our grant has been excellent value for money. Staff inputs have been excellent quality, procurement has been competitive, and costs shared with other donors and/or minimised through multi-country engagements where possible.

Quality of financial management during programme
ARC Agency uses the administrative and financial reporting systems of WFP, which are robust. Financial statements and narrative reports have been received regularly. We have received a final interim statement showing full utilisation of the DFID grant. The formal certified financial statement at project end is due in May 2015 in line with WFP procedures.

The financial management around the payouts to countries in support of their contingency plans are still untested – there will be independent audits as well as a whistleblower’s hotline, process audits and spot checks. Good control systems should identify any problems that occur, and feed these lessons into subsequent revisions of the plans in future years.

Date of last narrative financial report	November 2014
Date of last audited annual statement	31 May 2014 / Next due May 2015

E: RISK

Quality of risk management over the life of the programme
The delivery of this start-up support through ARC Agency was relatively low risk in itself as all procurement, financial and staff management was within the robust controls of WFP procedures. However, the eventual product – ARC Ltd established and offering insurance – was innovative and high risk. DFID therefore applied a robust risk management strategy - efforts were made to monitor risks on an ongoing basis and engage if needed to prevent or minimise the impact of them materialising. The negotiations to capitalise ARC Ltd involved close scrutiny of the controls and oversight (including the bye-laws, founding policies, accounting standards and reporting requirements) required for establishment and capitalisation of ARC Ltd., and DFID had a set of internal triggers and conditions precedent for our capitalisation payment that were based on sound governance foundations, solid management and financial plans being in place for ARC.

The design of ARC has incorporated checks and balances, and these have been strengthened on the basis of the recommendations of the Kimetrica review – for example, insurance contracts are explicit that payouts must be used for the delivery of approved plans, standard operating procedures have been agreed, independent experts now offer comments on the draft operations plans before approval, and the delivery of those plans will be monitored for compliance (with penalties for deviation) and results.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe:
This was a complex project to deliver, and took longer than originally planned - the original timeframe for this grant was extended twice, once with a no cost and also then a costed extension. It was worth a little extra time to get the structures and mechanism right.

Asset disposal and value obtained by DFID: N/A

Performance of partnership (s)
The partnership between DFID and ARC Agency has generally been good, with open and frank discussions that have contributed to the successful establishment of ARC Ltd.

G: MONITORING & EVALUATION

Programme monitoring, evidence and evaluation:
- ARC and ARV were reviewed by the African member countries as part of customisation, as well as by expert institutions including Swiss Re, the EU’s Joint Research Centre and Boston Consulting. The latter rated it 77-79% accurate for the six then-potential Pool 1 countries over the past decade. ARV is also monitored by ARC on an ongoing basis, and as part of the verification. ARV is also being used to inform analysis in the World Bank’s Drylands Report 2015.
- ARC commissioned two cost-benefit analyses of the ARC model (Boston Consulting Group and Clarke & Hill). These will be revisited in 2015 on the basis of actual numbers from the first year of implementation, as well as cross-check during the independent evaluation of ARC.
- ARC produced an evidence-based report assessing the appropriate legal/regulatory jurisdictions for the ARC insurance facility, which was also reviewed by DFID.
- In 2014, ARC commissioned an independent review of the ARC Contingency Planning Standards. The review showed that the initial ARC standards were aligned with the direction that disaster response and early intervention is moving. The review also made recommendations for practical improvements to the plans including new plan templates that enable planned activities to be better defined at the operational plan stage, and more quickly converted into detailed Final Implementation Plans in the event of a drought.

DFID monitoring: Quarterly reports and annual expenditure statements were scrutinised during the programme, with annual reviews assessing and reporting on progresses against outcomes and outputs.