Annual Review

Title: Strategic Partnership with UK Office for National Statistics
Programme Value £ (full life): £4,500,000		Review Date: July 2018 to June 2019
Programme Code: 300443	Start Date: Sept 2017	End Date: March 2020

Summary of Programme Performance
Year	2018	2019	2020
Programme Score	A	A
Risk Rating	Minor	Minor

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/15270940.odt
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/48156789.xlsx

A. Summary and Overview
This programme is building a strategic partnership between DFID and the UK Office for National Statistics (ONS). The programme builds on ONS’ current small scale international development work and is helping them to build their own capacity so they can scale up the technical assistance they provide to developing countries.
ONS have begun establishing new medium to long term partnerships with three African countries (Ghana, Kenya and Rwanda) and with the UN Economic Commission for Africa (UNECA) through their Africa Centre for Statistics (ACS). There has been good progress made so far on these partnerships, with advisers now in place in all four locations.
Alongside the four partnerships, ONS have also developed a flexible support component which has provided support to DFID and wider statistical capacity building initiatives. Over the last year there have been ten projects funded under the flexible facility, each varying in scope, scale and financial contribution. Over the last year there were four new projects:
FF10 - Commonwealth Head of Statistics conference 2018
FF11 - Scoping of new ONS partnerships
FF12 - Integrating non-traditional data sources in the production of official statistics
FF13 - Establishment of a Data Science Hub

This is the second Annual Review (AR) for the programme and focuses on activities from July 2018 to June 2019. Further detail on the scoring methodology is in Annex 1.
Summary supporting narrative for the overall score in this review
This programme continues to perform well scoring an ‘A’ for its second annual review. This indicates that the programme outputs ‘met expectations’. Progress in Ghana has exceeded expectations and in the other countries it has met expectations. Support to UNECA has been a little slower than expected, although the expectations were ambitious. The flexible facility has met expectations although some areas have been slower such as the project on improving labour market data. In contrast the new project to set up a data science hub has proceeded quickly and the hub is now operational.
Outputs			Weighting	Score
1	Kenya National Bureau of Statistics increases the availability and quality of SDG data, with ONS support		15%	A
2	Ghana Statistical Service increases the availability and quality of SDG data, with ONS support		15%	A+
3	Rwanda Statistics Office increases the availability and quality of SDG data, with ONS support		15%	A
4	UNECA provide an enabling environment for African National Statistics Offices, with ONS support		15%	B
5	Flexible short term technical assistance delivers effective results		40%	A
	Overall Output Score		100%	A
Recommendations for the year ahead
Outputs 1-4		Refine scoring for indicator 1.1 level 4 to reflect actual percentage of progress against workplan.
		ONS and DFID to refine the methodology for scoring “stories of change” to reflect the different impact of the various interventions.
Output 3		ONS to consider how the logframe can be flexible to include new areas of support.
Output 4		ONS to consider writing a case study on the Expert Group Meeting on censuses.
		ONS and UNECA to explore ways to gather feedback on the Expert Group Meetings to assess how well they are meeting countries’ needs.
Output 5		ONS should conduct further work to define clear milestones and targets for the flexible facility projects which do not currently have them.
Theory of Change		ONS and DFID to refine the case study methodology to reflect current and future impact in the scoring.

## B: DETAILED OUTPUT SCORING

Output Title	Kenya National Bureau of Statistics increases the availability and quality of SDG data, with ONS support
Output number per LF		1	Output Score	A
Impact weighting (%):		15	Impact weighting % revised since last AR?	Y was 20%

Indicator(s)	Milestone(s)	Progress
1.1 Progress towards establishing an effective project workplan (Annex 1)	4	4
1.2 Measure of partner commitment towards establishing effective partnership with ONS (Annex 1)	3	3
1.3 Number of national statistical strategies / sectoral modernisation plans or equivalent developed informed by ONS support and advice	2 (Strategic Plan & Comms Strategy)	2 (Strategic Plan & Comms Strategy)
1.4 Number of stories of change of where ONS support and delivery of the workplan has helped deliver changes to how KNBS operates	3	3
1.5 Number of people trained with ONS support and rating training as effective	5	4

Overall output 1 is meeting expectations.
Indicator 1.1 Milestone met. Although the ONS adviser has only been in post for eight months there has been good progress on the workplan with the Kenyan National Bureau of Statistics (KNBS), which has mainly been focused on support for the 2019 census. This work has been strategic and has had an impact on other outputs in the workplan as well as supporting the delivery of the outcome and impact. ONS, with UNECA, have supported IT work as well planning, gap assessments and problem solving. ONS have helped to coordinate and galvanize support in the British High Commission and with other donors.
Indicator 1.2 Milestone met. KNBS have interacted with the partnership positively and provided very positive feedback on the work undertaken with them so far. The activities undertaken so far on the census, have been primarily to meet KNBS needs which they identified.
Indicator 1.3 Milestone met. ONS ensured that modernization, big data and user engagement were adequately covered in the Strategic Plan to ensure that KNBS ambitions were met as these issues were missing from earlier drafts. ONS were only involved at the end of the process which meant massive changes could not be made, however, some of their inputs were taken on board.
The ONS Adviser provided assistance on how to structure the Communications Strategy and the elements that needed to be included. The main inputs were around user engagement and how to ensure user needs were incorporated as well as taking advantage of new dissemination tools and methods.
Indicator 1.4 Milestone met. There were three stories of change:
1. ONS arranged for an IT expert from UNECA to visit KNBS, and the universities involved with the census, to provide IT support which helped to ensure the census has gone smoothly;
2. The ONS also helped to raise awareness of the census with the British High Commission and with other donors helping to raise the profile for this crucial work; and
3. ONS also provided support to KNBS as they developed a new communication strategy providing new ideas of what is possible and what KNBS could do to improve their communications.
Indicator 1.5 Milestone slightly not met. Although the planned training activities have not taken place due to a focus on supporting the census, four staff from KNBS visited UNECA and the Central Stats Agency in Addis Ababa and received informal training on IT support for a census.
Lessons identified this year, and recommendations for the year ahead linked to this output
ONS support has been flexible helps to ensure it is both relevant and effective. It is important that the support continues to be flexible to respond to emerging needs. The peer-to-peer support provided by the UK National Statistician has been seen as very useful by the Head of KNBS.

	Recommendations
	Output 1	Refine scoring for indicator 1 level 4 to reflect actual percentage of progress against workplan.
		ONS and DFID to refine the methodology for scoring “stories of change” to reflect the different impact of the various interventions.
Output Title			Ghana Statistical Service increases the availability and quality of SDG data, with ONS support
Output number per LF				2	Output Score	A+
Impact weighting (%):				15	Impact weighting % revised since last AR?	Y was 20%

Indicator(s)	Milestone(s)	Progress
2.1 Progress towards establishing an effective project workplan (Annex 1)	4	4
2.2 Measure of partner commitment towards establishing effective partnership with ONS (Annex 1)	3	3
2.3 Number of cases of where ONS have provided advice on strategic policy documents: (e.g. Statistical Bill, communications strategy, other policy documents) and there is evidence that this advice has had an influence on the final product (cumulative)	2	4
2.4 Number of leaders mentored and/or trained by ONS support, and rating training as effective (cumulative number of individuals	20	40 leaders & 1 senior leader
2.5 Number of stories of where ONS support has enabled GSS to fill SDG data gaps, using admin data or other sources (cumulative).	3	3
2.6 Examples of where ONS support has led to more rigorous statistical infrastructure and systems; that are sustainable and promote good practice (e.g. statistical standards and concepts, adoption of national or international standards, programmes to upskill staff etc)	2	3

Overall this output is slightly exceeding expectations
Indicator 2.1 Milestone met. There has been good progress in Ghana in establishing and implementing a work plan. The advice and recommendations from ONS are being embedded by the Ghana Statistical Service (GSS). A key part of the workplan is support for census planning which is ongoing.
The ONS adviser helped with planning and implementation of field visits and media briefings and programmes for a Press Fellowship programme for SDGs led by the Global Partnership for Sustainable Development Data. This led to at least ten articles being published on Ghana’s efforts to collect data for development and how it’s being used to shape the lives of its citizens[1].
[1] http://www.data4sdgs.org/initiatives/data4sdgs-press-fellowship-ghana
Indicator 2.2 Milestone met. The ONS Strategic Adviser has forged strong working relationship with the current GSS Senior Leadership Team, who are engaged and responsive to ONS support. They have weekly bilateral meetings with the Government Statistician to discuss progress and new priorities.
As the partnership grows, GSS has identified a range of areas for additional support from ONS including national accounts, annual population estimates, human resources capacity however the key priorities remain the population census, economic and labour statistics.
ONS have forged strong relationships between the British High Commission in Ghana, DFID Ghana and GSS. The DFID Country Director has met with the Government Statistician and technical assistance on labour market statistics has also been shared with DFID and FCO in Ghana. The Strategic Adviser has joined the High Commission’s weekly Heads of Sections meeting, to ensure key progress is shared, work compliments 1HMG in Ghana and new collaborations are made.
Indicator 2.3 Milestone slightly exceeded. ONS has provided support in four areas:
- GSS Statistics Bill and Statistics Regulation: ONS provided advice to GSS on the formation of these regulatory two documents – many of ONS’ inputs have been incorporated into these working drafts. The most recent advice focused on the role of the Board and level of influence it should have over what the Government Statistician decides is appropriate. GSS will build on this advice and governance during their study visit to the ONS in August.
- Population and Housing Census: ONS provided a vast amount of technical advice on key population census project documentation including: updating workplans so that missing tasks, duplication of tasks and quality criteria are added at each stage, expanding the trial census strategy, from one to several rehearsals to ensure all business process are fully tested before March 2020. ONS is also undertaking some benefits management work so that GSS understands the uses and importance of census data which will help their data dissemination strategy and discussions around future funding.
- Communications Strategy: An ONS Communications expert provided technical advice on GSS’s Communication Strategy, with a view to making it operational including how they can make short-term economic indicators more accessible and understandable to both media and wider population.
- Learning and Development Strategy: ONS experts have been advising GSS on the importance of having a learning and development strategy, which meets the needs of staff now and in the longer term. The formation of this strategy has been the sole outcome of one-to-one coaching from ONS to GSS. This strategy draws on outcomes from the Strategic Advisor and includes input from a staff skills audit (completed by 89% of staff) and a staff perception survey (completed by 50% of staff) – in addition to, intelligence gathered from Sectional Heads to understand the business needs.
Indicator 2.4 Milestone has been substantially exceeded. The ONS Strategic Advisor has helped undertake a skills audit of all GSS staff, to understand current strengths and weaknesses. The outcomes will be used, together with business needs, to inform the next round of training, development and recruitment. ONS also helped with the following training and development areas:
- Management Skills: ONS in collaboration with GSS developed a three day programme for 20 Sectional Heads, that included: change management techniques; motivation skills; time management skills; project management; and negotiation skills.
- Strategic Leadership Training: This training involved 20 GSS senior leaders and included a360-degree feedback exercise as a precursor to the Leadership course. The course covered leadership and management skills based on the five principles agreed at the Leadership Masterclass in London (21 November 2018) at the Commonwealth Heads of Statistics Conference: communication; people leadership; strategy; knowledge; and integrity.
- Mentoring: ONS have set up a mentoring programme for the new GSS Government Statistician with a member of ONS’s senior leadership team and the sessions will start soon.
Indicator 2.5 Milestone met. There were at least three stories of where ONS support has enabled GSS to fill SDG gaps:
1. Improving the quality of the census – ONS provided a moderate level of support which is likely to lead to a major impact although this is likely to take some time as the census will only take place in 2020. Many of the SDG indicators rely on demographic data.
2. Improving capability in the GSS – ONS provided a major contribution assisting in a range of areas from developing an SDG national reporting platform to support on leadership and training. It is likely this will have a moderate impact.
3. Specific SDGs – ONS have supported a number of SDG projects looking to collect new data on areas such as waste management and gender statistics, through the provision of advice.
Indicator 2.6 Milestone met. There have been a number of areas where ONS support has led to more rigorous statistical infrastructure and systems including:
- ONS advice has led to GSS adapting its census approach to include more quality assurance of its statistical processes including support in validating enumeration areas using satellite imagery; moving from one trial census to several; and developing a benefits management paper.
- ONS Labour Market technical assistance including better identification of informal employment and advice on how GSS can use international labour market concepts and best practice, in the national context.
Lessons identified this year, and recommendations for the year ahead linked to this output
The work with GSS is going well. GSS have appreciated the support particularly as they have a new Government Statistician. The mentoring support for the new Government Statistician will provide useful support as he settles into this new role.

Recommendations
Output 2	As recommendation 1 and 2.

Output Title	Rwanda Statistics Office increases the availability and quality of SDG data, with ONS support
Output number per LF		3	Output Score	A
Impact weighting (%):		15	Impact weighting % revised since last AR?	Y was 20%

Indicator(s)	Milestone(s)	Progress
3.1 Progress towards establishing an effective project workplan (Annex 1)	4	4
3.2 Measure of partner commitment towards establishing effective partnership with ONS (Annex 1)	3	3
3.3 Number of national statistical strategies / sectoral modernisation plans or equivalent informed by ONS advice	1: Final NSDS published with clear evidence of ONS inputs and progress towards objectives being made	2: NSDS3 finalised and ToRs for ICT tender published
3.4 Number of joint data science projects, with published results	One published and one more underway	One completed and one making progress
3.5 Number of stories of change where ONS has helped NSOs to develop training materials / capacity development approaches	1: milestones towards establishing NISR Training Centre and Data Hub on track	3
3.6 Number of people trained with ONS support, and rating training as effective (cumulative)	270	52 staff trained on Python

Overall this output is meeting expectations.
Indicator 3.1 Milestone met. Good progress is being made on implementing the work plan including setting up an SDG National Reporting Platform which was recently launched.
Indicator 3.2 Milestone met. The National Institute for Statistics in Rwanda (NISR) engages positively and proactively ensuring ONS support is channeled to their most pressing needs (eg data protection law).
Indicator 3.3 Milestone slightly exceeded. ONS have helped NISR to shape two completed documents:
The third National Strategy for the Development of Statistics (NSDS3) includes several sections shaped by ONS input: narrative on the data revolution policy, sections relating to building capability and creating a legal framework for data sharing whilst protecting data; and
Terms of Reference for an Information and Communications Technology infrastructure tender which was published online in July 2019.
Indicator 3.4 Milestone met. ONS has supported NISR and the National Bank of Rwanda on a data visualization project which is complete and a project on building a reproducable analytical pipeline which is making good progress.
Indicator 3.5 Milestone exceeded. There have been at least three stories of change where ONS has NISR to develop training materials or to develop capacity:
1. ONS helped NISR to set up and launch their data science centre and to hold the 5th International Conference on Big Data for Official Statistics held in Kigali (https://unstats.un.org/bigdata/).
2. ONS helped to set up Rwandan National Reporting Platform, using the Open-SDG Platform. There is a team of five staff who are confident in uploading data and metadata and resolving issues.
3. A legal team from the UK Statistics Authority has helped to strengthen NISR’s policy and legal framework, providing safe researcher training, work to build stakeholder awareness on the benefits of sharing data in a secure way, and NISR’s role in the Data Revolution agenda.
Indicator 3.6 - Milestone not met. ONS delivered Python training to 52 staff through two courses in October 2018 and March 2019. There may be some double counting as a few people may have attended both courses. The target of 270 staff trained was ambitious and reflects NISR’s huge appetite for data science. The original plan was to use a train the trainer approach but this was unrealistic as four days training was not sufficient for this.
Lessons identified this year, and recommendations for the year ahead linked to this output
ONS have been working flexibly providing targeted support as needed which is proving very beneficial, however, it has also meant that some areas of support are not included in the logframe.

Recommendations
Output 3	As recommendation 1 and 2.
	ONS to consider how logframe can be flexible to include new areas of support.
Output Title		UNECA’s Africa Centre for Statistics (ACS) provide an enabling environment for African National Statistics Offices, with ONS support
Output number per LF			4	Output Score	B
Impact weighting (%):			15	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s)	Progress
4.1 Progress towards establishing an effective project workplan (Annex 1)	4	4
4.2 Measure of partner commitment towards establishing effective partnership with ONS (Annex 1)	3	2
4.3 Number of examples where ONS and UNECA have supported improvements to national statistics through improving the quality of the population census	3	2
4.4 Number of Africa Statistical Leaders mentored or trained through UNECA led, ONS supported training, and rated training as effective	30	0
4.5 Number of stories of change of where ONS support and delivery of the workplan has helped deliver changes to how UNECA operates	2	2
4.6 Number of examples where ECA have supported African countries in the use/application of data science techniques or jointly worked with African countries on data science projects	1	0
4.7 Number of examples of where ONS and UNECA have supported improvements to national statistics through support to the census office on specific topics (e.g. economic statistics, CRVS or gender data)	3	1

Overall this output is falling slightly below expectations
Indicator 4.1 Milestone met. The work plan is being implemented with several quick wins including: initiation of an Expert Group Meeting on electronic data collection and dissemination in Censuses held in July 2019; support to ECA data science initiatives with python training to 15 people in Addis and a lesson learning mission to ONS Data Science Campus organized in December 2018.
Some measurable progress includes contributions to support development of Supply and Use Tables in Eswatini; support to censuses in Kenya and Ghana with more countries starting to show interest in receiving similar assistance (e.g. Zambia); and, the leadership programme - development of a concept note, including detailed cost plans, produced and used to initiate resource mobilisation activities and pilots planned for summer 2019.
Indicator 4.2 Milestone is slightly below expectations. UNECA is engaged in the partnership and responds positively to suggestions from ONS, however, to date most of the areas of support have been driven by ONS and UNECA support has been slower than planned.  Vacant positions at UNECA, namely head of the Demography and social Statistics Section, is largely behind the slow progress. This position was not filled until February 2019 and this, along with other vacancies, significantly affected planning and development of support programmes for the census and CRVS which comprise more than 50% of the programme’s focus and advisor time.
Indicator 4.3 Milestone is slightly below expectations. UNECA have helped Kenya and Ghana with the planning for their census (see case study Improving UNECA’s role in supporting 2020 Census round in Africa). This work relies on countries requesting assistance. Zambia have requested assisted which ECA had planned to provide in June but this was delayed by ECA until July 2019 due to logistical reasons
ONS also initiated work to develop and organise an Expert Group Meeting (EGM) on electronic data collection and dissemination in censuses. This has the potential to have a positive impact on a wide range of countries and could be the subject of a future case study. The EGM took place in July and so fell slightly outside the annual review period. ONS have provided strategic advice to ECA on their census work plan to help them to prioritise key areas to focus on and better engage with stakeholders.
Indicator 4.4 Milestone is significantly below expectations. Two pilot projects to test the leadership training and begin mentoring were planned to occur in June consisting of 30 participants, but were postponed due to delays securing agreement from pilot countries which has meant that one pilot will occur in July (Namibia) and others are still being arranged. The delays were caused by the countries and not by ONS.
Indicator 4.5 Milestone met. There are two case studies which demonstrate ONS contribution and impact in the partnership:
1. Supply and Use Tables - the ONS expert, drawing on experience of working in other African countries and taking account of the established best practice, was able to suggest improvements to the ECA approach and materials.
2. Support for 2020 Census round – the ONS advisor has been involved in UNECA missions to scoping and reviewing assistance for two countries.  As part of this work he has developed terms of reference and a reporting template that will be used for future scoping visits. This will reduce time to re-develop templates and report on outcomes where similar structure and language can be used across countries; and will improve the consistency of outcome reporting.
Indicator 4.6 Milestone is significantly below expectations. Although some progress has been made on building on ECA capability in data science with a three-day python training course delivered by ONS Data science lecturers due to other priorities within ECA, including support to the Kenyan and Ghanaian censuses, this has been slower than planned.
Indicator 4.7 Milestone is significantly below expectations. ONS have provided technical assistance to Eswatini on economic statistics on the development of Supply Use Tables. This consisted of a team of experts assisting a country over a whole year providing continuity and increased understanding of a countries’ challenges.  An ONS expert has, so far, participated in one in-country visit (out of planned four or five) and provided regular remote advice.
Lessons identified this year, and recommendations for the year ahead linked to this output
Support to UNECA is more complex than peer-to-peer country support particularly as it relies on countries asking for support and then remaining engaged in the process and the agenda for this work is wide reaching and ambitious. Despite these challenges the work is going well and UNECA noted that they “would have struggled to provide the assistance and, quality of assistance” without the ONS adviser. Although some of this support has been slower than anticipated, since ECA have now filled their vacant posts, we expect this work to pick up pace over the next few months.

Recommendations
Output 4	As recommendation 1 and 2.
	ONS to consider writing a case study on the Expert Group Meeting on censuses.
	ONS and UNECA to explore ways to gather feedback on the Expert Group Meetings to assess how well they are meeting countries’ needs.

Output Title	Flexible Short Term Facility
Output number per LF		5	Output Score	A
Impact weighting (%):		40	Impact weighting % revised since last AR?	Y was 25%

Indicator(s)	Milestones	Progress
5.1 Weighted average (by spend) of scores for flexible facility activities related to ONS engagement in key data for development international events [FF3,4,9,10,11]	A	A+
5.2 Number of case studies of partner countries successfully cloning and using UK/US SDG platform as a direct result of ONS support (cumulative) [FF1]	3	3
5.3 Effective participation of ONS in ICP technical working groups [FF8]	A	A
5.4 Effective progress towards targets in workplan for project to improve the quality consistency and dissemination of statistics on employment and productivity [FF2]	A	B
5.5 Effective progress towards developing a new tool for storing, and analysing results and finances data – Data Trailblazer [FF5]	A	A
5.6 Effective progress towards targets in workplan for establishment of data science campus hub in DFID East Kilbride [FF13]	N/A	A++

Overall this output met expectations.
There have been ten projects in the past year through the flexible facility – six of which are ongoing and four new. Each project has a set of clear targets and indicators in the terms of reference which were agreed by the DFID/ONS Steering Committee. For the ongoing projects these have separate indicators (Indicator 5.2 to 5.5). For the shorter term projects these are measured under Indicator 5.1 [FF3,4,9,10,11].
Indicator 5.1 Milestone has been slightly exceeded. Based on the excellent performance of FF10 (Commonwealth Heads of Statistics Conference) overall this indicator has slightly exceeded expectations. More details of each of the projects are listed below.

Flexible Facility Project[2]	Budget Spent £	Overall weight	Project Score
FF3 - Age and Ageing	£11,096	23%	A
FF4 - Global Platform for Data	£0	0%	N/A
FF9 – UNESCAP	£942	2%	C
FF10 - Commonwealth Heads of Statistics Conference (CHOSC) November 2018	£33,825	72%	A+
FF11 - Scoping work	£1,606	3%	A+
TOTAL	£47,469	100%	A+
[2] Scores for FF 3,4,9,10 and 11 based on narrative reporting and overall indicator score is weighted by budget

Below is more detail on each of the active projects:
FF1 - SDG Reporting Platform (Indicator 5.2) – Milestone met
This project aims to provide developing countries with an open source tool for collecting and reporting SDG data, and with supporting materials to facilitate implementation and analysis. Through the ONS collaboration with US Government and the Center for Open Data Enterprise (CODE), they have combined code and features in the UK and US platforms into one product called ‘Open SDG’. This new version will allow countries to more easily adopt future developments and share resources such as translations. It will also include improved mapping features, a key requirement for our partner countries. Documentation has been produced to ensure comprehensive guidance is available to any country wishing to reuse ‘Open SDG’.
There are now eight countries using an SDG national reporting platform based on Open SDG or previous versions of the UK/US platforms: Rwanda, Ghana, Kyrgyzstan, Armenia, Kazakhstan, Namibia, Jamaica and Poland. The ONS SDG team visited Rwanda, Ghana and Kyrgyzstan (partner countries) to train staff on how to manage their platform. Support was also provided on mapping MDG indicators in existing systems such as DevInfo to the SDG indicators.

FF2 - Improving measurement of jobs and productivity (Indicator 5.4) – Milestone slightly not met
This project aims to improve the quality, consistency and dissemination of statistics on employment quality and productivity with the ultimate objective of creating more productive, high wage employment and productive economies in low income countries.
ONS have participated in an informal working group of labour statisticians which agreed the work should focus on two or three individual countries as case studies which will help to assess the detail, quality and conformity with ILO recommendations and account for the national data priorities. Terms of reference for the case studies have been drawn up, building on the knowledge base developed during the ONS high-level review of the global labour statistics system and have since been applied to a case study in Ghana. A similar case study has been planned for Kenya and the preparatory analysis of the published data sources has been completed. Zambia and Jordan are being considered for further case studies.
ONS have also provided technical support to the DFID Growth team to help them to develop a better jobs measurement framework within DFID. The in-country case studies are informing this work, through an assessment of the national labour statistics that are available, to support the evaluation of DFID’s job creation programmes, and how well DFID have used them, where suitable.
FF3 - Age and Ageing (Indicator 5.1)
This project aims to support the UN ‘Titchfield City Group on Ageing’ by helping to improve the collection, analysis and use of good quality data on age and ageing in developing countries. This is essential to both measure and to achieve the SDGs and to ensure no-one is left behind.
The second technical meeting of the Titchfield City Group) took place in June 2019 in Daejeon, South Korea.  Over 60 experts attended the two-day workshop, with 31 National Statistical Offices represented. Work continues between countries and civil society to progress the work stream planning in more detail.
Overall Score A: There were no milestones in the TORs and therefore it was hard to judge, but broadly the city group is on track to deliver on its goals.
FF4 - United Nations Global Platform for Official Statistics (Indicator 5.1)
This project aims to support the UN Global Platform for data and to ensure its relevance to developing countries. The Global Platform team launched the alpha for the Marketplace service at the UN Statistics Commission https://marketplace.officialstatistics.org/. The marketplace allows internet users the opportunity to easily search and explore data collaboratives, datasets, methods, partners and learnings from the statistical community. The draft business model options were well received by the UN Statistics Commission which approved continuing with the programme for the next 12 years.
The Global Platform for Official Statistics team attended the UN conference on Big Data held in Rwanda in April 2019. This event was focused on Africa, and discussed potential hubs in Rwanda and Ethiopia (UN Economic Commission for Africa). The Global Platform communications forum (Slack) now has over 270 members from across 16 times zones.
No funding was spent on this project during this phase but ONS continue to monitor developments and seek opportunities to increase the relevance for, and implementation of the Global Platform in developing countries. If funding is allocated in the future, indicators of success will be set at this time.
FF5 – Data Trailblazers (Indicator 5.5) – Milestone met
This project aims to support DFID in transforming their collection, management and analysis of data collected by partners and to create an efficient automated data management system, with agreed data standards, and systems for open data publication. ONS have been developing a new logframe tool, called DART (Development Activities Results Tracker), which could be used by partners and would enable automated transfer of data to the International Aid Transparency Initiative and to DFID. The tool is now being tested and further developed with data visualisations. The code is on GitHub to allow for further collaboration.
FF8 - Technical contribution to International Comparison Programme (Indicator 5.3) Milestone met
The International Comparison Programme (ICP) aims to estimate Purchasing Power Parities (PPPs) for use as currency convertors to compare the size and price levels of economies around the world. PPPs are used for a variety of purposes including updating the International Poverty Line and therefore the count of the global poor, the SDGs and the Human Development Index.
In September 2018, ONS presented at the third meeting of the ICP Task Force 2 on Country Operational Guidelines and Procedures. The lessons learnt document detailing the challenges that the UK faced during the recent calculation of SAFs and RRCPLS was well received. ONS team have also been the main author of a document providing guidance on producing sub national PPPs (regional data). To complete this Task Force participation, ONS prepared a case study on the UK Integration of CPI and ICP. The paper was highly praised by the chair of the group. Due to the delay with establishment of the other task forces, the ONS involvement to this programme was limited to two task forces.
FF9 – UNESCAP (Indicator 5.1)
The project aimed to support UNESCAP with their work on economic and financial statistics. There were plans for ONS to conduct a national statistical review in Sri Lanka but the work was delayed as a result of security issues there and there were also challenges for ONS to find the right staff with the availability. The project was eventually undertaken without ONS involvement because of the personnel issues. No other requests for support have been forthcoming from UNESCAP.
Overall Score C: This project has significantly under-performed.
FF10 – Commonwealth Heads of Statistics Conference (Indicator 5.1)
This project supported the Commonwealth Heads of Statistics Conference (CHoSC), hosted by the UK Statistics in London in November 2018. The over-arching theme was ‘Towards a Common Future’, and the Conference focused on five topics: Leadership – Oceans – Data Science – Education – Collaboration.
The topics on Oceans and Education were inspired by the 2018 Commonwealth Heads of Government meeting priorities. The conference also included a market place of 20 exhibitors.
It was attended by 170 participants from Commonwealth national statistical offices, other data communities, government institutions, private sector, civil society, and academia. It helped to share knowledge, good practice, discuss common statistical issues, build career-long friendships and discuss future Commonwealth engagement.
The Terms of Reference set out a number of specific targets which are shown below along with reflections of how the event scored against them:
- Deepening partnerships – the target was for participants to build new connections through sharing good practice and on-going interaction which this was over achieved. The UK Statistics Authority will be hosting a Commonwealth side event at the International Statistical Institute conference in Malaysia in August which will highlight the CHoSC Declaration, identify areas that have benefited from the collaboration and encourage further discussion. Further to this, ONS has developed a close relationship with the Commonwealth Secretariat and is in discussion with them on how to build data science skills. The leadership side event at CHoSC was also instrumental in ONS designing a Leadership Training Programme for African National Statistics Offices. The programme is based on the five key principles of leadership that were identified at the CHoSC18 Leadership Masterclass and agreed at the main conference.
- Diversity – the target was for at least 30% of official sessions to feature speakers or panelists from developing countries (measured by session registration and analysis) of the five panel sessions three (60%) featured speakers from developing countries.
- Inspiring ideas – the target was for the majority of participants, from developing countries, to indicate that they feel the Conference had helped to inspire ideas for statistical development in the key themes, working with policy leads, in their own countries. This was achieved and the wrap up session (with heads of National Statistical Offices) showed that the majority of developing country participants agree that the shared experiences around the themed topics were of great relevance and inspirational, in particular the areas of data science.
Overall score A+: The project has exceeded expectations.
FF11 – Scoping work (Indicator 5.1)
ONS have been engaged with potential future partners through a range of regional and global initiatives, in order to maintain momentum and further identify which of them would make most appropriate future partners discussing how to scale up their work and as part of this they have undertaken a range of activities:
- Conducted a scoping visit to Jordan Department of Statistics (costs were met through the Conflict Stability and Security Fund) and made plans to take this partnership forwards including recruiting a new Strategic Adviser to lead this project (from the UK);
- ONS Data Science Campus has a student from the Namibian Statistics Office working on her MSc thesis for three months. ONS are also in the process of arranging leadership training in Namibia (under the UNECA partnership) which will help them to consider a future partnership.
- Discussions have started with Zambia, Malawi, Uganda, Nepal and India to consider possible support for census and/or modernization of the statistics offices. Through their economic statistics projects, ONS has continued to support the national statistical offices of Zimbabwe, The Gambia, and Sierra Leone. ONS have also been engaging with the DFID team leading on the demographic pillar of the cross Whitehall “new strategic approach to Africa”.
Overall score A+: this project is exceeding expectations.
FF 12 – Integrating non-traditional data sources in the production of Official Statistics
This was a new area of work, which started in mid-2019, designed to help countries to integrate non-traditional data sources in the production of official statistics. It will help them to consider the institutional and organisational environment, cooperation, dialogue and partnerships which are needed to address these challenges. The main output is a national workshop organised jointly by UNSD and DFID with the support of UNECA, which will address the institutional and organisational environment for official statistics that would foster access to and use of non-traditional data sources, such as data from the private sector, civil society and the academia, to complement traditional data sources to produce official statistics and Indicators. This workshop took place in July 2019 and so will be reported in full in the next annual review.
FF13 - DataScience Campus Hub in DFID East Kilbride (Indicator 5.6) – Milestone substantially exceeded
This project is a new project to set up a data science campus hub in DFID, East Kilbride. As this was a new project no formal targets were set for the first year, however, the hub has been set up and is now operational which has been much faster than anticipated. Recruitment of staff and agreeing a work plan is moving forwards at a significant pace:
- Seven staff have been recruited despite the challenges of recruiting technical staff on civil service salaries;
- A series of workshops have been held with a wide range of stakeholders which have helped to shape an initial theory of change and is guiding the prioritisation of potential projects; and
- Using wider ONS Data Science Campus resources, a project has started with DFID to explore the feasibility of estimating livestock numbers in South Sudan using satellite imagery.
Lessons identified this year, and recommendations for the year ahead linked to this output
The flexible facility continues to provide fast, targeted support which is meeting countries’ needs, for example the recent support to Tanzania Bureau of Statistics on integrating official and non-official data sources (FF12).

Recommendations
Output 5	ONS should conduct further work to define clear milestones and targets for the flexible facility projects which do not currently have them.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES
Summarise the programme’s theory of change and any major changes in the past year
The theory of change (Figure 1) is based on the idea that ONS works in partnership with country governments and regional partners, to enhance the capacity of their statistical organisations, through dedicated technical assistance and capacity building work. Through these partnerships, the organisations’ capacity will improve and their commitment to quality data will be strengthened. The increased availability and frequency of data will help inform decision makers and enable citizens to hold their governments to account. As ONS conduct this work they will also learn more about practices used by other countries and this will also feedback into learning for the ONS in terms of how they collect and analyse data. For example, the ONS SDG team, through their discussions with Ghana and Rwanda, have identified a number of future enhancements which they will be making to the UK SDG platform.
Importantly this programme will work/ is working alongside other DFID programmes that are aiming to improve developing countries’ capacity to monitor the Global Goals, as well as the global community’s ambition to report on progress in 2020 and 2030.
The theory of change was reviewed earlier in 2019 but no major changes were made although it was agreed that separate theories of change would be developed for each country. The data science hub is also in the process of developing a specific theory of change.

Figure 1: Theory of Change

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead
The programme is currently on track to deliver the expected outcomes, although some areas of work have been slower than anticipated, others such as setting up the new data science hub have been faster than anticipated. ONS have produced nine case studies demonstrating the impact of their work, against a milestone of five case studies. These have been independently assessed by at least three different people using the scoring shown in Figure 1.

Figure 2: Methodology for scoring case studies
The case studies are listed below alongside an assessment of the ONS contribution and current impact:
Case Study Topic		ONS Contribution		Impact
1	Establishing NISR as regional data science hub	Moderate	Moderate
2	Improving the quality of the Kenya census	Minor	Moderate
3	Improving the quality of the Ghana census	Minor	Moderate but may become major
4	Improving UNECA's role in supporting 2020 census round in Africa	Moderate	Minor but could become major over time as support expands
5	Improving UNECA's role in supporting economic statistics in Africa	Minor	Minor although in Eswatini impact is moderate
6	Making leadership training available in African National Statistical Systems	Minor	Minor but expected to increase once training starts
7	Improving capability in the Ghana Statistical System	Moderate	Moderate
8	Improving the international labour market data system	Moderate	Minor although this may become more significant over time
9	International influencing on the role of an NSO in a modern data landscape	Moderate	Minor although difficult to judge and has potential for major impact

Four of the nine case studies are currently demonstrating at least moderate impact although others look likely to demonstrate this over a longer time frame.
Explain major changes to the logframe in the past year
The weights for each output have changed since last year to better reflect both the budget and the level of effort. Each country output is now weighted at 15% compared to 20% last year, support to UNECA has stayed the same at 15% and the flexible facility has increased from 25% to 40%.
Describe any planned changes to the logframe as a result of this review
Indicator 1 which measures progress towards establishing a workplan is measured on a scale of 1 to 5, however, this will be refined to show actual progress towards achieving the workplan. This was the first year that case studies were produced. Whilst they have provided useful qualitative information they are still subjective and more could be done to refine the methodology.
Further indicators will be added for specific activities within the flexible facility where these have not yet been defined. Later in 2019 there will be a review of the monitoring framework carried out by a monitoring and evaluation consultant.
Recommendations
Theory of Change	ONS and DFID to refine the case study methodology to reflect current and future impact in the scoring.

## D: VALUE FOR MONEY
The main cost drivers continue to be staff and travel costs. A series of value for money indicators were identified this year and have been measured as a baseline but no specific targets were set, see below.

VfM Mechanisms	Potential VfM Indicators
Economy
This programme is being implemented solely by ONS. The main costs are staffing and travel. Overall economies are achieved by ensuring staffing costs remain competitive and that travel costs are kept as low as possible, including only using economy flights. DFID and FCO contacts are used to obtain corporate rates with hotels and hotels and flights are booked as early as possible.	Average daily rate for overseas advisers / £570 / day / Costs of workshops or training events, some examples are; / CHOSC – UK - £28,457 / Data Science - UK - £23,601 / Learning & Development Training – Ghana - £9,000 / Average travel costs for each trip / £2200 / per person / trip / Negotiated savings for events and overseas trips / Systematic data has not been collected but ONS always seek to reduce costs, for example for one flight they were able to get a £1000 saving on the original quote
Efficiency
The largest financial proportion of this programme is staffing costs. All staff will be selected competitively, based on their capability and capacity to deliver the agreed work programme. Recruitment will follow ONS processes. / Overseas staff will be supported by the UK based team who will provide the strategic direction for the work as well as ensuring that staff have the right support at the right time.	Average time from posting of position description to offer: / Overseas – approx. 6 months / UK – approx. 6 – 8 weeks / Average time to process travel reimbursements for Partners, from date of submission of receipts / 1 week / Cost of frontline delivery staff versus support staff / Overseas staff costs / year = £1,138,514 / UK staff costs / year = £559,390
Effectiveness
This programme is helping to modernise national statistical offices to help ensure quality accessible, timely and reliable disaggregated data will be used to measure and to achieve the SDGs and ensure no one is left behind. Better statistics will help to inform policy making. Open data will help businesses to grow and will help citizens to hold governments to account.	Cumulative number of case studies which demonstrate at least a minor contribution from ONS and moderate or major impact / 4 / % of Partners (countries and UNECA) reporting a positive impact from the collaboration with ONS (based on feedback) / 100%. Feedback from UNECA and countries shows they appreciate the peer-to-peer support. It has been particularly useful in Ghana as they have a new head of the GSS.
Equity
The partnership with ONS is helping to support national statistics offices including in the area of better disaggregation of data to ensure no one is left behind. This includes setting up a new post in ONS working on technical support for the Inclusive Data Charter.	Number of case studies which include activities which support the creation and/or use of disaggregated data / 5 (1: NISR data science hub; 2: Kenya census; 3: Ghana census; 4: UNECA census support; 8: Labour market data)

This programme continues to represent good value for money. It is a key part of the Data for Development Team’s portfolio, contributing to a number of key areas: harnessing innovation (for example through the Open SDG platform and the data science projects) and seeking to modernise national statistical systems, which in turn should contribute to improved measuring and achieving of the SDGs. The partnerships with the three governments should improve their capacity, which will subsequently contribute to collecting and disseminating better data on the SDGs. It also works with UNECA which helps to ensure the longer term sustainability of the project as UNECA will be able to continue to work with these countries after the programme has finished.
The flexible facility provides good value for money as it allows small scale or short-term projects to be implemented quickly once approved by the programme’s steering committee. It provides excellent value for money as it enables activities to be set up quickly within the existing framework avoiding the need to manage separate projects. It is unlikely that many of the flexible facility activities would not have taken place without this mechanism.
The programme is helping to build ONS’s capacity to deliver international statistics programmes. It is helping to build programme management skills as well as political economy skills both of which are crucial in delivering effective programmes. In the next Comprehensive Spending Review ONS are planning to bid for their own Official Development Assistance (ODA) directly from Treasury rather than working through DFID. This partnership will have helped ensure that value for money is embedded into ONS’s international development programmes and that ONS have built up both the skills and the processes which will enable them to work effectively in a range of developing countries.
E: RISK
This programme’s risk continues to be classed as minor. Of the risks that are on the risk register, the highest risk is the “risk of association”. There is a risk that partners are accused of not operating with the same integrity as the UK Statistics Authority and ONS. This could be because of real or perceived political interference and pressures. This could result in ONS being associated with bad practices which could damage its broader reputation. This will be mitigated through ensuring all ONS’s work is of a high standard. If any issues do occur they should be discussed with the FCO and DFID in country to agree a common position.
ONS should continue to work with DFID and FCO experts in each country to ensure that any specific risks around the political economy or context in each country, are fully understood and monitored, as well as security risks.
As set out in the business case, ONS are the primary owners of the risks and will escalate to DFID as and when necessary. If any risks on the risk register increase they will act quickly to escalate these and take controlling actions. Moderate risks will be escalated to the DFID SRO and major and severe risks will be escalated to the Steering Group.
F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE
This programme has one partner, the ONS. DFID has found working with ONS extremely productive and they are an engaging and competent partner. ONS have communicated early with DFID as and when there have been any changes in spending level or if there have been any financial challenges. The overall spend was lower than anticipated in 2018 due to delays in recruiting the overseas advisers but these are now all in place and spend is now at the anticipated level.
ONS provide timely quarterly reports, which contain a detailed narrative of the activities, a breakdown of spending as well as forecasted spending over the next year. ONS have been especially responsive to any ad hoc requests for additional information.
In terms of the performance of the delivery partners, this partnership is between two government departments and so there are no delivery partners. ONS only use their own staff and how not contracted out any aspects of delivery.
ONS and DFID have developed a strong working relationship through this programme, the two departments coordinate attendance and briefing for external events and have regular discussions to ensure both departments are joined up. Messages to senior manages and Ministers are often done jointly which ensures the UK government is having a more coordinated approach to challenges and the opportunities in the measurement and achievement of the SDGs.
In January 2019 the Steering Committee agree to set up a new Data Science Hub based in DFID’s East Kilbride office but will be staffed by ONS. The Data Science Hub will be part of ONS’s Data Science Campus and will focus on international development challenges. This is a good example of joint working.

Date of last narrative financial report(s)	17 July 2019
Date of last audited annual statement (s)	4 July 2019

G: MONITORING, EVIDENCE & LEARNING
Monitoring
The steering committee provides strategic direction for the programme and an accountability mechanism. Each of the major partnerships (Ghana, Kenya, Rwanda and UNECA) have a set of outputs, outcomes, indicators, milestones and targets which they are monitored against, as do each of the flexible facility projects. ONS produce detailed quarterly reports for DFID outlining progress and explaining where progress may be off track, and the reasons for this. The ONS team have developed a new tool for storing and presenting results data for this project, in place of using the DFID logframe template (DART tool). The new tool is currently being piloted.
This annual review was conducted by the technical advisor to the programme. The annual review benefited by having discussions with ONS and inputs from DFID in-country staff, as well as input from DFID staff supporting the flexible facility. This review was drafted and agreed in partnership with ONS. The review was also peer-reviewed by a DFID statistician, not involved with the programme, before final quality assurance by DFID’s Chief Statistician.
Evidence
The recent Independent Commission for Aid Impact (ICAI) review on “How UK Aid Learns” looks at how well ODA-spending departments, including the ONS, learn in order to deliver aid effectively and provide value for money. The review notes that “learning is going both ways: returning experts share their experience with colleagues, and this in turn is reportedly informing the ONS culture and its approach to challenges in the UK.”
DFID and ONS are planning to conduct a review that will look at the effectiveness of ONS’ approach and their work, rather than focusing on whether the outputs have been successfully achieved or not. The review is likely to be conducted by a combination of staff from ONS, DFID and the Government Partnerships International (GPI)). The GPI team specialise in supporting UK government’s partnerships with recipient governments, and will be well placed to look at the success of the partnerships of this programme. The review has not been finalised but may consider (but is not limited to) the relevance of the ONS modernisation for developing country partners and the advice being given; and/or the efficiency and effectiveness of ONS’ international development approach. The review could also critically challenge the assumptions in the ToC and use the findings from the review to feed into the design and implementation of other DFID and ONS statistical capacity building programmes.
Learning
There continue to be opportunities for ONS and DFID learning: the program is contributing to knowledge available on peer to peer working, and on statistical capacity building – contributing to international debates on best practice ONS and DFID are also learning about processes related to ODA spending: for example embedding staff in country, travel policies; and also on the time and commitment from staff needed to run effective ODA programmes.
To build the learning and capacity of ONS internally, they have ensured that they use all cross-government opportunities to build the capacity of their staff e.g. through the GPI network and visiting other government departments who are further developed in this type of work. ONS are building up the number of staff with capability to apply their skills in a developing country context, by offering training (in thinking and working politically – delivered by GPI) and by pairing up staff on their first visit with someone more experienced in international working. ONS are also surveying staff to see how their experiences change over the lifetime of this project, and these results will help improve the quality of their international development programming.
Following clear demand from within DFID and in developing countries for help to enhance data science skills ONS have set up a satellite hub of the Data Science Campus based in DFID’s East Kilbride office. The hub will help to build data science skills in DFID as well as in development partner organisations and developing countries. The hub will have a strong focus on learning and will use a collaborative working style to conduct joint projects with other partners including academic organisations and developing country governments.
DFID and ONS are discussing options around scaling up ONS support to more countries as part of ONS’ expanded ODA programme. It will be important that any scaling up learns lessons from the current programme.
Progress on recommendations from previous reviews
Recommendations		Update
Output 1 (Kenya)	DFID and ONS to ensure the work programme with KNBS is flexible and is aligned with wider UK work on supporting Kenyan systems and capacity building work	Completed. This has been taken into account in the ToR and workplan and engagement with colleagues at the British High Commission has increased the profile of the partnership especially around work on the census. / The partnership is drawing on ONS support but also and crucially for the census, UNECA who are supporting Ethiopia with their digital census. ONS are encouraging KNBS to consider wider South-South support from countries that have undertaken a digital census. / Output level indicators have been added to the log frame.
Output 2 (Ghana)	Ensure future Ghana post-holder engages not only with UK government priorities, but brings other donors to support GSS’ work plan and aim to improve SDG reporting	Completed. ONS will aim to assist GSS to make the most of the available donor support. The donors input will be channelled to support Ghana beyond Aid strategy: to build GSS capability but not do the work for GSS.
	Add output indicators 2.3, 2.4 and 2.5 to the logframe and begin to monitor them.	Completed. Indicators added.
Output 3 (Rwanda)	Add output indicators 3.3, 3.4, 3.5 and 3.6 to the logframe and begin to monitor for NISR	Completed. Indicators added.
	DFID and ONS to look for creative ways to fill the adviser posts including using UK advisers travelling to the region and looking at creative ways to train and incentivise staff to work overseas	Completed. ONS and DFID have worked together over the past year to build a pipeline of interested staff. ONS has done a lot of internal comms and built up a pool of interested staff. UK based posts continue to receive high levels of interest. For the next phase, we are actively considering different models for managing the positions.
Output 4 (UNECA)	DFID and ONS to ensure the work programme is flexible but that it also has clear tangible outputs for UNECA’s workstream	Completed. The strategic adviser submitted a work plan with tangible outputs that was approved at the January steering committee.
Output 5 (Flexible Facility)	DFID to engage further with the Trailblazer work (FF5) and ensure there is joined up coordination across both departments, departments should consider working on a joint online platform to improve communication.	Completed. DFID has continued to engage in this work. / A new workplan for the trailblazer work was developed by DFID during a workshop in November 2018, which has enabled ONS to have greater clarity on the task. / Two clear outputs have been identified: 1. To develop a tool for results data management and 2. To develop an online repository of results data and indicators. / ONS has agreed to support both and has hired a data scientist to work on output 1. The second will be worked on by the new Data Science Campus hub.
	DFID and ONS to develop a prioritised action plan for the coming year and agree a new log frame indicator to capture the progress of FF5 in subsequent annual reviews	Completed - We will use the following scale to asses the first partof the work programme described above: / C: no tool with any use / B: a part developed tool / A: a tool which ONS international development team uses to store information and autogenerates required reports to DFID. / A+: a tool which is thought of by DFID as good practice and will ultimately be used by other DFID project partners. / A++: further work to think about how DFID could turn its currently available results information, into a similar format to that in DART, to enable analysis across its projects, and to encourage the use of common standards has been undertaken.
	It is recommended that ONS develop specific output based targets for each of the task forces in FF 8 and capture these in the log frame under target 5.3	Completed. / Each task force has its own timeline and agenda. ONS participation in: / • Task Force 2 - Operational Guidelines and Procedures; / • Task Force 4 - PPP Uses; / • Task Force 7 - PPP Quality and Reliability. / is agreed in principal. / Success will be measured in terms of the outputs of these task forces being delivered.
VFM	ONS and DFID to create VFM indicators for the programme in order to assess and quantify progress on VfM	Completed. / DFID has proposed the indicators in the table below, which ONS will need to report on for the 2019 annual review.
Risk	ONS to continue developing risks registers specifically related to individual country partnerships and develop their risk appetite	Completed. / The risk register now reflects country specific risks.
Overall	ONS to consider sustainability and exit of each of the partnerships and communicate this with partners	Completed. / ONS will make sure that each country workplan reflects the need for sustainability. Efforts have been made to include train the trainer events in all partner countries. / Exit strategies and ideal length of partnerships will be a focus of discussions in the second half of 2019, and a programme of work has been planned around this.
Additional:	It was suggested to change the output weights, so that all partner countries have an equal impact on the overall result (suggested to give 15% weight to each country), This will allow 40% weighting to be given to Flexible Facilities, which seems appropriate given the time spent.	Completed. Proposed by ONS in September 2018, and actioned.

ANNEX 1: Methodology for Indicators 1 and 2

Figure 3: Indicator 1- Measure of progress towards implementing the project workplan

0: No workplan in place

1: Potential areas for collaboration identified by not workplan developed

2: Clear workplan agreed between ONS and partner with tangible activities and measures of success identified

3: As per 2 with some quick wins taking place

4: As per 3 with measurable progress towards outputs taking place

5: All outputs in the workplan delivered

PARTNER	2017 (baseline)	2018 (target)	2018 (actual)	2019 (target)	2019 (actual)	2020 (target)
Kenya	0	2	1	4	4	5
Ghana	0	2	2	4	4	5
Rwanda	1	3	3	4	4	5
UNECA	0	2	1	4	4	5

Figure 4: Indicator 2 - Measure of partner commitment towards establishing effective partnership with ONS

0: Only a very preliminary indication of commitment from partner for partnership with ONS

1: Agreemetn that a partnership woudl be beneficial, but limited evidence of commitment from partner so far, content of partnersip and timings of visits largely being driven by ONS

2: Partner engaged with ONS, respond positively and quickly to suggestions or support, provides their views in an open and in a timely way eg. on priorities and timings for activities

3: Partner engages positively and proactively ensuirng that ONS support is being channelled to their most pressing needs

4: Agenda being fully driven by partner, setting the priorities, pushing ONS to deliver in a timely way
PARTNER	2017 (baseline)	2018 (target)	2018 (actual)	2019 (target)	2019 (actual)	2020 (target)
Kenya	0	2	1	3	3	4
Ghana	0	2	1	3	3	4
Rwanda	1	2	3	3	3	4
UNECA	0	2	2	3	2	4