Annual Review - Summary Sheet

Title: Mining Sector Reform Project
Programme Value: £ 28,433,000		Review Date: June - July 2015
Programme Code: 105 844	Start Date: 19/10/2011[1]	End Date: Project financial end date 30/04/17
[1] ProMines declared effective by the World Bank

Summary of Programme Performance
Year	2012	2013	2014	2015
Programme Score	C	B	B	A
Risk Rating	High	High	High	Low

Summary of progress and lessons learnt since last review

The Mining Sector Reform Project has this year scored an A. However this is against a dramatically reduced portfolio. The extractives programme was significantly scaled back in the period under review with the residual live components representing only a tiny fraction of the original spend. Thus the ‘A’ cannot be seen as an upwards trajectory from last year’s Annual Review as it does not compare like with like. Rather expectations are being met, but against a reduced ambition.

Since the last Annual Review, there was a successful exit from the ‘Growth with Governance in the Minerals Sector’ Technical Assistance Project (known as ProMines) in the DRC, effective from 4th November 2014. There are unspent funds in the World Bank Trust Fund which are yet to be returned to DFID, but DFID are working with the World Bank to resolve this.

The Accountable Grant with The Carter Centre on advocacy for transparency has reached its end, and was judged to be largely successful. We are in the process of approving funding for a second phase of this, to continue their important work with civil society on holding mining companies and the government to account on their transparency commitments.

Finally, work has begun on the scoping study for the Katanga Extractives Industries Development Initiative (KEIDI), a public-private partnership for Katanga province. The final report for this is expected in August.

Lessons learnt are outlined in more detail below, but these include, the length of time for resolution of the ProMines exit, the level of engagement needed for a relatively small Accountable Grant, and the length of time taken for the procurement processe of KEIDI.

Summary of recommendations for the next year

The main recommendations for the coming year are as follows:

1) Develop a new Business Case for the mining sector, in line with DFID’s current policies, and bring both future potential work with the Carter Centre and civil society, and the potential follow-up from KEIDI under it;

2) Close the existing programme by the end of the Carter Centre Phase 2 Accountable Grant;

3) Continue to monitor the cost effectiveness of the Carter Centre Accountable Grant and consider ways of reducing transaction costs;

4) Link mining sector programming more systematically to other DFID DRC and centrally managed programmes, particularly on governance, gender, environment and peace and stability in Eastern DRC;

5) Actively monitor manage the risks to mining sector programming stemming from the broader environment, in particular national elections and decoupage.

A. Introduction and Context

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/4145425.doc
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/4017477.xls

Outline of the programme

The context as outlined in the original project documentation has not significantly changed, and this is mirrored in the latest country poverty reduction diagnostic. DRC is a country with vast mineral wealth. According to World Bank calculations, the mining sector could contribute around 15-20% of GDP and 25% of Government revenues by 2020[2]. Extractives industries dominate exports (80-90%) and this has contributed hugely to recent growth. However, critical problems in the way in which the mining sector is governed have meant that the revenues generated from the sector have not been used effectively to contribute to sustainable economic development in DRC. Rent-seeking and corruption, insufficient institutional capacity, lack of credible information on mining sector assets, a weak policy, legal and regulatory framework and ongoing conflict in the East have all contributed to the dysfunctional administration of the sector at the national level. The role of State-Owned Enterprises in mining sector deals remains a source of controversy. There are relatively limited employment opportunities for Congolese in the industrial extractives industry. The formal private sector (excluding recently converted State Owned Enterprises) employs just 1.2% of labour force. At the local level, artisanal miners face challenges related to their access to mining areas, their illegal taxation by a multitude of private/ armed group and public state security actors and the lack of sufficient support they receive from the government of DRC. Artisanal and small-scale mining sites are also associated with serious environmental and social problems, including child labour and the sexual exploitation of women. Finally, Congolese NGOs active in this area often lack resources and expertise to hold government and companies to account.
[2] Figures from World Bank ProMines Project Appraisal Document

In this context, between 2011 and 2014 the UK provided £9 million out of the allocated £27 million through a World Bank-managed single donor trust fund for the ‘Growth with Governance in the Minerals Sector’ (ProMines) Technical Assistance Project in the DRC. It also allocated an additional £0.5 million to share the costs of a senior mining specialist within the Bank’s Kinshasa office for Project management and sector coordination. The World Bank contributed $50 million (£33 million) to the Project. In August 2014 the decision was taken by DFID to exit ProMines. Last year’s annual review detailed the reasoning behind this – but in summary this was based on poor progress of the project and concerns about the project’s ultimate ability to deliver on its objectives.

In addition to ProMines, the Mining Sector Reform Project also provides £1.24 million for General Support to the Minerals Sector of which the remaining £1.02 million was incorporated into this project from the Pilot Phase for DRC Minerals programme as a no cost extension in December 2012.

Out of this, a £136,927 Accountable Grant with The Carter Centre was funded, running from September 2013 to January 2015. This AG supports the third phase of TCC’s mining governance programme in the DRC. The ultimate goal of the programme is to increase accountability and transparency in DRC’s industrial mining sector. The specific Accountable Grant project works with civil society (specifically ACIDH[3], CdC[4], MMKi[5] and POM[6]) on advocacy for transparency to increase the Government of DRC and mining companies’ compliance with their information disclosure obligations, including, but not limited to, those found in: the new EITI Standard, the new Mining Code and Mining Regulation, ministerial decrees, contracts and conventions, corporate governance laws and international standards and best practices.
[3] l’Action Contre l’Impunité pour les Droits Humains
[4] Cadre de Concertation sur les Ressources Naturelles d’Ituri
[5] Maison des Mines des Kivus
[6] Plateforme des Organisations de la Societe Civile Intervenant dans le Secteur Minier

A scoping and design study for KEIDI, a public-private partnership whereby mining companies in Katanga can work with international donors to establish a socio-economic development programme in the province, is also being funded from this.The scoping study is being undertaken by Adam Smith International & JMN Consultants between May and August 2015.

The following diagram shows how current and planned programme activity contributes to reducing poverty in the DRC as analysed in the CPRD.

This Annual Review therefore covers the two existing activities – the Carter Centre Accountable Grant and the initial results of the KEIDI Scoping Study. The Carter Centre logframe will be used as the benchmark for measuring success as this has been the only ‘live’ logframe over the period of the review.

## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment

This has been a transition year for the extractives programme, with the successful exit from ProMines, and the subsequent extractives business case not yet fully developed. As such, progress towards outcome is judged on the basis of the Carter Centre Accountable Grant, which has met expectations.

Overall output score and description

Based on the Carter Centre logframe, the overall output score is A – met expectation. There were two main deliverables from this component, the analysis report of the legal and normative framework governing mining information, and the Transparency Index, a measure of the scope and quality of information available for mining projects in the DRC. Wider outcomes were improved capacity of CSOs and a positive contribution to the EITI process.

Key lessons

ProMines
The lessons learnt from engagement with ProMines were discussed in detail in the last Annual Review. In terms of lessons learnt from the exit itself, the process has been largely smooth so far with positive relations maintained with the Bank, but it has been incredibly lengthy and has still not reached its conclusion with DFID still awaiting the return of unspent funds.

The Carter Centre Accountable Grant
- Overall the engagement with The Carter Centre on this Accountable Grant has been positive, but there have been lessons learnt about setting clear objectives and common understanding at the start of the project, and expectations around reporting requirements.
- The Accountable Grant has needed a significant amount of hands-on management despite the small financial value of the grant. However it is judged that this has been worth the investment of time, given the Carter Centre’s unique placement to be able to undertake the work of capacity building of local CSOs. It is also expected that if we move forwards with a Phase 2 Accountable Grant we will be able to build positively on the existing relationship and incorporate lessons learnt.
- More specific lessons learnt over the course of the project are outlined in the challenges section for each output.

KEIDI Scoping Study
It was initially envisaged that this would take place under ProMines, however upon our exit we were informed by the World Bank that this would be dropped as part of the restructure process. DFID made the decision to pick up the activity themselves and tender under a local procurement process. The lesson here has been the extreme length of time for the procurement process, despite it being undertaken locally – almost 6 months from drafting ToRs to the supplier’s team arriving on the ground.

Key actions

Going forward, a new Business Case will be developed by the end of the year. It is likely that it will focus on three broad areas. At the national level, it will seek to build and expand on previous work aimed at improving the transparency and accountability for mining sector revenues from the industrial mining sector. At the provincial level, it will seek to leverage finance from mining companies and other donors to promote Katanga’s socio-economic development objectives through a public-private partnership vehicle. Finally, the Business Case may also consider concrete ways of improving the management of environmental impacts from mining as well as DFID’s potential support to artisanal miners in order to promote inclusive and sustainable growth.

Has the logframe been updated since the last review?

The ProMines logframe has now been dropped following DFID’s exit from the programme. As highlighted above, the Carter Centre logframe (which last year sat beneath the ProMines logframe) will be used for the purpose of this review. A new logframe will produced as part of the broader Extractives Business Case, which will incorporate the Carter Centre work, as well as the follow-up from KEIDI scoping.

## C: DETAILED OUTPUT SCORING

To note: output scoring for this Annual Review is against the logframe for The Carter Centre Accountable Grant (which last year sat beneath the overarching extractives / ProMines logframe) as it has been the only ‘live’ logframe linked to the extractives programme in the period of review.

Output Title	Local CSOs conduct thorough analyses of the current legal frameworks governing the mining sector.
Output number per LF		1	Output Score	A
Risk:		low	Impact weighting (%):	34
Risk revised since last AR?		n/a	Impact weighting % revised since last AR?	n/a

Indicator(s)	Milestones/ Target October 2013 – January 2015	Achieved	Status
1.1 Number of legal texts, norms, and standards analyzed (by ACIDH) in order to identify transparency obligations.	8	8	Outputs met expectation
1.2 Advocacy briefings developed based on legal framework analysis.	2	3	Outputs moderately exceeded expectation

Key Points

A sub grant was awarded by the Carter Centre to ACIDH to conduct legal and normative framework analysis based on transparency obligations in national and international regulations. A matrix of transparency obligations was developed in February - March 2014, and the subsequent analysis was turned into a report, including recommendations for revisions to the draft Mining Code. The report was then used to initiate advocacy activities with mining companies, government officials, international donors and other members of civil society.

In addition to this, the TCC also provided technical assistance to their partners CSOs for their contribution to the EITI process. A comprehensive methodology for collecting the contextual information required under the new EITI Standard was developed, and workshops were held to build CSOs capacity to analyse the EITI report’s scope and develop recommendations to improve it. Recommendations were submitted to the Multi-Stakeholder Group (MSG) in December 2014. Some concerns were addressed in the final report – but many were not.

Successes and challenges

In July 2014, the DRC was accepted as an EITI compliant country. This of course cannot wholly be attributed to the project, but its contribution to the process in terms of producing complementary analysis which was able to enhance the report is widely recognised.

Challenges related to the organisational structure and capacity of CSOs were initially encountered, however TCC noted that over the course of the project technical capacity significantly increased. This observation is supported by the findings of a recent field trip to Lubumbashi – the DFID team were impressed by first hand interactions with CSO partners who demonstrated a good understanding of mining sector issues.

Output Title	Local CSOs conduct monitoring of available information and continued gaps in government and company compliance.
Output number per LF		2	Output Score	A
Risk:		low	Impact weighting (%):	33
Risk revised since last AR?		n/a	Impact weighting % revised since last AR?	n/a

Indicator(s)	Milestones/ Target October 2013 – January 2015	Achieved	Status
2.1 List of information required to be disclosed for each mining project is developed.	List developed in Q1 2014	Yes	Outputs met expectation
2.2 Questionnaire for analyzing level of transparency of mining projects is developed.	Questionaire developed in Q3 2014	Yes	Outputs met expectation
2.3 Number of briefing notes drafted and submitted to mining companies or government entities based on Transparency Index analysis.	20	16	Outputs moderately did not meet expectation

Key Points

Under this component, CSOs used the Transparency Index tool to monitor available information and gaps in government and company compliance with national and international disclosure requirements. A Transparency Index questionnaire was developed containing indicators which encompassed the full EITI value chain but also extra information. At the start of this project, it was unclear whether the DRC would gain its compliant status with EITI or not, so development of the Transparency Index was one way to mitigate against this risk, as it offered another avenue for monitoring compliance and disclosure should the EITI process fail.

Based on a set of pre-defined criteria, mining companies were selected for assessment by CSOs against the Transparency Index. Desk and field research followed and workshops to discuss challenges, gaps, and initial recommendations. The Transparency Index Report was published in January 2015.

Challenges

There were a number of logisitical challenges which delayed the Transparency Index research and launch, including unpredictability and cancellations of UN flights making it hard to convene trainings and workshops for partners. The civil unrest in Kinshasa in January meant attendance at the report launch was limited.

CSOs faced challenges with Transparency Index research due to different levels of technical capacity of organisations, and the suspension of acitvities by one of the initial case study companies which meant a replacement case study was needed and associated delays.

Output Title	Local CSOs facilitate multi-stakeholder engagement in dialogue on and advocacy for transparency and information accessibility on mining activities in DRC.
Output number per LF		3	Output Score	A+
Risk:		medium	Impact weighting (%):	33
Risk revised since last AR?		n/a	Impact weighting % revised since last AR?	n/a

Indicator(s)	Milestones	Achieved	Status
Number of stakeholder meetings on mining sector transparency attended by local civil society organizations.	ACIDH - 3 / POM - 2 / CdC - 2 / MMKi - 2	ACIDH - 9 / POM - 9 / CdC - 3 / MMKi - 2	Outputs moderately exceeded expectation

Key Points

Under this component, CSOs engaged in multi-stakeholder dialogue on and advocacy for information transparency and accessibility based on the findings of the legal analysis report, the Transparency Index research and the EITI analyses.

There was an in-depth analysis of the 2011 EITI report, with a memo provided to the EITI Technical Secretariat which identified gaps. In response to this the EITI executive committee and technical secretariat worked to provide additional information in a complementary report which addressed these weaknesses.

TCC and CSO partners actively engaged in the Mining Code revision process under this component, receiving positive feedback from the Minister of Mines on this engagement as well as substantive feedback on specific issues.

There was engagement with key stakeholders around the launch of the Transparency Index report – and following the limited attendance at the launch event due to unrest in Kinshasa, a strategy was developed for alternative dissemination and advocacy, specifically through discussion on Radio Okapi and RFI and publication online including TCC’s Congo Mines website.

Successes and Challenges

Tight deadlines and shifting timelines for the EITI process posed challenges for TCC and CSOs’ engagement. However the project’s engagement with the process had a significant positive impact on both the 2011 report and DRC’s validation as EITI-compliant in July 2014. Feedback from the EITI International Secretariat was that information in the complementary report played a key role in the decision to lift DRC’s EITI suspension.

Delays in completing the Transparency Index meant there were knock on delays to planned advocacy activities, and civil unrest in Kinshasa in January compounded this, however alternative routes for dissemination and advocacy were found, and constructive dialogue has begun with key government and mining company stakeholders.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance

Over the period of the review cost drivers have been related to the Carter Centre Accountable Grant, and the scoping study for KEIDI. Cost drivers for the Carter Centre largely personnel and sub grant costs, as well as expenses relating to transport, office running costs and communications. Costs within the KEIDI scoping study relate to technical expertise from personnel, and associated expenses.

VfM performance compared to the original VfM proposition in the business case and assessment of whether the programme continues to represent value for money

The VfM metric in the business case related to ProMines and so cannot be applied to TCC Accountable Grant or the KEIDI scoping study. The KEIDI scoping study contract was awarded as part of a competitive tender process and the winning bid came out strongest of the three bids in the commercial evaluation demonstrating strong competitiveness of price and value for money. A new VfM proposition will be developed as part of the new extractives business case.

Quality of financial management

TCC’s Financial Management was timely, on a quarterly basis. Initial information gaps in quarterly financial reports were subsequently addressed in financial narrative reports covering the duration of the project.

Regarding ProMines, premature exit from the programme meant that DFID’s £27 million contribution specified in the Administration Arrangement was not made in full – only £9 million had been paid into the Trust Fund at the time of exit. At the time of the last Annual Review US$ 6.7 m of DFID funds had been spent. Subsequent conversations with the World Bank have indicated that the remaining funds were not fully committed against the procurement plan, and we are currently awaiting final confirmation from the World Bank about the balance that will be returned to DFID.

Date of last narrative financial report	April 2015 (The Carter Centre)
Date of last audited annual statement	March 2015 (The Carter Centre)

E: RISK

Overall risk rating: Low

Overview of programme risk

The exit from ProMines has significantly reduced DFID’s exposure. The residual risks to programme delivery are now considered to be low, given the programme’s limited areas of intervention. The table below provides an updated assessment of the external risks facing the programme

Risk	Probability	Impact	Mitigation Strategy	Update
Uneven commitment/ political will for sector-wide reform	High	High	Work with international development partners to achieve maximum influence over the GoDRC, including through the Groupe Thematique Mining, Hydrocarbons and Electricity and in consultation with the IMF / Expand network of contacts in government, civil society and the private sector to inform debates through a number of entry points	This risk materialised. The mitigation strategy was implemented, and has helped to some extent. Going forward, the new BC will need to retain flexibility to adapt to changing circumstances.
Reputational risk to DFID from poor programme delivery	Low	Low	Actively manage the risks associated with programme delivery	The exit from ProMines has significantly reduced DFID’s reputational risks. / It is judged that the residual risks to the programme are low.
Poor coordination with other sector interventions and activities and failure to take into account new developments	Low	Low	Coordinate with other sector interventions	The Carter Centre Accountable Grant was coordinated with other donors support (eg: GIZ support to POM) and joint monitoring arrangments were put in place. The KEIDI scoping study was also developed in conjucture with other donors, particularly USAID, who also sat on the technical evaluation panel.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe:

The Carter Centre Accountable Grant started on 1st October 2013 and was due to end 30th September 2014. The end date was extended to 31st January 2015 to allow for delays which occurred in the first few months of the project. The project logframe was adjusted to reflect this and the project remained on track against revised milestones for the remainder of its duration.

The KEIDI scoping study is still underway, but is on track against planned timeframe and deliverables.

Performance of partnership (s)

The partnership with the Carter Centre worked well, with the team highly engaged from the outset, and very quick to respond flexibly to DFID reporting requirements at an early stage. The team have also been very helpful in the wrap up of the first accountable grant as well as thinking through the potential phase 2. Looking forwards, if a phase 2 accountable grant is approved, the one slight area for adaption would be to formalise and regularise the in-person catch ups with the project coordinator, rather than having these on an ad hoc basis.

For the KEIDI scoping study, ASI were awarded the contract. There has also been a strong working relationship in this partnership so far, with open honest exchanges and DFID have been impressed by the capability of the ASI team.

Asset monitoring and control

n/a – there are no assets related to the Carter Centre Accountable Grant or the KEIDI scoping study contract.

G: CONDITIONALITY

Update on partnership principles (if relevant) : N/A

H: MONITORING & EVALUATION

Evidence and evaluation

Following the decision to exit ProMines, the theory of change and assumptions used in the extractives programme design will be revisited as part of the new extractives business case. In drafting the new business case the team will also look at latest evidence available to inform the proframme design and rationale. The original project appraisal document does not provide for a separate impact evaluation and, as at the last Annual Review, one is not anticipated for this phase of the programme.

Monitoring progress throughout the review period

In relation to the Carter Centre Accountable Grant, in addition to quarterly reporting, catch up meetings were held with the project team on a regular basis whenever they were in Kinshasa. In June 2015 there was a field visit made by the DFID programme manager, project officer and governance adviser to Lubumbashi to meet with TCC team and the downstream partners, the aim of which was to review the past accountable grant. This was a highly useful visit, offering an opportunity for the DFID team to engage directly with the civil society representatives. There was a comprehensive discussion on the successes and challenges of the programme, and direct feedback from CSOs was that their technical and organisational capacity, and ability to engage with processes such as EITI, had been strengthened by TCC support through the DFID Accountable Grant.

This Annual Review was conducted by the DFID DRC Economic Development team in July 2015, drawing on project documentation and reporting, findings from June 2015 visit to the Carter Centre field office in Lubumbashi, and meetings with the KEIDI scoping team.