## Mother
PROJECT NAME | Reducing Maternal & Neonatal Mortality 6 Countries
IMPACT | Impact Indicator 1 |  | Baseline (2011/12) | Milestone 1 (2012) | Milestone 2 (2014) | Milestone 3 (2015) | Target (2015/6)
Accelerated reduction in maternal and neonatal mortality | Maternal lives saved | Planned | Ethiopia: 0 Ghana: 0 Malawi: 0 Nigeria: 0 Sierra Leone: 0 Tanzania: 0 | Ethiopia: 420 Ghana: 20 Malawi: 70 Nigeria: 40 Sierra Leone: 20 Tanzania: 290 | Ethiopia: 2,500 Ghana: 150 Malawi: 420 Nigeria: 250 Sierra Leone: 110 Tanzania: 1,600 | Ethiopia: 3,600 Malawi: 590 Nigeria: 350 | Ethiopia: 5,000 Ghana: 280 Malawi: 770 Nigeria: 440 Sierra Leone: 200 Tanzania: 3,000 Total: 9,690
Achieved
Source
Multiple data sources used for projections - see LiST methodology
| Impact Indicator 2 |  | Baseline (2011/12) | Milestone 1 (2012) | Milestone 2 (2014) | Milestone 3 (2015) | Target (2015/6)
| Neonatal lives saved (excluding stillbirths) | Planned | Ethiopia: 0 Ghana: 0 Malawi: 0 Nigeria: 0 Sierra Leone: 0 Tanzania: 0 | Ethiopia: 3,900 Ghana: 350 Malawi: 330 Nigeria: 310 Sierra Leone: 180 Tanzania: 1,500 | Ethiopia: 23,000 Ghana: 2,100 Malawi: 1,800 Nigeria: 1,900 Sierra Leone: 1,100 Tanzania: 8,000 | Ethiopia: 32,200 Malawi: 2,500 Nigeria: 2,700 | Ethiopia: 43,800 Ghana: 4,000 Malawi: 3,700 Nigeria: 3,600 Sierra Leone: 2,100 Tanzania: 14,500 Total: 71,700
Achieved
Source
Multiple data sources used for projections - see LiST methodology
| Impact Indicator 3 |  | Baseline (2011/12) | Milestone 1 (2012) | Milestone 2 (2014) | Milestone 3 (2015) | Target (2015/6)
| Stillbirths averted | Planned | Ethiopia: 0 Ghana: 0 Malawi: 0 Nigeria: 0 Sierra Leone: 0 Tanzania: 0 | Ethiopia: 2,500 Ghana: 200 Malawi: 270 Nigeria: 180 Sierra Leone: 50 Tanzania: 900 | Ethiopia: 15,100 Ghana: 1,200 Malawi: 1,500 Nigeria: 1,100 Sierra Leone: 300 Tanzania: 5,300 | Ethiopia: 21,400 Malawi: 2,100 Nigeria: 1,600 | Ethiopia: 29,900 Ghana: 2,200 Malawi: 2,900 Nigeria: 2,100 Sierra Leone: 540 Tanzania: 10,000 Total: 47,640
Achieved
Source
Multiple data sources used for projections - see LiST methodology
OUTCOME | Outcome Indicator 1 |  | Baseline (2011/2) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 | Target (2015/6) | Assumptions
More and better, evidence-based, use of resources for MNH Ethiopia Resource allocation for MNH services informed by MDSR system Ghana Facilities equipped to save maternal and newborn lives Malawi Key resources for maternal and newborn health are in place at health facilities Nigeria Key resources for maternal and newborn health are in place at health facilities Sierra Leone Facilities equipped to save maternal and newborn lives Tanzania Facilities are equipped to save maternal and newborn lives | Use of evidence by national and sub-national health managers and health facility managers in their decision-making | Planned | Data for decision-making (DDM) scores: Ethiopia: 9% Ghana: 50% Malawi: 47% Nigeria: 43% Sierra Leone: 56% Tanzania: 53% Mean DDM score*: 50% * Mean excludes Ethiopia, because Ethiopia has a different indicator and a different method of score calculation. |  | Data for decision-making (DDM) scores: Ethiopia: 20% Ghana: 55%. Malawi: 53% Nigeria: 53% Sierra Leone: 61%. Tanzania: 58% Mean DDM score: 56% |  | Data for decision-making (DDM) scores: Ethiopia: 40% Ghana: 61% Malawi: 57% Nigeria: 63% Sierra Leone: 61% Tanzania: 60% Mean DDM score: %
Achieved
Source
Internal monitoring tool (DDM)
| Outcome Indicator 2 (all countries except Ethiopia) |  | Baseline (2012) | Milestone 1 (2013) | Milestone 2 (mid-2014) | Milestone 3 | Target (2015/6) | Assumptions
| Political will to improve quality of care and the use of evidence for decision-making | Planned | Politics, Power and Perception (PPP) scores: Ghana: 62% Malawi: 60% Nigeria: 54% Sierra Leone: 60% Tanzania: 60% Mean PPP score: 59% |  | Politics, Power and Perception (PPP) scores: Ghana: 70% Malawi: 65% Nigeria: 59% Sierra Leone: 65% Tanzania: 65% Mean PPP score: 65% |  | Politics, Power and Perception (PPP) scores: Ghana: 75% Malawi: 68% Nigeria: 64% Sierra Leone: 70% Tanzania: 68% Mean PPP score: % | Political instability does not undermine potential for impact. Governments receptive to efforts to increase political will. Project leverages additional resources to catalyse change. High-quality MNH data available. Theory of change is borne out in reality; more efficient use of resources plus improved use of data for decision-making plus increased political will leads to improved quality of care which leads to lives saved within 4 years. Ghana: Supportive supervision system increases BEmONC readiness at rural health facilities
Achieved
Source
Internal monitoring tool (PPP)
| Outcome indicator 3 |  | Baseline (year) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 (2015) | Target (2015/6)
| Ethiopia: Use of MDSR data in the MNH strategic planning process at national and regional level Ghana: % of facilities in E4A focal districts with an increased number of EmONC signal functions or facilitating factors (water, sanitation, electricity, transport) since 2011 Malawi: Number of district hospitals in 6 focal districts reporting stock-outs of antenatal corticosteroids in the preceding 3 months Nigeria: % of secondary facilities in 4 focal states with no stock-outs of magnesium sulphate over a 3-month period Sierra Leone: Number of health facilities in Bonthe and Koinadugu that are BEmONC compliant (according to Facilities Improvement Team criteria or another mechanism to measure facility readiness) Tanzania: Number of Government health centres in Mara providing CEmONC |  | Ethiopia (2012): In most regions, thre is no MDSR system. In some areas, MDRs are carried out, but the findings are not used in the strategic planning process Ghana (2011): 7 Malawi (May 2014): 5 Nigeria: Bauchi (2013): 43% Kano (2013): 22% Jigawa (2011): 25% Ondo (2013): 57% Sierra Leone (2012): 0 Tanzania (2012): 1 |  | Ethiopia: Regional planning and other resource allocation meetings include discussion of MDSR data Ghana: 9 Nigeria: Bauchi: 48% Kano: 33% Jigawa: 35% Ondo: 71% Sierra Leone: 4 Tanzania: 4 | Malawi: 4 | Ethiopia: National and regional strategic plans include priorities for resource allocation that reflect MDSR evidence Ghana: 10 Malawi: 3 Nigeria: Bauchi: 53% Kano: 44% Jigawa: 45% Ondo: 86% Sierra Leone: 8 Tanzania: 6
Achieved
Source
Ethiopia: meeting agendas, regional MDSR reports, regional strategic plans, National Health Sector Development Plan (HSDP-V) Ghana: AMDD EmONC Needs Assessment, QuIC Malawi: District Dashboard Nigeria: HMIS, ISS, E4A-commissioned data collection Sierra Leone: QuIC-FIT scorecards Tanzania: Mara strategy monitoring
| Outcome indicator 4 (Nigeria, Tanzania only) |  | Baseline (year) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 (2015) | Target (2015/6)
| Nigeria: % of secondary facilities in 4 states with a blood bank which has the capacity to store and screen blood Tanzania: % of live births in Mara attended by a doctor, clinical officer, nurse-midwife or MCH Aide |  | Nigeria: Bauchi (2013): 20% Kano (2013): 44% Jigawa (2012): 25% Ondo (2013): 43% Tanzania (2010): 30% |  | Nigeria: Bauchi: 25% Kano: 44% Jigawa: 40% Ondo: 57% Tanzania: 40 |  | Nigeria: Bauchi: 30% Kano: 56% Jigawa: 55% Ondo: 71% Tanzania: 45
Achieved
Source
Malawi: E4A-commissioned data collection (baseline), QuIC Nigeria: ISS, State MNH scorecard, E4A-commissioned data collection Tanzania: 2010 DHS, Mara strategy monitoring
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
19500000
INPUTS (HR) | DFID (FTEs)
0.5
OUTPUT 1 | Output Indicator 1.1 |  | Baseline (2011/2) | Milestone 1 (2012) | Milestone 2 (2014) | Milestone 3 (2015) | Target (2015/6) | Assumptions
Better information for better results: realising key parts of Commission on Information and Accountability (CoIA) recommendations in 6 countries. | Ethiopia: Maternal death surveillance and response (MDSR) system coverage: the number of focal regions and woredas implementing MDSR per national guidelines, with meetings occurring as stipulated in the guidelines Ghana: Use of MNH data for forward planning and resource allocation at district level. Malawi: Coverage of community maternal death reviews (c-MDRs). Nigeria, Sierra Leone: Coverage of maternal death reviews (MDRs) Tanzania: Coverage of maternal and perinatal death reviews (MPDRs) | Planned | Ethiopia: 0 (nascent system in Tigray; major hospitals only in other regions) Ghana: District Health Management Teams do not routinely review MNH evidence in their management meetings Malawi: There is no systematic approach to conducting community MDRs Nigeria: NGOs conduct MDRs in selected facilities. Elsewhere coverage is patchy. The efforts of different organisations are unco-ordinated. Sierra Leone: Facility-based MDR system recently piloted, but not yet rolled out. Tanzania: Most hospitals in Mara conduct MDRs, but it is not known whether they cover every maternal death, nor whether they use the nationally-approved protocol |  | Ghana: District Health Management Teams (DHMTs) in 6 focal districts have considered new MNH evidence at a management meeting. | Ethiopia: 2 (regional level and 23 focal woredas in Oromiya and Tigray) Malawi: c-MDRs conducted in 8 traditional authorities in 6 focal districts, according to the official guideline Nigeria: MDR data collected in all secondary facilities in 1 focal state, following standardised MDR guidelines and tools. | Ethiopia: 4 (regional level and all E4A focal woredas) Ghana: DHMTs in all 12 focal districts have considered new MNH evidence at a management meeting and used it for forward planning/resource allocation. Malawi: c-MDRs conducted in 18 traditional authorities in 6 focal districts, according to the official guideline Nigeria: MDR data collected in all secondary facilities in 2 focal states, following standardised MDR guidelines and tools. Sierra Leone: All designated CEmONC facilities in 2 focal districts conduct MDRs according to the national guideline Tanzania: All 8 hospitals in Mara region review maternal deaths according to the nationally-approved MPDR guidelines | High-quality data available. Government receptive to evidence-driven management culture. In-country partners receptive to capacity-building in data management and communication. Health service managers receptive to culture of 'no blame' performance management. Sufficient resources can be leveraged to collect data suitable for disaggregation to sub-national levels. Harmonisation among partners for better management of results is effective in practice. Theory of change is borne out in reality: better evidence (in combination with better advocacy and accountability) leads to improved quality of care, better use of evidence and increased political will within 4 years. Tanzania: Partners implementing MPDRs in non-E4A regions remain committed to the MPDR process Tanzania: RMNCH scorecard mechanism is launched in April 2014 and is functioning effectively through to 2016 Ethiopia: Ethiopian Public Health Institute continues to be committed to updating and managing an integrated database Ghana QuIC pilot will conclude that the methodology is suitable for rolling out more widely in Ghana Malawi QuIC pilot will conclude that the methodology is suitable for rolling out more widely in Malawi Tanzania: QuIC pilot will conclude that the methodology is suitable for rolling out more widely in Tanzania
Achieved
Source
Ethiopia: Training reports, committee ToRs/action plans, meeting schedules/agendas Ghana: meeting minutes, policy study Malawi: quarterly district MDSR reports Nigeria: State MDR reports Sierra Leone: MoHS reports Tanzania: National, district and regional MPDR committee meeting minutes and reports
| Output Indicator 1.2 |  | Baseline (2011/12) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 (2015) | Target (2015/6)
| Ethiopia: % of health facilities visited in the last quarter of the project year which are implementing MDSR according to the national guideline Ghana: Use of maternal death review (MDR) findings to identify and report problems in the system Malawi, Nigeria, Sierra Leone: Use of maternal death review (MDR) findings. Tanzania: Use of maternal death review (MPDR) findings | Planned | Ethiopia: No established MDSR system Ghana: Findings of MDRs are not being routinely used to identify and report problems in the system Malawi: The quality of facility MDR findings is not always good and it is difficult to maintain anonymity, so the findings are not always used to prevent further deaths. Nigeria: Findings of NGO-led MDRs are being used to improve service delivery in selected facilities. Elsewhere, teams are just being set up to review MDR findings and make recommendations. Sierra Leone: Findings of MDR pilot not yet used to prevent further deaths Tanzania: There is little follow-up on MDR findings |  | Ethiopia: Supportive supervision visits in all 4 focal regions/cities include the completion of a checklist/guide to establish whether the national guideline is being followed Ghana: E4A supported training on MDR feedback delivered to Ghana Health Service staff in 6 focal districts Malawi: Feedback mechanism operates via quarterly meetings in 6 districts Sierra Leone: National guideline on strengthening MDR response developed Tanzania: Training of hospital staff from 8 hospitals in Mara region on how to use MPDR findings (action and response) | Ethiopia: 33% Malawi: Data on factors contributing to maternal death in 6 districts disseminated to key stakeholders Nigeria: State review teams in 1 focal state track progress on implementation of MDR recommendations through bi-annual state-level scorecards | Ethiopia: 66% Ghana: E4A-supported training on MDR feedback delivered to Ghana Health Service staff in all 12 focal districts. MDR findings inform and are discussed by DHMTs during their quarterly meetings Malawi: 30% of MDR recommendations made in 2014 have been implemented Nigeria: State review teams in 2 focal states track progress on implementation of MDR recommendations through bi-annual state-level scorecards Sierra Leone: Mechanism in place in 2 focal districts for ensuring recommendations based on MDR findings are actioned. Plan for rolling out this mechanism nationally submitted to MoHS Tanzania: All MPDR Committees in Mara region (1 regional and 6 district) use MPDR data from health facilities to inform their decision-making, including resource allocation
Achieved
Source
Ethiopia: Analysis of completed checklists Ghana: DHMT meeting records Malawi: Quarterly meeting notes/action points; MDR follow-up forms Nigeria: scorecards and associated documents Sierra Leone: National guideline, mechanism outputs Tanzania: MPDR committee minutes and reports
| Output Indicator 1.3 |  | Baseline (2011/12) | Milestone 1 ( 2013) | Milestone 2 (mid-2014) | Milestone 3 (2015) | Target (2015/6)
| Ethiopia: Use by regional MDSR committees of MDSR data disaggregated by geography Ghana: Use of disaggregated maternal and newborn data (including indicators from the CoIA list) in progress and performance reviews Malawi: Use of disaggregated maternal and newborn indicators in progress and performance reviews at district level Nigeria, Tanzania: Use of disaggregated maternal and newborn indicators from the CoIA list in progress and performance reviews. Sierra Leone: Availability of disaggregated data on maternal and newborn indicators from the CoIA list | Planned | Ethiopia: No disaggre-gated MDSR data. Limited use of disaggre-gated MDR data in Tigray/Addis. No regional MDSR committees Ghana: Disaggregated data available for some CoIA indicators, but limited use in reviews and target-setting Malawi: Data from national surveys (e.g. DHS) are disaggregated to district level, but there are no ‘real time’ disaggregated data at district level Nigeria: Disaggregated data available for most MNH indicators, and used to some extent in reviews, but state-level data not generally available Sierra Leone: Disaggregated data available for 9 CoIA indicators, transparently reported, but not used in reviews Tanzania: Disaggregated data used in reviews to some extent |  | Ethiopia: Regional MDSR committees in two regions/cities have discussed disaggregated MDSR data at least once Ghana: Census workshop with MNH stakeholders Malawi: At least one round of data collection complete for the District Dashboard in all 6 focal districts Nigeria: MNH scorecards are populated bi-annually, and results discussed by State review team in 1 focal state Sierra Leone: Set of MNH indicators agreed at national level, including indicators from the CoIA list (the Sierra Leone indicator index) Tanzania: Disaggregated data used at a 6-monthly review meeting to evaluate progress against the 2013-2015 Mara Strategy | Ethiopia: Regional MDSR committees in all 4 regions/cities have discussed disaggregated MDSR data at least once Malawi: District Dashboard data collected at least twice a year in 4 focal districts Nigeria: MNH scorecards populated bi-annually, and results discussed by State review teams in 2 focal states Sierra Leone: HMIS upgraded to collect data on Sierra Leone indicators, disaggregated by district, and by age and sex as appropriate | Ethiopia: MDSR data (disaggregated by geography) is a standing item at regional MDSR committee meetings Ghana: Data on EmONC signal functions and health facility infrastructure disaggregated to health facility level disseminated and shared with GoG Malawi: DHSCs in 5 districts meet at least twice a year and produce recommendations/action plans informed by District Dashboard data Nigeria: Scorecards with disaggregated MNH data are populated bi-annually and disseminated to MTSS review teams in 2 focal states, and are used by them to inform decisions about resource allocation Sierra Leone: Disaggregated data on the Sierra Leone indicators communicated to MoHS and other stakeholders, for use in their progress and performance reviews Tanzania: Disaggregated data from the national scorecard are discussed by decision-makers at regional and district levels in 6 districts in Mara region at their regular meetings
Achieved
Source
Ethiopia: MDSR Committee meeting schedules/agendas Ghana: Workshop records, event records, stakeholder interviews Malawi: District Dashboard, DHSC meeting records Nigeria: Scorecards, State review team meeting minutes, SMS messages, MTSS meeting minutes, presentations with FMoH, DDM data, qualitative investigation, desk research Sierra Leone: National report, MoHS reports. Tanzania: Training records/materials, MPDR Committee minutes/reports
| Output Indicator 1.4 |  | Baseline (2011/12) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 (2015) | Target (2015/6)
| Ethiopia: Development of a database integrating data for IDSR (Integrated Disease Surveillance and Response) and MDSR (Maternal Death Surveillance and Response) Ghana: Coverage of mobile phone data capture system to monitor health facility readiness and ability to perform signal functions Malawi: Coverage of mobile phone data capture system to monitor health facility readiness and ability to perform signal functions (QuIC) Nigeria: Use of MNH evidence to support the development of annual state health sector plan and budgets Sierra Leone: Availability and accessibility of data on key MNH outcomes Tanzania: Coverage of QuIC data collection system to monitor health facility readiness and ability to perform signal functions | Planned | Ethiopia: IDSR database does not include MDSR data Ghana: Mobile phones are not used to monitor health facility readiness and ability to perform signal functions Malawi: Mobile phones are not used to monitor health facility readiness and ability to perform signal functions Nigeria: No system for MNH data to feed into annual plans and budgets Sierra Leone: MoHS Facility Improvement Team (FIT) Assessments conducted quarterly, but findings poorly communicated and assessment system too resource-intensive to be sustainable Tanzania: No QuIC data collection system |  | Ethiopia: Structure of integrated database is agreed and database is ready to be populated. Ghana: QuIC system is used to capture data from 67 health facilities in 16 districts Malawi: QuIC system is used to capture data from 35 health facilities in 4 districts Sierra Leone: First round of QuIC/QuIC-FIT system used to capture data from 22 health facilities in 2 focal districts Tanzania: One round of QuIC data collection completed in at least 50 health facilities in 6 focal districts | Ethiopia: Database is populated with up-to-date MDSR data from 4 regions Ghana: At least two rounds of QuIC completed in 16 districts Malawi: At least two rounds of QuIC data capture completed in 4 districts Nigeria: MNH data used by MTSS review teams in 1 focal state to develop annual state health sector strategies and budgets Tanzania: National stakeholder meeting convened to review QuIC pilot and discuss scaling up of the system beyond pilot districts | Ethiopia: Regional MDSR committees in all E4A focal regions/cities produce annual report informed by database Ghana: Plan for scaling up coverage of QuIC developed and shared with GHS Malawi: Plan developed for scaling up coverage of QuIC beyond 4 districts, and shared with MoH Nigeria: MNH data used by mid-term sector review teams in 2 focal states to develop annual state health sector strategies and budgets Sierra Leone: National MDR database established. District dashboard mechanism established (populated with baseline data) in 2 focal districts, containing data from DHIS, QuIC/QuIC-FIT and MDR database Tanzania: Plan for scaling up coverage of QuIC beyond Mara region developed, and shared with MoH
IMPACT WEIGHTING (%) |  | Achieved
31 |  | Source
Ethiopia: Database outputs, validation study report, regional MDSR Committee reports Ghana: QuIC documentation Malawi: QuIC documentation and outputs from hand-held devices Nigeria: MTSS meeting minutes Sierra Leone: QuIC documentation, outputs from the national MDR database, MoHS HMIS reports and District Dashboard outputs. Tanzania: QuIC documentation, meeting minutes/reports, protocol for scaling up of QuIC
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%) | RISK RATING
| 6045000 | [6 empty] | Medium
INPUTS (HR) | DFID (FTEs)
0.2
OUTPUT 2 | Output Indicator 2.1 |  | Baseline (2011/12) | Milestone 1 | Milestone 2 (2014) | Milestone 3 (2015) | Target (2015/6) | Assumptions
Political leadership and public momentum | Ethiopia: Integration of national MDSR guidelines in training and strategic plans Ghana: Percentage of MamaYe! press releases that lead to a published article or are featured on radio/TV, without incentive Malawi: Number of national TV programmes covering MNH issues, and number of district-level broadcasts/ publications covering MNH issues Nigeria: Number of news articles in a 3-month period making reference to MNH, in newspapers (including online) Sierra Leone: Percentage of MamaYe! press releases that lead to a published article in at least one newspaper, without incentive Tanzania: Local media coverage of MNH issues | Planned | Ethiopia: No national guidelines Ghana: No MamaYe! press releases Malawi: No regular national TV programmes about MNH, and very little coverage of MNH at district level Nigeria: 33 Sierra Leone: No MamaYe! press releases Tanzania: No local-level media journalists have been sensitised to the MamaYe campaign |  | Ethiopia: Training schools in 2 focal regions/cities have had orientation sessions on the MDSR system Ghana: Engaged advocates/ activists list includes 30 journalists sensitised to the campaign via training events or individual meetings Malawi: 10 programmes aired on national TV, which cover MNH issues. District-level journalists publish or broadcast at least 2 MNH stories per quarter Nigeria: 50% increase since 2012 in the number of news articles Sierra Leone: Engaged advocates/activists list includes 20 journalists sensitised to the campaign via training events or individual meetings Tanzania: Engaged advocates/activists list includes journalists from at least 19 regions, sensitised to the MamaYe campaign via training events | Ethiopia: Training schools in 4 focal regions/cities have had orientation sessions on the MDSR system Malawi: 6 programmes aired on national TV, which cover MNH issues. District-level journalists publish or broadcast at least 2 MNH stories per quarter Nigeria: 100% increase since 2012 in the number of news articles. Plans in place for launch of investigative MNH media fellowship. | Ethiopia: New health sector strategic plan includes MDSR and how data will be captured and used in MNH quality improvement Ghana: 50% Malawi: 3 programmes aired on national TV since November 2015, which cover MNH issues. District-level journalists publish or broadcast at least 2 MNH stories per quarter Nigeria: 150% increase since 2012 in the number of news articles. Investigative MNH media fellowship awarded annually. Sierra Leone: 50% Tanzania: Community radio stations in at least 19 regions feature MNH stories generated by local journalists who are MamaYe advocates/activists | Malawi MBC TV remains committed to producing a regular MNH show, and continues to provide airtime for it without charge Tanzania: Union of Tanzanian Press Club continues to be committed to carrying out regular monitoring of community media houses’ outputs
Achieved
Source
Ethiopia: Orientation session records, Health Sector Development Plan (HSDP-V) Ghana: Internal monitoring tool Malawi: media monitoring tool, recordings of national TV programmes Sierra Leone: Internal monitoring tool. Tanzania: Training session attendance lists, Union of Tanzanian Press Clubs' monitoring of community media houses, supported by E4A
| Output Indicator 2.2 |  | Baseline (2011/2) | Milestone 1 (2012) | Milestone 2 (2013) | Milestone 3 (2015) | Target (2015/6) | Assumptions
| Ethiopia: Number of community/religious leaders, local politicians, media representatives and CSOs engaged via E4A activities. Ghana, Malawi, Nigeria, Sierra Leone, Tanzania: Number of advocates and activists engaged through E4A-supported national advocacy campaign. Note: ‘engaged’ is defined as committed to E4A goals, and empowered by E4A with the power (evidence, information and/or strategy) to make change (real outcomes) | Planned | 0 in all countries |  |  | Ethiopia: 300 Malawi: 100 Nigeria: 400 | Ethiopia: 450 Ghana: 200 Malawi: 150 Nigeria: 600 Sierra Leone: 60 Tanzania: 300 | Advocacy groups receptive to working under unified national campaign. Advocacy messages do not create unforeseen conflict and tension. Political environment is conducive to independent media. Local and national media are receptive to using credible evidence for responsible reporting. Advocacy groups have potential for capacity development in branding, messaging and communication. Adequate numbers of skilled health workers are available to deliver improved quality of care (in both urban and rural areas). Theory of change is borne out in reality: better advocacy (in combination with better evidence and accountability) leads to improved quality of care, better use of evidence and increased political will within 4 years.
Source
Internal monitoring tools
| Output Indicator 2.3 |  | Baseline (2011/12) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 (2015) | Target (2015/6)
| Accessibility of relevant MNH information and resources for stakeholders. | Planned | Basic evidence and core documents that would be essential for planning, decision-making and advocacy are largely difficult to access, badly packaged, badly communicated and time-consuming to locate. There is a lack of synthesis and information-sharing between MNH initiatives. |  | Countries other than Ethiopia: Improved functionality of website via updates to structure of evidence pages | Ethiopia: MDSR documentation available on WHO website: guidance, training materials, policy briefs, case studies (including use of data and actions taken) | Ethiopia: Up-to-date MDSR documentation available on WHO website: guidance, training materials, policy briefs, updated case studies on using MDSR to improve MNH, appropriate links to FMoH website Ghana, Malawi, Nigeria, Sierra Leone, Tanzania: Website is contributing to raised awareness of MNH by regular updates to the content, including technical updates, new evidence added at least quarterly, and links to other relevant websites
Achieved
Source
E4A country design reports, website analytics, user feedback, website content
| Output Indicator 2.4 (not Ethiopia) |  | Baseline (2011/2) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 (2015) | Target (2015/6)
| Mean number of visits to national website per month, with "visits" as defined by Google Analytics at http://support.google.com/analytics/answer/2731565?hl=en-GB&topic=2524483&ctx=topic | Planned | 0 in all countries |  | Ghana: 820 Malawi: 580 Nigeria: 900 Sierra Leone: 700 Tanzania: 830 | Malawi: 650 Nigeria: 1,000 | Ghana: 950 Malawi: 700 Nigeria: 1,300 Sierra Leone: 800 Tanzania: 900
Achieved
Source
Google Analytics
IMPACT WEIGHTING (%) | Output Indicator 2.5 (not Ethiopia) |  | Baseline (2011/2) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 (2015) | Target (2015/6) | Assumptions
28 | Ghana, Nigeria, Sierra Leone: Adoption of MamaYe! campaign by key engaged advocates/activists Malawi: Number of MamaYe! clubs trained in 6 focal districts, and number of MNH seminars at the Kamuzu College of Nursing Tanzania: White Ribbon Alliance (Tanzania)’s capacity to influence MNH policy at national level | Planned | Ghana: No MamaYe! campaign or engaged advocates/activists Malawi: 0 Nigeria: No MamaYe! campaign Sierra Leone: MNH advocates and activists exist, but there is no co-ordination of effort on the MamaYe! ask and sub-asks Tanzania: White Ribbon Alliance (Tanzania) has only a weak institutional and operational base |  | Malawi: 6 MamaYe clubs trained, and 10 KCN seminars over the period November 2013 – October 2014 Sierra Leone: Activist engagement package delivered to district-level focal points, CSOs and partner organisations in 2 districts Tanzania: Formal capacity assessment carried out on WRA Tanzania, which informs institutional and operational capacity-building | Malawi: 10 KCN seminars over the period November 2014 – October 2015 Nigeria: MamaYe! activists advocate for E4A ask in Kano and Jigawa | Ghana: Advocacy Coalition partners and other stakeholders use MamaYe! branding for their own activities Malawi: 10 MamaYe clubs trained and 4 KCN seminars over the period November 2015-March 2016 Nigeria: MamaYe! activists advocate for E4A ask in all four focal states Sierra Leone: MamaYe! activists advocate for MamaYe! ask / sub-asks at national level Tanzania: E4A-supported evidence-based strategic planning process complete, resulting in a draft 5-year strategy for WRA Tanzania which is aligned with national commitments | Malawi: KCN remains committed to hosting the seminar series.
Achieved
Source
Ghana: E4A country reports, internal M+E reports, stakeholder interviews Malawi: MamaYe club reports, internal monitoring reports, stakeholder interviews Nigeria: Internal records of activist activities, media reports, meeting records Sierra Leone: 'Activist engagement package' records, E4A-commissioned operational research, records of the actions of activists Tanzania: Capacity assessment tool, WRA strategic plan, records of WRA activities
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%) | RISK RATING
Medium
5460000
INPUTS (HR) | DFID (FTEs)
0.1
OUTPUT 3 | Output Indicator 3.1 (not Ethiopia) |  | Baseline (2011/12) | Milestone 1 (mid-2013) | Milestone 2 (2014) | Milestone 3 (2015) | Target (2015/6)
Accountability & transparency mechanisms: Better oversight and transparency of the provision of maternal and neonatal health (MNH) services, for better accountability for mothers and their babies. | Ghana: Use of national accountability mechanisms to hold district health managers to account for the status of MNH services in E4A focal districts Malawi: Multi-sectoral, evidence-based community level accountability mechanisms in place, which include District health sub-committees Nigeria: National- and State-level accountability mechanism for service delivery Sierra Leone: Transparency of RCH budget Tanzania: RMNCH budget advocacy forms key activity for civil society coalition | Planned | Ghana: District health managers report regularly to regional health managers, but there are no clear, objective benchmarks for holding them accountable for service delivery Malawi: No district health sub-committees in E4A focal districts Nigeria: Some state-level accountability mechanisms for service delivery exist, but none uses data effectively to provide government with feedback on progress and action that needs to be taken Sierra Leone: No mechanism for budget tracking Tanzania: No co-ordinated advocacy on RMNCH funding and spend |  | Ghana: In 8 focal districts, there has been at least one round of data collection using the MNH scorecard mechanism Malawi: At least one District Health sub-committee meeting in 3 focal districts to produce action plans with use of evidence Kano and Jigawa Sierra Leone: National Health Accounts established with ability to isolate MNCH spending Tanzania: Supported provided to WRA(Tz) to increase their capacity for budget advocacy | Malawi: At least one District Health sub-committee meeting in 3 more focal districts to produce action plans with use of evidence Nigeria: Accountability mechanism to track progress against MNH commitments is multi-sectoral and meeting quarterly, both nationally and at State level in 1 focal state | Ghana: in 8 focal districts, data are collected every 6 months using the MNH scorecard mechanism, and results reviewed by district authorities Malawi: District health sub-committees in 6 districts meet twice per year and make action plans based on MNH evidence, which include resource allocation Nigeria: Accountability mechanism to track progress against MNH commitments is multi-sectoral and meeting quarterly, both nationally and at State level in 2 focal states Sierra Leone: Status of national MNCH financing is made publicly available on MamaYe website and used by members from the budget tracking consortiumto hold decision makers to account Tanzania: RMNCH financing is a key strategic objective for WRA (Tanzania) in its strategic plan for 2015-2020
Achieved
Source
Ghana: E4A country design reports, scorecard outputs, district authority meeting records Malawi: Internal monitoring tools, DHSC minutes/action plans Nigeria: Key stakeholder interviews with policy- and decision-makers and members of the mechanism, meeting minutes, media reports, desk research. Sierra Leone: National Health Accounts, scorecard outputs, press cuttings, records of CSO advocacy activity. Tanzania: Materials presented to WRA, WRA Strategic Plan, records of WRA activities.
| Output Indicator 3.2 |  | Baseline (2011/12) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 (2015) | Target (2015/6) | Assumptions
| Number of people supported to hold decision-makers to account in relation to MNH. | Planned | Ethiopia: 0 Ghana: 0 Malawi: 0 Nigeria: 0 Sierra Leone: 0 Tanzania: 0 |  | Ethiopia: 2,500 Ghana: 16,000 Malawi: 10,000 Nigeria: 18,000 Sierra Leone: 7,000 Tanzania: 10,000 | Ethiopia: 3,500 Malawi: 15,000 Nigeria: 25,000 | Ethiopia: 4,500 Ghana: 30,000 Malawi: 17,000 Nigeria: 34,000 Sierra Leone: 10,000 Tanzania: 26,000 | Appropriate civil society groups with potential to form accountability mechanisms exist. Political environment enables independent and legitimate accountability mechanisms to be established. National and subnational governments receptive to transparency of information and budgeting. Media are receptive to using credible evidence for responsible reporting. Accountability mechanisms able to enforce effective sanctions. Adequate numbers of skilled health workers are available to deliver improved quality of care (in both urban and rural areas). Theory of change is borne out in reality: better accountability (in combination with better advocacy and evidence) leads to improved quality of care, better use of evidence and increased political will within 4 years.
Achieved
Source
Internal monitoring tools
| Output Indicator 3.3 (Ethiopia & Ghana only) |  | Baseline (2011/2) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 (2015) | Target (2015/6)
| Ethiopia: Number of regions and health facilities producing MDSR action plans Ghana: Mechanism to encourage service providers to report their training and resource needs | Planned | Ethiopia: 0 Ghana: No supportive supervision system exists |  | Ethiopia: At least 1 hospital or health centre in each focal zone/city produces an action plan based on that facility’s MDSR data. Ghana: In 1 region (4 districts), teams are allocated to support supervision in districts. They visit at least once every 6 months and make a record of needs. | Ethiopia: All 4 focal regions produce an action plan based on data from that region’s MDSR system. At least 3 hospitals or health centres in each focal zone/city produce an action plan based on that facility’s MDSR data. | Ethiopia: All 4 focal regions produce an action plan based on data from that region’s MDSR system. At least 4 hospitals or health centres in each focal zone/city produce an action plan based on that facility’s MDSR data Ghana: In 2 regions (8 districts), team are allocated to support supervision in districts. They visit at least once every 6 months and make a record of needs. One supervision partner adopts the supportive supervision system and commits to continuing with it post-E4A.
Achieved
Source
Ethiopia: MDSR committee action plans at regional and facility level Ghana: Supportive supervision visit records, supervision partner records (e.g. meeting minutes)
IMPACT WEIGHTING (%) | Output Indicator 3.4 (Ethiopia only) |  | Baseline (2011/2) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 (2015) | Target (2015/6) | Assumptions
31 | Ethiopia: Percentage of MDSR recommendations from 2014 action plans which have been implemented | Planned | 0 |  | System in place for monitoring the number (and %) of recommendations which have been implemented | 30% | 50%
Achieved
Source
Monitoring system outputs
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%) | RISK RATING
| 6045000 | [6 empty] | Medium
INPUTS (HR) | DFID (FTEs)
0.1
OUTPUT 4 | Output Indicator 4.1 |  | Baseline (2011/12) | Milestone 1 (mid-2013) | Milestone 2 (2014) | Milestone 3 (2015) | Target (mid-2016)
Better alignment between national and regional MNH initiatives, including the realisation of Commission on Information and Accountability (CoIA) goals. | E4A countries' contribution to the CoIA learning process at the global level | Planned | CoIA aware of the existence of E4A and willing in principle to work together |  | ‘Evidence, Advocacy and Accountability Mid-term Lessons Learnt Brief’ produced by core team and communicated effectively to level 1 and level 2 partners at the global and regional level | Africa Health Budget Network has produced at least two quarterly newsletters and contributed to at least one regional event | Report submitted to the Independent Expert Review Group confirming that lessons have been learned in relation to supporting the development of country accountability mechanisms for MNH (and detailing what has been learned), including recommendations
Achieved
Source
Outline of proposed engagement between E4A and CoIA (Feb 2012), internal monitoring (email lists, meeting minutes, invitations to events), 'Lessons Learnt' brief, stakeholder interviews during DfID Annual Reviews.
| Output Indicator 4.2 |  | Baseline (2011/12) | Milestone 1 (mid-2013) | Milestone 2 (2014) | Milestone 3 (2015) | Target (mid-2016) | Assumptions
| Influence of CARMMA on MNH-relevant decisions made by heads of state and relevant ministries | Planned | E4A's advocacy team has engaged with CARMMA and relevant stakeholders, and identified significant potential for increasing CARMMA's capacity to influence decision-makers to effect positive change in MNH |  | Launch by CARMMA of regional award scheme to recognise good work in MNH by individuals or organisations in Africa. | Representatives of all E4A countries attend regional meetings/ conferences to raise the profile of MNH as an issue and share learning about the impact of the use of scorecards and best practice examples in national campaigns | African Health Stats website launched by the African Union Commission, strengthening transparency and accountability through improved access to evidence about progress against commitments | Global and regional political commitment to MNH is sustained. National programmes are able to draw on available regional resources. MDSR working group continues to exist. CARMMA continues to exist. Use of CARMMA comparative data/scorecards provokes action to improve maternal and newborn survival. CoIA remains willing to work together with E4A.
Achieved
Source
E4A advocacy strategy, media coverage of CARMMA award scheme, records of regional meetings/conferences, stakeholder interviews during DfID Annual Reviews.
IMPACT WEIGHTING (%) | Output Indicator 4.3 |  | Baseline (2011/12) | Milestone 1 (Feb 2013) | Milestone 2 (2014) | Milestone 3 (2015) | Target (mid-2016)
10 | Regional and national capacity for implementation of maternal death surveillance and response (MDSR) | Planned | MDSR working group exists, but unable to meet the increasing demands for ongoing, practical and technical assistance for MDSR implementation and scale-up |  | Professional MDSR, training and knowledge sharing network established in conjunction with the MDSR working group, to support scale-up of MSDRs regionally. Database of network members established. At least twice a year, updates sent by email on available MDSR resources, training opportunities and available technical guidance based on identified need | National MDSR networks in the six E4A focus countries are set up such that they function nationally as well as members being connected to the global MDSR network. In at least 3 countries, teams convene a virtual network of interested stakeholders | MDSR network institutionalised within an appropriate agency as a long-term resource for countries. Document and publish the experiences with action/response (within MDSRs) from the 6 E4A countries, in improving quality of care at regional and country levels and share with the MDSR working group
Achieved
Source
Database of network members (regional and national), copies of emails sent to members, MOU (or similar) with agency taking over the network in 2016, publications
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%) | RISK RATING
| 1950000 | [6 empty] | Medium
INPUTS (HR) | DFID (FTEs)
0.1

## Ethiopia
PROJECT NAME | Reducing Maternal & Neonatal Mortality Ethiopia
IMPACT | Impact Indicator 1 |  | Baseline (2011/12) | Milestone 1 (2012) | Milestone 2 (2014) | Milestone 3 (2015) | Target (mid-2016)
Accelerated reduction in maternal and neonatal mortality | Maternal lives saved | Planned | 0 | 420 | 2500 | 3600 | 5000
Achieved
Source
Multiple data sources used for projections - see LiST methodology
| Impact Indicator 2 |  | Baseline (2011/12) | Milestone 1 (2012) | Milestone 2 (2014) | Milestone 3 (2015) | Target (mid-2016)
| Neonatal lives saved (excluding stillbirths) | Planned | 0 | 3900 | 23000 | 32200 | 43800
Achieved
Source
Multiple data sources used for projections - see LiST methodology
| Impact Indicator 3 |  | Baseline (2011/12) | Milestone 1 (2012) | Milestone 2 (2014) | Milestone 3 (2015) | Target (mid-2016)
| Stillbirths averted | Planned | 0 | 2500 | 15100 | 21400 | 29900
Achieved
Source
Multiple data sources used for projections - see LiST methodology
OUTCOME | Outcome Indicator 1 |  | Baseline (2012/3) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 (2015) | Target (mid-2016) | Assumptions
Resource allocation for MNH services informed by MDSR system | Data for decision-making (DDM) score | Planned | 9% |  | 20% |  | TBC | Political instability does not undermine potential for impact. Project leverages additional resources to catalyse change. Theory of change is borne out in reality; improved use of MDSR data for decision-making leads to improved quality of care which leads to lives saved within 4 years.
Achieved
Source
Internal monitoring tools (DDM)
| Outcome Indicator 3 (no outcome indicator 2 in Ethiopia) |  | Baseline (2012) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 (2015) | Target (mid-2016)
| Use of MDSR data in the MNH strategic planning process at national and regional level | Planned | In most regions, there is no MDSR system. In some areas, MDRs are carried out, but the findings are not used in the strategic planning process |  | Regional planning and other resource allocation meetings include discussion of MDSR data |  | National and regional strategic plans include priorities for resource allocation that reflect MDSR evidence
Achieved
Source
Statement (April 2012) from maternal health adviser at MoH (baseline), meeting agendas, regional MDSR reports, regional strategic plans, fifth National Health Sector Development Plan
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
2925000
INPUTS (HR) | DFID (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline (2011/2) | Milestone 1 (2012) | Milestone 2 (2013) | Milestone 3 (2015) | Target (2016) | Assumptions
Better information for better results: realising key parts of Commission on Information and Accountability (CoIA) recommendations in 6 countries. | Maternal death surveillance and response (MDSR) system coverage: the number of focal regions and woredas implementing MDSR per national guidelines, with meetings occurring as stipulated in the guidelines | Planned | 0 (nascent system in Tigray; major hospitals only in other regions) |  |  | 2 (regional level and 23 focal woredas in Oromiya and Tigray) | 4 (regional level and all E4A focal woredas) | Government receptive to evidence-driven management culture. In-country partners receptive to capacity-building in data management and communication. Health service managers receptive to culture of 'no blame' performance management. Harmonisation among partners for better management of results is effective in practice. Additional funds leveraged to extend activities to 2 focus regions in addition to Oromia and Tigray. Ethiopian Public Health Institute continues to be committed to an integrated database
Achieved
Source
Training reports, MSDR committee terms of reference/action plans, MDSR committee meeting schedules/agendas
| Output Indicator 1.2 |  | Baseline (2011/12) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 (2015) | Target (mid-2016)
| % of health facilities visited in the last quarter of the project year which are implementing MDSR according to the national guideline | Planned | No established MDSR system |  | Supportive supervision visits in all 4 focal regions/cities include the completion of a checklist/guide to establish whether the national guideline is being followed | 33% | 66%
Achieved
Source
Completed checklists/guides
| Output Indicator 1.3 |  | Baseline (2011/12) | Milestone 1 (2012) | Milestone 2 (2014) | Milestone 3 (2015) | Target (mid-2016)
| Use by regional MDSR committees of MDSR data disaggregated by geography | Planned | No disaggregated MDSR data. Limited use of disaggregated MDR data in Tigray and Addis. No regional MDSR committees in any focal region/city |  | Regional MDSR committees in 2 focal regions/cities have discussed disaggregated MDSR data at least once | Regional MDSR committees in all 4 focal regions/cities have discussed disaggregated MDSR data at least once | MDSR data (disaggregated by geography) is a standing item at regional MDSR committee meetings (in all 4 target regions/cities)
Achieved
Source
MDSR committee meeting schedules/agendas
IMPACT WEIGHTING (%) | Output Indicator 1.4 |  | Baseline (2011/12) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 (2015) | Target (mid-2016)
40 | Development of a database integrating data for IDSR (Integrated Disease Surveillance and Response) and MDSR (Maternal Death Surveillance and Response) | Planned | IDSR database does not include MDSR data |  | Structure of integrated database is agreed and database is ready to be populated | Database is populated with up-to-date MDSR data from 4 regions | Regional MDSR committees in all E4A focal regions produce annual report informed by database
Achieved
|  | Source | [5 empty] | RISK RATING
|  |  | Database outputs, validation study report, regional MDSR committee reports |  |  |  |  | Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
1170000
INPUTS (HR) | DFID (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline (2011/12) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 (2015) | Target (mid-2016) | Assumptions
Political leadership and public momentum | Integration of national MDSR guidelines in training and strategic plans | Planned | No national MDSR guidelines |  | Pre-service and in-service training schools in 2 focal regions/cities have had orientation sessions on the MDSR system | Pre-service and in-service training schools in all 4 focal regions/cities have had orientation sessions on the MDSR system | New health sector strategic plan includes MDSR and how data will be captured and used in MNH quality improvement | Advocacy messages do not create unforeseen conflict and tension. Local and national media are receptive to using credible evidence for responsible reporting. Adequate numbers of skilled health workers are available to deliver improved quality of care (in both urban and rural areas).
Achieved
Source
Orientation session records, Health Sector Development Plan (HSDP-V)
| Output Indicator 2.2 |  | Baseline (2011/2) | Milestone 1 (2012) | Milestone 2 (2013) | Milestone 3 (2015) | Target (mid-2016)
| Number of community/religious leaders, local politicians, media representatives and CSOs engaged via E4A activities. | Planned | 0 |  |  | 300 | 450
Achieved
Source
Internal monitoring tools
| Output Indicator 2.3 |  | Baseline (2011/12) | Milestone 1 (2012) | Milestone 2 (2013) | Milestone 3 (2015) | Target (mid-2016)
| Accessibility of relevant MNH information and resources for stakeholders. | Planned | Basic evidence and core documents that would be essential for planning, decision-making and advocacy are largely difficult to access, badly packaged, badly communicated and time-consuming to locate. There is a lack of synthesis and information-sharing between MNH initiatives. |  |  | MDSR documentation available on WHO website: guidance, training materials, policy briefs, case studies (including use of data and actions taken) | Up-to-date MDSR documentation available on WHO website: guidance, training materials, policy briefs, updated case studies on using MDSR to improve MNH, appropriate links to FMoH website
Achieved
|  | Source | [5 empty] | RISK RATING
|  |  | E4A Ethiopia website, WHO website |  |  |  |  | Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
585000
INPUTS (HR) | DFID (FTEs)
OUTPUT 3 | Output Indicator 3.2 (no outcome indicator 3.1 in Ethiopia) |  | Baseline (2011/12) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 (2015) | Target (mid-2016) | Assumptions
Better national oversight and transparency of the provision of maternal and neonatal health (MNH) services, for better accountability for mothers and their babies. | Number of people supported to hold decision-makers to account in relation to MNH. | Planned | 0 | 500 | 2500 | 3500 | 4500 | Appropriate civil society groups with potential to form accountability mechanisms exist. Political environment enables independent and legitimate accountability mechanisms to be established. National and subnational governments receptive to transparency of information and budgeting. Accountability mechanisms able to enforce effective sanctions. Adequate numbers of skilled health workers are available to deliver improved quality of care (in both urban and rural areas). Additional funds leveraged to extend activities to 2 focus regions in addition to Oromia and Tigray.
Achieved
Source
Internal monitoring tool
| Output Indicator 3.3 |  | Baseline (2011/12) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 (2015) | Target (mid-2016)
| Number of regions and health facilities producing MDSR action plans | Planned | 0 |  | At least 1 hospital or health centre in each focal zone/city produces an action plan based on that facility's MDSR data | All 4 focal regions produce an action plan based on data from that region’s MDSR system. At least 3 hospitals or health centres in each focal zone/city produce an action plan based on that facility’s MDSR data | All 4 focal regions produce an action plan based on data from that region’s MDSR system. At least 4 hospitals or health centres in each focal zone/city produce an action plan based on that facility’s MDSR data
Achieved
Source
MDSR committee action plans at regional and facility level
IMPACT WEIGHTING (%) | Output Indicator 3.4 |  | Baseline (2011/2) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 (2015) | Target (mid-2016)
40 | Percentage of MDSR recommendations from 2014 action plans which have been implemented | Planned | 0 |  | System in place for monitoring the number (and %) of recommendations which have been implemented | 30 | 50
Achieved
|  | Source | [5 empty] | RISK RATING
|  |  | Monitoring system outputs |  |  |  |  | Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
1170000
INPUTS (HR) | DFID (FTEs)

## Ghana
PROJECT NAME | Reducing Maternal & Neonatal Mortality Ghana
IMPACT | Impact Indicator 1 |  | Baseline (2011/12) | Milestone 1 (2012) | Milestone 2 (2014) | Milestone 3 | Target (2015)
Accelerated reduction in maternal and neonatal mortality | Maternal lives saved | Planned | 0 | 20 | 150 |  | 280
Achieved
Source
Multiple data sources used for projections - see LiST methodology
| Impact Indicator 2 |  | Baseline (2011/12) | Milestone 1 (2012) | Milestone 2 (2014) | Milestone 3 | Target (2015)
| Neonatal lives saved (excluding stillbirths) | Planned | 0 | 350 | 2100 |  | 4000
Achieved
Source
Multiple data sources used for projections - see LiST methodology
| Impact Indicator 3 |  | Baseline (2011/12) | Milestone 1 (2012) | Milestone 2 (2014) | Milestone 3 | Target (2015)
| Stillbirths averted | Planned | 0 | 200 | 1200 |  | 2200
Achieved
Source
Multiple data sources used for projections - see LiST methodology
OUTCOME | Outcome Indicator 1 |  | Baseline (2012) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 | Target (2015) | Assumptions
Facilities equipped to save maternal and newborn lives | Use of evidence by national and sub-national health managers and health facility managers in their decision-making | Planned | Good data exist, but they are often not appropriately packaged and managers lack the statistical skills to make good use of the available data. Use of data for decision-making score: 50% |  | Use of data for decision-making score: 55% |  | Use of data for decision-making score: 61% | Political instability does not undermine potential for impact. Governments receptive to efforts to increase political will. Project leverages additional resources to catalyse change. High-quality MNH data available. Theory of change is borne out in reality; more efficient use of resources plus improved use of data for decision-making plus increased political will leads to improved quality of care which leads to lives saved within 4 years.
Achieved
Source
E4A monitoring tools summary analysis report
| Outcome Indicator 2 |  | Baseline (2012) | Milestone 1 (2013) | Milestone 2 (mid-2014) | Milestone 3 | Target (2015)
| Political will to improve quality of care and the use of evidence for decision-making | Planned | PPP score: 62% |  | PPP score: 70% |  | PPP score: 75%
Achieved
Source
E4A monitoring tools summary analysis report
| Outcome Indicator 3 |  | Baseline (2011) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 | Target (2015)
| Number of primary facilities in focal districts which have at least 5 of the 7 BEmONC signal functions | Planned | 7 |  | 9 |  | 10
Achieved
Source
2011 AMDD EmONC needs assessment, Quality of Institutional Care (QuIC) tool
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
2925000
INPUTS (HR) | DFID (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline (2011/2) | Milestone 1 (2012) | Milestone 2 (2013) | Milestone 3 (2014) | Target (2015) | Assumptions
Better information for better results: realising key parts of Commission on Information and Accountability (CoIA) recommendations in 6 countries. | Use of MNH data for forward planning and resource allocation at district level. | Planned | District Health Management Teams (DHMTs) do not routinely review MNH evidence in their management meetings |  |  | DHMTs in 6 focal districts have considered new MNH evidence at a management meeting. | DHMTs in 9 focal districts have considered new MNH evidence at a management meeting and used it for forward planning/resource allocation | High-quality data available. Government receptive to evidence-driven management culture. In-country partners receptive to capacity-building in data management and communication. Health service managers receptive to culture of 'no blame' performance management. Sufficient resources can be leveraged to collect data suitable for disaggregation to sub-national levels. Harmonisation among partners for better management of results is effective in practice. Theory of change is borne out in reality: better evidence (in combination with better advocacy and accountability) leads to improved quality of care, better use of evidence and increased political will within 4 years. QuIC pilot will conclude that the methodology is suitable for rolling out more widely in Ghana
Achieved
Source
DHMT meeting minutes, policy study
| Output Indicator 1.2 |  | Baseline (2011/12) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 | Target (2015)
| Use of maternal death review (MDR) findings to identify and report problems in the system | Planned | Findings of MDRs are not being routinely used to identify and report problems in the system |  | E4A-supported training on MDR feedback delivered to Ghana Health Service staff in 6 focal districts |  | E4A-supported training on MDR feedback delivered to Ghana Health Service staff in 9 focal districts. MDR findings inform and are discussed by DHMTs during their quarterly meetings
Achieved
Source
DHMT meeting records, internal training records
| Output Indicator 1.3 |  | Baseline (2011/12) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 | Target (2015)
| Use of disaggregated maternal and newborn data (including indicators from the CoIA list) in progress and performance reviews | Planned | Disaggregated data are available for 7 of the 11 MNH CoIA indicators, but there is limited use in reviews and target-setting |  | Census workshop with MNH stakeholders. |  | Data on EmONC signal functions and health facility infrastructure disaggregated to health facility level disseminated and shared with Government of Ghana for use in progress and performance reviews
Achieved
Source
E4A country design reports, Delphi on disaggregation of CoIA indicator data, workshop records, event records, stakeholder interviews during DfID Annual Reviews.
IMPACT WEIGHTING (%) | Output Indicator 1.4 |  | Baseline (2011/12) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 (Oct 2015) | Target (Dec 2015)
33.3 | Coverage of mobile phone data capture system to monitor health facility readiness and ability to perform signal functions | Planned | Mobile phones are not used to monitor health facility readiness and ability to perform signal functions |  | Quality of Institutional Care (QuIC) system is used to capture data from 67 health facilities in 16 districts. | At least two rounds of QuIC data capture completed in 16 districts | Plan for scaling up coverage of QuIC developed and shared with Ghana Health Service
Achieved
|  | Source | [5 empty] | RISK RATING
|  |  | QuIC documentation |  |  |  |  | Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
975000
INPUTS (HR) | DFID (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline (2011/12) | Milestone 1 (2012) | Milestone 2 (2014) | Milestone 3 | Target (2015) | Assumptions
Political leadership and public momentum | Percentage of MamaYe! press releases that lead to a published article or are featured on radio/TV, without incentive | Planned | No MamaYe! press releases |  | Ghana’s engaged advocates/activists list (see output indicator 2.2) includes 30 journalists who have been sensitised to the campaign via training events or individual meetings |  | 50% of MamaYe! press releases lead to a published article or are featured on radio/TV (at least 2 media outlets) | Advocacy groups receptive to working under unified national campaign. Advocacy messages do not create unforeseen conflict and tension. Political environment is conducive to independent media. Local and national media are receptive to using credible evidence for responsible reporting. Advocacy groups have potential for capacity development in branding, messaging and communication. Adequate numbers of skilled health workers are available to deliver improved quality of care (in both urban and rural areas). Theory of change is borne out in reality: better advocacy (in combination with better evidence and accountability) leads to improved quality of care, better use of evidence and increased political will within 4 years.
Achieved
Source
Internal monitoring tools
| Output Indicator 2.2 |  | Baseline (2011/2) | Milestone 1 (2012) | Milestone 2 (2013) | Milestone 3 | Target (2015)
| Number of advocates and activists engaged through E4A-supported national advocacy campaign Note: ‘engaged’ is defined as committed to E4A goals, and empowered by E4A with the power (evidence, information and/or strategy) to make change (real outcomes) | Planned | No national MNH campaign. Engaged advocates/activists: 0 |  |  |  | 200
Source
E4A country design reports, internal monitoring tools
| Output Indicator 2.3 |  | Baseline (2011/12) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 | Target (2015)
| Accessibility of relevant MNH information and resources for stakeholders. | Planned | Basic evidence and core documents that would be essential for planning, decision-making and advocacy are difficult to access at local level. There is a lack of synthesis and information-sharing between MNH initiatives. |  | Improved functionality of website via updates to structure of evidence pages |  | Website is contributing to raised awareness of MNH by regular updates to the content, including technical updates, new evidence added at least quarterly, and links to other relevant websites
Achieved
Source
E4A country design reports, website analytics, user feedback, website content
| Output Indicator 2.4 |  | Baseline (2011/2) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 | Target (2015)
| Mean number of visits to national website per month (with "visits" as defined by Google Analytics at http://support.google.com/analytics/answer/2731565?hl=en-GB&topic=2524483&ctx=topic) | Planned | 0 |  | 820 |  | 950
Achieved
Source
Google Analytics
IMPACT WEIGHTING (%) | Output Indicator 2.5 |  | Baseline (2011/12) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 | Target (2015)
33.3 | Adoption of MamaYe! campaign by key engaged advocates/activists | Planned | No MamaYe! campaign or engaged advocates/activists |  |  |  | Advocacy Coalition partners and other stakeholders use MamaYe! branding for their own activities
Achieved
|  | Source | [5 empty] | RISK RATING
|  |  | E4A country design reports, internal M+E reports, stakeholder interviews during DfID Annual Reviews. |  |  |  |  | Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
975000
INPUTS (HR) | DFID (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline (2011/12) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 | Target (2015) | Assumptions
Better national oversight and transparency of the provision of maternal and neonatal health (MNH) services, for better accountability for mothers and their babies. | Use of national accountability mechanisms to hold district health managers to account for the status of MNH services in E4A focal districts | Planned | District health managers report regularly to regional health managers, but there are no clear, objective benchmarks for holding them accountable for service delivery |  | In 8 focal districts, there has been at least one round of data collection using the MNH scorecard mechanism |  | In 8 focal districts, data are collected every 6 months using the MNH scorecard mechanism, and results are reviewed by District authorities (e.g. DHMTs, District Councils, District Assemblies) | Appropriate civil society groups with potential to form accountability mechanisms exist. Political environment enables independent and legitimate accountability mechanisms to be established. National and subnational governments receptive to transparency of information and budgeting. Media are receptive to using credible evidence for responsible reporting. Accountability mechanisms able to enforce effective sanctions. Adequate numbers of skilled health workers are available to deliver improved quality of care (in both urban and rural areas). Theory of change is borne out in reality: better accountability (in combination with better advocacy and evidence) leads to improved quality of care, better use of evidence and increased political will within 4 years. Supportive supervision system increases BEmONC readiness at rural health facilities
Achieved
Source
E4A country design reports, scorecard outputs, district authority meeting records
| Output Indicator 3.2 |  | Baseline (2011/12) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 | Target (2015)
| Number of people supported to hold decision-makers to account in relation to MNH. | Planned | 0 |  | 16000 |  | 30000
Achieved
Source
Internal monitoring tool
IMPACT WEIGHTING (%) | Output Indicator 3.3 |  | Baseline (2011/12) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 | Target (2015)
33.3 | Mechanism to encourage service providers to report their training and resource needs | Planned | No supportive supervision system exists |  | In 1 region (4 districts), teams are allocated to support supervision in districts. They visit at least once every 6 months and make a record of needs |  | In 2 regions (8 districts), team are allocated to support supervision in districts. They visit at least once every 6 months and make a record of needs. One supervision partner (e.g. GHS or a professional association) adopts the supportive supervision system and commits to continuing with it post-E4A
Achieved
|  | Source | [5 empty] | RISK RATING
|  |  | Supportive supervision visit records, supervision partner records (e.g. meeting minutes) |  |  |  |  | Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
975000
INPUTS (HR) | DFID (FTEs)

## Malawi
PROJECT NAME | Reducing Maternal & Neonatal Mortality Malawi
IMPACT | Impact Indicator 1 |  | Baseline (2011/12) | Milestone 1 (2012) | Milestone 2 (2014) | Milestone 3 (2015) | Target (mid-2016)
Accelerated reduction in maternal and neonatal mortality | Maternal lives saved | Planned | 0 | 70 | 420 | 590 | 770
Achieved
Source
Multiple data sources used for projections - see LiST methodology
| Impact Indicator 2 |  | Baseline (2011/12) | Milestone 1 (2012) | Milestone 2 (2014) | Milestone 3 (2015) | Target (mid-2016)
| Neonatal lives saved (excluding stillbirths) | Planned | 0 | 330 | 1800 | 2500 | 3700
Achieved
Source
Multiple data sources used for projections - see LiST methodology
| Impact Indicator 3 |  | Baseline (2011/12) | Milestone 1 (2012) | Milestone 2 (2014) | Milestone 3 (2015) | Target (mid-2016)
| Stillbirths averted | Planned | 0 | 270 | 1500 | 2100 | 2900
Achieved
Source
Multiple data sources used for projections - see LiST methodology
OUTCOME | Outcome Indicator 1 |  | Baseline (2012) | Milestone 1 (2013) | Milestone 2 (mid-2014) | Milestone 3 (2015) | Target (mid-2016) | Assumptions
Key resources for maternal and newborn health are in place at health facilities | Use of evidence by national and sub-national health managers and health facility managers in their decision-making | Planned | MNH data are used for decision-making at a national level, but less so at a sub-national level. HMIS data are not reliable and there are no feedback mechanisms. Use of data for decision-making score: 47% |  | Use of data for decision-making score: 53% |  | Use of data for decision-making score: TBC | Political instability does not undermine potential for impact. Governments receptive to efforts to increase political will. Project leverages additional resources to catalyse change. High-quality MNH data available. Theory of change is borne out in reality; more efficient use of resources plus improved use of data for decision-making plus increased political will leads to improved quality of care which leads to lives saved within 4 years.
Achieved
Source
Internal monitoring tool (DDM)
| Outcome Indicator 2 |  | Baseline (2012) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 (2015) | Target (mid-2016)
| Political will to improve quality of care and the use of evidence for decision-making | Planned | PPP score: 60% |  | PPP score: 65% |  | PPP score: TBC
Achieved
Source
Internal monitoring tool (PPP)
| Outcome indicator 3 |  | Baseline (May 2014) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 (2015) | Target (mid-2016)
| Number of district hospitals in 6 focal districts reporting stock-outs of antenatal corticosteroids in the preceding 3 months | Planned | 5 |  |  | 4 | 3
Achieved
Source
Baseline: E4A-commissioned data collection. Milestone/target: QuIC
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
2925000
INPUTS (HR) | DFID (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline (2011/2) | Milestone 1 (2012) | Milestone 2 (2013) | Milestone 3 (2015) | Target (2016) | Assumptions
Better information for better results: realising key parts of Commission on Information and Accountability (CoIA) recommendations in 6 countries. | Coverage of community maternal death reviews (c-MDRs) | Planned | There is no systematic approach to conducting community MDRs. |  |  | c-MDRs conducted in 8 traditional authorities in 6 focal districts, according to the official guideline | c-MDRs conducted in 18 traditional authorities in 6 focal districts, according to the official guideline | High-quality data available. Government receptive to evidence-driven management culture. In-country partners receptive to capacity-building in data management and communication. Health service managers receptive to culture of 'no blame' performance management. Sufficient resources can be leveraged to collect data suitable for disaggregation to sub-national levels. Harmonisation among partners for better management of results is effective in practice. Theory of change is borne out in reality: better evidence (in combination with better advocacy and accountability) leads to improved quality of care, better use of evidence and increased political will within 4 years. " QuIC pilot will conclude that the methodology is suitable for rolling out more widely in Malawi
Achieved
Source
Quarterly district MDSR reports
| Output Indicator 1.2 |  | Baseline (2011/12) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 (2015) | Target (mid-2016)
| Use of maternal death review (MDR) findings | Planned | The quality of facility MDR findings is not always good and it is difficult to maintain anonymity, so the findings are not always used to prevent further deaths. |  | Feedback mechanism operates via quarterly meetings in 6 districts | Data on factors contributing to maternal death in 6 districts disseminated to key stakeholders | 30% of MDR recommendations made in 2014 in the 6 focal districts have been implemented
Achieved
Source
Quarterly meeting notes/action points, MDR follow-up forms
| Output Indicator 1.3 |  | Baseline (2011/12) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 (2015) | Target (mid-2016)
| Use of disaggregated maternal and newborn indicators in progress and performance reviews at district level | Planned | Data from national surveys (e.g. DHS) are disaggregated to district level, but there are no sources of up-to-date or ‘real time’ disaggregated data at district level |  | At least one round of data collection complete for the District Dashboard in all 6 focal districts | District Dashboard data are collected at least twice a year in 4 focal districts | District Health Sub-Committees in 5 districts meet at least twice a year and produce recommendations/action plans informed by District Dashboard data
Achieved
Source
District Dashboard outputs, District Health Sub-Committee meeting records
IMPACT WEIGHTING (%) | Output Indicator 1.4 |  | Baseline (2011/12) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 (2015) | Target (mid-2016)
33.3 | Coverage of mobile phone data capture system to monitor health facility readiness and ability to perform signal functions (QuIC) | Planned | Mobile phones are not used to monitor health facility readiness and ability to perform signal functions |  | Quality of Institutional Care (QuIC) system is used to capture data from 35 health facilities in 4 districts | At least two rounds of QuIC data capture completed in 4 districts | Plan developed for scaling up coverage of QuIC beyond 4 districts, and shared with Ministry of Health
Achieved
|  | Source | [5 empty] | RISK RATING
|  |  | QuIC documentation, outputs from hand-held devices, QuIC scale-up protocol |  |  |  |  | Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
975000
INPUTS (HR) | DFID (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline (2011/12) | Milestone 1 (2012) | Milestone 2 (2014) | Milestone 3 (2015) | Target (mid-2016) | Assumptions
Political leadership and public momentum | Number of national TV programmes covering MNH issues, and number of district-level broadcasts/ publications covering MNH issues | Planned | No regular national TV programmes about MNH, and very little coverage of MNH at district level |  | 10 programmes aired on national TV across the year, which cover MNH issues. District-level journalists publish or broadcast at least 2 MNH stories per quarter | 6 programmes aired on national TV across the year, which cover MNH issues. District-level journalists publish or broadcast at least 2 MNH stories per quarter | 3 programmes aired on national TV since November 2015, which cover MNH issues. District-level journalists publish or broadcast at least 2 MNH stories per quarter | Advocacy groups receptive to working under unified national campaign. Advocacy messages do not create unforeseen conflict and tension. Political environment is conducive to independent media. Local and national media are receptive to using credible evidence for responsible reporting. Advocacy groups have potential for capacity development in branding, messaging and communication. Adequate numbers of skilled health workers are available to deliver improved quality of care (in both urban and rural areas). Theory of change is borne out in reality: better advocacy (in combination with better evidence and accountability) leads to improved quality of care, better use of evidence and increased political will within 4 years MBC TV remains committed to producing a regular MNH show, and continues to provide airtime for it without charge KCN remains committed to hosting the seminar series
Achieved
Source
Statement (May 2014) from editor of national newspaper (baseline), internal media monitoring tool, recordings of the national TV programmes
| Output Indicator 2.2 |  | Baseline (2011/2) | Milestone 1 (2012) | Milestone 2 (2013) | Milestone 3 (2015) | Target (mid-2016)
| Number of advocates and activists engaged through E4A-supported national advocacy campaign Note: ‘engaged’ is defined as committed to E4A goals, and empowered by E4A with the power (evidence, information and/or strategy) to make change (real outcomes) | Planned | No national MNH campaign. Engaged advocates/activists: 0 |  |  | Engaged advocates/activists: 100 | Engaged advocates/activists: 150
Source
E4A country design reports, monthly country updates, quarterly internal monitoring reports, review of advocacy effectiveness and sustainability.
| Output Indicator 2.3 |  | Baseline (2011/12) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 (2015) | Target (mid-2016)
| Accessibility of relevant MNH information and resources for stakeholders. | Planned | Basic evidence and core documents that would be essential for planning, decision-making and advocacy are largely difficult to access, badly packaged, badly communicated and time-consuming to locate. There is a lack of synthesis and information-sharing between MNCH initiatives. |  | Improved functionality of website via updates to structure of evidence pages |  | Website is contributing to raised awareness of MNH by regular updates to the content, including technical updates, new evidence added at least quarterly, and links to other relevant websites
Achieved
Source
E4A country design reports, website analytics, user feedback, website content
| Output Indicator 2.4 |  | Baseline (2011/2) | Milestone 1 (Feb 2013) | Milestone 2 (2014) | Milestone 3 (2015) | Target (mid-2016)
| Mean number of visits to national website per month, with "visits" as defined by Google Analytics at http://support.google.com/analytics/answer/2731565?hl=en-GB&topic=2524483&ctx=topic | Planned | 0 |  | 580 | 650 | 700
Achieved
Source
Google Analytics
IMPACT WEIGHTING (%) | Output Indicator 2.5 |  | Baseline (2011/2) | Milestone 1 (2012) | Milestone 2 (2014) | Milestone 3 (2015) | Target (mid-2016)
33.3 | Number of MamaYe! clubs trained in 6 focal districts, and number of MNH seminars at the Kamuzu College of Nursing | Planned | 0 |  | 6 MamaYe clubs trained, and 10 KCN seminars over the period November 2013 – October 2014 | 10 KCN seminars over the period November 2014 – October 2015 | 10 MamaYe clubs trained and 4 KCN seminars over the period November 2015-March 2016
Achieved
|  | Source | [5 empty] | RISK RATING
|  |  | MamaYe club reports, internal monitoring reports, videos and photos shared on social media, seminar advertisements and attendance records |  |  |  |  | Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
975000
INPUTS (HR) | DFID (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline (2011/12) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 (2015) | Target (mid-2016) | Assumptions
Better national oversight and transparency of the provision of maternal and neonatal health (MNH) services, for better accountability for mothers and their babies. | Multi-sectoral, evidence-based community level accountability mechanisms in place, which include functioning District health sub-committees | Planned | No district health sub-committees in E4A focal districts |  | At least one District Health sub-committee meeting in 3 focal districts to produce action plans with use of evidence | At least one District Health sub-committee meeting in 3 more focal districts to produce action plans with use of evidence | District health sub-committees in 6 districts meet twice per year and make action plans based on MNH evidence, which include resource allocation | Appropriate civil society groups with potential to form accountability mechanisms exist. Political environment enables independent and legitimate accountability mechanisms to be established. National and subnational governments receptive to transparency of information and budgeting. Media are receptive to using credible evidence for responsible reporting. Accountability mechanisms able to enforce effective sanctions. Adequate numbers of skilled health workers are available to deliver improved quality of care (in both urban and rural areas). Theory of change is borne out in reality: better accountability (in combination with better advocacy and evidence) leads to improved quality of care, better use of evidence and increased political will within 4 years.
Achieved
Source
Internal monitoring tools, DHSC minutes/action plans
IMPACT WEIGHTING (%) | Output Indicator 3.2 |  | Baseline (2011/12) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 (2015) | Target (mid-2016)
33.3 | Number of people supported to hold decision-makers to account in relation to MNH. | Planned | 0 |  | 10000 | 15000 | 17000
Achieved
|  | Source | [5 empty] | RISK RATING
|  |  | Internal monitoring tool |  |  |  |  | Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
975000
INPUTS (HR) | DFID (FTEs)

## Nigeria
PROJECT NAME | Reducing Maternal & Neonatal Mortality Nigeria
IMPACT | Impact Indicator 1 |  | Baseline (2011/12) | Milestone 1 (2012) | Milestone 2 (2014) | Milestone 3 (2015) | Target (mid-2016)
Accelerated reduction in maternal and neonatal mortality | Maternal lives saved | Planned | 0 | 40 | 250 | 350 | 440
Achieved
Source
Multiple data sources used for projections - see LiST methodology
| Impact Indicator 2 |  | Baseline (2011/12) | Milestone 1 (2012) | Milestone 2 (2014) | Milestone 3 (2015) | Target (mid-2016)
| Neonatal lives saved (excluding stillbirths) | Planned | 0 | 310 | 1900 | 2700 | 3600
Achieved
Source
Multiple data sources used for projections - see LiST methodology
| Impact Indicator 3 |  | Baseline (2011/12) | Milestone 1 (2012) | Milestone 2 (2014) | Milestone 3 (2015) | Target (mid-2016)
| Stillbirths averted | Planned | 0 | 180 | 1100 | 1600 | 2100
Achieved
Source
Multiple data sources used for projections - see LiST methodology
OUTCOME | Outcome Indicator 1 |  | Baseline (2012) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 (2015) | Target (mid-2016) | Assumptions
Key resources for maternal and newborn health are in place at health facilities | Use of evidence by national and state health managers and health facility managers in their decision-making | Planned | Evidence is gathered by various stakeholders but not always at state level and rarely effectively collated and disseminated, making it rarely used for decision-making. Use of data for decision-making score: 43% |  | Use of data for decision-making score (Kano & Jigawa): 53% |  | Use of data for decision-making score: TBC | Political instability does not undermine potential for impact. Governments receptive to efforts to increase political will. Project leverages additional resources to catalyse change. High-quality MNH data available. Theory of change is borne out in reality; more efficient use of resources plus improved use of data for decision-making plus increased political will leads to improved quality of care which leads to lives saved within 4 years.
Achieved
Source
Internal monitoring tools (DDM)
| Outcome Indicator 2 |  | Baseline (2012) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 (2015) | Target (mid-2016)
| Political will to improve quality of care and the use of evidence for decision-making | Planned | PPP score: 54% |  | PPP score (Kano & Jigawa): 59% |  | PPP score: TBC
Achieved
Source
Internal monitoring tools (PPP)
| Outcome Indicator 3 |  | Baseline (2013) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 (2015) | Target (2016)
| % of secondary facilities in 4 focal states with no stock-outs of magnesium sulphate over a 3-month period | Planned | Bauchi (2013): 43 Kano (2013): 22 Jigawa (2011): 25 Ondo (2013): 57 |  | Bauchi: 48 Kano: 33 Jigawa: 35 Ondo: 71 |  | Bauchi: 53 Kano: 44 Jigawa: 45 Ondo: 86
Achieved
Source
Bauchi: HMIS. Kano & Ondo: E4A- commissioned operational research. Jigawa: ISS
| Outcome Indicator 4 |  | Baseline (2013) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 (2015) | Target (2016)
| % of secondary facilities in 4 states with a blood bank which has the capacity to store and screen blood | Planned | Bauchi (2013): 20 Kano (2013): 44 Jigawa (2012): 25 Ondo (2013): 43 |  | Bauchi: 25 Kano: 44 Jigawa: 40 Ondo: 57 |  | Bauchi: 30 Kano: 56 Jigawa: 55 Ondo: 71
Achieved
Source
Bauchi: ISS. Kano & Ondo: E4A-commissioned operational research. Jigawa: State MNH scorecard.
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
2925000
INPUTS (HR) | DFID (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline (2011/2) | Milestone 1 (2012) | Milestone 2 (2013) | Milestone 3 (2015) | Target (2016) | Assumptions
Better information for better results: realising key parts of Commission on Information and Accountability (CoIA) recommendations in 6 countries. | Coverage of maternal death reviews (MDRs) | Planned | NGOs conduct MDRs in selected facilities. Elsewhere coverage is patchy. The efforts of different organisations are unco-ordinated. |  |  | MDR data collected in all secondary facilities in 1 focal state, following standardised MDR guidelines and tools. | MDR data collected in all secondary facilities in 2 focal states, following standardised MDR guidelines and tools. | High-quality data available. Government receptive to evidence-driven management culture. In-country partners receptive to capacity-building in data management and communication. Health service managers receptive to culture of 'no blame' performance management. Sufficient resources can be leveraged to collect data suitable for disaggregation to sub-national levels. Harmonisation among partners for better management of results is effective in practice. Theory of change is borne out in reality: better evidence (in combination with better advocacy and accountability) leads to improved quality of care, better use of evidence and increased political will within 4 years.
Achieved
Source
State MDR reports
| Output Indicator 1.2 |  | Baseline (2011/12) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 (2015) | Target (mid-2016)
| Use of maternal death review (MDR) findings | Planned | Findings of NGO-led MDRs are being used to improve service delivery in selected facilities. Elsewhere, teams are just being set up to review MDR findings and make recommendations. |  |  | State review teams in 1 focal state track progress on implementation of MDR recommendations through bi-annual state-level scorecards | State review teams in 2 focal states track progress on implementation of MDR recommendations through bi-annual state-level scorecards
Achieved
Source
Scorecards and associated documentation
| Output Indicator 1.3 |  | Baseline (2011/12) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 (2015) | Target (mid-2016)
| Use of disaggregated maternal and newborn indicators from the CoIA list in progress and performance reviews. | Planned | Disaggregated data are available for most MNH indicators, and used to some extent in progress and performance reviews, but state-level data are not generally available. |  | MNH scorecards are populated bi-annually, and results discussed by State review team in 1 focal state | MNH scorecards are populated bi-annually, and results discussed by State review teams in 2 focal states | Scorecards with disaggregated MNH data are populated bi-annually and disseminated to the mid-term sector review teams in 2 focal states, and are used by them to inform decisions about resource allocation
Achieved
Source
Scorecards, State review team meeting minutes, SMS messages, MTSS meeting minutes, presentations with FMoH, DDM data (see outcome indicator 4), qualitative investigation, desk research.
IMPACT WEIGHTING (%) | Output Indicator 1.4 |  | Baseline (2011/12) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 (2015) | Target (mid-2016)
33.3 | Use of MNH evidence to support the development of annual state health sector plans and budgets | Planned | No system for MNH data to feed into annual plans and budgets |  |  | MNH data are used by mid-term sector review teams in 1 focal state to develop annual state health sector strategies and budgets | MNH data are used by mid-term sector review teams in 2 focal states to develop annual state health sector strategies and budgets
Achieved
|  | Source | [5 empty] | RISK RATING
|  |  | Mid-term Sector Strategy (MTSS) meeting minutes |  |  |  |  | Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
975000
INPUTS (HR) | DFID (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline (2012) | Milestone 1 (2012) | Milestone 2 (2014) | Milestone 3 (2015) | Target (mid-2016) | Assumptions
Political leadership and public momentum | Number of news articles in a 3-month period making reference to MNH, in newspapers (including online) | Planned | 33 |  | 50% increase since 2012 in the number of news articles (50 articles) | 100% increase since 2012 in the number of news articles (66 articles). Plans in place for launch of investigative MNH media fellowship | 150% increase since 2012 in the number of news articles (82 articles). Investigative MNH media fellowship awarded annually | Advocacy groups receptive to working under unified national campaign. Advocacy messages do not create unforeseen conflict and tension. Political environment is conducive to independent media. Local and national media are receptive to using credible evidence for responsible reporting. Advocacy groups have potential for capacity development in branding, messaging and communication. Adequate numbers of skilled health workers are available to deliver improved quality of care (in both urban and rural areas). Theory of change is borne out in reality: better advocacy (in combination with better evidence and accountability) leads to improved quality of care, better use of evidence and increased political will within 4 years.
Achieved
Source
E4A country design reports, quarterly internal monitoring reports, annual media reports, internal summary report derived from media monitoring data.
| Output Indicator 2.2 |  | Baseline (2011/2) | Milestone 1 (2012) | Milestone 2 (2013) | Milestone 3 (2015) | Target (mid-2016)
| Number of advocates and activists engaged through E4A-supported national advocacy campaign. Note: ‘engaged’ is defined as committed to E4A goals, and empowered by E4A or partner organisations with the power (evidence, information and/or strategy) to make change (real outcomes) | Planned | No MNH campaign. Engaged advocates/activists: 0 |  |  | Campaign launched in 2 more states. Engaged advocates/activists: 400. | Engaged advocates/activists: 600.
Source
E4A country design reports, monthly country updates, quarterly internal monitoring reports, review of advocacy effectiveness and sustainability.
| Output Indicator 2.3 |  | Baseline (2011/12) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 (2015) | Target (mid-2016)
| Accessibility of relevant MNH information and resources for stakeholders. | Planned | Basic evidence and core documents that would be essential for planning, decision-making and advocacy are generally difficult to access, not well-packaged, not well-communicated and time-consuming to locate. There is a lack of synthesis and information-sharing between MNH initiatives. |  | Improved functionality of website via updates to structure of evidence pages |  | Website is contributing to raised awareness of MNH by regular updates to the content, including technical updates, new evidence added at least quarterly, and links to other relevant websites
Achieved
Source
E4A country design reports, website analytics, user feedback, website content
| Output Indicator 2.4 |  | Baseline (2011/2) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 (2015) | Target (mid-2016)
| Mean number of visits to national website per month (with "visits" as defined by Google Analytics at http://support.google.com/analytics/answer/2731565?hl=en-GB&topic=2524483&ctx=topic) | Planned | 0 |  | 900 | 1200 | 1300
Achieved
Source
Google Analytics
IMPACT WEIGHTING (%) | Output Indicator 2.5 |  | Baseline (2011/2) | Milestone 1 (2012) | Milestone 2 (2013) | Milestone 3 (2015) | Target (mid-2016)
33.3 | Adoption of MamaYe! campaign by key engaged advocates/activists | Planned | No MamaYe! campaign |  |  | MamaYe! activists (including media, community members, decision-makers, accountability mechanism participants, MDR committee members, Action Network members) advocate for E4A ask in Kano and Jigawa | MamaYe! activists (including media, community members, decision-makers, accountability mechanism participants, MDR committee members, Action Network members) advocate for E4A ask in all 4 focal states
Achieved
|  | Source | [5 empty] | RISK RATING
|  |  | Internal records of activist activities, media reports, meeting records |  |  |  |  | Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
975000
INPUTS (HR) | DFID (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline (2011/12) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 (2015) | Target (mid-2016) | Assumptions
Better national oversight and transparency of the provision of maternal and neonatal health (MNH) services, for better accountability for mothers and their babies. | National- and State-level accountability mechanism for service delivery | Planned | Some state-level accountability mechanisms for service delivery exist, but none uses data effectively to provide government with feedback on progress and action that needs to be taken |  |  | Accountability mechanism to track progress against MNH commitments is multi-sectoral and meeting quarterly, both nationally and at State level in 1 focal state | Accountability mechanism to track progress against MNH commitments is multi-sectoral and meeting quarterly, both nationally and at State level in 2 focal states | Appropriate civil society groups with potential to form accountability mechanisms exist. Political environment enables independent and legitimate accountability mechanisms to be established. National and subnational governments receptive to transparency of information and budgeting. Media are receptive to using credible evidence for responsible reporting. Accountability mechanisms able to enforce effective sanctions. Adequate numbers of skilled health workers are available to deliver improved quality of care (in both urban and rural areas). Theory of change is borne out in reality: better accountability (in combination with better advocacy and evidence) leads to improved quality of care, better use of evidence and increased political will within 4 years.
Achieved
Source
Key stakeholder interviews with policy- and decision-makers and members of the mechanism, meeting minutes, media reports, desk research (examining key documents such as AMHiN reports, National Health Accounts)
IMPACT WEIGHTING (%) | Output Indicator 3.2 |  | Baseline (2011/12) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 (2015) | Target (mid-2016)
33.3 | Number of people supported to hold decision-makers to account in relation to MNH. | Planned | 0 | 7000 | 18000 | 25000 | 34000
Achieved
|  | Source | [5 empty] | RISK RATING
|  |  | Monthly country updates, quarterly internal monitoring reports, external verification of E4A counts. |  |  |  |  | Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
975000
INPUTS (HR) | DFID (FTEs)

## Sierra Leone
PROJECT NAME | Reducing Maternal & Neonatal Mortality Sierra Leone
IMPACT | Impact Indicator 1 |  | Baseline (2011/12) | Milestone 1 (2012) | Milestone 2 (2014) | Milestone 3 | Target (2015)
Accelerated reduction in maternal and neonatal mortality | Maternal lives saved | Planned | 0 | 20 | 110 |  | 200
Achieved
Source
Multiple data sources used for projections - see LiST methodology
| Impact Indicator 2 |  | Baseline (2011/12) | Milestone 1 (2012) | Milestone 2 (2014) | Milestone 3 | Target (2015)
| Neonatal lives saved (excluding stillbirths) | Planned | 0 | 180 | 1100 |  | 2100
Achieved
Source
Multiple data sources used for projections - see LiST methodology
| Impact Indicator 3 |  | Baseline (2011/12) | Milestone 1 (2012) | Milestone 2 (2014) | Milestone 3 | Target (2015)
| Stillbirths averted | Planned | 0 | 50 | 300 |  | 540
Achieved
Source
Multiple data sources used for projections - see LiST methodology
OUTCOME | Outcome Indicator 1 |  | Baseline (2012) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 | Target (2015) | Assumptions
Facilities equipped to save maternal and newborn lives | Use of evidence by national and sub-national health managers and health facility managers in their decision-making | Planned | Use of data for decision-making score: 56% |  | Use of data for decision-making score (3 districts): 61% |  | Use of data for decision-making score (2 districts): 61% | Political instability does not undermine potential for impact. Governments receptive to efforts to increase political will. Project leverages additional resources to catalyse change. High-quality MNH data available. Theory of change is borne out in reality; more efficient use of resources plus improved use of data for decision-making plus increased political will leads to improved quality of care which leads to lives saved within 4 years.
Achieved
Source
Internal monitoring tool (DDM)
| Outcome Indicator 2 |  | Baseline (2012) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 | Target (2015)
| Political will to improve quality of care and the use of evidence for decision-making | Planned | PPP score: 60% |  | PPP score: 65% |  | PPP score: 70%
Achieved
Source
Internal monitoring tool (PPP)
| Outcome Indicator 3 |  | Baseline (2012) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 | Target (2015)
| Number of health facilities in Bonthe and Koinadugu that are BEmONC compliant (according to Facilities Improvement Team criteria or another mechanism to measure facility readiness) | Planned | 0 | 2 | 4 |  | 8
Achieved
Source
QuIC-FIT scorecards or similar
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
2925000
INPUTS (HR) | DFID (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline (2011/2) | Milestone 1 (2012) | Milestone 2 (2013) | Milestone 3 | Target (2015) | Assumptions
Better information for better results: realising key parts of Commission on Information and Accountability (CoIA) recommendations in 6 countries. | Coverage of maternal death reviews (MDRs) | Planned | Facility-based MDR system recently piloted, but not yet rolled out |  |  |  | All designated CEmONC facilities in 2 focal districts conduct MDRs according to the national guideline | High-quality data available. Government receptive to evidence-driven management culture. In-country partners receptive to capacity-building in data management and communication. Health service managers receptive to culture of 'no blame' performance management. Sufficient resources can be leveraged to collect data suitable for disaggregation to sub-national levels. Harmonisation among partners for better management of results is effective in practice. Theory of change is borne out in reality: better evidence (in combination with better advocacy and accountability) leads to improved quality of care, better use of evidence and increased political will within 4 years. MoHS remains committed to upgrading the HMIS by 2015.
Achieved
Source
MoHS reports
| Output Indicator 1.2 |  | Baseline (2011/12) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 | Target (2015)
| Use of maternal death review (MDR) findings | Planned | Findings of MDR pilot not yet used to prevent further deaths |  | National guideline on strengthening MDR response developed |  | Mechanism in place in 2 focal districts for ensuring recommendations based on MDR findings are actioned. Plan for rolling out this mechanism nationally submitted to MoHS
Achieved
Source
National guideline on strengthening MDR response, mechanism outputs
| Output Indicator 1.3 |  | Baseline (2011/12) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 (Sept 2015) | Target (Dec 2015)
| Availability of disaggregated data on maternal and newborn indicators from the CoIA list | Planned | Disaggregated data are available for 9 of the 11 CoIA MNH indicators, and where available they are transparently reported, but are not used in progress/performance reviews |  | Set of MNH indicators agreed at national level, including indicators from the CoIA list (the Sierra Leone indicator index) | HMIS upgraded to collect data on Sierra Leone indicators, disaggregated by district, and by age and sex as appropriate | Disaggregated data on the Sierra Leone indicators communicated to MoHS and other stakeholders, for use in their progress and performance reviews
Achieved
Source
E4A country design reports, Delphi on disaggregation of CoIA indicator data, E4A internal reports, stakeholder interviews during DfID Annual Reviews.
IMPACT WEIGHTING (%) | Output Indicator 1.4 |  | Baseline (2011/12) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 | Target (2015)
33.3 | Availability and accessibility of data on key MNH outcomes | Planned | MoHS Facility Improvement Team (FIT) Assessments conducted quarterly, but findings poorly communicated and assessment system too resource-intensive to be sustainable |  | First round of quality of Institutional Care (QuIC)/QuIC-FIT system is used to capture data from 22 health facilities in 2 focal districts |  | National MDR database established. District dashboard mechanism established (populated with baseline data) in 2 focal districts, containing data from DHIS, QuIC/QuIC-FIT and MDR database
Achieved
|  | Source | [5 empty] | RISK RATING
|  |  | QuIC documentation, outputs from national MDR database, MoHS HMIS reports, District Dashboard outputs |  |  |  |  | Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
975000
INPUTS (HR) | DFID (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline (2011/12) | Milestone 1 (2012) | Milestone 2 (2014) | Milestone 3 | Target (2015) | Assumptions
Political leadership and public momentum | Percentage of MamaYe! press releases that lead to a published article in at least one newspaper, without incentive | Planned | No MamaYe! press releases |  | Sierra Leone’s engaged advocates/activists list (see output indicator 2.2) includes 20 journalists who have been sensitised to the campaign via training events or individual meetings |  | 50% | Advocacy groups receptive to working under unified national campaign. Advocacy messages do not create unforeseen conflict and tension. Political environment is conducive to independent media. Local and national media are receptive to using credible evidence for responsible reporting. Advocacy groups have potential for capacity development in branding, messaging and communication. Adequate numbers of skilled health workers are available to deliver improved quality of care (in both urban and rural areas). Theory of change is borne out in reality: better advocacy (in combination with better evidence and accountability) leads to improved quality of care, better use of evidence and increased political will within 4 years.
Achieved
Source
Internal monitoring tools
| Output Indicator 2.2 |  | Baseline (2011/2) | Milestone 1 (2012) | Milestone 2 (2013) | Milestone 3 | Target (2015)
| Number of advocates and activists engaged through E4A-supported national advocacy campaign Note: ‘engaged’ is defined as committed to E4A goals, and empowered by E4A with the power (evidence, information and/or strategy) to make change (real outcomes) | Planned | Weak & disparate MNH advocacy activities. Engaged advocates/activists: 0 |  |  |  | Engaged advocates/activists: 60.
Source
E4A country design reports, monthly country updates, quarterly internal monitoring reports, review of advocacy effectiveness and sustainability.
| Output Indicator 2.3 |  | Baseline (2011/12) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 | Target (2015)
| Accessibility of relevant MNH information and resources for stakeholders. | Planned | Basic evidence and core documents that would be essential for planning, decision-making and advocacy are largely difficult to access, inefficiently packaged & communicated for limited audiences and time-consuming to locate. There is a lack of synthesis and information-sharing between MNCH initiatives. |  | Improved functionality of website via updates to structure of evidence pages |  | Website is contributing to raised awareness of MNH by regular updates to the content, including technical updates, new evidence added at least quarterly, and links to other relevant websites
Achieved
Source
E4A country design reports, website analytics, user feedback, website content
| Output Indicator 2.4 |  | Baseline (2011/2) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 | Target (2015)
| Mean number of visits to national website per month (with "visits" as defined by Google Analytics at http://support.google.com/analytics/answer/2731565?hl=en-GB&topic=2524483&ctx=topic) | Planned | 0 |  | 700 |  | 800
Achieved
Source
Google Analytics
IMPACT WEIGHTING (%) | Output Indicator 2.5 |  | Baseline (2011/2) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 | Target (2015)
33.3 | Adoption of MamaYe! campaign by key engaged advocates/activists | Planned | MNH advocates and activists exist, but there is no co-ordination of effort on the MamaYe! ask and sub-asks |  | Activist engagement package delivered to district-level focal points, CSOs and partner organisations in 2 focal districts |  | MamaYe! activists (individuals and CSOs/organisations) advocate for MamaYe! ask / sub-asks at national level
Achieved
|  | Source | [5 empty] | RISK RATING
|  |  | ‘Activist engagement package’ records, E4A-commissioned operational research, records of the actions of activists, e.g. photos of demonstrations, copies of petitions. |  |  |  |  | Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
975000
INPUTS (HR) | DFID (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline (2011/12) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 | Target (2015) | Assumptions
Better national oversight and transparency of the provision of maternal and neonatal health (MNH) services, for better accountability for mothers and their babies. | Transparency of RCH budget | Planned | No mechanism for budget tracking |  | National Health Accounts established with ability to isolate MNCH spending |  | Status of national MNCH financing is made publicly available on MamaYe website and used by members from the budget tracking consortium to hold decision makers to account | Appropriate civil society groups with potential to form accountability mechanisms exist. Political environment enables independent and legitimate accountability mechanisms to be established. National and subnational governments receptive to transparency of information and budgeting. Media are receptive to using credible evidence for responsible reporting. Accountability mechanisms able to enforce effective sanctions. Adequate numbers of skilled health workers are available to deliver improved quality of care (in both urban and rural areas). Theory of change is borne out in reality: better accountability (in combination with better advocacy and evidence) leads to improved quality of care, better use of evidence and increased political will within 4 years.
Achieved
Source
National Health Accounts, scorecard outputs, press cuttings, records of CSO advocacy activity
IMPACT WEIGHTING (%) | Output Indicator 3.2 |  | Baseline (2011/12) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 | Target (2015)
33.3 | Number of people supported to hold decision-makers to account in relation to MNH | Planned | 0 | 2500 | 7000 |  | 10000
Achieved
|  | Source | [5 empty] | RISK RATING
|  |  | Monthly country updates, quarterly internal monitoring reports, external verification of E4A counts. |  |  |  |  | Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
975000
INPUTS (HR) | DFID (FTEs)

## Tanzania
PROJECT NAME | Reducing Maternal & Neonatal Mortality Tanzania
IMPACT | Impact Indicator 1 |  | Baseline (2011/12) | Milestone 1 (2012) | Milestone 2 (2014) | Milestone 3 | Target (2015)
Accelerated reduction in maternal and neonatal mortality | Maternal lives saved | Planned | 0 | 290 | 1600 |  | 3000
Achieved
Source
Multiple data sources used for projections - see LiST methodology
| Impact Indicator 2 |  | Baseline (2011/12) | Milestone 1 (2012) | Milestone 2 (2014) | Milestone 3 | Target (2015)
| Neonatal lives saved (including stillbirths) | Planned | 0 | 1500 | 8000 |  | 14500
Achieved
Source
Multiple data sources used for projections - see LiST methodology
| Impact Indicator 3 |  | Baseline (2011/12) | Milestone 1 (2012) | Milestone 2 (2014) | Milestone 3 | Target (2015)
| Stillbirths averted | Planned | 0 | 900 | 5300 |  | 10000
Achieved
Source
Multiple data sources used for projections - see LiST methodology
OUTCOME | Outcome Indicator 1 |  | Baseline (2012) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 | Target (2015) | Assumptions
Facilities equipped to save maternal and newborn lives | Use of evidence by national and sub-national health managers and health facility managers in their decision-making | Planned | Data exist but decision-makers need support to interpret and use the data. Use of data for decision-making score: 53% |  | Use of data for decision-making score: 58% |  | Use of data for decision-making score: TBC | Political instability does not undermine potential for impact. Governments receptive to efforts to increase political will. Project leverages additional resources to catalyse change. High-quality MNH data available. Theory of change is borne out in reality; more efficient use of resources plus improved use of data for decision-making plus increased political will leads to improved quality of care which leads to lives saved within 4 years.
Achieved
Source
Internal monitoring tool (DDM)
| Outcome Indicator 2 |  | Baseline (2012) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 | Target (2015)
| Political will to improve quality of care and the use of evidence for decision-making | Planned | PPP score: 60% |  | PPP score: 65% |  | PPP score: TBC
Achieved
Source
Internal monitoring tool (PPP)
| Outcome Indicator 3 |  | Baseline (2012) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 | Target (2015)
| Number of Government health centres in Mara providing CEmONC | Planned | 1 |  | 4 |  | 6
Achieved
Source
Mara Strategy monitoring data
| Outcome Indicator 4 |  | Baseline (2010) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 | Target (2015)
| % of live births in Mara attended by a doctor, clinical officer, nurse-midwife or MCH Aide | Planned | 30 |  | 40 |  | 45
Achieved
Source
2010 DHS (baseline), Mara Strategy monitoring data
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
2925000
INPUTS (HR) | DFID (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline (2011/2) | Milestone 1 (2012) | Milestone 2 (2013) | Milestone 3 | Target (2015) | Assumptions
Better information for better results: realising key parts of Commission on Information and Accountability (CoIA) recommendations in 6 countries. | Coverage of maternal and perinatal death reviews (MPDRs) | Planned | Most hospitals in Mara conduct MDRs, but it is not known whether they cover every maternal death, nor whether they use the nationally-approved protocol. |  |  |  | All 8 hospitals in Mara region review maternal deaths according to the nationally-approved MPDR guidelines | High-quality data available. Government receptive to evidence-driven management culture. In-country partners receptive to capacity-building in data management and communication. Health service managers receptive to culture of 'no blame' performance management. Sufficient resources can be leveraged to collect data suitable for disaggregation to sub-national levels. Harmonisation among partners for better management of results is effective in practice. Theory of change is borne out in reality: better evidence (in combination with better advocacy and accountability) leads to improved quality of care, better use of evidence and increased political will within 4 years. Partners implementing MPDRs in non-E4A regions remain committed to the MPDR process RMNCH scorecard mechanism is launched in April 2014 and is functioning effectively through to 2016 QuIC pilot will conclude that the methodology is suitable for rolling out more widely in Tanzania
Achieved
Source
National, regional and district MPDR committee meeting minutes/reports
| Output Indicator 1.2 |  | Baseline (2011/12) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 | Target (2015)
| Use of maternal death review (MPDR) findings | Planned | There is little follow-up on MDR findings |  | Training of hospital staff from 8 hospitals in Mara region on how to use MPDR findings (action and response) |  | All MPDR Committees in Mara region (1 regional and 6 district) use MPDR data from health facilities to inform their decision-making, including resource allocation
Achieved
Source
Training records/materials, MPDR Committee minutes/reports
| Output Indicator 1.3 |  | Baseline (2011/12) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 | Target (2015)
| Use of disaggregated maternal and newborn indicators from the CoIA list in progress and performance reviews. | Planned | Disaggregated data are used in reviews to some extent. |  | Disaggregated data used at a 6-monthly review meeting to evaluate progress against the 2013-2015 Mara Strategy |  | Disaggregated data from the national RMNCH scorecard are discussed by decision-makers at regional and district levels in 6 districts in Mara region at their regular meetings
Achieved
Source
MPDR Committee minutes/reports, budget documents
IMPACT WEIGHTING (%) | Output Indicator 1.4 |  | Baseline (2011/12) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 (Sept 2015) | Target (Dec 2015)
33.3 | Coverage of QuIC data collection system to monitor health facility readiness and ability to perform signal functions | Planned | No QuIC data collection system |  | One round of QuIC data collection completed in at least 50 health facilities in 6 focal districts | National stakeholder meeting convened to review the QuIC pilot and discuss scaling up of the QuIC system beyond the pilot districts | Plan for scaling up coverage of QuIC beyond Mara region developed, and shared with Ministry of Health
Achieved
|  | Source | [5 empty] | RISK RATING
|  |  | QuIC documentation, meeting minutes/reports, protocol for scaling up of QuIC |  |  |  |  | Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
975000
INPUTS (HR) | DFID (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline (2011/12) | Milestone 1 (2012) | Milestone 2 (2014) | Milestone 3 | Target (2015) | Assumptions
Political leadership and public momentum | Local media coverage of MNH issues | Planned | No local-level media journalists have been sensitised to the MamaYe campaign |  | Tanzania’s engaged advocates/activists list (see output indicator 2.2) includes journalists from at least 19 regions, who have been sensitised to the MamaYe campaign via training events |  | Community radio stations in at least 19 regions feature MNH stories generated by local journalists who are MamaYe advocates/activists | Advocacy groups receptive to working under unified national campaign. Advocacy messages do not create unforeseen conflict and tension. Political environment is conducive to independent media. Local and national media are receptive to using credible evidence for responsible reporting. Advocacy groups have potential for capacity development in branding, messaging and communication. Adequate numbers of skilled health workers are available to deliver improved quality of care (in both urban and rural areas). Theory of change is borne out in reality: better advocacy (in combination with better evidence and accountability) leads to improved quality of care, better use of evidence and increased political will within 4 years Union of Tanzanian Press Clubs continues to be committed to carrying out regular monitoring of community media houses’ outputs
Achieved
Source
Training session records, Union of Tanzanian Press Clubs' monitoring of community media houses (supported by E4A)
| Output Indicator 2.2 |  | Baseline (2011/2) | Milestone 1 (2012) | Milestone 2 (2013) | Milestone 3 | Target (2015)
| Number of advocates and activists engaged through E4A-supported national advocacy campaign Note: ‘engaged’ is defined as committed to E4A goals, and empowered by E4A with the power (evidence, information and/or strategy) to make change (real outcomes) | Planned | Weak national MNH campaign. Number of engaged advocates/activists: 0. |  |  |  | Number of engaged advocates and activists: 500
Source
Internal monitoring tools
| Output Indicator 2.3 |  | Baseline (2011/12) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 | Target (2015)
| Accessibility of relevant MNH information and resources for stakeholders. | Planned | Basic evidence and core documents that would be essential for planning, decision-making and advocacy are largely difficult to access, badly packaged, badly communicated and time-consuming to locate. There is a lack of synthesis and information-sharing between MNCH initiatives. |  | Improved functionality of website via updates to structure of evidence pages |  | Website is contributing to raised awareness of MNH by regular updates to the content, including technical updates, new evidence added at least quarterly, and links to other relevant websites
Achieved
Source
E4A country design reports, website analytics, user feedback, website content
| Output Indicator 2.4 |  | Baseline (2011/2) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 | Target (2015)
| Number of visits to national website per month, with "visits" as defined by Google Analytics at http://support.google.com/analytics/answer/2731565?hl=en-GB&topic=2524483&ctx=topic | Planned | 0 |  | 830 |  | 900
Achieved
Source
Google Analytics
IMPACT WEIGHTING (%) | Output Indicator 2.5 |  | Baseline (2012) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 | Target (Dec 2015)
33.3 | White Ribbon Alliance (Tanzania)’s capacity to influence MNH policy at national level | Planned | White Ribbon Alliance (Tanzania) has only a weak institutional and operational base |  | Formal capacity assessment carried out on WRA Tanzania, which informs institutional and operational capacity-building |  | E4A-supported evidence-based strategic planning process complete, resulting in a draft 5-year strategy for WRA Tanzania which is aligned with national commitments
Achieved
|  | Source | [5 empty] | RISK RATING
|  |  | Capacity assessment tools,WRA Strategic Plan, records of WRA activities |  |  |  |  | Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
975000
INPUTS (HR) | DFID (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline (2011/12) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 | Target (2015) | Assumptions
Better national oversight and transparency of the provision of maternal and neonatal health (MNH) services, for better accountability for mothers and their babies. | RMNCH budget advocacy forms key activity for civil society coalition | Planned | No co-ordinated advocacy on RMNCH funding and spend |  | Support provided to White Ribbon Alliance (Tanzania) to increase their capacity for budget advocacy |  | RMNCH financing is a key strategic objective for White Ribbon Alliance (Tanzania) in its strategic plan for 2015-2020 | Appropriate civil society groups with potential to form accountability mechanisms exist. Political environment enables independent and legitimate accountability mechanisms to be established. National and subnational governments receptive to transparency of information and budgeting. Media are receptive to using credible evidence for responsible reporting. Accountability mechanisms able to enforce effective sanctions. Adequate numbers of skilled health workers are available to deliver improved quality of care (in both urban and rural areas). Theory of change is borne out in reality: better accountability (in combination with better advocacy and evidence) leads to improved quality of care, better use of evidence and increased political will within 4 years.
Achieved
Source
Materials presented to WRA(T), WRA(T) Strategic Plan, records of WRA(T) activities
IMPACT WEIGHTING (%) | Output Indicator 3.2 |  | Baseline (2011/12) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 | Target (2015)
33.3 | Number of people supported to hold decision-makers to account in relation to MNH. | Planned | 0 |  | 10000 |  | 26000
Achieved
|  | Source | [5 empty] | RISK RATING
|  |  | Internal monitoring tool |  |  |  |  | Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
975000
INPUTS (HR) | DFID (FTEs)