Programme Completion Report - Top Sheet

This Top Sheet captures the headlines on the programme performances performance over the course of its lifetime. Teams should attach summary sheets from each annual review over the life of the programme.

Review Date:	July 2015

Title: / iiG: Improving Institutions for Pro-Poor Growth (Oxford)
Programme Code: 113580	Start Date: / January 2007	End Date: / 30 June 2015

Summary of Programme Performance

Year	2010	2011	2012	2013	2014	2015
Programme Score	75/100	75/100	A	A	A	A
Risk Rating	Low	Low	Low	Medium	Medium	Low

Financial Position

Original Programme Value	£2,749,891
Extensions/ amendments	August 2007 - no cost extension changing end date from Dec 2010 to Dec 2011 / July 2009 - £75,109 approved for a mid-term review and a contingency, outside the contract with Oxford University. / July 2011 - £1,085,042 (Phase 2 £996,423 plus an additional £88,619 for research already approved). / July 2013 – no cost extension of 18 months / Total budget = £3,910,042
Log-frame revisions (with dates)	2011 (Quest 3177502) / 2013 (Quest 5070437)
Total programme spend	£3,854696 / Ph 1 - £2,827,969 / Mid-Term Review - £30,304 / Ph 2 - £996,423

Follow up actions required following closure: It is recommended that iiG or CSAE staff participate ein the Growth Research Team’s Cross Portfolio Assessment which will help to better understand the impact and influence the programme has had as well as assessing the programme’s structure, governance and value for money.

It is recommended that 12 – 18 months following the closure of the programme DFID should meet with iiG again for a final impact discussion. As Phase 2 still has papers pending it would be useful to know how many papers did materialise and where they have been published. It would also be useful to know how the work of Phase 2 has been able to further influence debate and change policy because, as discussed in the next section, the programme has fallen behind on these outcome indicators for Phase 2 due to initial delays.

In addition, it would be a good opportunity to discuss the potential of CSAE producing some synthesis ‘state of knowledge’ papers on the findings of iiG within the broader literature on particular topics. Finally, it would also allow DFID an insight into how CSAE is further engaging in policy space after Stefan Dercon rejoins Oxford working across CSAE and the Blavatnik School of Government.
A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-113580/documents/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-113580/documents/

Outline of programme and what it has achieved: Improving Institutions for Growth (iiG) is a DFID Research Programme Consortium focusing on pro-poor growth and poverty reduction in Africa and South Asia. It was launched for a five year period in January 2007 with an allocation of £2,749,891. In July 2011 approval was given to extend the project to December 2013 and provide additional funding of £1,085,042 to support an extension to the programme’s work. Total funding now stands at £3,834,933. Phase 2 was granted a no-cost extension of 18 months following the 2013 Annual Review, to compensate for the fact that iiG had experienced high staff turnover and delays to fieldwork. Phase 2 will now end in July 2015.

In addition to DFID, the William and Flora Hewlett Foundation and the Open Society Institute provided $250,000 and $210,000 respectively of funding to Phase 1 of the project (approximately £250,000 in total) although they are not active in Phase 2.

iiG research focuses on a range of projects aimed at providing strong and convincing evidence on these hypotheses. It builds, in many cases, on other work already underway and uses the extensive research network that exists at the Centre for the Study of African Economies (CSAE).

iiG Phase 1 focused on three themes: i) institutions to promote manufactured exports, ii) institutions for accountability, iii) institutions for rural development and empowerment. It took the shape of an international network of applied research insitutes and researchers across Africa, Asia, and Europe desgined to provide governments and civil society in Africa and Asia, and development agencies, with usable and useful knowledge as to how institutions can be redesigned so as to be more conducive to growth and empowerment.

Phase 1 has produced outputs which include:
- An accessible body of research output for skilled policy makers on the themes of the RPC
- Accessible, non-technical output based on the research on institutions, growth and poverty.
- New comparative and context specific quantitative data sets on institutions.
- Strengthened capacity of partner institutions in RPC, especially in Africa, in analyzing the role of institutions and their reform for growth and poverty.

Phase 1 drew to a close in December 2013, with dissemination of research projects ongoing.

Phase 2 of the iiG began during 2011, on the theme of Growth, firms and markets in Africa. This second research phase grew out of the theme of ‘Firm development and exports’ from phase 1, extending into a study of how private sector activity and markets can assist growth and development in Africa, and looking at the institutional constraints limiting the impact of the private sector on growth. Phase 2 uses quantitative methods combining both observational and experimental data, and focusses on three closely-related themes, the answers to which are central to understanding the potential for market-led development in Africa: 1) What are the constraints to firm expansion in Africa? Does firm size matter for firm performance, and how can small firms grow large?; 2) What role does innovation and entrepreneurship play in determining firm success? Can an entrepreneurial class be fostered?; and 3) What are the institutional constraints to making markets work better for growth in Africa? Can emerging private markets help to overcome failures in factor and output markets to ensure that markets work for the poor?

In many countries, public services do not work, states struggle to manage social tensions, and governments fail to secure broad and sustainable development for their citizens. Weak states represent not only a major challenge to achieving the MDGs but also the greatest potential for increased global conflict and instability. The programme has contributed to DFID’s overall poverty reduction objective by producing new knowledge on how institutions work in developing countries and how they can be made to work better.

High policy relevance is given to a Private Sector Development research agenda in DFID’s corporate objectives. As set out in DFID’s Structural Reform Plan, under ‘wealth creation’ private sector development has become a key priority. The extension to the programme in the form of Phase 2, focused on carrying out further work on firm development, filling crucial evidence gaps and complementing our overall research programme in the area of growth and developing work on Private Sector Development.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Overall Outcome Assessment : A - The stated outcome of this programme was “to provide governments and civil society in Africa and Asia, and development agencies, with usable and useful knowledge as to how institutions can be redesigned so as to be more conducive to growth and empowerment.” The two indicators used were: i) Number of major policy changes related to institutional design in the context of growth and poverty reduction and ii) IIG’s level of influence on debates on institutional design in the context of growth and poverty reduction.

In DFID’s 2013 Annual Review Phase 1 received an A+ for it’s outcomes as it had exceeded the key targets under this crucial output by a substantial margin, with a strong publication record underpinned by a large volume of working papers. Phase 1 achieved 4 major policy changes: i) Work on trade preferences was influential in securing more liberal rules of origin under the Economic Partnership Agreements between the EU and African, Caribbean and Pacific countries – in particular the single transformation rule for garments. ii) A paper on economic liberalisation in India has added considerably to debate in media and in policy circles on the nature of labour regulation and its consequences in India. iii) Evaluations of India’s RSBY health insurance scheme succeeded in influencing the future contract design of the scheme. In particular, research findings had shown low levels of take-up amongst the poor covered by the scheme. This was partly because the concessionaire insurance companies implementing the scheme had no incentive to provide information to ensure it was actually utilised. The design has now been altered so that the premium paid to the insurance concessionaire falls if utilisation falls below a certain rate. iv) iiG researchers worked with the Board overseeing the Constituency Development Fund (CDF) in Kenya to analyse its activites for the first time. The findings offered several recommendations to the Board on how the CDF could be modified, some of which were later implemented, in particular the suggestion that a stricter monitoring system on how MPs spend their CDF allowance be implemented.
In terms of influencing debates Phase 1 produced 11 clear examples in the following areas: educational reform in Kenya; agricultural strategy in Ethiopia; press coverage of and the Lagos State Government’s engagement with iiG’s findings on security in Lagos; Indian press reports of iiG’s findings that the rural work guarantee (NREGA) is a potentially important anti-poverty tool”; iiG’s work on education in Uganda which culminated in seminars with the participation of ministers and senior officials, as well as detailed press coverage; iiG findings supporting the OECD project ‘Global Factors Influencing the Risk of Conflict and Fragility’; NGO voter education projects during the Nigeria Elections; the prevention of electoral conflict in Kenya; iiG findings on the aspirations of rural Ethiopians informed the design of a $20m development programme called Graduation with Resilience to Achieve Sustainable Development (GRAD) by the NGO CARE; microfinance in Bangladesh; and voter education using mobile phones in Mozambique.
The delay to Phase 2 has meant that it has been difficult for iiG to begin to influence debates on change policy in the absence of outputs until 2014, particularly as translating research outputs into policy practice through dissemination and uptake activities can be timely. The no-cost extension granted to iiG was intended, in part, to create space for the programme to achieve some substantial successes in the area before programme completion. As it stands Phase 2 has generated 3 clear examples of influencing debate:

i) ‘Two sides of the Same Rupee? Comparing Demand for Microcredit and Microsaving in a Framed Field Experiment in Rural Pakistan’ has been presented in Pakistan to a domestic policy audience. In addition to this, the work has led to two subsequent collaborations with Pakistan’s National Rural Support Programme (NRSP) aimed at designing better savings and credit products for the poor, with a particular focus on women. Continued interest from NRSP at the highest level lets us hope that some of the financial product features that we tested over the course of four distinct experiments will find their way into NRSP’s own financial offerings to Pakistani households.

ii) ‘Aspire’ CSAE Working Paper WPS/2014-34 is generating interest in business spheres. Simon Quinn and Marcel Fafchamps have been contacted by private sector individuals and organizations keen to learn from the project experience. The paper has clear policy implications that have been shared with our research partners in Ethiopia, Tanzania, and Zambia. In Ethiopia, this paper has been distributed to the Federal Micro and Small Enterprise Development Agency (FeMSEDA), the Addis Ababa Trade and Industry Bureau as well as the Ministry of Industry. http://www.iig.ox.ac.uk/research/53-seed-funding-startup-investment-ethiopia-tanzania-zambia.htm

iii) The lead researcher on the project that has produced 'Expropriation, compensation and transitions to new livelihoods: Evidence from an expropriation in Ethiopia', CSAE Working Paper WPS/2015-04, Anthony Harris, discussed the research with officials in Kombolcha in Addis Ababa, Ethiopia. Kombolcha is the town where the expropriations took place, and the City Manager Mr Habtu’s office was responsible for administering the land expropriation programme. Officials including the Mayor and Deputy Mayor were briefed on the first two rounds of the research results, and gave permission for a third round to be collected late 2014. It is anticipated that when further land expropriations are planned for the area, that these survey results will be taken in to account. http://www.iig.ox.ac.uk/research/58-land-transactions-repressed-markets-ethiopia.htm
Phase 2 has not yet demonstrated any examples of clear policy changes but these examples do provide potential opportunities and should be followed up during an impact meeting in 12 – 18 months. However, given that Phase 2 has not met the low indicators for either of these outcome indicators (0 against a low target of 2 for policy changes and 3 against a low target of 4 for influencing debate) it must be scored a B. Given the high performance of Phase 1, cumulatively the programme has met outcome expectations and therefore should score an A overall.

Output Score and Description: A – The project is Meeting Expectations - in terms of performance against logframe targets, the programme is likely to come to completion very close to target on all cumulatative indicators. The project scores an “A”.

1. In terms of producing research on links between institutions, growth and poverty, quantitatively validated and with specific recommendations for institutional and policy design, severe delays to fieldwork in Phase 2 have meant that for indicator 1 (number of papers in peer reviewed journals) Phase 2 has only met the lowest target. However in indicators 2 and 3 it has met the medium and high target respectively. In addition, given the high performance of Phase 1 that has continued to produce outputs beyond it’s closure cumulatively the programme has met the highest target in all 3 indicators. The results of Phase 1 set a good precedent for Phase 2 also producing outputs beyond it’s closure, as confirmed by iiG with papers still pending for the majority of projects – iiG are committed to submitting to high level journals for the best academic impact which DFID supports. Therefore for output 1 the programme scores an A+.

2. The programme has performed relatively well against indicator 1 (number of papers per year with co-authors from partner institutions published in peer reviewed journals, book chapters and in working paper series with Phase 1 producing 18 against a target of 10, Phase 2 exceeding the medium target by producing 2, and cumulatively producing 34 against a high target of 13. However, the programme is falling behind on the expected number of peer-reviewed papers reaching 7 against a target of 9. This serves to underline the very low publication rate of these papers relative to iiG’s output overall, where over half of papers make their way to journals. In regards to indicator 2, this was only applicable to Phase 1, during which the programme underperformed spending £682,556 on developing country partners against a cumulatative target of £899,636. Taking these two indicators together, for strengthened capacity of the partner institutions in the RPC in analyzing the role of institutions and their reform for growth and poverty, the programme scores a B.

3. This output regarding research on links between institutions, growth and poverty, quantitatively validated and with specific recommendations for institutional and policy design, with a clear gender dimension on is only applicable for Phase 2, however it should be acknowledged that Phase 1 did deliver a series of papers and policy briefs with a strong gender component. Phase 2 has produced 2 papers on the theme of firms and markets with a clear gender dimension and does not have any others in the pipeline, thus only meeting the low target. The programme therefore scores a B.

4. In terms of effective communication of research outputs Phase 1 met or exceeded targets for all 3 indicators. However, Phase 2 has been limited by the lack of underlying research outputs making it impossible for iiG to achieve the highest standards - it achieved 5 briefing papers just exceeding the low target of 4. However cumulatively the programme has produced 33 briefing papers, exceeding the medium target and just missing the highest target of 35. In addition, Phase 2 and the programme overall has exceeded expectations for the number of workshops conducted with at least 5 relevant stakeholders, conducting 4 in Phase 2 against a high target of 4 and cumulatively conducting 26 against a high target of 10. Finally, the website has remained up-to-date throughout the lifetime of the programme and over the last 12 months 222,000 visits were made to web pages on the iiG website, and 245,000 to PDF files. Therefore the programme scores an A for this output.

Lessons and how these have been shared: The key assumptions made prior to programme implementation were: i) sufficient time available for core research as well as writing research papers and ii) data collection and analysis proceeds on track, taking account of any external constraints. Whilst during Phase 1 these assumptions did hold, Phase 2 experienced severe delays throwing into question both of these assumptions. Phase 2 started seven months later than originally planned due to contracting delays. This initial delay meant iiG effectively lost the chance for any large data collection efforts during summer 2011. No costs had been incurred during the period of delay so a substantial no-cost extension of 18 month was provided to try and eliminate the problem of the late start. However, a relatively large turnover of senior level staff led to additional programme delays, and a subsequent rescheduling of the research programme. This has meant that although Phase 2 is still broadly on track for producing outputs, the delays have caused the programme to fall below some targets and mean that Phase 2 still has a relatively high number of outputs pending. Whilst staff turnover is often unpredictable, lessons should be learned and shared with the Growth Research Team from the contracting issues that caused the initial delay. The risk of similar issues arising in other programmes could be mititgated by inception phases, even mid way through a programme between phases.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Research on links between institutions, growth and poverty, quantitatively validated and with specific recommendations for institutional and policy design.
Output number per LF		1	Output Score	A+
Risk:		Low	Impact weighting (%):	50%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of papers in peer-reviewed journals	Ph1 Milestone 2009 - 15 / Ph1 Milestone 2011 – 30 accepted, 10 more submitted / Ph1 Target 2012 - 30 accepted, 10 more submitted / Ph2 - A, B or C additional journal papers on the theme of firms and markets, on top of Phase 1 target / Ph2 Milestone 2013 – A:1, B:0, C:0 / Ph2 Milestone 2014[1] – A:5, B:3, C:2 / Ph2 Target 2015 – A:10, B:6, C:3 / Cumulative Target 2015 - A:40, B:36, C:33	Ph1 2009 - 21 / Ph1 2011 – 29 accepted, 4 more submitted / Ph1 2012 – 37 accepted, 4 more submitted / Ph2 2013 – 1 (A) / Ph2 2015 – 1 (C) / Cumulative 2015[2] – 60 (A)
Number of working papers, book chapters and research reports	Ph1 Milestone 2009 - 12 / Ph1 Milestone 2011 - 25 / Ph1 Target 2012 - 25 / Ph2 - A, B or C additional working papers on the theme of firms and markets on top of Phase 1 target / Ph2 Milestone 2013 – A:5, B:2, C:1 / Ph2 Milestone 2014 – A:10, B:5, C:2 / Ph2 Target 2015 – A:15, B:10, C:5 / Cumulative Target 2015 – A:40, B:35, C:30	Ph1 2009 - 23 / Ph1 2011 - 41 / Ph1 2012 - 62 / Ph2 2013 - 3(B/A) / Ph2 2015 – 10 (B) / Cumulative 2015 – 100 (A)
Number of data sets	Ph1 Milestone 2010 – Kenya dataset on web / Ph1 Milestone 2011 - 3 datasets from Bangladesh, Kenya, and Ethiopia on web within 24 months of completion of survey work. / Ph1 Target 2012 - 3 datasets from Bangladesh, Kenya, and Ethiopia on web / Ph2 - A, B or C more datasets added on the theme of firms and markets / Ph2 Milestone 2013 – A:1, B:0, C:0 / Ph2 Milestone 2014 – A:2, B:1, C:0 / Ph2 Target 2015 – A:4, B:2, C:0 / Cumulative Target 2015 – A:7, B:5, C:3	Ph1 2010 / Ph1 2011 – 1 dataset (Kenya) / Ph1 2012 – 5 datasets / Ph2 2013 – 1 (A) / Ph2 2015 – 5 (A) / Cumulative Target 2015: 12 (A)
[1] Please note that for all outputs figures for December 2014 targets are not available as the iiG year runs from June – May. Outputs up until May 2014 are captured in ‘2013’ and outputs from June – December 2014 are captured in ‘2015’.
[2] For the majority of output indicators the cumulative figure includes additional outputs produced by Phase 1 following it’s closure. Hence cumulative figures are likely to be higher than simly the sum of Ph1 2012 and Ph2 2015.

Key Points: Phase 1 has exceeded expectations on all three indicators: by December 2012 37 papers had been accepted into peer-reviewed journals against a target of 30, 62 working papers, book chapters and research reports had been produced against a target of 25 and 5 datasets had been produced against a target of 3 (See Annex A). Phase 2 suffered from severe delays and consequently has not yet produced the expected number of journal articles – producing only one additional article on the themes of firms and markets by June 2015. However, nearly all projects are still expected to produce papers following the closure of the programme. This has not affected the programmes overall performance which has cumulatively produced 60 journal articles against and high target of 40 by June 2015. In addition, despite delays, Phase 2 has remained broadly on track for the latter two indicators and has met expectations in terms of the number of working papers, book chapters and research reports produced (10), bringing the cumulative figure to 100 by June 2015 against a high target of 40 and 5 data sets bringing the cumulatative figure to 12 against a high target of 7.

Summary of responses to issues raised in previous annual reviews (where relevant): In 2012 it was reported that the Ethiopia survey work for the third dataset had been severely delayed and iiG should therefore work at pace to provide additional datasets from other projects in Nigeria and Uganda/Tanzania. There was an agreement that iiG would move to publish datasets wherever possible and do so on a separate data section of the project website. iiG’s commitment to this is evident in the current figure of 7 datasets now available. In 2014 DFID recommended that iiG post the 3 working papers produced on the website following completion of the review and should accelerate work to complete all remaining working papers and begin the process of journal submission. Both of these recommendations have now been fulfilled.

Recommendations for future programmes: As delays to fieldwork cause severe delays in output 1, future programmes should seek to manage the assumption that there is sufficient time available for core research as well as writing papers within their allotted timeframe.
Output Title	Strengthened capacity of partner institutions in RPC in analyzing the role of institutions and their reform for growth and poverty.
Output number per LF		2	Output Score	B
Risk:		Low	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of papers per year with co-authors from partner institutions published in peer reviewed journals, book chapters and in working paper series.	Ph1 Milestone 2009 - 6 papers total, 2 in peer-reviewed journals / Ph1 Milestone 2011 – 10 papers, min 4 in peer reviewed journals / Ph1 Target 2012 - 10 papers total, min 4 in peer reviewed journals / A, B or C additional papers including authors from partners in developing countries on the theme of firms and markets of which at least one in peer reviewed journals. / Ph2 Milestone 2013 – A:1, B:0, C:0 / Ph2 Milestone 2014 – A:2, B:1, C:0 / Ph2 Target 2015 – A:3, B:1, C:0 / A, B or C additional papers including authors from partners in developing countries on the theme of firms and markets of which at least five in peer reviewed journals. / Cumulative Target 2015 – A:13, B:11, C:17	Ph1 2009 – 6 papers total, 2 in peer-reviewed journals[3] / Ph1 2011 – 19 papers total, 3 + 1 peer reviewed / Ph1 2012 – 18 papers total, 3 peer reviewed / Ph2 2013 – 1 (A) / Ph2 2015: 2, 1 peer reviewed (A/B) / Cumulative 2015 – 34 of which 7 are peer reviewed (A)
Spend on developing country partners (cumulatative)	Milestone 2008 - £162,315 / Milestone 2009 - £408,855 / Milestone 2010 – £574,057 / Cumulatative Target 2011 - £899,636	Milestone 2008 - / Milestone 2009 - £408,885 / Milestone 2010 – £574,057 / Cumulatative Target 2011 – £621,645
[3] 2010 AR stated ‘Significant proportion of the work is co-authored. Of particular note one book chapter and two working papers include Africa-based researchers (Alemayehu Seyoum and Germano Mwabu); both led the teams collecting the data and were main authors of the analysis. Two of the papers in peer-reviewed journals and several more working papers were co-written by researchers based in Africa that have since moved to research posts outside Africa. Three of the briefing papers were also co-authored and based on work by African partner researchers. There is also joint work with collaborators in BRAC (2 papers).’

Key Points: Phase 1 exceeded expectations on indicator 1, producing 18 papers against a target of 10, however the target of 4 in peer reviewed journals was missed by 1. Phase 1 fell behind on its target spend in its final year. In June 2011 DFID reported that the “the amounts invoiced to DFID have differed significantly from the forecasts of expenditure provided. This has caused difficulties for us in our financial management of our programme portfolio as well as in our financial reporting.” Phase 2 performed well against indicator 1, producing 2 additional papers including authors from partners in developing countries on the theme of firms and markets of which one was peer-reviewed (see Annex A). Cumulatively the programme has greatly exceeded the high target for indicator 1, producing 34 against a target of 13, however against a target of 9 being peer-reviewed it has only achieved 7.
Summary of responses to issues raised in previous annual reviews: Throughout the lifetime of the programme iiG produced many more papers co-authored with partner institutions than the target but often just missed the publication target. This serves to underline the very low publication rate of these papers relative to iiG’s output overall, where over half of papers make their way to journals.In 2014 it was recommended that iiG continue to involve developing country researchers in the writing up of remaining work. One additional working paper has been written and co-authored. Although there were no specified targets for spend in Phase 2, in the initial years there was significant underspend, however the project remained on track against financial forecast from 2014 onwards.

Recommendations for future programmes: Expectations were modest around indicator 1, as Phase 2 is conducted entirely in house without the involvement of partner institutions based in the South. Future programmes could consider building and maintaining partnerships dedicated to co-authoring of work and could be more specific in their planning and reporting of relationships with partner insitutions. Future programmes should ensure that they take into account the unintended consequences for research of revised EU legislation on VAT, and the subsequent interpretation by the Oxford VAT office. This effectively taxes fieldwork at 20%, and it is worth noting for future planning for research programme budgets.
Output Title	Research on links between institutions, growth and poverty, quantitatively validated and with specific recommendations for institutional and policy design, with a clear gender dimension
Output number per LF		3	Output Score	B
Risk:		Medium	Impact weighting (%):	15%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of papers per year on the theme of firms and markets with a clear gender dimension	A, B or C papers on the theme of firms and markets with a clear gender dimension. / Ph2 Milestone 2013 – A:1, B:0, C:0 / Ph2 Milestone 2014 – A:3, B:2, C:1 / Ph2 Target 2015 – A:5, B:3, C:2 / Cumulative Target 2015 - A:5, B:3, C:2	Ph2 2013 – 0 (B) / Ph2 2015 – 2(C) / Cumulative 2015 – 2 (C)

Key Points: Phase 2 has produced 2 papers on the theme of firms and markets with a clear gender dimension:

B71 Uzma Afzal, Giovanna d'Adda, Marcel Fafchamps, Simon Quinn and Farah Said, 'Two Sides of the Same Rupee? Comparing Demand for Microcredit and Microsaving in a Framed Field Experiment in Rural Pakistan', CSAE Working Paper WPS/2014-32, December 2014

B81 Rachel Cassidy and Marcel Fafchamps, 'Can community-based microfinance groups match savers with borrowers? Evidence from rural Malawi', CSAE Working Paper WPS/2015-13, May 2015

Although the programme has not quite met expecations on this indicator, as it was introduced at a later date, expectations around this indicator have been relatively low. In June 2014 the risk rating was raised to ‘medium’ as although 2 papers were in the pipeline, none had yet been produced. As these two papers have been completed by project completion and iiG phase 1 delivered a series of papers and policy briefs with a strong gender component it is appropriate to score the programme a ‘B’ in this indicator.

Summary of responses to issues raised in previous annual reviews (where relevant): In 2013 it was recommended that an 18 month no-cost extension be implemented to allow the programme an opportunity to produce outputs. This was granted, and although only 2 papers have been produced to date, this is in line with the general delay to output 1. In 2014 it was recommended that iiG prioritise gender-related work in the pipeline as much as possible – given that outputs rose from 0 to 2 between that annual review and this project completion report it is fair to say that this was prioritised in line with DFID recommendation.

Recommendations for future programmes: This output was unavoidably dependent on output 1 so whilst any future programme should seek to prioritise gender-related output, more generally, the time taken to conduct fieldwork and start producing papers should be estimated as realisitically as possible and potential delays identified, and if possible mitigated, as soon as they arise.

Output Title	Effective communication of research outcomes
Output number per LF		4	Output Score	A+
Risk:		Medium	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of briefing papers on research outcomes (cumulatative)	Ph1 Milestone 2009 – 10 briefing papers / Ph1 Milestone 2011 – 20 briefing papers / Ph1 Target 2012 - 20 briefing papers / A, B or C additional briefing papers / Ph2 Milestone 2013 – A:10, B:6, C:2 / Ph2 Milestone 2014 (cumulative from 2013) – A: 12, B:8, C:3 / Ph2 Target 2015 (cumulative from 2013) – A: 15, B:10, C:4 / Cumulative Target 2015 – A:35, B:30, C:24 (at least a third on theme of firms and markets)	Ph1 2009 – 10 + briefing papers / Ph1 2011 – 26 briefing papers + 4[4] / Ph1 2012 – 28 briefing papers + 4 / Ph2 2013 – 0 (C) / Ph2 2015 – 5 (C) / Cumulative 2015 – 33 (A/B)
Number of workshops with at least 5 relevant stakeholders (cumulatative)	Ph1 Milestone 2010 – 2 workshops / Ph1 Milestone 2011 – 6 workshops / Ph1 Target 2012 – 6 workshops / A, B or C additional workshops / Ph2 Milestone 2013 – A: 2, B:1, C:0 / Ph2 Milestone 2014 (cumulative from 2013) – A: 3, B:1, C:0 / Ph2 Target 2015 (cumulative from 2013) – A: 4, B:2, C:1 / Cumulative Target 2015 – A:10, B:8, C:6 (at least a quarter on theme of firms and markets)	Ph1 2010 – 5 workshops / Ph1 2011 – 18 workshops / Ph1 2012 – 22 workshops / Ph2 2013 – 0 (C) / Ph2 2015 – 4 (A) / Cumulative 2015 – 26(A)
Project website, kept up to date.	Ph1 Milestone 2009 - All briefing papers, data and research papers available on website in structured form / Ph1 Milestone 2011 – as above / Ph1 Target 2012 – as above / Ph2 Milestone 2013 – as above / Ph2 Milestone 2014 – as above / Ph2 Target 2015 – as above / Cumulative Target 2015 – as above	Ph1 2009 - Yes / Ph1 2011 – Yes but with recommendations[5] / Ph1 2012 - Yes / Ph2 2013 - Yes / Ph2 2015 - Yes / Cumulative 2015 - Yes
[4] Policy lessons papers
[5] DFID recommended that iiG Address the minor website issues and set up a data page. We also agreed to use the CSAE blog where possible to promote findings from iiG research and raise the profile of the programme.

Key Points: The programme met or exceeded expectations for all three indicators during Phase 1. Phase 2 has done less well on indicator 1, meeting only the lowest target for 2015, but cumulatively scoring between medium and high.	The potential output of this indicator in Phase 2 was obviously limited by the lack of underlying research outputs, making it impossible for iiG to achieve the highest standards. In addition, iiG took the decision to delay the production of briefs so that they would be higher quality. Regarding indicators 2 and 3, Phase 2 has performed well, greatly exceeding expectations of the number of workshops conducted (4 additional in Phase 2), resulting in a cumulative figure of 26 at project completion. The iiG website has been kept up to date. iiG outputs have become too numerous and complex to manage using the previous manual workflow method, and CSAE are now implementing more automated processes. Automating has revealed some previously undetected manual errors, and consequently there were a lot of changes in website content during this transition period. Over the 12 months to June 2015, 222,000 visits were made to web pages on the iiG website, and 245,000 to PDF files. The new statistics are provided by the University's hosting service, and attempt to exclude visits from search engines and other robot content-crawlers.
Summary of responses to issues raised in previous annual reviews (where relevant): In 2012, 2013 and 2014 it was recommended that 2 of iiG’s future policy briefs will cover: i) Gender aspects of private sector development and ii) Poverty and job creation. The programme has now produced policy briefs on gender aspects of private sector development, however it has yet to produce policy briefs on poverty and job creation (Annex A).

Recommendations for future programmes: As this output is heavily reliant on research outputs, future programmes should take into careful consideration the need to set realistic targets and timeframes.
## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

The key cost driver throughout the programme has been (direct) research costs (i.e. fieldwork). This was identified in the original business case and has not changed. While personnel is a significant item - particularly for some of the remaining activities like writing up working papers, the preparation of non-academic / communications material etc. – these are excluded from direct research costs which refer to the cost of conducting the surveys themselves. Direct costs were actually somewhat lower than forecast thanks to successful cost control and revisions to the method of data collection.

VfM performance compared to the original VfM proposition in the business case

While no VFM measures were agreed for Phase 1, DFID performed an internal assessment in early 2013 by combining iiG’s earlier reporting with Google Scholar citation records. Furthermore in 2014 DFID produced tentative calculations for value for money performance. Both are discussed below.
iiG’s regular financial reporting includes breakdowns of expenditure by category and Phase 2 accounts are also structured by sub-project to allow greater scrutiny. In November 2013 the University of Oxford introduced a new accounting system and information has been sent to DFID. More broadly, all procurement of goods and services by the University must be in accordance with the purchase to pay processes drawn up by the Finance Division. These require that the university seek value for money from suppliers for all purchases, with a tender process stipulated for purchases above £25,000 which must be carried out by the Purchasing Office for transactions over £100,000.

Assessment of whether the programme represented value for money

In terms of value for money iiG has performed consistently well. During the mid-term review in 2009 DFID reported that the iiG “is excellent value for money, in the sense that it has successfully leveraged significant external funds for many of its projects. One example puts this into perspective. The evaluation of BRAC‟s ultra-poor programme by iiG is costing GBP 130,000 – but this is part of almost GBP 1.3 million which BRAC are spending on the programme (drawn from other programme funding, including DFID). Throughout the iiG programme one sees examples in which iiG have strategically invested relatively small amounts of money to enable the scientific exploration of issues embedded in much larger programmes.”
In 2013 DFID found that iiG Phase 1 achieved an h-score of 18, meaning that it had produced 18 journal articles that had been cited at least 18 times. While there are few h-scores available for programmes of similar scale and maturity, this is a healthy result (some much larger programmes achieve similar scores

Quality of financial management during programme

While Phase 1 concluded largely as planned in 2012 (with a small underspend of £10,539), by June 2013 Phase 2 had spent at about half the rate planned (£0.26m relative to £0.5m originally forecast) due to slow progress in implementing fieldwork. Activity was also suspended for the first three months of 2013 while the Annual Review discussions were taking place. In May 2013 DFID granted an18-month extension and iiG submitted and a revised financial forecast through to June 2015. Against this forecast the programme has remained broadly on track.

Date of last narrative financial report	June 2015
Date of last audited annual statement	NA[6]
[6] Not required in contract

E: RISK (½ page)

Quality of risk management over the life of the programme

From the outset of this programme risks were identified within the logframe and monitored throughout the lifetime of the programme. Until 2013 the overall risk rating remained low with some initial risks being borne out. However, in June 2013 the overall risk rating of the project was raised to medium following serious problems that had hampered delivery over the previous 12 months. Furthermore, specific risks were thoroughly assessed (see Annex B).
For Phase 2 the key risks identified were 1) personnel turnover; 2) fieldwork delays due to government policy change; and 3) inadequate budget for personnel. iiG was hit particularly hard by senior personnel turnover, leading to delays in programme delivery. This situation resolved over time, and the programme has delivered on the revised project proposals. Reported fieldwork delays affecting project 55 ‘Re-ravelling’ the credit market in urban Tanzania’ have also been resolved in the last 12 months.
The risk of iiG misusing DFID funds has remained low over the course of the programme : the University of Oxford is a known and trusted partner and an exempt charity regulated by the Higher Education Funding Council for England (HEFCE). The University has a well-developed risk management framework involving a series of internal controls and underpinned by annual external audit in line with HEFCE guidance. Climate chage and environment risks have also been consistently low. Through its activities and actions the University recognises it impacts on the environment, locally, nationally and globally. The University will work to enhance its positive impact and reduce its negative impacts.
The main risk now facing the programme is that the networks established as part of iiG phase 1, and the research programme developed during iiG phase 2, will be lost without any specific follow up research programme. The CSAE has worked hard to ensure the continuing participation of the iiG phase 1 network partners, and many were involved in the March 2015 dissemination conference. The CSAE continues to foster these links. It is committed to maintaining the iiG website, and will undertake to update the output tracking tools until 2017 in the first instance.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

Phase 1 concluded broadly on-track, although continuing fieldwork (funded by other organisations) has delayed delivery of papers by 9 of the 48 sub-projects (about 10% of the programme in terms of value).
iiG Phase 2 fieldwork was put on hold during late 2012/early 2013 while proposed revisions to fieldwork were agreed, following the senior management changes. This initial delay meant iiG effectively lost the chance for any large data collection efforts during summer 2011. In 2013 3 of the 10 sub-projects cancelled outright. The remaining 7 were revised and rescheduled and a substitute introduced so that the Phase 2 portfolio was made up of 8 projects and a formal system was introduced for any further changes to the programme, which involved working sequentially down a list of preferred back-up projects should the need arise in 2013, while from January 2014 it was agreed that projects that experienced further delays would be cancelled outright. The project life was extended by 18 months to complete the second phase of work focusing on the private sector until June 2015.
Despite these factors, the programme output was back on on course by June 2014, with nearly all fieldwork completed. iiG are now anticipating that quite a long period of dissemination will occur after the official programme end.
Performance of partnership (s)

During Phase 1 DFID reported at mid-term that the iiG Programme had struggled with certain partner relationships since the outset of the programme and cited dependence on key individuals as well as political and institutional uncertainty as problematic factors in building institional relationships. However despite this iiG were able to create strong connections and ownership by key stakeholders, including NGOs and government ministries, through their approach of working with strongly motivated partners well connected with the policy process. Furthermore, in the 2013 Annual Review it was reported that there were three encouraging examples of collaboration with local partners in Uganda, Ethiopia and Nigeria that were likely to continue after DFID funding comes to an end.

Asset disposal and value obtained by DFID:

No assets to dispose of.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

No new evidence is available that fundamentally challenges the rationale for this research programme.

iiG will participate in a cross-portfolio assessment that has now be commissioned by DFID. This is an external review of the performance, value for money and potential influence of six growth research programmes. The findings will be used by the Growth Research Team (GRT) to help shape its future programme as well as looking to improve the programmes themselves. This assessment corresponds well to the recommendation of previous annual reviews that an evaluation should be commissioned to assess iiG outputs and influence.
In adidition, iiG intend to continue tracking iiG outputs for the immediate future, and at least until 2017. This tracking effort will include phase 1 as well as phase 2. The also anticipate welcoming phase 1 and 2 partners to annual CSAE conferences to present their iiG based research in 2016 and 2017.

Monitoring progress throughout the programme

This report has been conducted by members of the DFID Growth Research Team (Research and Evidence Division), led by the Senior Economist. A visit to iiG in Oxford was conducted and the report has subsequently been informed by discussions between iiG staff including the current Research Director and a leading academic.

Direct feedback from the academic, Simon Quinn, was very positive, with particular reference to the programme maintaining high academic integrity and being confident in it’s submissions to high level journals. They also spoke highly of the potential policy influence of the outputs of Phase 2, in particular their work in Pakistan which has led to two subsequent collaborations with Pakistan’s National Rural Support Programme (NRSP) aimed at designing better savings and credit products for the poor, with a particular focus on women. Continued interest from NRSP at the highest level lets us hope that some of the financial product features that we tested over the course of four distinct experiments will find their way into NRSP’s own financial offerings to Pakistani households.

Throughout the lifetime of the programme the iiG underwent thorough annual reviews, all of which are available on Quest.

Annex A – Phase 2 Outputs[7]
[7] As Phase 1 was signed off at 2013 Annual Review only Phase 2 outputs will be documented here.

Output 1 Indicator 1: articles in peer reviewed journals
A28 Stefan Dercon, Daniel Ayalew and Madhur Gautam, 'Property rights in a very poor country: Tenure insecurity and investment in Ethiopia', Agricultural Economics, Vol. 42 (1), pp. 75-86, 2011

Output 1 Indicator 2: Number of working papers, book chapters and research reports
B71	Uzma Afzal, Giovanna d'Adda, Marcel Fafchamps, Simon Quinn and Farah Said, 'Two Sides of the Same Rupee? Comparing Demand for Microcredit and Microsaving in a Framed Field Experiment in Rural Pakistan', CSAE Working Paper WPS/2014-32, December 2014
B72	Stefano Caria and Marcel Fafchamps, 'Cooperation and Expectations in Networks: Evidence from a Network Public Good Experiment in Rural India', CSAE Working Paper WPS/2014-33, August 2014
B73	Marcel Fafchamps and Simon Quinn, 'Aspire', CSAE Working Paper WPS/2014-34, December 2014
B74	Anthony Harris, 'Expropriation, Compensation and Transitions to New Livelihoods: Evidence from an Expropriation in Ethiopia', CSAE Working Paper WPS/2015-04, January 2015
B75	Elwyn Davies and Andrew Kerr, 'Firm Survival and Change in Ghana, 2003-2013', CSAE Working Paper WPS/2015-06, 2015
B76	Stefano Caria and Marcel Fafchamps, 'Can Farmers Create Efficient Information Networks? Experimental Evidence from Rural India', CSAE Working Paper WPS/2015-07, January 2015
B78	Elwyn Davies and Marcel Fafchamps, 'When No Bad Deed Goes Punished: A Relational Contracting Experiment in Ghana', CSAE Working Paper WPS/2015-08, March 2015
B79	Matthew Collin, Justin Sandefur and Andrew Zeitlin, 'Falling Off the Map: The Impact of Formalizing (Some) Informal Settlements in Tanzania', CSAE Working Paper WPS/2015-09, March 2015
B81	Rachel Cassidy and Marcel Fafchamps, 'Can Community-Based Microfinance Groups Match Savers with Borrowers? Evidence from Rural Malawi', CSAE Working Paper WPS/2015-13, May 2015

Output 1 Indicator 3: Number of datasets

G09	Dataset for: Daniel Ayalew Ali, Stefan Dercon and Madhur Gautam, "Property rights in a very poor country: tenure insecurity and investment in Ethiopia", Agricultural Economics Vol 42 (1): pp75-86, 2011
G10	Dataset for: Uzma Afzal, Giovanna d'Adda, Marcel Fafchamps, Simon Quinn and Farah Said, "Two Sides of the Same Rupee? Comparing Demand for Microcredit and Microsaving in a Framed Field Experiment in Rural Pakistan", CSAE Working Paper WPS/2014-32, 2014

G11	Dataset for: Stefano Caria and Marcel Fafchamps, "Cooperation and Expectations in Networks: Evidence from a Network Public Good Experiment in Rural India", CSAE WPS/2014-33, 2014
http://www.iig.ox.ac.uk/output/datasets/g11/iigdataset-g11.htm

G14	Dataset for: Elwyn Davies and Marcel Fafchamps, "When No Bad Deed Goes Punished: A Relational Contracting Experiment in Ghana", CSAE WPS/2015-08, 2015
http://www.iig.ox.ac.uk/output/datasets/g14/iigdataset-g14.htm

G15	Dataset for: Simon Quinn and Marcel Fafchamps, "Aspire", CSAE WPS/2014-34, 2015	http://www.iig.ox.ac.uk/output/datasets/g15/iigdataset-g15.htm

Datasets in progress (will be available on website in due course):

Project 55: ‘Re-ravelling’ the credit market in urban Tanzania: Are property rights the answer to credit market failure?

Project 58: Land transactions when markets are repressed: Evidence from Ethiopia

Project 61: Explaining insurance demand: Lessons from experiments in Ethiopia

Project 62: Savings, lending and default in community-based microfinance groups: Evidence from rural Malawi

Output 2 Indicator 1: Number of papers per year with co-authors from partner institutions published in peer reviewed journals, book chapters and in working paper series.

Peer reviewed journal article

A28 Stefan Dercon, Daniel Ayalew and Madhur Gautam, 'Property rights in a very poor country: Tenure insecurity and investment in Ethiopia', Agricultural Economics, Vol. 42 (1), pp. 75-86, 2011
Working paper
B71 Uzma Afzal, Giovanna d'Adda, Marcel Fafchamps, Simon Quinn and Farah Said, 'Two Sides of the Same Rupee? Comparing Demand for Microcredit and Microsaving in a Framed Field Experiment in Rural Pakistan', CSAE Working Paper WPS/2014-32, December 2014

Output 3 Indicator 1: Number of papers per year on the theme of firms and markets with a clear gender dimension
B71 Uzma Afzal, Giovanna d'Adda, Marcel Fafchamps, Simon Quinn and Farah Said, 'Two Sides of the Same Rupee? Comparing Demand for Microcredit and Microsaving in a Framed Field Experiment in Rural Pakistan', CSAE Working Paper WPS/2014-32, December 2014

B81 Rachel Cassidy and Marcel Fafchamps, 'Can community-based microfinance groups match savers with borrowers? Evidence from rural Malawi', CSAE Working Paper WPS/2015-13, May 2015

Output 4 Indicator 1: Number of briefing papers on research outcomes

C20 Daniel Clarke and Gerhard Toews, 'Insurance products for the poor should not be poor products', iiG Briefing Paper 17, November 2011

C27 Stefan Dercon, Ruth Vargas Hill, Daniel Clarke, Ingo Outes-Leon and Alemayehu Seyoum Tafesse, 'Offering rainfall insurance to informal insurance groups: evidence from a field experiment in Ethiopia', BREAD Policy Paper 032, November 2012

C30 Uzma Afzal and Farah Said, 'Microcredit and microsavings: Two sides of the same coin?', iiG Briefing Paper 25, March 2015

C31 Rachel Cassidy, 'Do community based microfinance groups work for their members?', iiG Briefing Paper 27, March 2015

C32 Anthony Harris, 'Coping with land expropriation in rural Ethiopia', iiG Briefing Paper 26, March 2015

Output 4 Indicator 2: Number of workshops with at least 5 relevant stakeholders

iiG events are reported on the website. Below is a list of the main events at which iiG phase 2 research was presented, with relevant weblinks if available.

CSAE Conference 2013, March 2013, CSAE, Oxford	http://www.csae.ox.ac.uk/conferences/2013-EdiA/

CSAE Conference 2014, March 2014, CSAE, Oxford	http://www.csae.ox.ac.uk/conferences/2014-EdiA/

iiG Conference 2015: Improving Institutions for Growth, March 2015, CSAE, Oxford	http://www.iig.ox.ac.uk/events/2015-03-20-iig-conference.htm
Microfinance and Enterprise Development Research Prospects and Challenges, 16 April 2015, Lahore School of Economics, Pakistan	http://www.iig.ox.ac.uk/events/2015-04-16-iig-conference.htm

Annex B: Risk Management

Risk	Probability	Impact	Comments/Revisions
iiG fails to gain access to high-level policy makers	MEDIUM	HIGH	This risk rating is being raised to MEDIUM due to the limited time iiG will have to disseminate mature outputs. Although it is developing plans for a major end-of-programme conference which should mitigate this, iiG should consider what other activities will help to achieve its outcome targets.
Key policymakers targeted by the programme cease to be influential.	LOW	HIGH	While iiG has little choice but to work with incumbent governments to implement new research, it disseminates the knowledge generated as a public good available to all, and promotes the findings to other stakeholders
Insufficient time available for core research as well as writing papers.	MEDIUM	HIGH	While fieldwork is largely complete, some analysis remains to be done in a very limited time to publish papers, so the MEDIUM rating remains appropriate.
Data collection and analysis delayed (due to external constraints e.g. project to be studied itself delayed)	MEDIUM	HIGH	There have indeed been delays to this activity, so although it is drawing to a concluding phase the rating of MEDIUM remains appropriate.
Co-authors from participating institutions cease to be involved or there is high CSAE staff turnover.	MEDIUM	HIGH	A steady team has remained in charge of iiG for the last two years, but any disruption to the research teams at this critical time would also be highly disruptive, so the risk rating of MEDIUM, though conservative, remains in place.
Those whose skills were developed in terms of briefing paper writing cease to be involved in RPC.	LOW	LOW
Research does not produce any findings that are worthy of communication (i.e. the research is carried out properly but can't produce conclusive results)	LOW	LOW