Annual Review

Title: Support to the United Nations Relief and Works Agency for Palestine Refugees in the Near East (UNRWA) Syria Emergency Appeals 2017-2020
Programme Value £ (full life): £36,000,000		Review Date: 13/09/2019
Programme Code: 300389	Start Date: 01/10/17	End Date: 31/03/2020

Summary of Programme Performance
Year	2017	2018	2019	2020
Programme Score	A	A
Risk Rating	Severe	Severe

DevTracker Link to Business Case:	32128197
DevTracker Link to Log frame:	36335894

A. Summary and Overview

Table 1: Budget breakdown by Financial Year
Component 300388-101	FY 2017/18	FY 2018/19	FY 2019/20	Total
Total	£12m	£17m	£7m	£36m

Description of programme

DFID is providing the United Nations Relief Works Agency for Palestinian Refugees in the Near East (UNRWA) with £36,000,000 over three years as a contribution to the Syria Emergency Appeal (EA). UK support to UNRWA Syria (hereby referred to as UNRWA) aims to provide essential humanitarian support to the 438,000 Palestine refugees inside Syria (PRS) affected by the ongoing crisis.

The UK’s contribution amounted to 19% of UNRWA’s Syria EA in 2018. This contribution was used by UNRWA to provide cash assistance to 405,644 of the 438,000 PRS (for food, household items, shelter and other necessities), allowing them to meet their basic needs. In 2018, with UK support, UNRWA provided inclusive, quality and safe education to almost 50,000 Palestine refugee students in Syria. UNRWA also supported PRS families with healthcare, either conducting primary healthcare visits through UNRWA health facilities or supporting PRS to access hospitals should they need further care. Finally, UNRWA implemented activities such as psychosocial care and legal assistance to address protection issues linked to conflict-related violence.

This is the second Annual Review for the programme and covers UNRWA’s 2018 Syria EA activities. This review is based on results presented within the UNRWA Annual Operational Report (AOR) 2018, received in June 2019. It also provides some updates from the first two quarters of 2019 (Jan-Mar and Apr-June).

Summary supporting narrative for the overall score in this review

UNRWA has delivered well against their 2018 milestones, scoring an A (meeting expectations) overall. Several key points should be noted:

The vulnerability of PRS remains high: 90.5% of PRS households live in absolute poverty (less than USD 2 person/day), and 79.5% live in extreme poverty (less than USD 1.5 per person/day). Of the 438,000 Palestine refugees remaining in Syria, 60% have been displaced at least once, 13,500 are in hard-to-reach areas and 126,000 have been identified by UNWRA as extremely vulnerable.

UNRWA is the only agency mandated to provide services to this population. While they coordinate with other agencies, PRS fall strictly under UNRWA’s mandate and are generally not provided services by other UN or NGO agencies (except for some instances where UNRWA has no access, such as in Idleb). Inside Syria, UNRWA is often the only organisation with the access, permission, international mandate and capacity required to assist PRS. Without DFID’s continued support to UNRWA there is a risk that the needs of this vulnerable group will not be met (in Damascus/Rif Damascus, Aleppo, Hama, Homs, Latakia, and Dar’a).

UNRWA maintain a flexible and adaptable response to the conflict in Syria. For example, in 2018, by increasing service provision as new areas became accessible (such as resuming the provision of basic services and emergency assistance in the South of Syria) and addressing barriers to access (such as providing a one-time emergency cash assistance grant to families in Eastern Ghouta and Southern Damascus affected by hostilities).

This is despite ongoing and increasingly severe underfunding faced by UNRWA organisationally, and especially the Syria EA. In January 2018, the United States confirmed it was withdrawing its support for UNRWA. The US has long been the largest individual donor to UNRWA, pledging about one third of the Agency’s $1.2bn annual budget. The US contributed 70% ($85m) of UNRWA’s Syria EA funding, so this decision has caused a financial crisis for UNRWA.

All activities, programming and systems have been impacted by the funding crisis. In response UNRWA have undergone substantial efficiency measures, but the Syria Field Office’s internal capacity is now one of the key challenges to their operations and is impeding their ability to sustainably deliver. Efforts to reduce operating costs and increase efficiency have resulted in difficulties recruiting and retaining staff, driven by internal uncertainty, visa delays, short-term contracts and deprioritising recruitment.

The number of beneficiaries reached has not decreased in line with the funding deficit: in 2018, almost all 438,000 PRS were reached by UNRWA with emergency assistance interventions, despite the Syria Emergency Appeal being only 12.5% funded. This means UNRWA staff are still delivering to the same number of beneficiaries. Despite challenges with capacity, UNRWA continued to deliver services through available resources (including human resources) and are pursuing recruitments to restore capacity, but this should be monitored.

UNRWA’s extensive use of cash assistance makes them an important partner for DFID in Syria. Their well-established cash transfer system allows them to reach almost all PRS rapidly. It also enables them to absorb additional funds at scale. If further funds became available, UNRWA could increase their cash transfers rapidly with no impact on their current staff capacity or increased operating costs.

Protection is integral to UNRWA’s work. Protection is mainstreamed throughout UNRWA’s work, but funding constraints combined with capacity shortfalls limit UNRWA’s ability to prioritise protection. Given the significant protection issues amongst the PRS community, such as housing, land and property, this is of concern.

Table 2: Summary of Output scores

#	Output	Impact weighting	Score
1	Palestinian refugees are able to meet their essential life-saving needs and cope with sudden crises	40	A
2	Palestine refugees’ emergency health needs are met	20	B
3	Palestine refugee children in Syria are able to access quality, equitable and inclusive basic education, recreational activities and psychosocial support	20	A+
4	Strengthened prevention and protection response for Palestinian refugees	10	A
5	Palestinian refugees’ water, sanitation and public health needs are met	10	A

Table 3: Key recommendations for the year ahead

#	Actions	Target completion date	Owner
1	Cash assistance: UNRWA and DFID’s cash assistance leads to attend next quarterly meeting	Dec 19	UNRWA/ DFID
2	NFIs: DFID and UNRWA to agree wording of Indicator 1.3 to avoid double-counting.	Dec 19	DFID/UNRWA
3	PSS: UNRWA to consider sharing the evaluation/ engaging with DFID’s Social Development Advisor and Education Advisor on PSS activities	Mar 20	UNRWA/ DFID
4	Education: UNRWA to continue attending DFID’s bi-quarterly education meetings to facilitate learning and best practice approaches across DFID’s portfolio.	Ongoing	UNRWA
5	Protection: UNRWA should consider weighting any additional funding for the 2019 Emergency Appeal towards protection activities	By end 2019	UNRWA
6	WASH: DFID and UNRWA to discuss possible revision of WASH and public health indicators	Dec 19	DFID/ UNRWA
7	Outcome indicators: DFID and UNRWA to explore the possibility of an evaluation or alternative narrative to assess the outcomes of this programme.	Mar 20	UNRWA
8	Internal capacity: UNRWA to consider recruiting technical posts through the Standby Partnership Programme to rapidly increase their human resources at short notice. DFID (and other donors) can then consider funding these posts.	Mar 20	DFID
9	Safeguarding: Given their unique operating model, UNRWA should explore ways to ensure their anonymous safeguarding reporting channels are communicated to affected populations.	Mar 20	UNRWA

## B: DETAILED OUTPUT SCORING

Output Title	Palestinian refugees are able to meet their essential life-saving needs and cope with sudden crises.
Output number per LF		1	Output Score	A
Impact weighting (%):		40	Impact weighting % revised since last AR?	Y (↑ 10%)

Indicator(s)	2018 Milestones	Progress
1.1 Number of Palestinian refugees provided with cash assistance during the latest distribution round (disaggregated)	410,000	405,644 (212,469 female; 193,175 male) (99% achieved)
1.2 Number of Palestinian refugee individuals provided with in-kind food assistance during the latest distribution round	410,000	395,499 (96% achieved)
1.3 Number of Palestinian refugee individuals receiving NFIs	34,000	35,000 (103%)
1.4 Number of displaced people receiving shelter at UNRWA facilities	0	0 (100% achieved)

Provide supporting narrative for the score

Performance on Output 1 scored an A, with all indicators meeting expectation (within a 5% tolerance). The activities carried out under Output 1 strongly contributed to achievement at the outcome level. UNRWA estimates that 438,000 Palestinian refugees remain in Syria and, against challenging external contexts, they reached 405,644 PRS, or 93% of the total PRS population, with one or more emergency assistance intervention in 2018.

Indicator 1.1- Number of Palestinian refugees provided with cash assistance during the latest distribution round

Three rounds of cash were distributed in 2018, reaching 405,644 PRS. In the first round, each beneficiary received the equivalent of US$64 in Syrian pounds (as they did in 2017) to assist in covering their basic needs for two months ($32 per person per month - $20 for food and $12 for NFIs in line with the Syria Humanitarian Response Plan.) Due to the funding shortfalls, UNRWA reduced the amount of cash assistance provided per person during the second and third distribution rounds; and scaled down the number of rounds from six to three. Each beneficiary received US$46 to cover their needs for two months ($23 per month). UNRWA prioritised support to ensure that the limited funding available was used as effectively as possible to maintain beneficiary reach, despite reducing the frequency and volume of assistance.

UNRWA prioritised spend on this Output in 2018, spending US$55,974,710 (or 69.4%) of their received contributions on cash assistance. Of DFID’s implementing partners, this makes UNRWA one of the largest cash assistance providers in Syria. This is in line with DFID’s Humanitarian Strategy, which emphasises prioritising cash where feasible and emergency response and basic service provision to those most in need.

Cash assistance ensures UNRWA are reaching the most in need. Through their partnership with two Syrian banks and one money transfer organisation, UNRWA distributes cash to 50 collection points across Syria. In besieged or hard-to-reach areas, UNRWA have a well-tested delegation system in place so people can collect money on behalf of other beneficiaries. UNRWA have recently introduced ATM cards for transferring money digitally. They are currently running a pilot with 10,000 families and plan to expand this mechanism if it is successful.

In addition to reaching people in besieged or hard-to-reach areas, cash assistance allows UNRWA to respond flexibly to the ongoing crisis. For example, in addition to the 405,644 PRS reached through the cash assistance rounds, UNRWA provided a one-time emergency cash assistance grant of US$70 per family to 2,527 families affected by hostilities in Eastern Ghouta and Southern Damascus during the intense fighting.

Given the scale of UNRWA’s cash assistance intervention and its priority within DFID’s Humanitarian Strategy, we recommend cash assistance leads from both UNRWA and DFID attend the next quarterly meeting (Dec 19) to exchange knowledge and best practice.

Recommendation: UNRWA and DFID’s cash assistance leads to attend next quarterly meeting (Dec 19)

Indicator 1.2- Number of Palestinian refugee individuals provided with in-kind food assistance during the latest distribution round

In 2018 UNRWA conducted three food distribution rounds, reaching 388,564 beneficiaries in the first round, 387,530 in the second, and 395,499 in the last round, which concluded in December 2018.

UNRWA’s assessment of their in-kind food assistance showed positive feedback from beneficiaries. 89% of the respondents did not face any challenges when collecting their food assistance, while 11% faced challenges that included transport to the distribution centre, misunderstandings with distribution staff and wrong date of ration collection. In terms of the food baskets, most of the beneficiaries were satisfied with the duration of the food rounds and found the quality of the food basket to be generally good. Food baskets contained items such as canned beef, sardines, sunflower oil, milk, dry beans, sugar and bulgur wheat (designed to ensure PRS households have acceptable food consumption). However, respondents said that the basket was small, and they could not make up the difference from the market through the cash assistance. This reflects the fact that the majority of the PRS depend on humanitarian assistance as their source of food.

To note, UNRWA have now introduced a targeting approach to their food-assistance. From 2019, UNRWA began only distributing food assistance to people that are categorised as the most vulnerable (and extended to persons in access-restricted areas such as Yalda and in certain instances to cases of spontaneous returns upon assessment). This is discussed further below.

Indicator 1.3- Number of Palestinian refugee individuals receiving non-food items (NFIs)

In 2018, 35,000 PRS were provided with NFI’s, including hygiene kits, blankets, and mattresses. The hygiene kit includes items such as sanitary napkins, soap, toothbrushes, and towels and other items. The also take into consideration gender needs, intended to help maintain women’s dignity and support their mobility during crisis situations. The availability of these items (or lack of) will directly impact the dignity, health, mobility, and security of women and girls. NFI were mainly distributed in areas affected by conflict and situations of fresh displacement such as in Eastern Ghouta, Yalda, and Dar’a.

UNRWA’s results-based monitoring system doesn’t track which individual people receive NFIs. Rather it tracks the number of NFI’s (hygiene kits, blankets etc.) distributed to PRS (including their location). On that basis, the same person could receive several NFIs. The current indicator risks double-counting NFI’s given to the same people. We therefore recommend reviewing the wording of this indictor, to, for example, ““Number of NFIs distributed to Palestine refugees based on need”.

Recommendation: DFID and UNRWA to agree wording of Indicator 1.3 to avoid double-counting (by Dec 19).

Indicator 1.4- Number of displaced people receiving shelter at UNRWA facilities

At the start of the year, UNRWA was hosting 1,706 IDPs in nine collective shelters. After intense fighting, large numbers of PRS were forced to leave major camps or displacement areas, such as Yarmouk camp. Given the urgent need, UNRWA opened collective shelters in their facilities, such as their schools, for PRS to temporarily live.

UNRWA closed the last collective shelters in May 2018. The collective shelters were closed by UNRWA as part of their strategy to provide sustainable accommodation to the IDPs and to return the IDP shelters to Education Programme.

At the start of 2018 the milestone for indicator 1.4 was 1500. Had the collective shelters remained open, UNRWA would have exceeded this milestone. However, because of the intentional decision to close the shelters, we revised the target to zero during the year so as not to distort UNRWA’s achievements.

Before closing the shelters, UNRWA conducted in depth assessments with all shelter residents to ensure that they had accommodation. The level of support to refugees relocating to alternative accommodation was determined based on a vulnerability assessment, paying special attention to more vulnerable families and individuals. Cases raising concerns were assessed through a review committee, and protection cases were managed on an ad-hoc basis according to needs. All IDPs in temporary shelters received food and NFI assistance from UNRWA until the closure of the shelters in May 2018. All families then received a one-time case assistance grant to help them relocate to alternative accommodation. The buildings were then handed back to the Education Programme to serve as schools, seven of which were rehabilitated and reopened in time for the start of the academic year in September 2018.

Lessons identified this year, and recommendations for the year ahead linked to this output

Targeting

In the 2017 Annual Review DFID recommended UNRWA implement a targeting approach for their emergency assistance interventions. The driver for this was two-fold: it would allow UNRWA to focus on those with the most acute needs within this already vulnerable population, and, given the significant funding constraints, it would deliver even greater value for money. The Vulnerability Assessment identified four categories that UNRWA now refer to as the ‘most vulnerable’ (noting that the entire PRS population is ‘vulnerable’): female headed households; the elderly; people with disabilities; and orphans.

UNRWA’s Vulnerability Assessment survey and data collection was completed in December 2017. The analysis and report were then finalised in 2018 and were used to inform the planning for 2019 Emergency Appeal. Although this was recommended by DFID in the 2017 Annual Review, the targeting approach was not used in 2018 because this required preparation in UNRWA’s registration system and updating the records of eligible refugees who could fit under the four categories identified above. The new targeting approach started by the first round of food distribution in 2019 and the second round of cash assistance in 2019. The first round of cash assistance in 2019 was still using the old approach because when UNRWA launched it in January, they were still updating their records. They also had to await approval from GAPAR on the approach and feasibility. Although UNRWA delivers to all PRS, we will continue to monitor the potential harm caused to those not included within the targeting approach. In particular, we have asked UNWRA to closely monitor the risk that people who fall outside these categories, who may perceive themselves as being excluded from aid distributions, become marginalised and at risk of radicalisation.

Post Distribution Monitoring Assessment

During the reporting period UNRWA undertook a Post Distribution Monitoring Assessment (PDM) to assess how reliably and efficiently beneficiaries were accessing the assistance they were entitled to and to clarify how they used the assistance. UNRWA conducted interviews with 600 households (0.5% of the 118,000 households they support) and 584 valid questionnaires were returned.

The PDM found that 96% of the respondents stated that they prefer cash over food as a form of assistance. In light of this (and given cash assistance is generally considered to empower beneficiaries and increase efficiency), UNRWA Syria are now targeting their food-assistance. From 2019, UNRWA began only distributing food assistance to people that are categorised as the most vulnerable (and extended to persons in access-restricted areas such as Yalda and in certain instances to cases of spontaneous returns upon assessment). This is discussed further below.

The PDM also found that PRS spend most of their cash grants on rent, with 66% of the respondents ranking it their number 1 expenditure. This reflects the general situation faced by the majority of PRS who lost their homes and are currently renting. Anecdotal evidence suggests this remains the case, despite UNRWA not having finalised the results from the recent PDM. UNRWA is increasingly concerned about this- shelter is one of the biggest needs for PRS, and often the highest cost burden. This further exacerbates the already adverse socio-economic conditions PRS face.

Output Title	Palestine refugees’ emergency health needs are met.
Output number per LF		2	Output Score	B
Impact weighting (%):		20	Impact weighting % revised since last AR?	Y (↑ 5%)

Indicator(s)	2018 Milestones	Progress
2.1 Number of Palestinian refugee visits to UNRWA heath facilities (disaggregated)	850,000	842,158 (451,978 female; 390,180 male) (99% achieved)
2.2 Number of UNRWA health centres, health points, and mobile clinics	26	24 (92% achieved)
2.3 Number of UNRWA hospitalisations accessed by PRS patients	17,000	11,838 (70% achieved)
2.4 Percentage of health centres with no stock-out of 12 tracer items	100%	78% (78% achieved)

Briefly describe the output and provide supporting narrative for the score

Performance on Output 2 technically scored a B, with three indicators not meeting expectation and the other meeting expectation within the 5% tolerance. This is because the targets weren’t adjusted to reflect planned changes, rather than because UNRWA did not achieve their intended results. Details are included under the relevant indicator.

UNRWA continued to deliver critical health services to Palestine refugees, including referrals to secondary and tertiary care. Moreover, feedback from DFID’s independent monitoring conducted in 2018 showed a very high level of satisfaction with the quality of care and of staffing. In order to ensure that in future, UNRWA’s score on this indicator better reflects their achievements, we should work to solve the monitoring and evaluation issues.

Recommendation: UNRWA to resolve monitoring and evaluation issues on Output 2.

Indicator 2.1- Number of Palestinian refugee visits to UNRWA heath facilities

In 2018, UNRWA provided 842,158 primary health care consultations through 22 health facilities and two mobile clinics in Syria. 53% of these consultations were with females, 47% with males. Services included maternal and child healthcare, treatment for non-communicable diseases, laboratory tests and dental care.

Results against this indicator improved during 2018. In 2017, UNRWA achieved 82% of the target for health consultations. In 2018, this increased to 99%. UNRWA report that this is due to the implementation of the health reforms, including (i) the e-Health system, a patient appointment system that contributes to a more streamlined workload for doctors, improved service coverage and quality, and better tracking of patient information, particularly regarding treatment; and (ii) a Family Health Team approach, which is a person-centred approach to improve the quality and delivery of public primary health care taking into consideration the comprehensive health status or the family history of an individual. These reforms have led to an increase in the quality of reporting against services provided and better clarity on patient tracking, thus eliminating potential duplicate records of cases not requiring medical staff’s attention (e.g. patients collecting prescribed periodic medication). This milestone has been revised downwards for the 2019 Emergency Appeal to 840,000.

Indicator 2.2- Number of UNRWA health centres, health points, and mobile clinics

UNRWA started 2018 with 27 health care facilities. In addition, one health centre was re-opened in Sbeineh camp. Four health points in collective shelters and gatherings were closed with the complete closure of all collective shelters in May 2018. The collective shelters were closed by UNRWA as part of their strategy to provide sustainable accommodation to the IDPs and to return the IDP shelters to Education Programme. PRS who were in collective shelters and gatherings were then able to register at health centres in their new place of residence (contributing to Output 2.1). Those that moved to Sbeineh camp were registered in the new health centre in the camp. Although UNRWA technically missed this target, the planned closure of the collective shelters and UNRWA’s continued provision of primary healthcare to all PRS means that, in practice, UNRWA are meeting our expectations.

Indicator 2.3- Number of UNRWA hospitalisations accessed by PRS patients

UNRWA marginally missed this target. This wasn’t due to a lack of hospitalisations, rather it is a monitoring and evaluation issue. UNRWA refers patients to hospitals, who then invoice UNRWA the cost of the care. However, this can take several months, meaning UNRWA’s reporting is delayed. In this case, had UNRWA had the December 2018 referrals when finalising their 2018 results, they would have achieved 87% of the target. UNRWA are reviewing this indicator to try and improve the reporting issues.

UNRWA’s health facilities provide primary, day-to-day healthcare which is available in all UNRWA’s areas of operation and the first place PRS go when they need health advice or treatment. If patients require further treatment, UNRWA have two mechanisms through which they support PRS to access secondary or tertiary care.

The first is referrals to hospitals. UNRWA have agreements with 27 hospitals across Syria to which they can refer their patients. Once the patient has been referred and undergone care, UNRWA then reimburse the patient for the cost of the treatment. In most circumstances, patients pay 25% of the cost and UNRWA reimburse 75%. In hardship cases, UNRWA reimburse 95% of the cost. The second is subsidising further treatment. If there is a medicine or test that a patient needs that UNRWA does not provide through their facilities, patients can go to other pharmacies or clinics and UNRWA will subsidise the cost.

Historically, PRS were able to access free health care through the Syrian public health system. The conflict has put immense pressure on the entire Syrian public sector, including the health system. In 2017 new instructions were issued to ensure free hospitalisations applied only to Syrian nationals. This resulted in increased demand for subsidised care. There was an expectation that, given their mandate, UNRWA would pick up the cost of this for PRS. UNRWA began budgeting for this under the Emergency Appeal, but, given the need, in 2018 this assistance measure was predominately supported by non-EA earmarked grants.

Indicator 2.4- Percentage of health centres with no stock-out of 12 tracer items

Although UNRWA missed this target, it was predominately down to access constraints outside of UNRWA’s control which improved towards the end of the year. All UNRWA health clinics in Syria received regular medical supplies in the second half of 2018, showing an improvement compared with the first six months of the year when disruptions in medical stocks were reported in Muzeirib clinic in Dera’a governorate due to access constraints, with patients having to travel to Dera’a city to seek medical support through UNRWA’s clinic in that area. In the fourth quarter of 2018, none of the health facilities experienced shortages of drugs, achieving 100 per cent of the expected target of health centres operating with no stock-out of 12 tracer items for quarter four 2018. DFID’s Results Advisor should consider whether this indicator fairly reflects changes throughout the year that are outside UNRWA’s control, and whether this indicator could be adjusted to better reflect such issues.

Output Title	Palestine refugee children in Syria are able to access quality, equitable and inclusive basic education, recreational activities and psychosocial support.
Output number per LF		3	Output Score	A+
Impact weighting (%):		20	Impact weighting % revised since last AR?	Y (↓ 5%)

Indicator(s)	2018 Milestones	Progress
3.1 Number of school-age children enrolled in regular classes in UNRWA schools	48,100	49,682 (24,438 girls; 25,244 boys) (103%)
3.2 Number of school-age children receiving psychosocial support (PSS)	30,000	40,465 (20,320 girls; 20,145 boys) (135%)
3.3 Number of Palestine refugee students provided with educational/ recreational materials (back-to-school kits, PSS/recreational kits, stationery)	48,100	49,682 (24,438 girls; 25,244 boys) (103%)

Provide supporting narrative for the score

Performance on Output 3 scored an A+ (moderately exceeded expectation). UNRWA educates almost 50,000 children in Syria. Although they don’t have exact figures, UNRWA believe they are educating almost all Palestine refugee children in Syria. UNRWA’s schools are in areas where most PRS live (such as camps and major gathering areas) and, in this year’s ninth-grade exams UNRWA’s schools outperformed the national schools (achieving an 81.7% success rate compared to the national average of 65.6%), so there are clear incentives for PRS to enrol their children in UNRWA schools.

Indicator 3.1- Number of school-age children enrolled in regular classes in UNRWA schools

During the reporting period, UNRWA provided education to Palestine refugee students in Syria through 103 schools in the 2017/2018 academic year, most operating on a double-shift basis. UNRWA use the curriculum of the host country in all their fields of operation- in this case, UNRWA use the national Syrian curriculum. UNRWA Headquarters review each curriculum and supplement it with other learning areas if they deem necessary.

In the first semester of 2017/2018, enrolment increased slightly from the previous school year, from 46,733 pupils in May 2017 to 47,585 at the beginning of the 2017/18 school year (23,469 girls and 24,116 boys), mainly due to the reopening of schools in Sbeineh, Barzeh and Husseinieh and parents moving their children from regime schools back to UNRWA schools. Total enrolment increased to 49,682 students (24,4381 girls and 25,244 boys) at the beginning of 2018/19 academic year due to the reopening of rehabilitated schools as well as the return of Palestine refugees in Sbeineh and Khan Eshieh.

A total of 40,954 students completed their end of year exams for grades 1 to 8 in June 2018. In addition, 3,213 students (1,722 girls and 1,491 boys) out of 3,934 passed their ninth-grade exam achieving an 81.7% success rate (84.7% girls; 78.4% boys), compared to the national average of 65.6%. This reflects the quality of the UNRWA education programme in Syria supported by Agency wide education reforms and the Education in Emergency programme, including school- based teacher development, provision of learning support classes to ninth graders, provision of back to school kits as well as mainstreaming of PSS and support to children with disabilities.

Indicator 3.2- Number of school-age children receiving psychosocial support (PSS)

UNRWA substantially exceeded the target for this indicator. This was due to it being paid for by project-based funding that complemented the education interventions under the Emergency Appeal, rather than the Emergency Appeal alone.

UNRWA trained and deployed 100 PSS counsellors in all 103 schools, who provided individual and group counselling to 40,465 (20,320 female; 20,145 male) students. Group counselling is given on a regular basis as part of the children’s day-to-day learning, where children are given exercises and games to help them deal with psychosocial issues.

For children who manifest more severe symptoms, the councillors provide individual care. Either the councillors will recognise these children themselves, or they will be referred by teachers and parents. The Education Programme provides regular training to teachers and parents involved in the Parent-Teacher Associations on recognising PSS symptoms.

UNRWA recently hired a Guidance and Counselling specialist. One of their tasks is to quality-assure the PSS activities. If approved by the regime, UNRWA are hoping to do an evaluation of their PSS work, including interviews and focus groups, which should be completed by the end of the year.

Recommendation: UNRWA to consider sharing the evaluation/ engaging with DFID’s Social Development Advisor and Education Advisor on PSS activities

Indicator 3.3- Number of Palestine refugee students provided with educational/ recreational materials (back-to-school kits, PSS/recreational kits, stationery)

All students enrolled in UNRWA-managed schools were provided with educational/recreational materials, including back-to school kits, during the 2017/18 academic year. These materials include basic stationary, uniforms and textbooks.

We challenged UNRWA on the necessity of these materials- the extent to which these materials are essential for children enrolling, staying in school and their learning outcomes. UNRWA’s view is that these materials encourage children to want to come to school and to perform when they’re there. Providing them to all students also means that children whose families are unable to buy such materials can start the school year on an equal footing. These are basic items but give children the tools they need to learn.

Lessons identified this year, and recommendations for the year ahead linked to this output

Tracking Displacements

UNRWA use the enrolment of children into their schools as an informal means of tracking displacements. When families relocate, UNRWA say that often the first thing they do is enrol their children in the local UNRWA school. UNRWA also track drop-outs- when children drop out of school between grades UNRWA contacts the parents to discuss their reenrolment in a new location. This allows UNRWA to develop a picture of IDP and refugee movements and returns.

Leaving No One Behind

In previous years (2013/14/15), when large numbers of PRS were living in besieged and hard-to-reach locations, UNRWA developed distance-learning materials to support continuing education. These innovative initiatives had a positive impact on the lives of thousands of children. However, the majority of PRS now reside in regime-controlled Damascus, Dar’a, Aleppo and Homs. This means most children are now in areas where they can access school, so UNRWA is no longer providing distance-learning. To ensure their programming is conflict-sensitive, UNRWA also allow Syrian-national children to enrol in their schools (paid for by UNRWA).
UNRWA has committed to participate in disability inclusive programming and works to ensure that people with disabilities have equal access to assistance and services, including education. DFID has recently commissioned a report on disability inclusive education approaches in the Syria context. UNRWA have agreed to provide information on how they have approached the issue, the activities they have found to be effective and challenges faced. This will compliment information by DFID’s other partners providing education in Syria. We will discuss the findings of this report with UNRWA in due course and provide recommendations if necessary, through the quarterly meetings.
Recommendation: UNRWA to continue attending DFID’s bi-quarterly education meetings to facilitate learning and best practice approaches across DFID’s portfolio.
Output Title	Strengthened prevention and protection response for Palestinian refugees.
Output number per LF		4	Output Score	A
Impact weighting (%):		10	Impact weighting % revised since last AR?	N

Indicator(s)	2018 Milestones	Progress
4.1 Number of older people who received PSS support	600	872 (145%)
4.2 Number of UNRWA staff members trained on protection	1500	2,167 (144%)
4.3 Number of Palestine refugees with a disability who received assistive devices	1500	1290 (86%)
4.4 Number of Palestine refugees with a disability provided with psychosocial support	1000	720 (72%)

Provide supporting narrative for the score

Performance on Output 4 scored an A, with two indicators exceeding expectation and two indicators moderately not meeting expectation. Throughout 2018, UNRWA continued to address protection concerns faced by PRS. Protection is mainstreamed both in and through UNRWA’s service delivery, alongside five Family Support Offices which offer specific support, such as legal counselling. Responding adequately to protection issues remained a challenge for UNRWA Syria throughout 2018, due in part to the withdrawal of US funding (who provided 70% of protection funding), an absence of any official referral system in Syria, and the lack of staff capacity to deal with protection work. In 2019, protection teams across all fields of UNRWA operation will develop a detailed analysis of protection audit findings that will, in turn, form the basis of audit recommendations to be implemented during 2019-20 and reported on thereafter.

Agency-wide, advocacy efforts during 2018 covered a wide range of protection issues including the impact of the Syrian conflict on Palestine refugees, including in relation to the protection of civilians, freedom of movement, humanitarian access, civil documentation and housing, land and property rights.

Indicator 4.1- Number of older people who received PSS support

Psychosocial activities were implemented with the community and community-based organisations, with a focus on elderly (872 older people received PSS support) and other vulnerable groups, including children and persons with disabilities. Activities for older persons varies from area to area as the initiative is largely community driven and follows a participatory approach from design stage to implementation. In Khan Eshieh for example, young persons in the community received basic first aid training and now visit older persons in their home, monitoring basic health changes and assisting them to attend the clinic where required. Latakia on the other hand have an active group of older persons who meet several times per month purely for the social aspect, they will directly do house visits if any regulars are absent. Community Development Social Workers often assist in initial stages of forming the groups, having direct knowledge of older persons in their camp, older persons who have effectively been left abandoned through family migration or fragmentation are specifically targeted. Periodically, or at the end of a larger activity older persons are invited to give their option of the activities and participate in the design of new ones.

The overachievement of this target is due to an earmarked grant provided by Japan for training that was not in the pipeline during the planning phase.

Indicator 4.2- Number of UNRWA staff members trained on protection

Despite financial constraints, 2,167 of UNRWA Syria’s 3,630 staff were trained on protection in 2018. UNRWA’s Protection Mainstreaming training, developed by UNRWA’s Headquarters, supports staff to understand protection principles (such as enhancing the safety, dignity and rights of people) and how they should be applied in practice. UNRWA also run other training for their staff and volunteers, such as a two-day training session on disability inclusion. The protection trainings are conducted over 1 or 2 days depending of the training type, and the availability of staff to be away from their work. It remains challenging to get frontline staff off duty for that long, particularly during times of escalating conflict. UNRWA continues to prioritise staff who have not received the training, including new staff and volunteers. Complimentary training is being discussed that directly responds to needs within individual departments (e.g. disability access to installations). UNRWA will also seek to roll out protection trainings related to addressing violence against children and the prevention and response to sexual exploitation and abuse.

Indicator 4.3- Number of Palestine refugees with a disability who received assistive devices

People with disabilities are provided with assistive devices (such as hearing aids, glasses and prosthetic limbs) either through the health care teams or through a referral to the health care teams by social workers in the Relief and Social Services Department (who are present in schools, nurseys etc.).

Indicator 4.4- Number of Palestine refugees with a disability provided with psychosocial support

Specific activities to support the psychosocial health of persons with disabilities are primarily conducted through Community Based Organisations in the camps. These activities vary slightly from area to area and are designed based on need, resources and capacity. Both participants, their carers and CBO volunteers come together to discuss regular and ad-hoc programming. In Neirab camp, additional PSS activities were also aimed at carers.

Lessons identified this year, and recommendations for the year ahead linked to this output

Protection Indicators

Despite protection being UNRWA’s first strategic objective in their Medium-Term Strategy, the current indicators under this Output don’t adequately reflect all UNRWA’s protection work. UNRWA’s Syria 2017 Emergency Appeal initially included more specific indicators on the “% of individuals identified as experiencing a protection risk (gender-based violence and general/child protection) provided with assistance” and “% of UNRWA facilities that are part of a functioning referral system for protection cases”. In the last Annual Review, DFID recommended UNRWA include specific indicators on gender-based violence and child protection in future Emergency Appeals. However, because of concerns on the quality of data and challenges in operationalising referral and case management systems, UNRWA has not been able to report against these.

UNRWA Syria cannot use the protection database system that is now being used across UNRWA’s other fields of operation[1]. The software used elsewhere, ActivityInfo, is a monitoring and evaluation software for humanitarian operations. ActivityInfo is a Dutch company and is therefore subject to European Union sanctions. The EU has restrictive measures in place to stop support to the Syrian regime and won’t therefore licence the software for use in Syria. This means the Syria Office cannot use it for their protection data. They don’t have any other infrastructure in place to manage protection cases and referrals and don’t currently have the capacity to provide accurate enough data for these indicators. The Syria Office continues to have discussions with their headquarters on how to best respond to this gap.
[1] Jordan, Lebanon, the Gaza Strip and the West Bank, including East Jerusalem.

Protection Capacity

More broadly, UNRWA’s capacity to work on protection is limited. In 2018, the UNRWA protection function was significantly impacted by the Agency’s financial crisis, as 70% of protection funding was provided by the United States. This workstream was moved under the programme budget, rather than the Emergency Appeal, to create more stability, but still requires further funding (and subsequently more dedicated internal capacity).

Certain protection issues are particularly pertinent for the PRS population. For example, PRS are stateless residents of Syria, meaning they have fewer and at times unclear in terms of property claims and face critical housing, land and property (HLP) issues, including land ownership. In the case of Yarmouk for example, previously home to the largest Palestine refugee community in Syria, it remains unclear what the regime is planning to return, and potential compensations should urban development laws be applied. It is unclear what will happen to the people that lived there and if permissions for return will be granted. Where homes were destroyed in Government recognised camp lands, it remains unclear what, if any, legal claim PRS will have to the land on which the homes were built. UNRWA are heavily involved in the HLP technical working group, but, as with their wider protection work, internal capacity limits their ability to prioritise this workstream.

On the other hand, UNRWA, unlike most other UN agencies, has continued to deliver legal aid despite the national ban. This is possible because it was approved by the General Authority for Palestinian Arab Relief (GAPAR) before the conflict started and because UNRWA’s case load is small and defined (suggesting that UNRWA would also be banned if they started providing legal aid to Syrian nationals). Six Field Family Support Officers meet annually, including with GAPAR representatives to discuss changes to Syrian laws and the impact on PRS.

Recommendation: UNRWA should consider weighting any additional funding for the 2019 Emergency Appeal towards protection activities.

Output Title	Palestinian refugees’ water, sanitation and public health needs are met.
Output number per LF		5	Output Score	A
Impact weighting (%):		10	Impact weighting % revised since last AR?	Y (↓ 10%)

Indicator(s)	2018 Milestone	Progress
5.1 Percentage of accessible Palestinian refugee camps receiving repair, rehabilitation, or reconstruction of water and sanitation networks by UNRWA	100%	100%

Provide supporting narrative for the score

Performance on Output 5 scored an A (meeting expectations). In 2018, UNRWA continued to provide essential WASH services in all accessible Palestinian refugee camps and UNRWA collective shelters (until their closure in late May 2018). This includes ongoing repair and rehabilitation of water and sanitation networks, maintenance of sewage networks, provision of solid waste management services, and municipal cleaning and maintenance. Specific attention is given to areas and camps where access has been recently restored, such as the Sbeineh PRS camp, where approximately 15,000 individuals are now benefiting from improved water supply service following the rehabilitation of the main water supply and water well.

In addition to regular WASH services, UNRWA also responded to emergency WASH needs. In March 2018, following the intense military operation in Eastern Ghouta, UNRWA provided four units of sanitary latrines to serve IDPs in government collective shelters, as part of the inter-sector coordinated response. As part of its emergency response, UNRWA also distributed 16,300 hygiene kits to Palestine refugees displaced from Eastern Ghouta and Yarmouk.

Lessons identified this year, and recommendations for the year ahead linked to this output

While UNRWA successfully provided maintenance and rehabilitation services to all accessible camps, expanding its services as more camps became accessible, it is difficult with the indicator provided to assess the quality, scale and timeliness of services. As per the last Annual Review, it is recommended that UNRWA consider how to better measure performance for this output, and contribution to outcomes in terms of public and environmental health.

Recommendation: DFID and UNRWA to discuss possible revision of WASH and public health indicators (by Dec 19)

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change and any major changes in the past year

Theory of Change:

The Theory of Change remained valid in 2018. There were no major changes to needs, or how UNRWA programming met those needs through their activities. Through the Humanitarian Process Cycle, UNRWA contributes annually to the Syria Humanitarian Needs Assessment (HNO), which assess the needs of the Syrian population across each sector, and the subsequent Humanitarian Response Plan (HRP). This ensures that UNRWA are working in harmony with other actors in Syria and meeting the needs of all PRS. Should the HNO assessment show a change in needs for the PRS population, we would work with UNRWA to adapt the programme accordingly.

The importance of the donor funding input was evident in 2018. Donor funding is the basis through which UNRWA can operate, and the significant shortfall in funding impacted on all activities and outputs (and in turn, all outcomes and the overall impact). Nonetheless, with only 12.5% of funding requirements received in Syria, UNRWA prioritised meeting essential life-saving needs and providing access to quality assistance, over resilience-building outcomes. Activities planned under “livelihoods, microfinance and vocational training” were not implemented under the Syria Appeal (limited livelihoods activities were implemented under core funding). This is in line with DFID’s Humanitarian Strategy for Syria and advocacy regarding the humanitarian response, which emphasises prioritising emergency response and basic services provision to those most in need, over resilience or reconstruction activities.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead

Against the current outcome indicators, the programme is on track to achieve the expected outcomes and impact. Despite considerable financial constraints, UNRWA has performed well with regards to the outcomes, particularly enabling PRS to meet their essential life-saving needs and providing basic services.
DFID currently uses UNRWA’s outcome indicators to assess progress at the outcome level. This reflects strong progress against UNRWA’s outcomes. However, these outcomes (and indicators) don’t map directly onto DFID’s Theory of Change outcomes and, arguably, better assess the output level than the outcome level.
When we reach the end of this programme, we want to assess the ‘distance travelled’- the impact UNRWA have had on the lives of PRS, how much better off PRS are because of UNRWA and whether PRS would revert to their pre-programme level of need and resilience without UNRWA’s support. We want to assess whether UNRWA, with UK support, have achieved the intended impact: Lives saved, civilians protected, suffering reduced and resilience built. We want to better assess the impact the programme is having, rather than the numbers of beneficiaries reached. Impact would need to be attributable to the programme, taking into consideration the external factors that may have impacted PRS lives. We recognise this is difficult because UNRWA runs an annual appeal, rather than a multi-year programme (and there are limitations in gaining approval to do evaluations in Syria) so does not measure progress over time. However, we encourage UNRWA to consider how better we can assess impact.
Recommendation: DFID and UNRWA to explore the possibility of an evaluation or alternative narrative to assess the outcomes of this programme.

Explain major changes to the logframe in the past year

Outputs and indicators for the UNRWA Syria programme are based on UNRWA Syria’s Annual Emergency Appeal. Some indicators are subject to change from one Appeal year to the next as UNRWA designs Appeal indicators to best reflect the most appropriate interventions based on the changing context and changing needs inside Syria.

The only major change to 2018 indicators was the omission of two indicators for Output 3:
- Number of students who participated in at least one recreational and extracurricular activity
- Number of self-learning materials (SLMs) reviewed against the UNRWA curriculum framework

Describe any planned changes to the logframe as a result of this review

Following the implementation of the targeting approach for Output 1, the 2019 Appeal now includes separate indicators for the most vulnerable PRS and other vulnerable PRS:

- Number of most vulnerable Palestine refugees (tier 1) provided with cash assistance during the last completed distribution round
- Number of vulnerable Palestine refugees (tier 2) provided with cash assistance during the latest completed distribution round
- Number of most vulnerable Palestine refugees (tier 1) provided with food assistance during the last completed distribution round

Two new indicators have also been added to Output 3 to assess the quality of the education services provided:

- Number of students graduating from basic education (Grade 9)
- Number of Palestine refugee students completing end of year exams (Grades 1-8)

## D: VALUE FOR MONEY

Assess VfM compared to the proposition in the Business Case, based on the past year

The business case assessed that UNRWA would deliver good value for money, predominately through:
- UNRWA’s operating model of delivering regular services and emergency assistance directly through its 3,630 staff and 219 facilities in Syria;
- operating an end-to-end supply chain, with no downstream partners, where goods remain in UNRWA’s custody from delivery at the port/airport of arrival until direct distribution or issue to beneficiaries;
- their extensive use of cash assistance, which is internationally recognised as a cost-effective and cost-efficient humanitarian intervention;
- and their long-established presence and reach in Syria, allowing them unique access to highly vulnerable population.
This holds true: UNRWA continue to provide a hard-to-replicate comparative advantage in terms of their ability to support the Palestinian refugee population.

Economy

Staffing and supplies remain the key cost drivers for UNRWA. UNRWA offers universal health and education services to all Palestine refugees. This large service delivery presence is delivered through their 3630 staff in Syria (only 14 of which are international staff), through 219 facilities (including 23 healthcare facilities and 103 schools).

UNRWA’s staff costs include the provision of salaries for teachers, health professionals and other frontline service delivery staff. UNRWA’s staff salaries are broadly harmonised with those paid by other UN Syria agencies, staff salaries across UNRWA’s fields of operation and take pay levels of the Syrian regime into account. Given the devaluation of the Syrian pound as a result of the conflict, UNRWA fixed their salaries at the pre-crisis rate and pay their staff in US dollars (which is converted into Syrian pounds). This ensure staff are receiving a fair salary for their work, despite fluctuations in the Syrian economy.

Moreover, because UNRWA staff are largely PRS themselves, and part of the PRS community inside Syria, the direct payment of their salaries contributes to the wellbeing of the wider PRS community providing livelihoods, training and stability. Making additional cost savings on salaries is difficult; UNRWA’s staff unions are strong and well organised. There is also a disincentive of reducing staff costs in terms of UNRWA internal capacity and their ability to retain staff. This is discussed further in the Risk section below.

UNRWA’s supplies include emergency in-kind food assistance, NFI’s, educational materials, healthcare and medication. Given UNRWA’s financial situation, making cost savings on supplies is of paramount importance. Their extensive use of cash assistance helps achieve this objective. As below, UNRWA spent 69.4% of their received contributions on cash assistance in 2018. Their well-established model allows them to rapidly distribute cash assistance to a large population across Syria, with lower operating costs then their other interventions. In addition to this, in order to allocate more funds to priority interventions such as cash assistance, UNRWA have now introduced a targeting approach to their food-assistance. From 2019, UNRWA began only distributing food assistance to people that are categorised as the most vulnerable (and extended to persons in access-restricted areas such as Yalda and in certain instances to cases of spontaneous returns upon assessment). This is discussed further below.

Where UNRWA do acquire goods and services, they make cost savings primarily through procurement. For example, by enabling economies of scale: consolidating procurement requirements across all field offices for items such as rice, sugar, oil, pharmaceuticals and vehicles. All other items which are available locally in Syria are procured through competitive tendering. UNRWA has also established Long Term Agreement (LTA) contracts for items procured on a recurring basis to fix costs (e.g. blankets, hygiene kits, food items and mattresses.) and launch local tenders in both Syria and Lebanon to increase market reach/competition. This is proving to be effective: their cost per beneficiary shows that UNRWA’s average spending across their fields of operation, as per their Annual Operational Report 2018, is US$ 831 per pupil on basic education (compared on average to US$ 8,643.5 spent by other OECD countries) and US$ 28.6 on health expenditure per person (compared on average to US$ 4,003 spent by other OECD countries).

Efficiency

By delivering all activities through their own staff with no downstream partners, UNRWA minimises layers of administration costs and risks and has direct oversight over procurement and delivery. This has enabled UNRWA to make several efficiency gains. For example, the roll out of the e-Health system and Family Health Team approach in Syria has enabled swift access to medical records, an improved appointment system and flow of patients, strengthened supervision of health services, and enhanced monitoring and reporting capabilities.

Where possible, UNRWA collaborates with other agencies to ensure a more efficient response. For example, participating in UN inter-agency (IA) convoys in instances where only UNRWA can access specific areas to ensure both PRS and Syrian civilians are served, and collaborating with other UN agencies to perform assessments such as socio-economic surveys of PRS.

Effectiveness

PRS are almost entirely reliant on UNRWA for their basic requirements as well as humanitarian needs, despite UNRWA’s chronic underfunding. It is therefore important that UNRWA spends their limited funding wisely and on interventions that are likely to result in the desired outcomes (and impacts).

UNRWA have three funding streams across their five fields of operation: a programme budget that supports core operations; emergency appeals; and specific projects to improve services without increasing recurrent costs. The Syria Emergency Appeal was launched to cover the increased needs of PRS caused by the ongoing conflict which could no longer be covered by the programme budget alone.

In order to meet the programme’s outcome and impact objectives, through the Syria Emergency Appeal UNRWA prioritised meeting essential life-saving needs and providing access to quality assistance, over resilience-building outcomes. This is in line with DFID’s Humanitarian Strategy for Syria. Activities planned under “livelihoods, microfinance and vocational training” were then implemented under the programme budget. UNRWA deem this to be the most effective use of their resources.

One caveat to UNRWA’s effectiveness going forward is the US withdrawal of funds as of 2018, which will continue to have negative impacts on UNRWA’s capacity to deliver. With no long-term solutions to UNRWA’s financial crisis imminent, the reductions in human resources as well as a reduction in UNRWA’s operational scope could severely impact the quality and efficacy of interventions for PRS. This is noted in the Risk section below.

Equity

The vulnerability of PRS remains high and all indicators suggest they are an acutely in need population. A vulnerability assessment undertaken by UNRWA concluded that 90.5% of PRS households live in absolute poverty (less than USD 2 person/day), and 79.5% live in extreme poverty (less than USD 1.5 per person/day). Of the 438,000 Palestine refugees remaining in Syria, 60% have been displaced at least once, 13,500 are in hard-to-reach areas and 126,000 have been identified by UNWRA as extremely vulnerable. The Syria Humanitarian Needs Overview (HNO) highlights that across the board, sectors consider PRS to be one of the most vulnerable groups.

It is ‘assumed’ by both the international community and the Syrian authorities that UNRWA will exclusively serve all PRS needs. This assumption stands regardless of UNRWA’s available funding and capacity to deliver. UNRWA support is often then the only channel to this minority group. Ensuring UNRWA deliver equitably to the entire PRS population given their overall vulnerability, as well as prioritising the most vulnerable within the PRS population, is therefore important.

As aforementioned, UNRWA have implemented a targeting approach to their emergency assistance. They now give a higher amount of cash and in-kind assistance to female headed households; the elderly; people with disabilities; and orphans. This allows UNRWA to focus on those with the most acute needs within this already vulnerable population, and, given the significant funding constraints, deliver even greater value for money. UNRWA have also been working with DFID’s Disability Inclusion Advisor to ensure their education and health initiatives are inclusive and meet the needs of people with disabilities.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio

Based on the VfM proposition made in the business case and in the context of the wider portfolio, this programme continues to deliver good value for money. UNRWA’s unique mandate and access to PRS ensures that this vulnerable population is not left behind, and we can be confident that their approach is delivering economical, efficient and effective aid. In addition, UNRWA’s extensive use of cash (a priority area for DFID) enables them to absorb additional funds at scale. In 2018, for example, UNRWA provided a one-time emergency cash assistance grant of US$70 per family to 2,527 families affected by hostilities in Eastern Ghouta and Southern Damascus. If further funds became available, UNRWA could increase their cash transfers rapidly with no impact on their current staff capacity or increased operating costs.

There is a broader question about the merits of UNRWA as the sole agent in meeting PRS needs, or whether other organisations would be better placed to do so. Some argue that the existence of UNRWA sustains the exclusion of the PRS population, who would otherwise be served by other humanitarian actors (as all Syrian nationals are). We have not explored the extent to which we could achieve better VfM by taking this approach. The reason for this is threefold: (i) we know that inside Syria, UNRWA is often the only organisation with the access, permission and capacity required to assist Palestine refugees; (ii) just because PRS aren’t being served by UNRWA, doesn’t mean they will automatically be served by other actors- we would need to be sure other agencies were meeting PRS needs and they weren’t excluded; and (iii) Palestine refugees fear that dismantling UNRWA will result in no political solution to the Israel/ Palestine conflict and will exacerbate instability. On that basis, we currently deem that the exiting approach delivers the best VfM.

E: RISK

Overview of programme risk and mitigation

The overall risk rating for this programme is severe but remains steady and within DFID’s risk appetite. Some of the programme’s major risks are outlined below; recommendations for specific risks are detailed in their respective relevant sections elsewhere in this review.

UNRWA are operating in a highly complex and volatile environment but continue to manage delivery and security risks effectively. As outlined below, UNRWA have relatively good access and we are confident in their ability to reach this highly vulnerable population.

UNRWA’s monthly monitoring reports on aid diversion show minimal loss. In the first two quarters of 2019, March saw the highest loss of US$1,904.09 (0.2% of total value of assistance). Most losses are a result of damage due to physical circumstances such as packaging, weather conditions, transportation etc. More broadly, fraud and safeguarding cases are minimal. At the time of writing, the most significant fraud case is concerning media reports of an internal UN investigation into misconduct by UNRWA’s senior management. This case is being led by DFID OPT’s and DFID’s Counter-Fraud Section. DFID continues to closely monitor aid diversion and will open investigations if necessary.

Financial pressures put significant strain on UNRWA in 2018, with all activities, programming and systems impacted by the funding crisis (as outlined in Section F below). Austerity measures were put in place, but such measures inevitably led to increased risks across the programme. For example, direct assistance was prioritised over support costs, and as such, areas such as fleet management and maintenance fell behind, exasperating delivery risks.

Linked to this, UNRWA’s internal capacity is one of the key challenges to their operations and is impeding their ability to sustainably deliver. Difficulties recruiting and retaining staff (driven by internal uncertainty, visa delays and deprioritising recruitment) mean a smaller number of staff are now delivering to the same number of beneficiaries, reducing their oversight and increasing the risk to DFID funds.

We suggest UNRWA consider bidding for additional technical posts through the Standby Partnership (SBP), which is a network of bilateral agreements between organisations and UN agencies. The SBP enables humanitarian experts to fill staffing needs in UN operations. Fourteen UN agencies currently benefit from the mechanism, including: FAO, IOM, OCHA, UNDP, UNESCO, UNFPA, UNHABITAT, UNHCR, UNICEF, UNMAS, UNRWA, UNWOMEN, WFP and WHO. The SBP allows the UK to provide timely, niche and innovative support to the UN, so they can take a more appropriate approach to protracted crises. The average length of DFID deployments are between 4 to 6 months.

Recommendation: UNRWA should consider recruiting technical posts through the Standby Partnership Programme to rapidly increase their human resources at short notice. DFID (and other donors) can then consider funding these posts.

Politically, the US withdrawal of funding in 2018, increased talks about the US “deal of the century” (which, if supported, would see increased pressure to dismantle UNRWA) and efforts expended by the US administration in this regard, have been accompanied by rising attacks on UNRWA and on its mandate. UNRWA’s mandate is due to be renewed at the UN General Assembly in September 2019. While we anticipate their mandate will be renewed, the UK will continue high-level policy dialogue with other member states in support of UNRWA.

The DFID Syria Risk Register for the UNRWA Syria programme was designed by DFID Syria in collaboration with the Risk and Results Team and in consultation with and agreed by UNRWA Syria. Risks and mitigations are discussed at quarterly meetings, and the DFID Syria risk register is updated accordingly. In addition, the UNRWA Syria 2018 Emergency Appeals and Annual Reports include an agency-wide risk register, identifying the risks faced by the Agency due to challenges in the operating environment, and the risk mitigation strategies. These are updated six-monthly as part of the reporting cycle, and UNRWA Syria Field Office feeds in as part of this revision process. The overall UNRWA risk register is reviewed alongside the DFID Syria risk register to ensure that they are aligned.
F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Performance of Partnerships

DFID’s partnership with UNRWA continues to be collaborative and constructive, both at the country and headquarter level. DFID have quarterly face-to face meetings in Beirut with UNRWA Syria, and ad hoc discussions as necessary. UNRWA Syria’s willingness to update DFID during times of intensified conflict (despite being overwhelmed operationally) has been critical for DFID to get an accurate picture of activities inside Syria and the challenges faced.

DFID’s Occupied Palestinian Territories (OPTs) team leads DFID’s relationship with UNRWA’s headquarters in Amman, overseeing the UK’s support to UNRWA’s programme budget in all five fields of operation (Jordan, Syria, Lebanon, West Bank, and Gaza), plus the OPT’s Emergency Appeal. This is working well: it allows OPT’s to see the whole picture of what is funded in Syria, coordinate internal corporate requirements and helps manage DFID’s relationship with UNRWA through more aligned messaging.

Delivery

As outlined throughout this review, UNRWA continues to deliver the programme effectively and are meeting DFID’s expectations (as set out in the agreement) and making good progress towards subsequent recommendations. The agreement between DFID and UNWRA is a multi-year contribution agreement for £36,000,0000 over a period of 3 appeal years (2017-2020). It sets out the payment amounts and dates of disbursal, type and frequency of reporting, indicators to be reported against[2] and required M&E commitments.
[2] Indicators subject to change based on UNRWA’s Annual Emergency Appeal indicators.

One of DFID’s requirements is delivery partner mapping. DFID requires a clear line of sight on fund flows from initial receipt to the impact on the ground. In this case, UNRWA has no downstream partners, and directly implements programmes, employing 3630 staff to deliver education, health and relief services in Syria through 219 facilities. With a workforce predominantly comprised of Palestine refugees (and only 14 international staff), UNRWA has a large service delivery presence. UNRWA’s supply chain is managed internally, operating an end-to-end supply chain where goods remain in UNRWA’s custody from delivery at the port/airport of arrival until direct distribution or issue to beneficiaries or via UNRWA clinics and schools.

Although UNRWA does not implement activities through downstream partners, they do contract suppliers. From a counter-terrorism perspective, UN agencies are not legally subject to UK counter terrorism legislation or Member State sanctions regimes, but DFID mandates all partners to ensure funds do not support terrorist activity. UNRWA has confirmed that it complies with all applicable UN anti-terrorism resolutions and sanctions and they provide DFID with a list of suppliers contracted in Syria which DFID checks against European Union sanctions to ensure UK funds are not used to support terrorist activity.

Access

Although UNRWA do face some access issues operating in regime-controlled areas (like almost all DFID’s partners, although to a lesser degree than some), broadly they have consistent and direct access to PRS. This allows them to reach, and provide services too, most of the PRS population. Monitoring, assessment and data gathering (such as the upcoming PDM), even when in their own facilities with their own staff and only to PRS, is the biggest challenge. Several factors make UNRWA access easier to negotiate than other UN agencies. These reasons are:
- UNRWA have a clear mandate to serve a defined and contained population, making the Syrian authorities, who historically have had sympathy for Palestine refugees, less motivated to assert controlling frameworks;
- their relatively defined locations of operation (camps and “gathering areas”) make the regime’s facilitation letter process possible to standardise and regularise;
- because of their presence in Syria prior to the conflict (since 1951), some arrangements in place to facilitate their access and work have been maintained;
- one clear interlocker within the Syrian authorities, the General Authority for Palestinian Arab Relief (GAPAR) within the Ministry of Social Affairs (MOSA), which provides, for the most part, a single channel for access negotiation. This is simpler than for other UN and Damascus INGO agencies;
- and a decentralised approach, whereby sub offices with national staff can and do negotiate access at the local level.

Reporting
DFID receives quarterly results and financial updates, half-year progress reports and Annual Operational Reports (the principal means through which UNRWA informs donors how Appeal contributions have been used and results obtained) from UNRWA. In addition, as a member of the Advisory Commission (AdCom), DFID OPTs monitors any substantial changes to UNRWA’s rate of expenditure and global operational reserves through the following reports:
- Monthly financial report – providing detail on budget received and disbursed resources.
- UN Board of Auditors report issued annually. This provides an overview of financial and management issues, and recommendations to improve UNRWA’s performance.
- Annual report of UNRWA’s Department of Internal Oversight Services (DIOS) which covers UNRWA’s internal audit, investigations, ethics and evaluations findings.
- Annual report from the Commissioner General of UNRWA to the UN General Assembly. The report includes political, economic, operational and organisational development, as well as a financial overview of income and expenditure.
- AdCom periodic updates on progress against reform and Grand Bargain workstreams
In addition to this, and in line with the DFID Data Disaggregation Action Plan, for a set of key indicators DFID receives from UNRWA Syria a complementary quarterly breakdown of associated results disaggregated by governorate, sex and age group. In the first quarter of 2019, UNRWA began reporting on DFID’s online results platform, Cascade. This ensures that DFID continues to build on the evidence base of what works in Syria, helps us to identify gaps in our response and ensure greater programme transparency. As agreed, UNRWA Syria also reports to DFID how many people with disabilities they have supported in Syria each year.

Financial Update

UNRWA Financial Overview

The Syria Emergency Appeal was significantly underfunded in 2018. The Appeal requirements for 2018 were US$408.9m (covering interventions in Syria, Jordan, Lebanon and regionally). UNRWA received US$125.2m, leaving a funding gap of US$283.7m, or 87.5%. US$80.6m (or 64.4%) of the received contributions were allocated to Syria. In addition, US$ 43.4m was allocated to Syria under the Programme Budget to support core programmes and activities.

In January 2018 the US decided to withhold funding to UNRWA. The decision caused a financial crisis for UNRWA, particularly for the Syria programme, as US money for 2018 completely excluded Syria, whereas in 2017, the US contributed 70% of UNRWA’s Syria Emergency Appeal funding. In addition to this, UNRWA’s budget is financed almost entirely by voluntary – and often unpredictable – contributions.

Despite reductions in US funding, a far greater number of governments- over 40- increased their level of voluntary contributions to UNRWA in 2018, testament to UNRWA’s effective Resource Mobilisation Strategy. Contributions from traditional donors in absolute terms increased in 2018 in comparison to the previous year, while the percentage share of these contributions decreased, owing to a greater overall diversification of funding. UNRWA has also made around $500m in cost savings in the last five years. But it’s clear that the pressure on its budget will continue.

DFID’s Contribution

Of the £36m approved budget for this programme, £30m has been paid to UNRWA. The final £6m payment is forecasted to be made in November 2019. DFID brought forward £5m from the planned 2019 budget into 2018, making our contribution in 2018 £17m, or 19% of the total Appeal contributions.

Expenditure by Output

Expenditure by Output

The graph above shows UNRWA’s expenditure by output. Through the Emergency Appeal, UNRWA spent the majority (US$55,974,710, or 69.4%) of their received contributions on cash assistance. This is in line with DFID’s prioritisation of cash assistance in humanitarian responses. Saying this, UNRWA only received 31% of the required amount of funding for this Output. Hence, UNRWA reduced the amount of cash assistance provided per person during the second and third distribution rounds; and scaled down the number of rounds from six to three.

Asset monitoring and control
There are no DFID-attributable assets associated with any of the components of this funding arrangement. As this is a contribution towards an emergency appeal, any assets purchased would not be directly attributable to DFID.

Date of last narrative financial report(s)	24/07/2019
Date of last audited annual statement (s)	24/07/2019

G: MONITORING, EVIDENCE & LEARNING

Monitoring

UNRWA

UNRWA undertakes monitoring visits monthly across their sites of operation. For example, in December 2018 a total of 79 monitoring missions were conducted across Rural Damascus, Damascus, Dera’a, Homs, Hama, Latakia, Aleppo and Yalda. UNRWA reports monthly to DFID on the number of visits undertaken each month and to which locations.

UNRWA has developed a set of strategic outcomes set out in the Agency’s Medium-Term Strategy (MTS) 2016-21. Agency-wide, UNRWA uses a results-based monitoring system, which enables data collection and analysis against MTS strategic outcomes for the entirety of UNRWA operations. Embedded in this system are structures for monitoring the Syria Emergency Appeal, as well as other projects and frameworks under UNRWA. Where possible, this system seeks to establish links between project data. Data is analysed on a quarterly basis at field level, and on a semi-annual basis through Agency-wide results review. In addition, UNRWA reports against targets on a monthly basis through the inter-agency cluster system, tracking what, where, when and who conducted activities.

DFID

DFID has mechanisms in place to continually review and monitor programme performance: a delivery plan, risk register and log-frame – all of which are reviewed at least once a quarter. The log-frame mirrors indicators from the UNRWA Emergency Appeal for efficiency. The risk register identifies the risks faced by UNRWA due to challenges in the operating environment and the risk mitigation strategies. Finally, through the delivery plan, we monitor progress on how the programme is responding to recommendations.
Every quarter, DFID Syria meets UNRWA Syria to discuss and monitor the areas of progress, context, needs, risk and aid diversion. This now includes a discussion of the quarterly disaggregated results which UNRWA provide to DFID for publication on DFID’s Cascade system.
In lieu of DFID staff being unable to visit projects in Syria, DFID has contracted an independent supplier to conduct and document a one-day field monitoring visit to UNRWA Syria operations each year. In May 2018, Syrian field monitors reviewed UNRWA’s cash distribution and health facilities.
The report concluded that UNRWA’s cash programming is successfully addressing the high rates of poverty among PRS, allowing them to cover the cost of their basic needs. It also highlighted that the cash distribution process is well organised, generating beneficiary satisfaction, and that the project has put an authorisation system in place to allow vulnerable individuals in non-Government-controlled areas to receive cash assistance, ensuring equity in delivery. The report recommended that UNRWA should increase the frequency of cash distributions, which UNRWA will consider going forward should funding allow. The report also recommended that UNRWA continue to regularly conduct rigorous verification exercises and population headcounts. UNRWA notes this will be a challenge going forward if funding remains limited, which could have implications for the quality of cash distributions.
Regarding health services, the report noted that the health services provided by UNRWA are highly needed and delivered in a timely fashion. Beneficiaries describe the health centre staff as qualified and are highly satisfied with their overall experience at the health centres. The report also highlighted that there were adequate supplies at the health centres visited, and that physical disability is highly considered. However, a key issue raised by the report was a need to strengthen the beneficiary feedback and complaints systems across UNWRA Syria field sites. UNRWA received and responded to the draft report and is working on strengthening the complaints reporting mechanism as well as the logging of the feedback received through the hotline.

Evidence

This programme is a well-tested humanitarian intervention with a strong evidence base. On that basis, DFID does not plan to conduct an external evaluation of the programme. We believe that the risks of carrying out an evaluation inside Syria do not outweigh the benefits the findings could provide. However, the European Union is conducting an evaluation which will be completed in 2019 (covering the health, education and microfinance projects the EU funded in 2018). We will discuss the findings and proposed recommendations with UNRWA.

Despite this programme being grounded in a solid evidence base, monitoring, assessment and data gathering, even when in UNRWA’s own facilities with their own staff and only to Palestine Refugees, remains challenging. Gaining approval from the Syrian authorities is bureaucratic, leading to substantial time delays, and often unsuccessful. This restrictions on UNRWA’s abilities to monitor their own activities.

Saying this, as above, UNRWA have been providing quarterly disaggregated results to DFID. This disaggregates data by sex, age, governorate and district. We also have two specific indicators on disability inclusion. This is helping DFID’s understanding of who and where PRS are, their needs and how well UNRWA are responding to them.

Learning

Conflict Sensitivity

In June 2018 UNRWA submitted a Conflict Sensitivity plan to DFID, outlining how they ensure UNRWA’s assistance does not worsen the situation and instead, positively addresses the causes of instability and insecurity. This is particularly pertinent to UNRWA because of their mandate to only serve one group of refugees, rather than all those in need. For example, this may occur if UNRWA programmes are perceived to be giving more assistance to PRS than internally displaced Syrians who are experiencing the same conditions, resulting in tensions on the ground. To prevent this, in times of displacements and acute emergencies, UNRWA has accommodated Syrian nationals in their collective shelters, so as not to create any tension or gaps in response.

Through the plan, UNRWA committed to adopt a context sensitive approach to delivering humanitarian assistance and development programmes in general, in line with the rest of the UN agencies in Syria. This considers the impact of assistance on the context and vice versa. UNRWA is actively reviewing interventions and responses to crisis in order to assess and monitor their impact on the broader environment through intervention design, implementation, monitoring and evaluation.

Accountability to Affected Populations

UNRWA considers accountability to affected populations to be a crucial element of quality service delivery. UNRWA requires, and highly values, the participation of Palestine refugees as partners. The refugee population actively participates in the assessment, design, implementation, monitoring and evaluation of UNRWA services. For example, the Post Distribution Monitoring (PDM) assessment is a formal, bi-annual process, that allows UNRWA to better track the impact of cash and food distributions and adjust programming accordingly. Meaningful participation means that the community is not just informed but integrally involved as partners. UNRWA emphasises the importance that the participation process includes the most vulnerable.

Engagement with PRS is grounded in the unique platforms provided by the: (i) workforce of around 3,630 UNRWA staff, the vast majority of whom are engaged in the direct-delivery of assistance and are drawn from the Palestine refugee communities they serve; and (ii) extensive network of area offices, camp services offices, schools (including school parliaments and parent-teacher associations), health centres (including health centre friendship committees) and other installations. This ensures that refugees have direct and regular access to Agency staff.

Disability Inclusion

UNRWA has committed to participate in disability inclusive programming and service provision. In 2018, UNRWA’s Syria Field Office worked with DFID’s Disability Inclusion Advisor to help us to get a full picture of UNRWA’s efforts, achievements and challenges relating to disability inclusion in Syria. This highlighted good progress being made by UNRWA in this area, alongside making some recommendations. For example, in response to the finding that many of UNRWA’s installations still have physical barriers that limit accessibility, DFID recommended that UNRWA ensures the Inclusive Standards are incorporated, as required, in all new engineering -implemented projects. It also recommended continuing training on disability inclusion for all frontline staff members and volunteers.

Gender Equality

In 2018, following the publication of ‘A Shared UK Government Approach to Gender in Syria’, DFID collated a set of Gender Minimum Standards to which all partners must adhere. UNRWA Syria provided written responses explaining how UNRWA meets the Gender Minimum Standards, including how women and girls are included in the design and implementation of UNRWA’s programmes.

Gender mainstreaming is a core theme in UNRWA’s Gender Policy and Gender Equality Strategy 2016-2021. In the Gender Policy, UNRWA states its commitment to making women’s as well as men’s concerns an integral dimension of the design, implementation, monitoring and evaluation of policies and programmes. Key points to note include:

- The UNRWA log frame has gender sensitive indicators and this enables the M&E to track gender related changes amongst the Palestine refugees’ overtime.
- All quantitative indicators are disaggregated by age, sex and disability.
- UNRWA also tracks the number of women receiving assistance or participating in livelihood related activities (such as microfinance). The results from this informed UNRWA’s decision to make financial support specifically for women in order to increase their participation.
- In some cases, such as in the technical and vocational education and training (TVET), UNRWA have more young females than young males participating.
Furthermore, UNRWA’s Gender Equality Strategy proposes actions to ensure a gender-sensitive organisational culture with more women in senior positions an increased gender balance among UNRWA staff and within its representative bodies, including the Unions. In terms of staff breakdown by sex in the Syria Field Office, 47% of staff members are male and 53% are female.

Safeguarding

In March 2018, the Commissioner General for UNRWA received a letter from the Secretary of State informing the agency of DFID’s new Safeguarding Minimum Standards. By October 2018, UNRWA had completed DFID’s Enhanced Safeguarding Due-Diligence Assessment. The assessment concluded that UNRWA has adequate and “satisfactory” systems in place in four policy areas (Safeguarding, HR, Governance and Accountability and Code of Conduct) and two ‘’partially satisfactory’’ (Whistleblowing and Risk Management).

UNRWA has a ‘’Zero Tolerance’’ approach to all forms of violence, harassment and abuse, including sexual exploitation and abuse (SEA). UNRWA Syria has a delegated focal point for SEA, in addition to focal points for GBV and Protection. UNRWA Syria keeps its own formal registry of all types of allegations, including SEA. There were no SEA allegations in 2018. There was one allegation from 2017 that was assessed by the Investigation Committee at field level, who recommended a full investigation. The case is still under review. During initial stages of the investigation a second allegation was made against the staff member in relation to staff misconduct, this matter also proceeded to investigation. As a result of the two investigations being conducted in parallel, additional time has been required. The investigation is in final stages with UNRWA Department of Internal Oversight Services.

UNRWA’s embeddedness within communities is of huge strategic advantage. However, with regards to SEA, this might make it more difficult for victims to report. Victims and survivors commonly fear a backlash from perpetrators, who have access to resources and people in power, and the ability to deny them vital aid. Engrained attitudes towards sexual activity outside of marriage and fear of stigma can also allow abuse to perpetuate and go unreported.

UNRWA operates a dedicated complaints telephone and email hotline administered by the Department of Internal Oversight Services (DIOS), which is independent of UNRWA programmes and services and consists of dedicated independent investigative staff. DIOS staff are also available to assist victims of SEA in safely submitting confidential complaints. This is good, but it’s important that beneficiaries are aware of this.

Recommendation: Given their unique operating model, UNRWA should explore ways to ensure their anonymous safeguarding reporting channels are communicated to affected populations.

Progress on recommendations from previous reviews

September 2017 Annual Review Recommendations	Progress
Targeting: UNRWA to implement the vulnerability assessment criteria to prioritise cash distribution to those most acutely in need; and to clarify targeting approach with regards to response in hotspots (cash or in-kind).	Complete- The targeting approach is now being implemented.
Protection: Review approach to protection including specific indicators on GBV and child protection in Annual Emergency Appeals.	Ongoing- As above, we now understand why the indicators were omitted and the protection challenges faced. We will continue to work with UNRWA on their protection response.
Log frame: UNRWA to adapt Annual Appeal indicators and targets based on changing context, capacity to deliver, and priority needs.	Complete- The targets for 2019 have now been agreed based on the current context, capacity and priority needs.
Value for Money: DFID to work with UNRWA Syria to develop more formalised approaches to VfM and an overall VfM strategy	Ongoing- DFID to reconsider whether this is a priority in the current programme, or whether it would be more efficient to develop a VfM framework ahead of any future funding.
Fraud Reporting: DFID Syria to share the monthly aid diversion report from UNRWA with DFID Counter Fraud Section lead	Complete/ Ongoing- UNRWA now share a monthly aid diversion report with DFID’s Counter Fraud Section lead.
Cash Evaluation: UNRWA to share the completed evaluation with lessons learned to be circulated to other humanitarian actors and used to inform future UNRWA activities.	Ongoing – Only recently (September 2019) obtained authorization from GAPAR to go ahead with the evaluation. UNRWA expect the report to be out by December 2019.
Accountability: UNRWA to take measures to ensure that the accountability recommendation from the Independent Commission for Aid Impact (ICAI) and Field Monitoring Report are implemented, including improving communications on how feedback mechanisms work, and ensuring that there is capacity for beneficiary feedback at all sites of operation including distribution centres and health facilities.	Ongoing – UNRWA ensures accountability to beneficiaries through conducting vulnerability assessment, third party monitoring, and protection audits among other mechanisms. A complaint mechanism is in place to allow beneficiaries to voice their concerns. In addition, a hotline is established for beneficiaries of humanitarian assistance. Beneficiaries can also reach out directly to area offices and field office in Damascus.
Safeguarding: UNRWA to agree to DFID Minimum Safeguarding Standards, both centrally at and field level	Complete- UNRWA have completed DFID’s Enhanced Safeguarding Due-Diligence Assessment and findings are being acted upon.
Population verification: DFID to discuss with UNRWA the specific constraints to carrying out a population verification, particularly for cash programming	Pending - UNRWA has been conducting verification of physical presence of each family in Syria in each cash round. UNRWA deploys its staff to the distribution outlets to verify the physical presence of at least one adult member of each family. / UNRWA did not conduct a verification of physical presence of all PRs (18 years and above) in for the last one year. In 2018, due to active conflict, thousands of PRs were displaced. Considering the dire situation of the PRs conducting verification was not pragmatic. The introduction of the targeting approach in 2019 excluded almost 65% of the refugees to receive food ration. Furthermore, the non-vulnerable groups also receive half of the cash assistance comparing the vulnerable groups. Because of all the changes introduced, the environment was not conducive to conduct a full verification during this period. SFO will strive to conduct a verification in 2020.