Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Neglected Tropical Diseases Implementation Research Programme.
Programme Value: £7,012,587 (currently under review)		Review Date: 24 June 2015
Programme Code: 203089	Start Date: 1 November 2014	End Date: 31 October 2019

Summary of Programme Performance
Year	2014
Programme Score	A
Risk Rating	N/A

Summary of progress and lessons learnt since last review

At the time of the last review the programme had not yet begun and the review was “light touch” and based predominantly on the procurement cycle/ process. This year the review will not be able to look at the programme in depth as the inception phase started on 1 October and has been running for approximately 6 months.

COUNTDOWN has used the initial period of the contract to interact with partners and to agree a workplan for rolling out the research. The Ebola outbreak in Liberia (one of the anticipated partner countries) has resulted in a change to the original focus and work in Liberia has been put on hold for the time being, with the potential for a minimal programme of research to take at a later stage (much smaller than originally planned). Initiation of any activities in Liberia would be subject to approval by DFID, and based on DFID guidance on working in Liberia.

As an alternative to Liberia, COUNTDOWN was asked by DFID to consider scaling-up the implementation research in Nigeria which has one of the highest burdens of Neglected Tropical Diseases(NTDs) in the world. COUNTDOWN produced an informal concept note, proposing the potential focus on the research in Nigeria. Following feedback from DFID, COUNTDOWN has developed a proposal for additional funding with a revised workplan, which is currently under consideration.

Summary of recommendations for the next year

1. With the reduction in activities in Liberia, DFID to look into the potential to expand activities in Nigeria. DFID to review COUNTDOWN proposal to expand research in Nigeria (ACTION – DFID by August 2015)
2. COUNTDOWN to lay out a specific very limited proposed scope of work for what can be achieved in Liberia, identifying and taking account of the constraints following the Ebola epidemic (ACTION – COUNTDOWN by end of inception period)
3. Following the inception period, reduction in programme in Liberia and potential expansion in Nigeria, the logframe, indicators and milestones will need to be updated. COUNTDOWN are planning to do this at the monitoring and evaluation meeting on 1-3 September. This overall output will also need changing, as it is more specific for the inception period (ACTION – COUNTDOWN by end of inception period)
4. To ensure that COUNTDOWN is continuing to share information and collaborate on a regular basis with the range of DFID funded NTD programmes involving mass drug administration, including programmes tackling lymphatic filariasis (Centre for Neglected Tropical Diseases), schistosomiasis (Schistosomiasis Control Initiative), trachoma (Sightsavers) and integrated NTD programme in Nigeria (Sightsavers) (ACTION – COUNTDOWN ongoing)

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-203089/documents/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-203089/documents/

Outline of the programme

DFID has committed £245million to supporting the control of Neglected Tropical Diseases (NTDs) over the period 2011-15. This commitment includes approved support to the control of schistosomiasis, lymphatic filariasis, onchocerciasis, and trachoma. It also includes the funding of an Integrated NTD Control Programmes in Nigeria.

The main pillar of Integrated NTD Control Initiatives is delivery of Mass Drug Administration (MDA) programmes to treat and control up to 7 NTDs (schistosomiasis, lymphatic filariasis, onchocerciasis, trachoma and three soil transmitted helminths) simultaneously. Other NTDs and/ or control activities may also be included but this will depend upon the country context and stakeholder preferences.

DFID’s Research and Evidence Department (RED) commissioned a programme of NTD Implementation Research that will directly contribute to the achievement of the 2020 NTD elimination and eradication goals through providing a greater understanding of how best to cost-effectively and sustainably deliver integrated NTD Control Programmes at scale.

The focus of the research is around delivery of NTD programmes to control the 7 diseases responsible for 90% of the total NTD burden, together with a wider range of complementary control activities.

The total amount of funds available for the programme was £15 million. Following a tendering process, Liverpool School Liverpool School of Tropical Medicine was awarded a contract for £7,012,587 (currently under review) for delivering this research programme.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

It is too early to make an outcome assessment as the programme is still in its inception period, although work is progressing in line with the expected overall outcomes. The only major change from what was initially planned was the research in Liberia is currently in hold as a result of the Ebola epidemic, and COUNTDOWN have therefore proposed to expand the programme in Nigeria.

Overall output score and description: A – outputs met expectations

This programme is still in its inception period, and therefore this annual review is based on limited activities within a small time period. However key activities have taken place including the inception planning workshop, signing of contracts and co-organisation of several international and national NTD meetings.

The focus of the initial proposal from COUNTDOWN was to cover Cameroon, Ghana and Liberia with a very limited focus on Nigeria. In initial negotiations and during the inception period, it was agreed to significantly limit the focus on Liberia, due to the challenges in starting new research very soon after the Ebola epidemic. The research questions are not specific to the context, and could be asked in other countries that are not tackling multiple competing priorities as the health system recovers. COUNTDOWN have submitted a proposal to expand the research in Nigeria to take account of the reduction in Liberia. Nigeria is a high priority country for implementation NTD research, as it has one of the highest burden of NTDs globally. It also has new integrated NTD programmes established recently, funded by DFID (led by Sightsavers) and USAID (led by RTI). COUNTDOWN have submitted a proposal, which is currently being reviewed by DFID.

Key lessons

This programme is still in its inception period, and therefore there has been no time to identify any key lessons.

Key actions

With the reduction in activities in Liberia, DFID to look into the potential to expand activities in Nigeria. DFID to review COUNTDOWN proposal to expand research in Nigeria (ACTION – DFID by August 2015)

COUNTDOWN to lay out a specific very limited proposed scope of work for what can be achieved in Liberia, identifying and taking account of the constraints following the Ebola epidemic (ACTION – COUNTDOWN by end of inception period)

Following the inception period, reduction in programme in Liberia and potential expansion in Nigeria, the logframe, indicators and milestones will need to be updated. COUNTDOWN are planning to do this at the monitoring and evaluation meeting in September 2015. (ACTION – COUNTDOWN by end of inception period)

Has the logframe been updated since the last review?

No. However the logframe needs to be updated before the next annual review.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Establishment of a vibrant consortium with national NTD programmes and international stakeholders to identify research questions and develop research protocols.
Output number per LF		1	Output Score	A
Risk:		Low	Impact weighting (%):	20
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
A balanced operational consortium consisting of 4 organisations and 4 sub Saharan Africa countries, and international stakeholder dialogue established.	No milestone established for inception period	This has been achieved. A consortium established with 5 organisations and 4 countries. International stakeholder dialogue has been established
Research questions identified, clearly framed with an associated protocol and workplan.	No milestone established for inception period	Research questions have been identified, for which protocols and metrics are being developed.
Research uptake strategy completed & approved by consortium & provisional workplan target indicators fulfilled.	No milestone established for inception period	COUNTDOWN has been involved in co-organising several international and national NTD meetings

Key Points
The COUNTDOWN programme commenced in November 2014 and was formally reported in a plenary lecture given by the Director at the Annual Meeting of the Coalition for Operational Research on NTDs (COR-NTD) and the American Society for Tropical Medicine & Hygiene (ASTMH) in New Orleans, 2014. An inception planning workshop took place in March, at which the COUNTDOWN Management Committee first formally convened. Following the launch the Country Management Teams in Ghana, Cameroon and Liberia were assembled and functional by June. All inception year contracts have been agreed and issued (with FHI360, Pamoja Communications, Ghana Health Service and the Universities of Yaoundé and Buea, Cameroon). The work in Liberia has been on hold due to the recent Ebola epidemic.

The research positioning and uptake has included co-organisation and representation at several strategic international and national NTD meetings. The COUNTDOWN team has identified and contextualised key knowledge gaps within the delivery of integrated NTD control and significant deficits within the health system that need investigation. Questions around scale-up and promoting health equity have been framed and initial workplans are being reviewed. The ethical review process in underway and will be submitted to the LSTM Research Ethics Committee and in-country national ethical approvals, shortly after the end of the inception period.

Recommendations
1. With the reduction in activities in Liberia, DFID to look into the potential to expand activities in Nigeria. DFID to review COUNTDOWN proposal to expand research in Nigeria (ACTION – DFID by August 2015)
2. COUNTDOWN to lay out a specific very limited proposed scope of work for what can be achieved in Liberia, identifying and taking account of the constraints following the Ebola epidemic (ACTION – COUNTDOWN by end of inception period)
3. Following the inception period, reduction in programme in Liberia and potential expansion in Nigeria, the logframe, indicators and milestones will need to be updated. COUNTDOWN are planning to do this at the monitoring and evaluation meeting on 1-3 September. This overall output will also need changing, as it is more specific for the inception period (ACTION – COUNTDOWN by end of inception period)

Output Title	Provide rigorous and gereralisable evidence to improve community-based MDA programmes in targeted countries.
Output number per LF		2	Output Score	A
Risk:		Medium	Impact weighting (%):	30
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of evidence-based strategies identified and published by COUNTDOWN.	No milestone established for inception period	This would not have been expected to start during the inception period
Number of operational plans that include evidence-based strategies as identified by COUNTDOWN.	No milestone established for inception period	This would not have been expected to start during the inception period

Key Points

As the programme is in the inception period there have been limited activities in this area, looking at how to produce evidence to improve community-based MDA programmes in targeted countries.

As described in output 1, activities within the inception period have ensured that the consortium has been established, and mechanisms put in place to enable evidence to be shared when possible.

Recommendations

Output Title	Develop knowledge management strategy and multi-sectoral platforms for dialogue to ensure open access to knowledge products tailored to the implementation needs of NTD control programmes.
Output number per LF		3	Output Score	A
Risk:		Medium	Impact weighting (%):	30
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Knowledge management strategy tailored to country needs and capabilities.	No milestone established for inception period	Work has started to develop the strategy
Multi-sectoral platform(s) developed to allow for interactions between researchers and programme staff.	No milestone established for inception period	This would not have been expected to start during the inception period
Number of open access knowledge products produced and disseminated.	No milestone established for inception period	This would not have been expected to start during the inception period

Key Points

A research uptake planning meeting took place in Ghana which brought together 25 participants from government, academia, and the media. A similar meeting has been planned for the USA/UK stakeholders and stakeholders in Cameroon.

COUNTDOWN has co-organised a number of international meetings to introduce COUNTDOWN and gather information on research priorities and potential barriers to research utilisation. This has included a meeting on HIV and female genital schistosomiasis (www.fgsworkshop.org), which has already impacted the work in the government of Ghana, where efforts are being made to better map and act upon this manifestation of the disease. A number of outputs are being developed including a paper for Open Democracy (on action to address female genital schistosomiasis) and a research chapter entitled “The social and economic impact of neglected tropical disease in sub-Saharan Africa” with one of the COUNTDOWN team as lead author.

In April 2015 the COUNTDOWN website was visited by 764 users who viewed 2072 pages. In an absence of research findings, COUNTDOWN is actively blogging as a way of communicating the process that we are following during the planning phase. In the past six months the COUNTDOWN blog has been visited by 1893 users from 83 countries (top 10 countries: UK, USA, Angola, Nigeria, Portugal, Spain, Switzerland, France, South Africa & Ghana) who have viewed 3715 pages. The COUNTDOWN Twitter account has sent 1028 tweets and has 867 followers.

Recommendations

To ensure that COUNTDOWN is continuing to share information and collaborate on a regular basis with the range of DFID funded NTD programmes involving mass drug administration, including programmes tackling lymphatic filariasis (Centre for Neglected Tropical Diseases), stosomiais (Schistosomiasis Control Initiative), trachoma (Sightsavers) and integrated NTD programme in Nigeria (Sightsavers) (ACTION – COUNTDOWN ongoing)

Output Title	Increase research capacity in targeted countries and improve understanding of multi-sectoral evidence-based NTD programmes among health stakeholders.
Output number per LF		4	Output Score	A
Risk:		High	Impact weighting (%):	20
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of research uptake officers trained and actively participating in research at national and district level.	No milestone established for inception period	Some training has taken place in setting the research uptake landscape (around 45 people in Ghana and the annual meeting received social media training and an introduction to research uptake
Number of health stakeholders who apply research evidence to policy planning and budgeting.	No milestone established for inception period	There is ongoing work by COUNTDOWN in Ghana to show the connection between NTDs and gender related issues (with regards to LF and schistosomiasis)
Number of operational plans that include a multi-sectoral approach to NTD control and sustainability.	No milestone established for inception period	This would not have been expected to start during the inception period

Key Points

This programme is in its inception period, and therefore specific activities have not commenced. However due to the structure of this programme, engagement within the targeted countries has already started in the inception period, such as the planning meeting in Ghana, which brought together 25 participants from government, academia, and the media in order to identify key stakeholders, conduct a policy and practice analysis and devise an inception phase work plan.

Recommendations

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

Work within inception year has concentrated on finalising budgets for country partners which has seen negotiations take place to secure the best value for money and cost-sharing practises between partners. The project is presently on track with procurement set to take place in support of Year 2 operations.

COUNTDOWN has been able to synergise with external funders with the delivery of meetings e.g. Merck-Serono as well making use of web-based communication media reducing the need for international travel and telephone-based costs.

VfM performance compared to the original VfM proposition in the business case

As this is in the inception period it is too early to make any accurate judgement on value for money indicators.

Assessment of whether the programme continues to represent value for money

This programme continues to represent value for money, but as it is still in the inception period it cannot be fully assessed at this stage.

If there is a change in the focus of activities with reducing activities in Liberia and increasing activities in Nigeria this has the potential to increase value for money. Nigeria has a much greater burden of NTDs, and therefore any impact of the research would benefit from economies of scale. DFID is also funding NTD implementation programmes in Nigeria, and therefore there is the potential for sharing resources where possible between the DFID funded research and implementation NTD programmes. Any results should also be able to have a direct impact on improving the effectiveness of the DFID funded integrated NTD programme in Nigeria.

Quality of financial management

Although still in the early stages, financial requests and reporting to date have been satisfactory. Forecasting has been reasonably accurate; we will however expect this to improve once workplans have been fully developed and as the programme moves forward into its implementation phase – from October 2015,

Following a request from DFID to expand the scope of work in Nigeria, we are currently working with COUNTDOWN to agree an amendment to the contract. Through discussions and refinement of the research envisaged, we are currently considering an increase of approximately £1 million. The financial details in the proposal have been well presented and provides a clear vision of where the additional costs will be incurred.

Date of last narrative financial report	29/04/2015
Date of last audited annual statement	N/A

E: RISK (½ page)

Overall risk rating: Medium

Overview of programme risk
The Ebola epidemic had a significant impact on the feasibility of NTD implementation research in Liberia. Mitigating actions have been taken by putting the programme in hold in Liberia, and significantly reducing the scope of work in the work plan. The situation in Liberia is being closely monitored, and a final decision on the scope of work in Liberia will be taken by DFID and COUNTDOWN during the inception period.

The proposed expansion in Nigeria by COUNTDOWN is likely to include states in Northern Nigeria. Therefore the security situation in Nigeria will be closely monitored in order to assess the feasibility of research in this area. Research in Nigeria is very important due to the burden of NTDs, but any decisions need to take into account the increased risk that research in this area will present.

Undue delays in obtaining ethical approval pose a possible risk to the programme but hope to be minimised by centrally coordinating ethics submissions within the Liverpool based team. The Liverpool School of Tropical Medicine (LSTM) Research Ethics Committee have been approached and fully briefed on the COUNTDOWN project with a planned intention to submit timetable.

Outstanding actions from risk assessment
The potential expansion of the programme into Nigeria is justified by the burden of disease - Nigeria has the greatest number of people living with NTD infections in Africa, all of the targeted NTDs are endemic over large areas of the country and it is estimated that over 100 million persons (2 of every 3 Nigerians) suffer or are at risk from one or more of these diseases. However it does bring additional security and implementation risks, due to the insecurity, particularly in the research being undertaken in Northern Nigeria. This is mitigated by the choice of organisation that COUNTDOWN has identified in Nigeria. Sightsavers has more than 40 years’ experience in Nigeria, and has strong experience in delivering integrated NTD programmes in Northern Nigeria. Sightsavers has its main Nigeria office within Northern Nigeria, its staff have excellent knowledge of the context and they continually monitor the security situation. There are strong security procedures in place, and the organisation is ideally placed for delivering programmes in this area despite the security challenges. DFID and the programme will keep the situation under review.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

All activities are taking place in line with the planned timeframe (with the exception of activities in Liberia which are currently on hold due to the Ebola epidemic).

Performance of partnership (s)

COUNTDOWN is using the inception period to develop their relationships with partners in the four focal countries and to agree roles and responsibilities going forward. This will be monitored during the coming year and will be reported in the next Annual Review.

Asset monitoring and control

There are currently no assets as the programme is still in its inception phase. As purchases are made, COUNTDOWN will record and maintain details on an asset register. This will be made available to DFID on request and routinely submitted as part of the Annual Report. We will instigate “spot-checks” of assets periodically, including during programme visits to partner sites.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

This is not applicable for this programme, which is a research programme, working with academic partners, rather than providing funding through central government systems.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

In February 2015, two major additions to the relevant literature and the future NTD funding landscape were realised upon publication of the 3 Report of the WHO on NTDs 'Investing to overcome the global impact of Neglected Tropical Diseases' on 19 February at The Royal Society, London. On 20 February, a policy-led discussion meeting “Beyond 2020: A discussion on neglected tropical diseases (NTDs)” took place at the London Offices of the Bill & Melinda Gates Foundation, chaired by Richard Horton, editor of The Lancet. Both meetings were attended by COUNTDOWN staff and discussed within the consortium, but do not have an impact on the scope of work of the programme.

Monitoring progress throughout the review period

FHI360 is responsible for monitoring and evaluation of the COUNTDOWN programme. Roles and responsibilities for data capture have been agreed within the consortium to measure progress within the Logframe. A draft “activity matrix” has been prepared and will be finalised in the September workshop. In early September, FHI360 will host a round-table discussion to finalise the log-frame and indicators documents, assembling theme leaders and country partner key personnel for the meeting. The COUNTDOWN external Advisory Panel of 10, people representative from a variety of NTD stakeholders, is set to first convene in November 2015 to provide an annual oversight and strategic guidance.

DFID has been in regular contact with COUNTDOWN during the inception period. This has included two DFID officials attending the COUNTDOWN launch meeting. There have been ongoing communication with COUNTDOWN, particularly around the impact of the Ebola epidemic on the programme in Liberia, and the potential for expansion of the programme in Nigeria. The review was conducted by members of the Human Development Research Team following meetings with the COUNTDOWN team and discussions with NTD leads in USAID.