Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Building Disater Resilience in Pakistan
Programme Value: £76.3 million		Review Date: 10 July 2015
Programme Code: 203264	Start Date: 20-7-2014	End Date: 31-03-2020

Summary of Programme Performance
Year	n/a
Programme Score
Risk Rating

Summary of progress and lessons learnt since last review

This is the programme’s first Annual Review. The business case was approved in July 2014. However, staffing constraints meant that procurement was delayed, which was also in part in part due to the need for further design work. The team has used the time to resolve resourcing gaps, consult relevant stakeholders, streamline delivery mechanisms and develop a governance structure. Resourcing constraints are now being resolved and a dedicated adviser will be in place from October 2015. Field vists have informed a more rigorous cost basis and a revised scope of the first two years of the CBDRM component of the programme. Concepts from the World Bank and Food and Agriculture Organisation of the UN (FAO) have been reviewed and are under consideration.

Consultations with potential implementing partners, the Government of Pakistan’s Disaster Management Authority (PDMA) at the provincial and federal level now need to move beyond the Terms of Reference for the Community Based Disaster Risk Management (CBDRM) component and initial concepts, and into a detailed discussion of governance arrangements and prioritisation.

Summary of recommendations for the next year

Overarching recommendations:

The programme needs to be adequately resourced and the pace of implementation must pick up or the programme risks losing credibility. This should now be possible as the team now has more resources available to dedicate to the programme and will be fully staffed from October.

Extend the programme by a year: the team should seek approval to extent the programme by a year to make up for the delayed procurement and ensure there is a full six years of delivery.

Governance arrangements:

Respective roles and responsibilities should be clear between FAO and supplier.

There should be a clear mechanism for ensuring that perspectives and lessons that arise from delivery at the community level inform the institutional strengthening component (output 3).

Coordination mechanisms should be clarified to ensure coherence between components, and between different partners delivering at the same component level.  Effective delivery will rely heavily on there being strong coordination across these dimensions, given the theory of change assumes accountability will be supported at local level through the CBDRM work and the institutional strengthening.

Indicators (as seen in output 1 below) to measure the success of the governance structure should be further developed; the MYHP AR in December 2015 should consider how the management of the Multi Year Humanitarian Programme (MYHP) interacts with the governance structure of the Building Disaster Resilience Programme (BDRP), particularly around Natural Disasters / CBDRM and Pakistan Evidence and Learning Platform (PELP).

A decision on whether to establish a Secretariat outside of DFID needs to be taken urgently. The role of the Secretariat in helping facilitate relationships between the different delivery partners should be considered and the functions of any Secretariat (whether funded through FAO MoU or expanded from the CBDRM Programme Implementation Unit should be clearly articulated and discussed with all stakeholders.

Interaction with other programmes

Link the disaster risk financing component to planned centrally funded initiatives on disaster risk financing (e.g. proposed Global Parametrics, KfW platform).

The PELP should work with other relevant research funders, such as Research and Evidence Division’s Humanitarian Research Team. This should be worked into the inception plan for the service provider.

Establish meetings between implementing partners and Asia Regional Team’s Climate Proofing Growth and Development implementing partners and potentially Climate Services team to consider building more formalised partnerships as a result of future recommendations. This could improve delivery on similar outcomes, for example, by determining the respective programmes’ comparative advantage on different levels of early warning systems and short term forecasting and modelling in context of risk insurance. The meetingscould be timed for after their Annual Reviews.

The programme should benefit from the MYHP Annual Review in December, particularly through analysis of the evolving response trigger mechanisms and the PELP procurement.

Management of the programme:

In future, to maintain momentum in the programme, sufficient staffing capacity for implementation should be ensured.

The logframe should be updated immediately after the Annual Review, to reflect delays and set achievable milestones for 2016 and address the points mentioned below. This should happen before the more comprehensive changes are made in consultation with suppliers and based on their work during the inception period.

The PELP, which sits across the Multi-Year Humanitarian Programme and the Building Disaster Resilience Programme, should be a helpful way to ensure the programmes learn from one another, whilst reducing overheads of similar functions through different programmes. Both programmes should adopt a coherent approach to M&E, to a) ensure strong and joined up evaluation through the PELP procurement and b) an effective relationship with VALID[1] the independent evaluators. The Annual Review for the MYHP should be used to check that this joint M&E approach is developing well.
[1] VALID have been contracted by RED and CHASE to run a multi-country evaluation of multi-year humanitarian and resilience programmes. The will predominantly be focusing on VFM for multi-year humanitarian verses annual financing through: - Operational cost saving (staff, procurement, proposal writing and currency risk) - Early action (speed of responses) - Predictability (pre-positioning of stocks, pooling orders, leveraging of additional funds, cost savings from long-term investments).

The team should use the procurement period to design effective systems for reporting and associated financial management which can be reflected in the Delivery Plan. The reporting elements should be consistent with PELP components under the Multi-Year Humanitarian Programme (MYHP) and – where possible – with the reporting for the Natural Disasters pillar of the MYHP. ,DFID should develop systems for monitoring the progress following a due diligence exercise once the key supplier for CBDRM is on board. Regular engagement with the supplier early in the contract will be crucial in setting the right expectations on budget utilisation, forecasting and overall financial performance.

Procurement:

The OJEU Terms of Reference should be clearer and explicitly request bidders to:

  1. identify how they will work together with FAO;
  2. demonstrate their knowledge and understanding of community based approaches (especially for resilience building and disaster risk management (DRM)) and how they will put this knowledge into practice during delivery;
  3. should identify how this initiative will link with and learn from other relevant initiatives in Pakistan.

The risk management system for procurement should incude mitigating actions against delivery delays – such as holding pre-supplier pre-bid meetings. In particular, this will help manage relationships between FAO and the service provider.

Technical:

The team should consider how PELP could include ‘institutional incentives’ as a research area, particularly focussed on how the right incentives can be established for resilience and disaster preparedness in the Pakistan context.

Methodologies for risk assessment should be consistent and co-ordinated between the CBDRM and institutional strengthening components.

In order to ensure strong evaluation of bids and working with suppliers through inception periods along with overall management of the programme, this programme should learn from other programmes working oncommunity based approaches, institutional capacity building, research and innovation approaches.  This will help ensure that the design is well matched to context early on, which will be essential to delivering early.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	n/a (going through OJEU)
DevTracker Link to Log frame:	n/a (going through OJEU)

Outline of the programme

The UK Government is providing an investment of £76.3 million over six years (2014-2020) to help build disaster resilience in Pakistan. Investing in resilience to natural disasters effectively reduces people’s vulnerability to shocks, and enables better and more appropriate responses. This investment will not negate the need to support people who have been affected by humanitarian disasters in the short to mid-term. Beyond the ‘effective governance’ output (1), the programme focus is split into three main components:

(Output 2) Community Based Disaster Risk Management to help village communities to plan and prepare for disasters with improved early warning systems. While also assisting in the establishment of disaster responder teams and locally managed funds aimed at disaster-proofing infrastructure in high-risk areas of Pakistan. The original target for the CBDRM output was to work in 8,750 villages (reaching an estimated 3.7 million men and women) for emergency preparedness.

(Output 3) Institutional Strengthening of Disaster Management Authority architecture to support greater government capacity at national and provincial level to plan and respond to disasters. Through this there is a specific emphasis on improving linkages between communities and provincial level disaster management agencies. This component will enhance government capacity to help contextualize DRR strategies, allow for better responses and increase government ownership.

(Output 4) Pakistan Evidence and Learning Platform(PELP) (linked to the MYHP) which is designed to generate knowledge and evidence in Disaster Risk Reduction (DRR) and building resilience to help better inform good practice and enhance interventions. This component will also deliver Third Party Monitoring.

To ensure a smooth join–up with planning around preparedness, DRR and humanitarian response, the programme supports the implementation of the GoP’s National Disaster Risk Management Plan. Programme components are also aligned to contribute to MDG 1: eradicating extreme poverty and MDG 7: ensuring environmental sustainability.

The delivery of this programme will be separate to the MYHP however there are two areas of potential overlap where there is a need for coherence. These are firstly between the Natural Disaster pillar of the MYHP, where DFID will prepare for and respond to natural disasters through a consortium approach; and secondly through the PELP which bridges the programmes. These need to be monitored carefully, inform a review in December 2017 at the end of phase 1, to determine the potential scale up of the CBDRM component and the effectiveness of the approach overall.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

Delivery arrangements are being put in place, with procurement for Output 2 due to begin by 20 July and procurement for Output 4 in August. Programme implementation has been delayed due to:

Staffing constraints. Whilst some interim support has been provided, for example through short term technical assistance, it has not been sufficient to maintain momentum. However, staff gaps are now almost fully addressed, and a full time Resilience Adviser is expected to be in place by mid October.

Staff changes in GoP posts. This has meant additional time has been required for consultation on the programme.

Delayed procurement of Output 4 (PELP, sitting across MYHP and BDRP) due to the need for design and consulation to inform both the TORs and DFID’s internal decision about the appropriate procurement mechanism for this output. The procurement is now going to through DFID’s Global Evaluation Framework Arrangement or OJEU In August

As a result of these delays, milestones for 2016 need to be revised by the time the CBDRM contract is signed in January 2016.

Overall output score and description

A summary of the ratings / scores of individual Outputs is presented below.

Output	Title	Weight	Output Rating
1	An effective governance structure	15%	B
2	Inclusive community disaster management committees implement plans; financed projects based on risk assessment	50%	B
3	Government of Pakistan's Disaster Risk Reduction Policy implemented effectively with improved coordination, systems, expertise and capacity at all levels	25%	C
4	A comprehensive research programme initiated to pilot and test new innovations and approaches to DRR and DRM to inform better future development of national resilience plans and priorities.	10%	C
Overall Programme Rating			B

Key lessons:

This programme has multiple delivery channels, and will be delivering in a complex political environment and fragile context. For this reason, it is essential that the governance and management structure set up for this programme have strong buy-in from partners and securing maximum accountability and VFM to DFID. The proposed governance structure does not clearly spell out roles and responsibilities, particularly at the management structure level, and how the different delivery partners will coordinate. A key lesson from delivery of other programmes, is that getting governance right at the outset is worthwhile investment of time and that strong oversight early on can help mitigate the risks of the programme going off track at an early stage.

There are other activities in the region which the programme should coordinate and be coherent with to help reinforce delivery, e.g. the Asia Regional Team’s Climate Proofing for Growth and Development programme and the scoping study for Climate Services. The programme should also consider how it relates to relevant centrally funded initiatives, such as Building Resilience and Adaptation to Climate Emergencies and Disasters (BRACED) and work being commissioned by the Humanitarian Research Team.
Suppliers and partners should be asked to demonstrate how they will build on past practice and experience, even if from other sectors.

Key actions

The team has secured part of an A1 Governance Adviser’s 10% to quality assure the governance structure and sub-national governance focus of the programme. This Governance Adviser’s inputs should clarify the governance structure and consider how it could be reinforced, as well as ensuring a clear process for early discussion of new proposals with partners to ensure maximum buy-in from stakeholders. (approach determined by end August 2015)

Agree how Asia Regional Team’s programme activities will be coordinated with this programme; (by end September 2015).

Scope out opportunities for collaboration between Research and Evidence Division and the Pakistan Evidence and Learning Platform (PELP).

Revise the logframe to link to Multi-Year Humanitarian Programme and develop a draft M&E approach for the management of the programme overall so that VALID’s evaluability assessment, and the subsequent MYHP Annual Review in December 2015 is aware of M&E priorites of the programme. The MYHP AR should also consider how the BDRP and MYHP programmes can maximise effectiveness by working together, while managing delivery risk

Has the logframe been updated since the last review?

The logframe has been updated to add a governance output, which will ensure that the different components relate to each other and that decision taking is made at the appropriate level. Process milestones were also added to reflect the procurement requirements.

A revised logframe is in development with a slightly amended impact statement and indicators.

It should include the following:

Show a clear relationship to the logframe for the MYHP through the Pakistan Evidence and Learning Platform.

Revised costings for deeper work in fewer villages for the first two years for Community Based Disaster Risk Management. The numbers of beneficiaries may then be revised depending on the review at the end of phase 1. The ‘depth’ of the intervention will need to be measured so as to show clearly how the quality ( sustainability) compares to the quantity ( numbers of beneficiaries).

Understand partner perspectives and agree new logframe with all partners (for example, this can be done through sharing revised indicators with World Bank for the institutional strengthening component);

Work as a nested logframe so that standard indicators for CBDRM work feed into an overall output at the higher level logframe, leaving space for the higher level logframe to focus on the interaction between components.

C: DETAILED OUTPUT SCORING (1 page per output)

Output 1: Governance

Output Title	An effective governance structure
Output number per LF		1	Output Score	B
Risk:		High	Impact weighting (%):	15%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
Strategic and management committee meeting being operational and meeting frequently	Federal and Provincial buy-in to the governance structure of Strategic and Management Committees (agreed with NDMA, PDMAs, WB and FAO). Clearly reflected to potential CBDRM suppliers. Secretariat function agreed and in place.	The level of consultation with Federal and Provincial governments has broadly been adequate although more is required in particular areas (Punjab and Sindh). The governance structure is more clearly represented in the CBDRM Terms of Reference.
Sharing between provinces and linkages between components through information sharing	Governance structure in place	Consultation with the PDMAs and NDMA and potential implementing partners has agreed the overarching structure. The first Strategic Committee is due in August.

Key Points

There have been personnel changes in all of the PDMAs along with the NDMA over the last year, meaning that new relationships have had to be built. The programme team has co-ordinated with the centrally funded Disaster Risk Financing programme, delivered throught the World Bank, to help establish relationships with the Government.

After consultation, the broad governance structure was revised so as to have a strategic committee and a management committee rather than only one layer (the ‘steering committee’). This will protect strategic level decision making and help ensure operational issues are dealt with promptly. To ensure that there is the appropriate level of engagement with PDMAs in particular, the programme team should learn from other DFID Pakistan programmes working at provincial and district level. In particular, changes which will affect District Disaster Management Authorities (DDMA) in Punjab after local elections, when the Chairs of the DDMAs will become elected local appointees, should be considered with the relevant DFID governance advisers so as to prepare for additional buy-in now.

Additional detail on how the governance structure will become operational, to what timescale and with what accountability lines will be important over the next two to three months. In particular, a workable provincial level steering arrangement between the components needs to be determined and agreed, in consultation with Provincial and District level governments.

A Secretariat has been considered, funding for which could be channelled through the FAO MoU. The primary justification for an extetrnal Secretariat was to invest in the initial relationships between components and in particular to ensure that the programme was closely linked to, for example, the Implementation Unit for the National Disaster Management Plan and different Provincial roadmaps. If this Secretariat goes ahead it will be important to monitor this cloely for effectiveness and to determine whether the model needs to be adjusted.
Summary of responses to issues raised in previous annual reviews (where relevant) N/A

Recommendations

Indicators to measure success of the governance structure should be improved; the MYHP AR in December 2015 should also consider how the management of MYHP interacts with the governance structure of BDRP, particularly around Natural Disasters / CBDRM and PELP.

The role of the Secretariat in helping facilitate relationships between the different delivery partners should be considered and a decision on whether to procure a Secretariat outside of DFID based on the costs versus risks needs to be taken. The functions of any Secretariat (whether funded through the FAO MoU or expanded from the CBDRM Programme Implementation Unit) should be clearly articulated and discussed with all stakeholders and reviewed after the first year to ensure the model is appropriate for the programme.

Output 2: Community Based Disaster Risk Management

Output Title	Inclusive community disaster management committees implement plans; financed projects based on risk assessment
Output number per LF		2	Output Score	B
Risk:		Medium	Impact weighting (%):	50%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
Number of inclusive community disaster managment committees formed (developing existing committees or building new committees) and maintained, which are progressing with high quality planning and delivering against plans.	Procurement significantly underway for service provider to begin activities in September 2015	Procurement has started but has been delayed (see above) and therefore is not as advanced as originally planned.
% target population scoring between 4-6 on resilience scorecard from village level interventions
% target population benefitting from Union Council (UC) level projects
Number of good quality proposals put to local districts for financing or co-financing

Key Points

This output covers activities that will support building disaster resilience of communities and Union Council. The scope of the work is clear and it must complement the work that will take place through Output 3 (Institutional Strengthening). A wealth of knowledge and experience has been gained from decades of community based management work – for instance in health, water and sanitation, natural resources and disaster risk reduction sectors. In order to deliver on the outcome, it is very important that this programme uses the inception period to learn from past experience. Whilst the focus on risk assessment and hazards, planning and small projects is appropriate, it is also important to ensure that the work through the Institutional Strengthening component (output 3) delivers the right enabling policy and institutional environment for the community level work to proceed.

Following early delays, procurement of the supplier is now underway and delivery should commence by January 2016.

The team is now looking for further technical assistance (in addition to the supplier) through a partnership with FAO to bring in further specialist knowledge on building resilience of smallholder agriculture and local food systems. This should help accelerate work in this sector. In order to make this support deliver effectively, FAO’s management and staff, will have to be fully integrated with management and staff of the supplier. There is an urgent need to clarify respective roles and responsibilities to reduce the risk of duplication and misunderstandings, including placing unnecessary additional burden on the communities.

Summary of responses to issues raised in previous annual reviews (where relevant) N/A

Recommendations
More work needs to be done on the BRDP governance structure to ensure that:

- respective roles and responsibilities are clear between FAO and supplier
- there is a mechanism for ensuring that perspectives and lessons that arise from delivery at the community level inform the Institutional Strengthening component (output 3).

The Terms of Reference for OJEU should explicitly request bidders to:

- identify how they will work together with FAO;
- demonstrate their knowledge and understanding of community based approaches (especially for resilience building and DRM) and how they will put this knowledge into practice during delivery;
- identify how this initiative will link with and learn from other relevant initiatives in Pakistan.

Output 3: Intistutional Strengthening

Output Title	Government of Pakistan's Disaster Risk Reduction Policy implemented effectively with improved coordination, systems, expertise and capacity at all levels
Output number per LF		3	Output Score	C
Risk:		Medium	Impact weighting (%):	25%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
a) Staff at PDMA and DDMA level in Sindh and the Punjab trained in disaster risk asessment and response. b) Information and guidance including codes, advice and construction methods developed and disseminated; c) Coordination mechanisms between response agencies and community organisations/civil society; d) Standard Operating procedures making funds available to PDMAs and NDMAs in a timely manner; / e) Staff of Line Department incorporating DRR/DRM in project designs (PC-1) and in monitoring formats. / f) A national risk assessment platform comprising technical agencies (geology, meteorology), flood commission and others	World Bank proposal developed based on joint discussions with PDMAs	The development of the concept has been somewhat delayed by other WB work following 2014 floods, difficulty in setting up joint PDMA meetings and in part by DFID’s own capacity. / A revised concept is now underway, more heavily based on consultation with relatively new PDMA DGs.
a). Comprehensive GIS based database established reflecting all known risks and natural/man-made hazards (Climate change, earthquakes, weather events, conflict etc); b) A risk financing strategy developed to enable the Government to access liquidity after disasters; / c) Partnerships developed with the private sector for the provision of life and asset insurance cover.
a) Existing and planned donor-financed activities mapped and share with the GoP at regular intervals; / b) National capacity developed to measure the impact and options for investments in DRM c) Regular high level donor/government meetings held to ensure coordination and information exchange.

Key Points

Activities under this output will extend existing work being carried out by the World Bank in Balochistan province, to two new provinces (KP and Sindh). This work will complement that taking place under the Community Based Disaster Risk Management component (output 2) and needs to be informed by lessons and experience at the community level, so that capacity building and institutional development are delivered according to the needs of people that are most affected by disasters, and can then empower people to respond.

The institutional framework, at provincial and district levels, is complex with many different institutions involved, and many overlapping mandates. There is scope for the implementing partner (World Bank) to streamline these, and develop alternative / new approaches for decentralised disaster management that can be transferred to other districts / provinces. However, DFID should closely monitor progress and the logframe should include indicators that can demonstrate progress against institutional development within this output.

On coordination and integration of resilience and disaster management across the range of different sectors and institutions found at the decentralised levels, there are useful lessons to be learnt from gender and climate / environment ‘mainstreaming’ experience. For instance, the importance of ensuring that divergent policies and approaches are removed, the avoidance of overly technocratic approaches, and ensuring appropriate incentives. There is key opportunity to align budget processes across sectors, so that resources are available at lower levels, for better coordination and operations on resilience building and decentralised disaster management. This programme could usefully engage more closely with the Asia Regional Team’s Climate Proofing for Growth and Development programme, which will be working at national level to better integrate climate and resilience related issues into budget and planning processes.

Attention should be paid to the assessments and risk methodologies which underpin the CBDRM and Institutional Strengthening components dovetail so that they are sufficiently consistent to agree on priority areas for delivery.

The programme could also learn from the Asia Regional Team commissioned scoping study on climate services, which identified work across the region – including Pakistan - to look at current capacities and needs for supporting climate services. If ART decides to take a regional climate services programme forward to implementation, then BDRP needs should be factored into the regional programme.

Summary of responses to issues raised in previous annual reviews (where relevant) - N/A

Recommendations

Arrange meeting between the BDRP partners and the appropriate leads of the Asia Regional Team’s Climate Proofing for Growth and Development programme to identify how these programmes could work more effectively together.

Methodologies for risk assessment being developed and applied under this output (must be consistent and coordinated with the methodologies being applied for the CBDRM work.

Link the disaster risk financing component to the planned centrally funded initiatives on disaster risk financing (e.g. proposed Global Parametrics, KfW platform).

Output 4: Research

Output Title	A comprehensive research programme initiated to pilot and test new innovations and approaches to DRR and DRM to inform better future development of national resilience plans and priorities.
Output number per LF		4	Output Score	C
Risk:		Medium	Impact weighting (%):	10%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
Number of evidence studies and documents produced on DRR to climate extremes that are based on consultation with a wide number of players and then disseminated		Procurement imminent for a joint Pakistan Evidence and Learning Platform
Number of meetings held with key line departments and with NDMA to encourage uptake and inclusion of research results into policy documents and annual work plans	Independent evaluators (VALID) contracted and conducted baseline studies; Cost benefit analysis updated	VALID has been contacted, with an evaluability assessment put back so as to have more partners in place by the time VALID visits Pakistan. Baseline studies delayed due to delayed procurement of components. Cost benefit analysis in the process of being updated on the back of revised costings.

Key Points

Under this output, a Pakistan Evidence and Learning Platform will be commissioned that will work to the BDRP as well as the Multi-Year Humanitarian Programme. This could be highly innovative, including looking at how building resilience can deliver better outcomes in terms of preparedness and recovery. Getting this information will be key to underpinning the case for resilience building at community, district and provincial levels. Producing this type of knowledge at earlier stages of the programme could help build up necessary momentum for Outputs 2 and 3.

Summary of responses to issues raised in previous annual reviews (where relevant) - N/A

Recommendation

Ensure that the research component includes looking at institutional incentives and particularly how can establish the right incentives for resilience and disaster preparedness in the Pakistan context.

The PELP should demonstrate how it will work with other relevant research funders, such as Research and Evidence Divisions Humanitarian Research Team.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

Since the business case stage, there has been no change to the cost drivers. For the CBDRM component, £10m out of the £60.5m budget related to delivery of the component has been approved by the SofS for the first two years of programme delivery by the supplier. Currently, £44.5m is in pipeline on ARIES and will be approved upon a review of supplier performance after two years.

The component breakdown is summarized as follows:

Component	Budget (£m)	Spend to date (£m)

Design Work for Building Resilience to Disaster in Pakistan	0.09	0.09
Community Based Disaster Risk Management [OJEU in process]	60.5	0
Monitoring, Reviews, Assessments	0.8	0.01
Institutional Capacity Building of Government Agencies [World Bank]	10.0	0
Research and Evidence on Disaster Risk Management	5.0	0
Total	76.39	0.1

VfM performance compared to the original VfM proposition in the business case

The cost benefit analysis used in the business case assumed that there would be future natural disasters in Pakistan, and in the event of these, the cost of the entire programme would be less than the additional DFID humanitarian response required if CBDRM were not delivered.   Since then, further work has been done to build a more comprehensive set of costs to deliver sustainable CBDRM.  This work has concluded that a slightly greater cost is required per village to ensure more sustainable CBDRM. The more robust set of costs still ensures a net benefit for the component, with additional developmental benefits which will be quantified before the contract is signed. The greater cost per village means that, for the first two years at least (phase 1), the component will be delivering in fewer villages than expected in the Business Case. As phase 1 is being used as a pilot phase, the budget is capped at £10 million. Depending on results, the second phase will either work at a greater or lesser depth, i.e. fewer or more villages, to react to value for money lessons learnt through phase 1.

Assessment of whether the programme continues to represent value for money

The overarching value for money framework is that the cost of the intervention is lower than the cost of humanitarian response due to people being better able to prepare for and react to shocks.   This still holds true.

Quality of financial management

To date, programme expenditure has been very low. Expenses have related to business case design work and consultancy fees for technical support provided to the programme team through CHASE OT. The OJEU process for the CBDRM component has started and a total of £10 million ringfenced for two years. The team is working closely with PCD to finalise the procurement route for the PELP.

The team has used the time to strengthen and streamline delivery structures and financial controls, in collaboration with key stakeholders including the Government as well as the UN system.

VFM will be achieved through effective negotiations of budgets while controls such as robust financial reporting from partners, due diligence, spot checks and annual external audits will help provide further assurance.

Recommendations:

DFID to develop a due diligence action plan / monitoring framework once the key supplier for CBDRM is on board. Key milestones and / or triggers and a robust reporting mechanism need to be finalised during the inception phase.

Regular engagement with the supplier to monitor budget utilization, forecasting and overall financial performance.

Date of last narrative financial report	N/A
Date of last audited annual statement	N/A

E: RISK (½ page)

Overall risk rating: Medium

Overview of programme risk: Given the programme has yet to begin implementation, the delivery risk remains unchanged at medium. However the team will need to closely monitor the following risks:

- Likelihood of disasters, corresponding preparedness: This programme is focussing on building capacity for preparedness at the community level, complimented by strengthening ownership. It is possible the proposed interventions may not make communities resilient enough to larger scale disasters, although the ‘deeper’ focused based on a new cost structure for the first phase will help to mitigate this.
- Federal & provincial relationships: The CBDRM component will be delivered in close coordination with the national and provincial and district level Disaster Management Authorities. A positive working relationship between the federal and provincial counterparts is a key driver of success, and the programme laso depends on engagement and ownership of key stakeholders.
- Selection : NDMA and PDMA will play a critical role in selection of most vulnerable districts. The CBDRM supplier will then need to propose an appropriate and robust methodology for selection of beneficiaries. The availability of appropriate and timely data will help mitigate the chances of selection bias.
- OJEU process & potential delays: The OJEU process is due to start by 20 July. The team anticipates several risks including the likelihood of a limited supplier response, lengthy negotiations and technical clarifications and a potential lack of ownership from the GoP partners. The programme lead and lead adviser will need to manage these risks.
- Synergies: As it stands, the research and evidence component under MYHP and BDRP is cross cutting and will help identify research / evidence gaps and areas of potential overlaps within the programme. The stocktake after two years of implementation will be key in determining potential synergy of components.

Outstanding actions from risk assessment: N/A

Recommendations:

- Inception phase: DFID will use the first phase of the OJEU process for district selection in consultation with PDMAs / NDMAs. FAO’s hazard mapping will help identify the most vulnerable districts which will then be provided to the post Pre-Qualification Questionairre stage suppliers.
- Overarching integrated risk management plan: Following the award of contract, the primary supplier will develop a risk matrix in consultation with DFID and other key stakeholders. This matrix should include external threats such as including security / access as well as appropriate mitigation strategies. The plan will be reviewed quarterly.
- Relationship building: Once the primary supplier for CBDRM is on board, DFID, the NDMAs and the PDMAs should further refine the delivery approach, proposed systems for clarity of roles and responsibilities.
Review and stocktake: Building in a stocktake after two years of implementation will test the proposed theory of change, refine delivery approach and identify synergies based on lessons learnt.

F: COMMERCIAL CONSIDERATIONS (½ page)

Formal approval for the programme came through in July 2014 however the procurement process did not get underway until July 2015. Delays have mainly been due to:
1. Resourcing constraints: staffing constraints within the team in the latter half of 2014 delayed the Terms of Reference for CBDRM.
2. Agreement on delivery route: An alternative approach to CBDRM delivery involving the UN was explored. However this proved not to be feasible. . and the team agreed to continue with OJEU plans but seek to engage FAO as a UN entity separately to be the technical assistance lead, ensuring livelihoods work to FAO standard.
3. Change in leadership: Changes in senior management at NDMA resulted in a significant delay in the approval of the terms of reference for CBDRM. The new Chairman of NDMA came on board in early January 2015 and the team has since then been regularly engaging with the Government to ensure their comments are incorporated within the TOR. The TOR were subsequently approved in June 2015 and the OJEU has been published. The team is regularly liaising with the PCD to ensure final contract is awarded by December 2015.

DFID is also working to engage the World Bank for institutional strengthening particularly towards capacity building of the local governments for preparedness and response. Delivery is expected to begin in September 2015. Procurement options for the PELP are being agreed with DFID’s Procurement and Commercial Department. The aim is to have a contract is in place by early 2016.

Recommendation:
The team recommends the programme end date is revised. The core programme structure will be fully operational in early 2016, but the impact of resilience interventions will not be visible untill 2017. To ensure the programme has the approved amount of time to deliver, a no-cost extension should be requested, extending the programme until FY 2021 as currently the business case covers six years of delivery. The revised timelines are as follows:

	Month	DFID FY
Programme Approval	Jul-14	14/15
Procurement	June-Dec 2015	15/16
Full Programme Implementation begins	Jan-16	15/16
Six Years of programme delivery ends	Dec-21	21/22
PCR of programme due	Mar-22	21/22

Performance of partnership (s)
Delivery of the resilience programme has been summarized below:

Component	Implementing partner	Agreement	Focus areas
Community Based Disaster Risk Management (CBDRM)	Management Agent	OJEU Contract (not signed)	Community Based Disaster Risk Management to help village communities to plan and prepare for disasters with improved early warning systems. Assisting in the establishment of disaster responder teams and locally managed funds aimed at disaster-proofing infrastructure in high-risk areas of Pakistan.
Institutional strengthening	World Bank	Likely to be channelled through GFDRR (not signed)	Institutional Strengthening of Disaster Management Authority architecture to support greater government capacity at national and provincial level to plan and respond to disasters. Specific emphasis on improving linkages between communities and provincial level disaster management agencies
Research & evidence pillar	Management Agent (and OCHA - to be agreed)	OJEU contract (and framework agreement – to be agreed) (not signed)	Pakistan Evidence and Learning Platform designed to generate knowledge and evidence in Disaster Risk Reduction and building resilience to help better inform good practice and enhance interventions

To ensure complementarity with the wider Humanitarian / DRR response, DFID has aligned its implementation to the GoP’s National Disaster Response Plan. The team will sign an ‘exchange of letters’ with the NDMA, to clarify management arrangements, and provide a framework on which to work together for the duration of the programme.

Additionally DFID will also be directly managing the partnerships with the World Bank and FAO but will ensure that all partners work in close coordination to contribute towards delivery of overall results of the programme. This will be achieved thorugh bilateral relationships and use of the Strategic Committee.

Programme performance will be reviewed through DFID’s quarterly management committee and a 6-monthly Strategic Committee, chaired by the NDMA. The SC will provide strategic direction, and ensure lesson learning, information-sharing and coordination between the different programme components. The management committee, will be attended mainly by the implementing partners but with NDMA / PDMA presence. Seperately DFID will continue to monitor supplier performance through regular monthly meetings to ensure delivery is on track.

Asset monitoring and control
The DFID team will ensure that the supplier contracted under the CBDRM pillar adopts DFID’s asset policy covered under the Smart Rules. Limited asset purchase is envisioned under the institutional capacity building and research pillars, however the team will ensure all partners understand DFID’s asset policy and meet DFID’s reporting requirements. Suppliers will be required to ensure a transparent and competitive purchasing process.. An asset register to record all assets purchased using programme funds will need to be submitted to the DFID team quarterly; regular spot checks will also be conducted.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

Not applicable

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

The evidence base for large scale CBDRM work in Pakistan is low, hence the phased approach of this component. The evidence base for CBDRM joined with other institutional strengthening interventions is slightly higher.

Since business case approval, there has been a more thorough analysis of the costs involved in order to deliver a more sustainable intervention. This will capture more developmental benefits during and after the programme (for example, saved income more reliable sources of electricity).

Further evidence from DFID related programmes, both focusing in supply/demand governance and other community based approaches, should be collated during the procurement phases to better inform DFID’s review of inception and implementation plans.

Third Party Monitoring under PELP will be helpful in further testing of assumptions in the Theory of Change. Specifically, the interaction between more specific village and UC level resilience investment plans and a better prioritisation of local government focus to those at risk areas will be crucial to determine the overall likely impact of the programme.

Monitoring progress throughout the review period

The team will continue to use the Delivery Plan as key tool for monitoring against the original timeline for procurement processes, finalizing agreements and associated milestones. This should include using Annual review recommendations to monitor core progress. Key monitoring systems once the programme has been set up includes:

Monthly review meetings with the key supplier(s) for stocktake, discussing challenges and solutions as well as identifying priorities (effective work planning);

Ensuring synergies with MYHP- using PELP for evidence gaps, overlaps and merging of components. Feeding into programme stocktake after second year of implementation;

Use of independent evaluators. DFID Pakistan has replaced DFID Yemen in being the fourth country for the multi-year humanitarian and resilience programme evaluation which will be conducted by VALID.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessmen
Key points
Summary of response to iprogrammessues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process