Annual Review - Summary Sheet

Title: Strengthening prevention of gender-based violence in Rwanda
Programme Value: £4.6 million		Review Date: 11th August 2015
Programme Code: 204142	Start Date: August 2014	End Date: August 2018

Summary of Programme Performance
Year	2014	2015
Programme Score	n/a	A
Risk Rating	Medium	Medium

Summary of progress and lessons learnt since last review

The first year of the ‘Strengthening prevention of gender-based violence in Rwanda’ programme was an inception year. Originally anticipating to take nine months, the inception phase was extended to September 2015 to allow for harmonisation of evaluation and programme approaches. The programme team, led by CARE, secured technical assistance from a range of experts in the field to support their review and finalisation of a new, innovative intervention model that combines curriculum and activism approach to prevention of intimate partner violence. The programme is entitled Indashyikirwa, meaning ‘agents of change’. The DFID centrally-funded ‘What Works to Prevent Violence’ research consortium (£25 million, 2014-2019) worked collaboratively alongside this process to design an appropriate and robust impact evaluation and operation research model, and also provided technical assistance on the intervention model. The intervention model and evaluation approach have been agreed, and the implementing partners and evaluation team are now finalising their work, for example pre-testing curriculum materials and securing ethics approval, ready to start programme implementation in October 2015.

The programme also provides support to UNICEF in devising and delivering a national child protection programme, with DFID’s funding focussing on curriculum development and training of child protection community workers and volunteers. This work is progressing well, although some minor delays have been encountered. The inclusion of this funding in the wider DFID gender-based violence prevention programme and the sharing of the Ministry of Gender and Family Promotion (MIGEPROF) as a GoR lead has provided an opportunity to ensure shared learning and alignment of approaches on the related issues of child protection and intimate partner violence.

Summary of recommendations for the next year

- With the transition to programme implementation, changes in the way that coordination has been managed will need to be considered. Tools and process to improve coordination will need to be effectively and proactively used, and the approach regularly reviewed. A focus on building the capacity of leading implementing partners (where required) to play greater role in day to day management of partners inputs may be required. CARE UK, CARE Rwanda and DFID should work together to consider how best to provide relevant levels of support to programme staff to ensure effective coordination and develop and agree time bound plan (by December 2015).
- Milestones and indicators should be revised to reflect all agreed programme design changes (September2015).
- To maintain and strengthen Government buy-in, particularly at local levels, an engagement strategy and plan for Local Authorities should be developed by CARE and project partners. This should be aligned with both existing plans for introducing programme implementation at local levels and with the annual cycle of imihigo planning, by end of the DFID reporting cycle period (September 2015).

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-204142/documents/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-204142/documents/

Rates of GBV are high in Rwanda. It is estimated that nearly half of all women aged 15-49 (48%) have suffered physical or sexual violence.[1] Intimate partner violence, especially physical violence, is the most pervasive form of violence, but rates of sexual violence are also high - more than one third of survivors of sexual violence first experienced sexual violence as teenagers aged 15-19 and 14% were aged between 10-14 years old.[2] Children are no strangers to violence in Rwanda. One representative national survey indicates that nearly two thirds of male respondents and over 50% of women reported being victims of physical violence as children.[3] In addition, 44% of male respondents and 40% female respondents confirmed that they had witnessed acts of violence between their parents.
[1] Republic of Rwanda (2010) Rwanda: DHS 2010. National Institute of Statistics of Rwanda and Ministry of Finance and Economic Planning.
[2] Republic of Rwanda (2010) DHS
[3] Sleigh H and A Kimonyo (2010) “Masculinity and Gender Based Violence in Rwanda. Experiences and Perceptions of Men and Women” Images research, commissioned by Rwanda MenEngage Network
The UK is providing up to £4.6m over 4 years (2014-2018) to strengthen capacity at community level to prevent violence against women and children in Rwanda. £3.99 million has been allocated to CARE International to further develop and roll out its community-level programming on Gender-Based Violence (GBV) prevention to seven districts, working with two partner Rwandan civil society organisations (CSOs). £400,000 has been allocated to United National Children’s Fund (UNICEF) to support the development and roll out of a new community-level child protection system in Rwanda, a key programme in the Government of Rwanda (GoR)’s new Family Promotion policy (2014). A separate research and evaluation component will be implemented alongside the programme, which will be funded by DFID’s ‘What Works to Prevent Violence Against Women and Girls (VAWG)’ facility. The majority of DFID funds (£3.99m) will be allocated to CARE International, which has a proven community-level platform for engagement (Village Savings and Loans Associations) and the technical expertise and institutional capacity to further develop and scale up programming on GBV prevention.
After an initial period of lesson-learning to further develop and document the community-level GBV prevention package, the bulk of the funding will support the implementation of this package across seven districts in Rwanda. CARE International will work with two Rwandan CSOs (Rwandan Men’s Resource Centre (RWAMREC) and Rwanda Women’s Network (RWN) to coordinate and deliver the community-level interventions. Outputs include:
- Best practice community-based GBV prevention package developed and implemented in 7 districts.
- Community members have the knowledge, skills, motivation and support to promote gender equality and challenge GBV:
- Partnerships and systems to prevent VAWG and Violence Against Children (VAC) at community level strengthened.
- Improved evidence base on GBV and programming to prevent GBV in Rwanda.
In addition, DFID is providing £400,000 to UNICEF to support the development and roll out of a new community-level child protection system in Rwanda, a key programme in the GoR’s new Family Promotion policy (2014). This will include the development and roll-out of a complementary approved national child protection curriculum targeting new and existing community workers and volunteers.
This project will help to deliver DFID Rwanda’s (DFIDR) refreshed Operational Plan 2011-2015, which commits DFIDR to intensify its support for women and girls, including doing more to address VAWG. The project will complement other DFIDR interventions which are delivering change for women and girls: such as work on land tenure regularisation, which has brought land titles to women and men (key for protecting assets from male relatives and for accessing credit) and our support of the flagship social protection programme, Vision 2020 Umurenge Programme (VUP), which has improved access to cash and employment opportunities for women, bringing economic assets direct to women. It will also complement DFIDR work to get girls through secondary school and the 12+ programme which provides training and information on violence avoidance and sexual and reproductive health and rights to 10-12 year old girls.
## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment
Progress during the inception period has been good overall. There have been some delays but at the time of this AR all milestones have either been delivered or are on-track to be delivered before the end of the DFID reporting cycle period in September.

This has been a complex and challenging inception period, which has required flexibility by all partners. An adaptive programme of this nature has required that DFID lead much of the process, bringing together different components and combining implementation with research and evaluation within the design. In consequence, there have been ‘many moving parts’ and different lines of accountability and reporting, with funding for the different components coming from both DFIDR and DFID HQ. Melding these into a coherent programme has taken a lot of staff resource to ensure a high quality design.

At this stage there is a high degree of confidence amongst partners, including the government that the agreed intervention model and its sister research/evaluation component are fit for purpose, and that stakeholders and a much wider international audience will learn a significant amount about how to deliver effective and sustainable social norms change programmes to address VAWG, specifically intimate partner violence (IPV). It is important to note that the redesign has had implications for the reach of the programme and the number of direct beneficiaries. This is off-set however by the quality of interventions planned, and the opportunity for learning that will inform potential scale up. Uniquely the programme is the only Rwandan GBV project directly targeting prevention, while also aiming to generate high quality evidence of what works, how and why. Beyond the immediate potential this provides for programme scale up, the findings will offer others working on these issues in the region and globally the evidence they need to adapt and hence maximise the impact of similar interventions.

Overall output score and description
Overall the output score is A (A, B, A, A score profile across outputs). For an inception phase review it is clear that it is not possible to report against outcomes, but the design and preparations for the programme are sufficiently robust to give the reviewers a high degree of confidence in delivery. A limited number of milestones are off-track in respect to the timeframes agreed for the inception period, but plans are in place to address these. In the context of the priority to design a high quality intervention owned by all stakeholders, a number of logframe indicators and milestones are clearly not time bound priorities for an inception year and as a consequence the rationale to deprioritise these at this stage is sound.

Key lessons
A major lesson from the inception period is that an adaptive approach requires a good deal of management and leadership to ensure effective coordination. All partners commented on the challenges they faced during the inception and the compromises they have made in reaching an agreed intervention model.

A considerable amount of technical assistance has been provided both through the research partners from What Works and leveraged by CARE – either from the CARE confederation technical expertise on SGBV (particularly CARE USA) or from Raising Voices (a Ugandan NGO focussed on violence prevention). It is worth noting that the individuals from What Works are experts in the field of GBV practice and programme delivery, bringing more than research skills. They have offered an unusually high degree of support to the implementing partners.

That the research and implementation components of the programme have been funded under different budgets and are accountable through different reporting structures has at times been difficult to manage. With no single programme manager among partners, the process has required the DFID Rwanda Social Development Adviser (DESA) to lead much of the troubleshooting and coordination effort. Whilst this level of DFID engagement was anticipated during the inception phase, as the programme moves into an implementation phase, partners will need to rely more heavily on their own planning and management tools, and use them proactively.

Key actions
Individual output recommendations are recorded in the main body of this review. Here are the priorities.

- With the transition to programme implementation, changes in the way that coordination has been managed will need to be considered. Tools and processes to improve coordination will need to be effectively and proactively used, and the approach regularly reviewed. A focus on building the capacity of leading implementing partners (where required) to play greater role in day today management of partners inputs may be required. CARE UK, CARE Rwanda and DFID should work together to consider how best to provide relevant levels of support to programme staff to ensure effective coordination and develop and agree a time bound plan (by December 2015).
- Milestones and indicators will need revising to reflect all agreed programme design changes (December 2015).
- To maintain and strengthen Government buy-in, particularly at local levels, an engagement strategy and plan for Local Authorities will need to be developed. This should be aligned with both existing plans for introducing programme implementation at local levels and with the annual cycle of imihigo planning by end of the DFID reporting cycle period (September 2015) (CARE and project partners).

Has the logframe been updated since the last review?
This is the first annual review. The logframe has been updated as part of inception phase.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Best practice community-based GBV prevention package developed and implemented
Output number per LF		1	Output Score	A
Risk:		Medium	Impact weighting (%):	30%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
Evidence-based package: Community GBV prevention package improved and agreed based on evidence, lesson learning and exchange between CSOs and the GOR.	New package developed on basis of learning across Rwandan civil society + GOR + SASA! Model + global evidence base.	Milestone Achieved. A new intervention model has been designed, based on the best available evidence.
Geographical coverage = Number of sectors in which community-based GBV prevention model is being evenly and consistently implemented.	Target number of sectors to be agreed during inception period	Milestone Achieved. Agreement on the overall number of sectors has been reached (n=15)
Population coverage = Number of (i) direct and (ii) indirect beneficiaries of the GBV prevention package	Trajectory to be agreed during inception period	Milestone Achieved. Direct number of beneficiaries (n=82,455). Indirect beneficiaries (15 sectors, n= 236,250)
GOR participation = GOR participation (at appropriate level within appropriate ministry) in development, refinement and scale up of GBV prevention package	Director of Family Promotion and Child Protection actively participates in the development of GBV prevention package, while PS MIGEPROF has oversight	Milestone Achieved. Director of Family Promotion and Child Protection and the PS MIGEPROF are explicitly supportive of the programme

Key Points
- The intervention model has been significantly refined. The co-produced design now balances both programme and evaluation requirements. The model has drawn on evidence from experience in the region, global sources and technical assistance has been provided both through the research partners from What Works and leveraged by CARE – either from the CARE confederation technical expertise on SGBV (particularly CARE USA) or from Raising Voices. Confidence in the model among partners and the GoR is good. It will be tested by the evaluation.
- Coordination has proved challenging. This is to be expected in an adaptive planning approach, but has implications in terms of staff resources, and the capacity of partners, particularly in the transition to full implementation.
- The redesign has led to a reduction in the target sectors (from 70 to 15). This reflects the lack of available funding from the Access to Financing Rwanda (AFR) facility (on which CARE Rwanda had assumed an expanded VSLA platform would be based), but also the deliberate focus on quality not quantity. This has impacted on the number of beneficiaries that the interventions will reach (e.g. revising the original plan to ‘cascade’ couples training, where each person trained directly would train a further 20 individuals), noting the intervention is now arguably stronger and more likely to have impact in the wider community population.
- MIGEPROF supportive and content with the limit in beneficiary numbers to accommodate learning. Very keen on scale up, and notion of a national programme. Maintaining GoR ownership at all levels and managing expectations remains vital.

Recommendations
- The use of programme management tools (joint workplans, regular scheduled meetings) and continued improvement in communications is required to anticipate and deliver periods of intense joint work. Tools to be developed and proactively used by partners (December 2015).
- With the expected reduction in DFID staff time available (i.e. Social Development Adviser (DESA)) to support the project into implementation from June 2016, partners will need to agree how to transition to taking on greater leadership in coordination. A focus on building the capacity of leading implementing partners to play a greater role in day today management of the project and partners may be required. CARE UK and CARE Rwanda to consider how best to provide relevant levels of support (in support of the above, by December 2015).
## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Community members have the knowledge, skills, motivation and support to promote gender equality and challenge GBV
Output number per LF		2	Output Score	B
Risk:		Medium	Impact weighting (%):	40%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
Number of Journey of Transformation ‘Plus’ (JoT+) -trained couples with positive attitudes towards gender equality and against GBV	Trajectory to be agreed at the end of inception phase	Milestone off-track. Baseline data will provide source for agreeing trajectory this is due Dec 2015
No, types and frequency of interventions taken by Community Activists to promote gender equality and challenge GBV	Trajectory to be agreed at the end of inception phase, including typical types of interventions	Milestone delivered. Number of activists agreed (n=420). Types defined, 2 actions per activist per month.
Proportion of local authorities at sector level who include indicators related to GBV prevention and response in their performance contacts (imihigo)	Baseline and trajectory to be set at the end of inception phase	Milestone off-track. Baseline and trajectory due December 2015
Number of community members reporting hearing messages promoting gender equality or challenging GBV: (i) From community leaders; (ii) Via the radio or print media	Baseline and trajectory to be set at the end of inception phase	Milestone on-track. Information to be derived from the Research Protocol due for consideration at the MINEDUC ethics committee meeting in August 2015.

Key Points
- Indicators for output 2.1 do not currently reflect accurately the intervention design. Nevertheless establishing baselines and trajectories for the new design is reliant on the baseline study that will be implemented in September 2015. The results of this are not anticipated until December. This delay is consistent with the overall 3 month delay to the implementation period which will not now complete until September. To this extent the milestone is on track according to the new design and plans of partners, this accounts for the A score given above.
- Identifying the number of Local Authorities (LAs) at sector level who include GBV indicators in performance contracts (imihigo) remains an important priority, but whether this can happen in this calendar year is dependent on two issues: That in terms of the national imihigo processes and budget cycles there is opportunity to include these indicators, and that the programme must be formally introduced to sector-level LAs ahead of any effort to leverage indicators in the imihigo. CARE and implementing partners recognise the importance of this output, but also the delicate and locally appropriate ways to introduce this issue to sector-level authorities.

Recommendations
- An engagement strategy for LAs (imihigo) will need to be developed and aligned by CARE and project partners with both existing programme plans for introducing the implementation at local levels and with the annual cycle of imihigo planning by end of DFID reporting cycle period (September 2015).
- Milestones and indicators will need revising by all partners to reflect programme design changes (e.g. the JoT+ cascade model). It should also be noted that the term ‘JoT+ curriculum’ needs to be revised to reflect that the new curriculum draws on many other models than JoT. A suggested name is the ‘indashyikirwa curriculum’ to match the programme title. (September 2015).
## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Partnerships and systems to prevent VAW and VAC at community level strengthened.
Output number per LF		3	Output Score	A
Risk:		Medium	Impact weighting (%):	15%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
Development and roll-out of national community-based child protection system	Curriculum for Child Protection Workers developed based on international good practice and adapted to Rwandan context	Milestone on track. Curriculum under development. Procurement by UNICEF delayed, but training roll out due late August/September 2015.
Quality of programme delivery by Rwandan CSO partners (RWN and RWAMREC)	Due diligence checks on CARE international conducted by DFID; RWN and RWAMREC staff recruited and trained to implement agreed GBV prevention package; Programme monitoring and data collection systems developed. Annual workplan for 2015/16 in place.	Milestone on track. Due diligence and due diligence spot checks completed (Quest no. 5063887). All partners completed staff recruitment. Initial training of trainers sessions held in June. Remaining training (pre-testing) planned to be completed before end Sept. M+E systems development on track, due for finalisation before Sept 2015 - following submission of research protocols. 2015/2016 Annual Workplan drafted - to be finalised with partners by due date (Sept).
MIGEPROF coordination of implementation of national GBV-prevention programme	Programme Advisory Committee (PAC) set and up running effectively, with relevant membership agreed and engaged.	Milestone delivered. PAC established and meeting according to quarterly timetable (minutes produced and shared with partners)
Quality of information sharing and lesson learning between CSOs and with GOR on violence against women and children	Initial lesson learning workshop of CSO GBV network to discuss community-level GBV prevention approaches; Initial meeting between CSO GBV network and GOR to share information and lessons on community-level GBV prevention approaches	Milestone not delivered. CARE has brokered agreement that Profemme Twese Hamwe (a Rwanda national women’s organisation) will lead this work. Lesson learning workshop not yet planned for.

Key Points
- Good progress has been made on establishing a PAC. This is being effectively chaired by the PS of MIGEPROF with co-chair and support from DFID R. The PAC provides a useful forum for partners and has facilitated technical discussions and identified synergies between the CARE GBV prevention programme and UNICEF’s child protection work.
- Under the UNICEF programme a national facilitators team has been identified. This team has received a comprehensive briefing and will be instrumental in rolling out both the identification process for trainers as well as capacity building initiatives. The latter is scheduled to take place in the last quarter of 2015 onwards.
- Due diligence checks have not identified any issues of concern. Ongoing training of field staff for GBV interventions is due to continue in September 2015.

Recommendations
- Maintain a focus on supporting the PAC to strengthen ownership by GoR and actively use the PAC to discuss synergies between project components and to address strategy and deliver. (DFID and all partners throughout next DFID reporting year)
- To assist in maintaining good coordination and planning, the 2015 - 2016 annual workplan (drafted by CARE) will need to be shared with partners and extended to become a joint planning tool. (by the next PAC in September 2015)
- CARE will need to work with PROFEMME to ensure that they effectively plan for regular networking events on GBV (by end of first quarter 2016).
## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Improved evidence base on ‘what works’ to prevent GBV in Rwanda
Output number per LF		4	Output Score	A
Risk:		Medium	Impact weighting (%):	15%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
Independent impact evaluation for DFIDR GBV programme delivers high quality research findings	Evaluation fully designed, agreed with implementing partners and DFIDR, and has ethical approval.	Milestone on track. Evaluation component designed and agreed. Due for submission to ethics committee early August.
Evidence from impact evaluation is disseminated to relevant policy, programme and academic stakeholders in Rwanda	National-level evaluation communications strategy developed and agreed	Milestone on track – partners to develop and agree a strategy by September 2015.

Key Points
- The ‘What Works’ evaluation team began their substantial engagement on the Indashyikirwa programme in January 2015, four months after the programme inception phase started. Since then, they have worked collaboratively with the implementing partners to devise an evaluation design that is rigorous and meets the ‘What Works’ consortium standards while being practical to implement without excessive disruption to the programme. This collaborative approach has been supported by a series of visits and workshops, in January, April and May 2015 and the appointment of a full-time qualitative research specialist based in Rwanda. The resulting evaluation design is a mix of quantitative and qualitative methods, and has the endorsement of the implementing partners.
- The ethics committee that will need to approve the evaluation design is the only remaining formal hurdle before pre-testing and training can get underway. The committee meets on the 8th August. Approval is expected without revisions before the end of the reporting period. If revisions are sought the team are confident that they will be able to address these before the end of Sept. As such the milestone is on-track.
- The national level evaluation communications strategy is an important element of the overall programme and will be required to share evidence on what works, how and why with the GOR and other national stakeholders. Given the amount of work that has been redirected to support the new design of the intervention model, it is to be expected that this milestone has been de-prioritised by What Works for the current period. Partners are still aiming to agree an evaluation communications strategy by the milestone deadline of September 2015.

Recommendations
Revisions to the milestone for the national-level evaluation communications strategy will need to be made to accurately reflect the plans of What Works. Revisions should be made before the end of the DFID reporting cycle period.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
There have been no notable changes identified to the cost drivers and performance since programme approval.
- CARE component: The CARE programme budget for years 2 to 4 has been reforecast to reflect changes in the programme model and delivery (e.g. increased staffing, reduction of geographical coverage).
- UNICEF component: An 8% management fee has been added to the original budget line as this was originally omitted. This is in line with DFID guidance and below the regional averages of 16-18% as stated in the original Business Case.

VfM performance compared to the original VfM proposition in the business case
The evaluation component of the programme will provide an assessment of whether the programme offers value for money against the indicators and parameters set out in the business case. At the time of this review, the following holds:
Economy
Salary Structures and per diems are benchmarked to similar programmes in Rwanda.
In terms of the ratio of management costs to total costs, the regional bench mark of 16-18% is actually high compared to programme admin costs for the UNICEF component. The latter is currently 8% of overall programme costs.
Efficiency
It is too early to assess the unit costs against all the parameters set out in the business case. The impact evaluation will address these issues in more detail, once the baseline study has been finalised within this DFID reporting cycle period.
Effectiveness
The parameters set out in the Business Case are based on outcome measures and the impact of the programme overall in terms of reductions of GBV. It is too early in the programme to assess impact. However the parameters are in line with the logframe outputs and therefore programme results will assess VFM on effectiveness.

The cost per programme participant has gone up from the original estimate. The unit cost per participant is now approximately £48 per individual beneficiary. The Business Case suggested the costs would be a low as £17 per beneficiary, compared to a regional bench mark for similar programmes of between £58-£61. That the unit cost has gone up reflects changes in the availability of funding for the establishment of the originally intended number VSLAs (from the Access to Financing Rwanda facility), and changes to the design of both the intervention package and the research component (e.g. revising the original plan to ‘cascade’ couples training, where each person trained directly would train a further 20 individuals). Arguably, for the Indashyikirwa programme, implementation cost per cluster (i.e. the cost of implementation only, not including the inception phase) is a better unit of measurement than unit cost per participant, as this is the minimum unit of division in the programme design that will determine decisions about potential future scale up. DFID R should work with CARE and partners to identify this implementation cost per cluster

Assessment of whether the programme continues to represent value for money
The programme still represents VFM, despite higher, but still reasonable unit cost per beneficiaries. The intervention design draws significantly on the available evidence for similar approaches, and the revisions made will ensure a higher level of quality in the delivery of training, which will likely have an impact on the effectiveness of the overall approach, and the changes in attitudes and behaviours that the programme seeks to deliver. This will be tested through the evaluation component.

DFIDR is working closely with the VAWG team in London to review approaches to VFM e.g. calculations of beneficiary numbers. The current programme will draw on and ensure consistency with the work being conducted at the centre.

Quality of financial management
CARE component: This accountable grant arrangement provides payment in advance of the quarter, and the accountable grant agreement is with CARE UK, while the programme is delivered by CARE Rwanda. Our agreed narrative and financial reporting requirements are as follows: we receive financial and narrative reports for actual spend for quarter A, along with the forecast for quarter B. This is received at the end of month one of quarter B. This information is checked and approved, and a disbursement for funds for quarter B is made in month two of quarter B. This structure has been adhered to as agreed with CARE UK.

There has been an issue of underspend against forecasts for one disbursement (quarter 3). As the disbursement requested was relatively small, it was agreed with CARE that they would be able to absorb the costs in the underspent funds they held. However, it was identified that this underspend was due to financial forecasts being requested earlier than normal to work around Spring leave – the impact this had on the accuracy of forecasting has been noted to avoid a similar underspend again in the future.

UNICEF component: The MOU with UNICEF sets outs a biannual timetable of financial and narrative reporting for payment for the past six month’s activities. This schedule has been adhered to and financial and narrative reports have been of good quality.

Date of last CARE narrative financial report	16 June 2015
Date of last CARE audited annual statement	n/a
Date of last UNICEF narrative financial report	3 June 2015

E: RISK (½ page)

Overall risk rating: Medium
The overall Risk rating remains at medium.

Overview of programme risk
The programme maintains a risk register that is regularly updated by DFID (CARE Rwanda also have their own risk register that they maintain with implementing partners). The risk category F relating to capacity, as per the original Business Case, is currently the only area of risk that requires careful monitoring. Other identified risks remain as stated in the BC.

Management, coordination and communication between the various components and partners are key to the successful implementation of the programme. The programme is complex and there are many moving parts. Aligning implementation with research to ensure successful and timely delivery requires that the lead agency has the requisite programme management capacity and tools to enhance management performance in coordination and communication.

Outstanding actions from risk assessment
It will be important for DFID to work with CARE Rwanda to ensure that the relevant tools (i.e. workplans) and processes (i.e. regular meetings) are in place to ensure effective coordination and to improve communications between partners.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
There have been some delays to the inception period and it has effectively been extended. This is due to the use of an adaptive approach to planning and design. The melding together of two separate programmes (contracted by Inclusive Societies Department and DFIDR respectively) represents an innovative approach and some delays are in consequence. Any delays to this inception period are unlikely to delay the overall delivery of the intervention, but it will be essential for the partners and the lead implementing agency (CARE) to ensure there are clear time bound joint work plans in place and that these are used effectively to ensure timely delivery during the implementation period. Financial forecasts have been reprofiled to match changes in timeframes.

Performance of partnership (s)
Overall individual partners are performing as expected. Through the consultations involved in this AR it is clear that the various implementing partners are clear about their roles and responsibilities and understand the overall objectives of the programme. There are good structures in place to offer enhanced cooperation (a Programme Advisory Committee or PAC, regular monthly meetings, and a joint workplan). There is good overall cooperation between partners. As an adaptive approach to programme design has been adopted, partners are actively learning as the programme evolves.

During the inception period the DFID Social Development Adviser (DESA) has played a strong and pro-active role in establishing and managing the partnerships, as initially planned due to the ‘What Works’ evaluation team sitting externally to the programme accountability structure . Going forward DFID will need to work closely with partners to ensure that there is a smooth transition to the lead implementing partner (CARE) taking on a more direct role in coordination.

Asset monitoring and control
CARE component: There is reasonable confidence in the management of programme assets. The Due Diligence Assessment and resulting Action Plan recommended that asset registers are established by CARE Rwanda, RWN and RWAMREC and that the CARE Rwanda routinely spot checks assets in all three organisations throughout the year (an update from previous practice of annual checks only). The Due Diligence Spot Check was conducted by DFID in July 2015 and found that assets were mostly procured between November 2014 to January 2015. The CARE internal auditor has included audits of RWAMREC and RWN in his FY 2016 plan, during which he will provide assurance on the existence and safeguarding of assets. RWAMREC and RWN shared their asset registers with CARE Rwanda, and CARE Rwanda has its own asset register in place which has been shared with DFID (all are kept by the internal auditor).

UNICEF component: UNICEF is not procuring assets in this programme.  No issues were identified in the Due Diligence Assessment of UNICEF; UNICEF Rwanda was deemed to have a low level of governance and control risk. The UNICEF spot check will be conducted in October 2015.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)
This project is delivered through civil society organisations, and therefore we do not apply the partnership principles,

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
This programme has a strong M+E approach built in. This is broadly consistent with what was presented in the original Business Case, both evaluating the impact of CARE (and partners) intervention and conducting operational research. The evaluation, which has been designed in collaboration with programme implementing partners, will provide baseline, midline and endline data that is an integral part of the programme monitoring approach.

In addition, the Logframe provides a tool for all partners to monitor progress on a regular basis – this will need to be institutionalised on a quarterly basis within the programme, and it would be useful to consider including a quick status update as a regular PAC agenda item. CARE has a dedicated M+E officer contracted to work on the programme.

Monitoring progress throughout the review period
The review period has focused on inception and establishing M+E tools and procedures. In addition to dedicated workshop sessions to put the Logframe / results framework together, regular monthly meetings, and quarterly Programme Advisory Committee meetings (PAC) provide the means to regularly monitor progress.