Annual Review – Summary Sheet
Title: Health Pooled Fund (HPF) South Sudan
Programme Value: £92 million from DFID[1] / £51 million from partners[2] / Total £143 million			Review Date: / 26–30 October 2015
Programme Code: 203109	Start Date: October 2012	End Date: April 2018
[1] This includes £56 million for the first phase (Oct 2012 to Apr 2016) and £36 million for the extended phase (Apr 2016 to Mar 2018), also referred to as HPF2.
[2] This is for the first phase only. Partners are yet to confirm their commitment for HPF2.

Summary of Programme Performance
Year	2013	2014	2015
Programme Score	A	A	A
Risk Rating	Medium	High	High

Summary of progress and lessons learnt since last review
HPF performed well, making solid progress towards its main outcome of increasing access to quality health services, in particular by children, pregnant women and other vulnerable groups, in South Sudan. Although the programme overall has scored an A, as in the previous two years, there have been some notable areas of improvement, despite the continued disruption, as a result of conflict, of project activities in one target state (Unity). The situation in the remaining five project states continued with more normal project activities, despite occasional localised conflicts and the cholera outbreak of late 2014 into 2015.
HPF’s community component has moved forward, with more focus provided by the additional staff hired. The community strategy was updated. Clear central guidance is still missing but, the HPF is supporting the government’s new community strategy, the Boma Health Initiative, which should provide this guidance. Focused attention is needed to improve the local feedback and accountability mechanisms by establishing further health committees and platforms of joint dialogue (community, health facility, implementing partner (IP) and County Health Department).
HPF has increased its emphasis on leadership and governance, part of the Health Systems Strengthening (HSS) component facilitating a harmonised approach between government/IPs, and supporting a government-led health system at all levels. All counties have produced a single joint plan and review system. A state strategic plan was developed for Warrap and similar plans will be supported for the other five states in the next year. HPF continued to support the roll out of a harmonised payroll system through County Health Departments (CHDs) and IPs, implement the Human Resource Information System (HRIS), and implement the government supervision tool. A contingency plan has also been developed for a scenario where the government are unable to procure medicines.
A Performance Improvement Plan, agreed between DFID and the fund manager, had its desired effect with improvements made. The Programme Audit of December 2014, raised a number of significant issues which resulted in an action plan being agreed between DFID and the fund manager. Most issues were adequately addressed, however some recommendations were noted in the follow-up audit in 2015.
HPF continued to respond well to the humanitarian needs resulting from the armed conflict. The programme allowed flexibility for the IPs to address the needs that arose in their areas of operation and assisted the IPs to continue support health services delivery for both the indigenous populations and for internally displaced persons in camps in the affected counties.

Summary of recommendations for the next year :
- Monitor closely the final hospitals needing upgrades to provide Comprehensive Emergency Obstetric and Neonatal Care (CEmONC), to ensure milestone is met.
- Increase emphasis on quality record-keeping at the facility level to ensure more accurate reporting (including medicine stock-outs).
- Focus on establishing, re-establishing and maintaining health committees in all functional health facilities,
- Investigate ways of improving the role of the health committees beyond construction, maintenance and logistics.
- Given that the Ministry of Health (MOH) is commencing the Boma Health Initiative, HPF should engage in the design process to provide support and insight where needed.
- Support the MOH in developing a quality assurance policy and standards.
- Start discussions between HPF, the MOH and other fund managers about the sustainability of HSS tools and processes used beyond the project period.
- Use the Human Resource Information System (HRIS) data collected to analyse the current health workforce levels against health services information to help planning for distribution of health workers.
- Additional focus is needed on monitoring essential drug stocks at facilities.
- Support the MOH in implementing the Hospital Health Management Information System (HMIS).
- Respond to the audit follow-up recommendations.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-203109/documents/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-203109/documents/

Outline of the programme
The UK, along with four other donors (Australia, Canada, the European Union and Sweden) are collectively contributing an initial £107m through the Health Pooled Fund (HPF) from October 2012 to April 2016. This is to support the delivery of the Health Sector Development Plan 2012-16 (HSDP) of the Government of the Republic of South Sudan (GRSS), in six of the country’s ten States (Eastern Equatoria, Unity, Western Bahr el Ghazal, Northern Bahr el Ghazal, Lakes and Warrap) to assist the transition from a Non-Governmental Organisation (NGO) led health service to one that is led by government.
Before the start of HPF, multiple NGOs supported health service delivery through an individual health facility based model, with funding from at least five major humanitarian funds/projects. This funding came to an end in December 2012 and the HPF was designed to replace this with comprehensive support for primary health care delivery using a county based model of support. (Health services in South Sudan’s other four states are funded, separately, by USAID and World Bank, using a similar county based model). In this model, County Health Departments (CHDs) lead and manage the delivery of health services, supported by the National and State Ministries of Health (MOH).
The HPF co-finances, with GRSS, the delivery of a basic package of health services in the six states with support going to all levels of care, including primary health facilities, county and state hospitals. A central Fund Manager sub-contracts Implementing Partners (IPs) at county and hospital levels in the six states. The programme also provides TA and capacity development support to the central and state level MOH and CHDs to enable them to lead and manage the health systems and provide effective health services. HPF is a government-led programme overseen by a steering committee chaired by the MOH, co-chaired by DFID, with representation from other government ministries, the Health NGO Forum and donors. State and County Oversight Committees provide project oversight at the lower levels. The fund manager of HPF is Crown Agents, which leads a consortium of organisations with a mandate to deliver the programme including both fund management and technical support.
The project had an initial focus on sustaining essential health services in the absence of adequate government resources. Once this support was in place the focus shifted to one on health system strengthening activities including strengthening public financial management for the transfer of health worker salaries from NGO to government payrolls and also supporting work to establish structures at the community level to increase the local accountability of health services.
The impact of this programme is intended to be Government led health systems that save lives. The overall outcome will be increased access to quality health services, in particular by children, pregnant women and other vulnerable groups. The outputs this programme will deliver to achieve the outcome are:
1. Strengthened delivery of health services, particularly responsive to the needs of women and children,
2. Increased ownership, governance and demand of communities for health service,
3. Strengthened health systems at state and county levels.
The programme began in October 2012 with an inception period extending until June 2013. In December 2012, bridging contracts were issued to 16 NGOs to continue health services delivery in 281 facilities in the six states. Long term contracts, based on the County Health Model have now replaced the bridging contracts for the 39 counties in the 6 target states. Eight county hospitals, seven faith-based hospitals and six state hospitals are now being supported through a similar model. In late 2014, an NGO was contracted to provide family planning services in the six project states.
Armed conflict erupted in South Sudan in mid-December 2013 necessitating the evacuation of HPF team members and IP staff for around six weeks. Subsequently the operating environment was extremely difficult and programme interventions were disrupted. While the acute conflict situation subsequently eased in most states, except Unity, it was only in August 2015 that a peace agreement was reached. Despite the peace agreement, it is anticipated that there will continue to be intermittent, localised incidence of violence in parts of South Sudan while the possibility of the resurgence of more active conflict cannot be excluded.
The ongoing violence has had a significant effect on the fiscal position of the GRSS. Significantly reduced oil production as well as low international prices have reduced government revenue while very high levels of inflation have detrimentally affected GRSS health expenditure. High spend on security forces has also impacted negatively on service delivery budgets.
The current phase of the programme ends in April 2016, however DFID and partners (Ministry of Health and co-financing donors) have agreed to extend the programme by two years (referred to as HPF2), as was envisaged in the original business case. DFID has had Ministerial approval for an additional funding of £36 million (in addition to the £56 commited for the first three and a half years, bringing its total contribution to £92 million over five and a half years) and other donors are in a process to confirm their additional commitment.

## B: Performance and Conclusions (1-2 pages)
Annual outcome assessment
Impact Indicatorsa	Baseline (2010)	Target (March 2016)	Progress / (June 2015)
1. Under 5 mortality rate (per 1,000 live births)a	106/1,000	95/1,000	N/A
2. Maternal Mortality Ratio (per 100,000 live births) a	2,054/100,000	1,643/100,000	N/A
Outcome Indicatorsb
1. Percentage of 1-year-olds vaccinated with a third dose of DPT vaccineb	18,000 (11%)	50%	50.7%
2. Proportion of children under 5 with fever in the last 2 weeks who were taken to a health facilityc	15.3%	30%	LQAS
3. Contraceptive Prevalence Ratec	6.5%	11%	LQAS
4. % of births attended by skilled health personnelb	7,311 (2.8%)	42,870 (15%)	25,495 (8.2%)

Notes:
1. National surveys required to measure Impact Indicators. Maternal Mortality Ratio survey anticipated early 2016.
2. Source for Outcome Indicators 1 and 4 HPF Annual Report 2014–2015.
3. Source of data is the MOH Lot Quality Assurance Sampling (LQAS) Household Survey currently being analysed.
The impact indicators used in the project are national targets not specific to HPF and will be measured through future national surveys. No national surveys have taken place to update these indicators recently. The UN Maternal Mortality Estimation Inter-agency Group estimates a reduction from 1,000/100,000 in 2005 to 730/100,000 in 2013.[3] The Inter‑agency Group for Child Mortality Estimation estimates a reduction from 115/1,000 in 2010, to 93/1,000 in 2015.[4] Both show a decreasing rate for the impact indicators.
[3] Trends in Maternal Mortality 2009–2013. Source: http://www.maternalmortalitydata.org/, accessed 26 October 2015
[4] Source: http://www.childmortality.org/index.php?r=site/graph#ID=SSD_South Sudan, accessed 26 October 2015
Outcome indicators 1 and 4 reflect progress up to the end of June 2015.[5] The March 2016 target for the proportion of children fully vaccinated with DPT has already been achieved and is therefore expected to substantially exceed expectations. For the next annual review, because Pentavalent vaccine[6] started to replace DPT in July 2014, children will be reaching their third Pentavalent dose, therefore both DPT-3 and Penta-3 should be reported. The final project target for the proportion of births attended by a skilled health worker is not likely to be achieved. The LQAS survey, which will provide data for Outcome Indicators 2 and 3, is still being analysed.
[5] Progress in outcomes and outputs may not be attributable to HPF alone, because other programmes contribute to the results, e.g. drugs supplied centrally from MOH/EMF; immunisation supported by UNICEF and WHO, etc.
[6] Pentavalent vaccine includes two antigens in addition to the three in a DPT.
Overall output score and description – A
The HPF has been successful in increasing demand for health care in all six supported states, including Unity State. HPF has increased the numbers of qualified health workers, however, shortages remain. Underachievement of Outcome Indicator 4, is due to a lack of available skilled health workers in South Sudan, especially in more remote areas, limited availability of 24-hour care; and poor referral system.
Linked to service delivery, drug procurement and management will become a risk for the remainder of the project, because of the end of the Emergency Medicines Fund, with stock-outs expected to begin in early 2016.Donors have put in place a plan to address this for the next two years (e.g. significantly higher allocation to essential medicines in HPF2), however this remains a long term risk.
Work on community involvement with the health services has been carried out, focusing on establishing health committees and platforms for dialogue between CHDs/IPs, the health committees and facility staff. HPF direction has improved, with appointment of staff at the national and state levels; however, concerted efforts are needed to ensure all health facilities have the health committees and platforms for dialogue established.
There is evidence of strengthened health systems through the improvements in planning, supervision and information. Five out of six HSS intervention milestones are likely to be met.
Key lessons
- Measuring impact and outcome indicators using external sources, primarily on the HMIS, results in reliance on others for key measures of the project.
- Considerable effort has been made to expand the health services network; however, no data is available on improvements to access since an MOH health-facility mapping conducted in 2010.
- The number of health workers, either in South Sudan or in neighbouring countries, who are available and willing to work in more remote facilities is limited, reducing the possibility of all primary care facilities having the full complement of staff as required by the Basic Package of Health Services. This issue has worsened due to the depreciation of the South Sudanese Pound (SSP).
- Security was and is a significant concern, limiting activities in a number of states, most notably Unity State.
Key actions
- Review the barriers to increasing the number of births attended by skilled birth attendants.
- Map skilled birth attendants’ availability across the HPF states and develop recommendations to increase their numbers, exploring use of South Sudanese or regional health workers.
- It would be appropriate to disaggregate indicators to both include and exclude Unity State while conflict and access issues continue.
- Report DPT-3 and Penta-3 in the final year’s HPF logframe.
Has the logframe been updated since the last review? Yes
In response to recemmendations in 2014 annual review, a logframe revision was agreed with DFID in early 2015, with the addition of new indicators and revisions to some output indicators, baseline figures, milestones and targets.
## C: Detailed Output Scoring (1 page per output)

Output Title	Strengthened delivery of health services, particularly responsive to the needs of women & children
Output number per LF		1	Output Score	A
Risk:		High	Impact weighting (%):	50%
Risk revised since last annual review?		N	Impact weighting % revised since last annual review?	N

Indicator(s)	Milestones (March 2016)		Progress (June 2015)
1.1 Total no. of children <5 yrs. Out Patients Department (OPD) consultations and <5 yrs. OPD consultations disaggregated by gender and preventive/promotive	Male curative	500,000	Male curative	738,216
	Female curative	500,000	Female curative	756,020
	Preventive M&F	500,000	Preventive M&F	411,081
	TOTAL	1,800,000	TOTAL	1,905,317
			Milestone likely to be substantially exceeded by March 2016
1.2 % of children <5 yrs with diarrhoea who receive oral rehydration therapy (ORT)	90%		83% / Milestone likely to be met by March 2016
1.3 % of women who attended antenatal care at least 4 times during pregnancy	38%		30.4% / Milestone likely to be met by March 2016
1.4 No. of acceptors new to modern contraceptives	9,000		10,742 / March 2016 milestone already exceeded
1.5 No. of facilities with capacity to offer Emergency Obstetric care (disaggregated BEmONC and CEmONC)[7]	All 20 HPF-supported hospitals provide CEmONC		16 out of the 20 HPF-supported hospitals provide CEmONC[8] / Milestone likely to be met by March 2016 / (Rumbek Hospital is an exception, explained in footnote 8)
	34 of HPF 39 counties have at least 1 PHCC with BEmONC		34 of HPF 39 counties have at least 1 PHCC with BEmONC[9] / March 2016 milestone already met
1.6 % of ante-natal care (ANC) attendees who received second dose of intermittent presumptive treatment for malaria (IPT2)	50%		60% / March 2016 milestone already exceeded
[7] BEmONC/CEmONC = Basic/Comprehensive Obstetric and Neonatal Care.
[8] The indicator was not reported in the HPF Annual Report Logframe and following discussions with HPF, the current status is 16 can provide CEmONC functions, 3 more will provide by the end of 2015. Apart from these 19 hospitals, Rumbek State Hospital can perform surgery however the government has decided that a private facility nearby will focus on CEmONC. Koch PHCC was planned to provide CEmONC however has been destroyed during the conflict.
[9] Minus 1 signal function of assisted vaginal delivery using forceps delivery and or vacuum extractors.

Key points
The majority of indicators on the uptake of services have either achieved already or are likely to meet the March 2016 milestone. Service delivery indicators have seen a steady progress over the years, exceeding expectations for most of the indicators in the review year, despite restricted operating environment in most of Unity state. The results for the indicators which are likely to meet March 2016 milestone, however, have to be closely monitored to ensure they are met. For example: The proportion of children <5 yrs with diarrhoea who receive ORT can be affected by a combination of poor data records at the facility level and stock-outs. Similarly, hospitals that can provide CEmONC, can have temporary suspension of caesarean sections due to temporary situational changes (e.g. the only surgeon is off sick or away on leave). The logframe does not measure performance of hospitals separately, which should be considered in the next phase. Insecurity continued in Unity State, where health facilities were looted for medicines, supplies and equipment.
Summary of responses to issues raised in previous annual reviews (where relevant)
HPF was recommended to support the MOH in the development of a Quality Assurance Policy and Procedures for the CHD. This is unlikely to occur in the current phase, and therefore should be part of the next phase (HPF2).
Preparation of Information, Education and Communication (IEC) materials is ongoing. HPF supports the MOH revision of the broader Integrated Management of Childhood Illnesses (IMCI) guidelines. HPF will print the materials after finalisation.
Recommendations
- Quality of care remains an issue and therefore the project should support the MOH in developing a quality assurance policy and standards.
- Prepare IEC materials for health facilities, which focus on diagnosis and treatment of most common diseases (malaria, pneumonia and diarrhoea).
- Increase emphasis on data record-keeping at the facility level to ensure that indicators (such as 1.2) is more accurately reported combined with improved knowledge of stock-outs.

Output Title	Communities have increased ownership, governance and demand for health services
Output number per LF		2	Output Score	B
Risk:		Medium	Impact weighting (%):	20%
Risk revised since last annual review?		N	Impact weighting % revised since last annual review?	N

Indicators	Milestones (March 2016)	Progress (June 2015)
2.1 No. of health facilities with a health committee in place for communities to give feedback regarding health services	100% of all HPF-supported facilities have a functioning health committee	81% of facilities have a committee[10] / Milestone not likely to be achieved by March 2016
2.2 No. of documented joint meetings between the CHD/IP and the health committee and facility staff	At least 1 joint meeting held and documented per quarter in all Primary Health Care Centres (PHCCs) and in 50% of Primary Health Care Units (PHCUs) (50% of HF in county have conducted a joint meeting)	In 3 months, 33% of health facilities have held joint meetings involving IP/CHD/Health Committee/Health facility[11] / Milestone not likely to be met by March 2016
2.3 No. and % of health committee representatives who are women	At least 40% of committee members are women.	38% of health committee members are women. Milestone likely to be met by March 2016
[10] The HPF Annual Report Logframe states 64.8% and when discussed with HPF, it was stated that a mistake had been made. Figure given was 473 health committees for 585 primary health care facilities (81%)
[11] The HPF Annual Report Logframe figure used. The number of joint meetings held are reported as 1219, however it is not possible to disaggregate by quarter or health facility type.

Key points
Outputs 2.1 and 2.2 are likely to moderately not meet expectations. In several counties affected by insecurities in Warrap, Lakes and Unity States, there are very few health committees and access remains unpredictable. In Unity, several counties are controlled by opposition forces, making joint meetings impossible with the CHD.
The HPF Annual Report states that health committees help with day-to-day running of facilities, particularly in the areas of construction, maintenance and logistics.
HPF expanded the health promotion and prevention messages to include the prevention of postpartum haemorrhage, training health committees, traditional birth attendants and home health promoters.
The indicators could not easily be disaggregated by PHCC/PHCUs and so it is not possible to ascertain if all PHCCs with functional health committees also have platforms for joint communication. Furthermore, the community indicators continue to focus on quantity rather than quality of activities.
Summary of responses to issues raised in previous annual reviews (where relevant)
- The Community Strategy was updated; the project hired a Community Mobilisation Advisor and state-level Community Mobilisation Officers to provide more focus to community activities.
- The community guidelines were not finalised during the year; the government commenced a new comprehensive initiative for community activities, the Boma Health Initiative.
Recommendations
- Focus on establishing, re-establishing and maintaining health committees in all functional health facilities.
- The locations where health committees have not been formed should be mapped and time spent investigating the reasons and potential solutions.
- While recognising the difficulties in establishing community monitoring systems, the project should strengthen monitoring of the indicators, and set a target for the remaining time.
- Investigate ways of improving the role of the health committees beyond construction, maintenance and logistics, such as health facility management (including the future government health facility grant), referral systems and feedback to the CHDs/IPs.
- Given that indicators focus on quantity, the project should sample the locations where there are functioning health committees to gain an understanding of their quality, and collate feedback from the community on its perception of services and how to increase, for example, the number of pregnant mothers seeking a skilled birth attendant for deliveries.
- Given that the MOH is commencing the Boma Health Initiative, HPF should engage in the design process to provide support and insight where needed. HPF should help to share information with IPs, state- and county-level actors through the coordination platforms established.

Output Title	Strengthened health systems at State and County levels with detailed focusing on Policy, Human resources for Health, Health Financing, Health Information and Leadership and Governance
Output number per LF		3	Output Score	A+
Risk:		High	Impact weighting (%):	30%
Risk revised since last annual review?		N	Impact weighting % revised since last annual review?	N

Indicator(s)	Milestones (March 2016)	Progress (June 2015)
3.1 No. of HPF Steering Committee meetings chaired by the Government of the Republic od South Sudan (GRSS) and no. of State Oversight Committee (SOC) meetings held	(a) 14 (cumulative) HPF Steering Committee meetings chaired by GRSS / (b) At least 3 State Oversight Committee meetings held in each state except Unity	(a) 12 (cumulative) HPF Steering Committee meetings chaired by GRSS[12] / (b) At least 2 SOC meetings held in each state except Unity / Further meetings scheduled for final quarter of 2015-16 / Milestone likely to be met by March 2016
3.2 No. of facilities with quarterly integrated supervision conducted by county health department using Quantified Supervisory Checklist (QSC) tool	70% of HPF-supported health facilities	72% / March 2016 milestone met already
3.3 No. of health facilities submitting HMIS reports through the District Health Information System (DHIS) (according to the data policy flow)	80%	88% / March 2016 milestone considerably exceeded already
3. 4 Proportion of counties with one joint plan, and one review system for all government and NGO health services	Proportion of counties with 1 joint plan = 75% Proportion of counties with 1 review system =60% Proportion of counties with 1 joint plan and 1 review system = 60%	Proportion of counties with 1 joint plan = 100% Proportion of counties with 1 review system =100% Proportion of counties with 1 joint plan and 1 review system = 100% / March 2016 milestone considerably exceeded s already
3.5 No. of counties submitting South Sudan Electronic Payroll System (SSEPS) forms, disaggregated by government and implementing partner (no. of SSEPS forms completed and sent to HPF)	100% of counties apply and submit SSEPS for all IP staff. / 50 % of HPF-supported counties submit SSEPS for staff on the government payroll	100% of counties apply SSEPS for IP paid salaries / 62% of counties applied SSEPS for government paid staff / March 2016 milestone exceeded already
3.6 % of counties in which HRIS is implemented, disaggregated by (a) facility staff and (b) CHD staff	100% of counties using HRIS	100% in 5 states. Unity not included. / Milestone likely to not be met (because of Unity)
[12] 13 if the inaugural formation meeting of the Steering Committee is also counted “Steering Committee 0”.

Key points
The year has shown significant improvements on indicators 3.2–3.5 compared to 2014, attributed to a concerted effort by the project team and increased engagement of state ministries. There continue to be signs of trust between partners, increasing synergy. The state supervision fund continued and is noted as particularly useful for relationship-building between the State MOH and CHDs. The Essential Medicines Fund (EMF) is predicted to start running out towards the end of the year. The government primary healthcare Health Management Information System (HMIS) is functioning well and harmonised with the HPF mechanism; however, the hospital HMIS remains weak. Indicator 3.6, a new indicator introduced since the previous annual review, is likely not to meet expectations due to the difficulty in implementing the Human Resource Information System (HRIS) in Unity State (if Unity is excluded, the indicator has already met March 2016 milestone). The HRIS requires health facilities to be visited and staff met; access constraints and security risks remain, therefore inhibiting any large-scale travel planning.

Summary of responses to programme issues raised in previous annual reviews (where relevant)
- Guidance and support for leadership provided at all levels: county plans have been developed for all states; a state strategic plan was developed for Warrap and similar will be supported for all states in the next year; and a national annual review took place involving all states.
- MOUs have been developed between IP and state MOHs.
- HPF developed a contingency plan for a scenario where the MOH was unable to procure the medicines.
- The GRSS Bureau of Statistics has released population projections for the next 5 years.
Recommendations
- Given that the current phase of HPF is now in its final year, discussions should take place between HPF, the MOH and other fund managers about ensuring support in the extended phase (HPF2) for continued use of the tools and processes institutionalised so far.
- HPF should use the HRIS data collected to analyse the current health workforce levels against health services information to help planning for distribution of health workers. Furthermore, HPF should advocate that other states become part of the HRIS so the MOH can undertake national planning.
- Additional focus is needed on monitoring essential drug stocks at facilities, including developing efficient feedback mechanisms when stock-outs occur. Continue discussions with DFID on drug procurement mechanism possibilities for the next period and adjust the HPF contingency plan.
- Support the MOH in implementing the Hospital HMIS and therefore improving HPF’s monitoring of the 20 supported hospitals.

## D: Value for Money & Financial Performance (1 page)
Key cost drivers and performance
- The major cost driver identified in the Business Case (BC) was the number, type and location of project supported health facilities. Other cost drivers identified were salaries of health workers and pharmaceuticals. In 2014/15 the IPs procured more drugs than in previous years and hence expenditure on pharmaceuticals increased, although this cost driver has still proved less significant than originally anticipated. With the recent ending of the EMF it is to be expected that HPF pharmaceutical spend may increase in the current year.
- The more mature workstreams, County Contracts lot 1 & 2, have, as anticipated, increased their rates of expenditure (Lot 1 -72%, Lot 2 - 64%) while the more recent contracts (hospitals and family planning –(FP)) are lagging with State Hospitals (26%) and FP (13%) particularly slow.
- The financial statements from inception to June 2015 indicate that £73m (63%) of approved budget for the current phase (until April 2016) has been spent with £95m (82%) forecast to be spent by December 2015. £61.4m (84%) of a total spend was on IP contracts. The balance was mostly management fees (£9.5m, 13%) in accordance with contract. A further £1.9m (3%) was spent on the HSS initiative – less than 30% of the donor pooled fund budget allocated to this activity.
- An analysis of the IP spending indicates that, in accordance with BC expectations, the largest spending category was salaries of health workers, 38% of the total, similar to the previous year. A further 31% of IP expenditure was to support other aspects of programme delivery (drugs, rehabilitations, community participation, training etc.). Support to the IPs themselves, through “Service Provider Support” plus IP overhead fell from 39% the previous year to 31% in 2014/15. This is close to the expected 30% and is a result of the overall increase in IP expenditure on direct costs.
- There has been very high inflation during 2015. This has had a significant effect both on procurement such as the fuel but also GRSS health worker salaries. This has, to a great extent, negated the efforts to harmonise MOH and NGO health workers salaries and led to demands for NGOs to ‘dollarize’ their salary payments. However, as yet it has not had significant impact on HPF’s salary expenditure.
VfM performance compared to the original VfM proposition in the business case
The BC VfM section focusses primarily on the core area of the programme – health service delivery.
However, the BC does not disclose the full underlying DALY calculations, and the annual review could not generate DALY data for comparison, but considers that the strong progress on key indicators outlined under Output 1 demonstrate that the value expected in health service delivery is likely to have been achieved.
HPF produced a VfM strategy as required by their Terms of Reference (TOR) in 2013; however this had not been updated during the year.

DFID has initiated a process to tender for a fund manager for HPF2 to test market and drive commercial advantage and best VfM through competition.

Assessment of whether the programme continues to represent value for money
It is clear from indicator movements in Output 1 that the project, together with other initiatives, has added significant value. It is more difficult to demonstrate value in the areas of Outputs 2 and 3. Areas in which value is likely to have been added include:
- HPF IPs have provided support to CHDs which may not impact indicators immediately;
- HPF IPs have contributed to the training of health cadres and pioneering the County Model;
- There is a significant increase in services utilisation although no evidence yet of improved health outcomes;
- A government-led health service is being built – a key objective.
- The introduction of county (faith-based and government) and state hospitals has improved the integration of services at the county and state levels
- The development of one plan for each county across partners helps to reduce duplication of activities
- The ongoing HRIS & SSEPS promises to support significant VfM in the health sector as a whole, through the identification and removal of ghost workers from the payroll.
The points made in the BC still hold: in the absence of HPF six of the ten states in South Sudan with a population of approximately 5 million, would have significantly reduced health services.
Quality of financial management
By June, 2015, £61.15m had been spent from a budget of £107m budget for the current phase (October 2012 to April 2016), representing 57% after 33 months. HPF has introduced advance payments to 14 contracts during the year. Spending quickened in the last quarter, increasing from £8.3m (January to March) to £13.4m (April to June).
The Programme Audit conducted in December 2014, examined the way that grant funds had been spent, the adequacy and appropriateness of the financial controls and the governance of the programme. The audit raised a number of significant issues and an action plan to address them has been developed, agreed between DFID and Crown Agents. The Follow Up Programme Audit of October 2015 reported that Crown Agents had adequately responded to the majority of recommendations, with 14 recommendations requiring no further review. The audit follow-up review and substantive agreed-upon procedures found some recommendations which are being reviewed by Crown Agents.

Date of last narrative financial report	August 2015
Date of last audited annual statement	October 2015

E: Risk (½ page)
Overall risk rating: High
Overview of programme risk
The following table presents the programme business case risk that have changed from the previous Annual Review. Scores given in 2014 are in (parenthesis). A full list is in the previous Annual Review.
Risks	Probability / 3 high, / 1 low	Impact / 3 high, / 1 low	Comments
Budget: Decrease in projected government health budget over the next three years due to decreasing revenue, continued diversion of resources into defence and security making it difficult for GRSS to support procurement of drugs, expansion of HRH, and payment of salaries.	3	3 (2)	The 2015/16 MOH budget allocation is lower than the previous year. Despite this, funds are being focussed on service delivery with significantly increasing salaries for primary health care workers as CHDs complete the HRIS/SSEPS process. Direct, earmarked grants to CHDs are being implemented albeit with some problems. Direct earmarked grants to health facilities have been included in the 2015/16 MOH budget. No funds have been allocated for the procurement of medicines. / Very high levels of inflation have resulted in significant problems for both MOH and IP budget implementation.
Fiduciary risk inherent in the programme at both programme management and IP level and the additional fiduciary risk that may arise from non-compliance with good practice and/or guidelines issued	1 (3)	2	Annual financial audits of both the HPF and the Implementing Partners carried out. / HPF responded to recommendations of 2014 audit.
Adverse impact on operations due to inflation/ currency management issues and its impact on NGO operating costs etc. fuel.	3 (2)	2	There has been very high inflation during 2015. This has had a significant effect both on procurement such as the fuel but also GRSS health worker salaries. This has, to a great extent, negated the efforts to harmonise MOH and NGO health workers salaries and led to demands for NGOs to ‘dollarize’ their salary payments.
Fragmentation in service delivery across the country due to the three different funding mechanisms using different modes of service delivery	1 (2)	1 (2)	All three funding mechanisms take broadly the same approach albeit with some variation. The three fund managers collaborate with, for example, HPF implementing the USAID designed PPH programme in the 6 states.
Low financial, procurement and distribution capacity contributes to unreliable and interrupted supplies of commodities such as drugs that are essential for service delivery	3	3 (2)	The EMF ended in mid-2015 and an anticipated further procurement by the GRSS did not take place. Drug shortages are anticipated by the end of 2015. Partners are in discussions with GRSS to address this but, with the time required for procurement, shortages seem inevitable. HPF and IPs are aware of this and have increased allocations for the procurement of drugs to cover shortages.
Business continuity: NGOs are unable to hand over operational responsibility for clinics to the MOH at the end of the fund.	3 (2)	2 (3)	The HPF is strengthening CHDs and various health systems, including payroll. GRSS is unlikely to be in a position to take over funding of health services at the end of the project. An extended phase (HPF2) until March 2018 have already agreed by DFID and partners and is under design.
Risk of Epidemic disease outbreaks disrupting health services delivery	3	2	A significant cholera outbreak in 2014/15 disrupted services in areas it affected diverting resources and limited management capacity to its control.

The programme has developed a Risk Management Strategy (RMS) in accordance with the ToR and it incorporates a substantive section on fiduciary risk. The RMS was updated in August 2015. The programme maintains contract and programme risk matrices which are monitored and updated monthly by HPF. Any major changes are discussed with DFID and in the steering committee and necessary actions taken. For example, the steering committee decided to terminate two IP contracts in Lakes State based on contract and programme risk monitoring, when the IP failed to demonstrate improvement in their performance despite feedback. A fiduciary risk strategy depends primarily on a very thorough due diligence process on IPs, which incorporates an initial assessment reviewing technical capacity, financial standing and ethical policies; a procurement assessment; and a Financial Management Assessment (FMA) which reviews the financial arrangements of the applicant for management of HPF funds. Note that the conflict risk was particularly highlighted in the last Annual Review.
Outstanding actions from risk assessment
The most urgent issue for programme and DFID consideration are (i) the ending of the EMF and the ensuing, highly likely, drug shortages projected for late 2015, and (ii) the high level of inflation of the SSP with the resultant call for salary increases for IP staff. If this happens the difference between NGO and GRSS salaries will increase again, counteracting the effort put in by HPF and GRSS to harmonise salaries.
F: Commercial Considerations (½ page)
Delivery against planned timeframe
Despite the delay caused by the 2013-14 and ongoing security situation, the contract is largely on track against timescales detailed in the HPF contract, although a number of the health systems-strengthening activities have only started to be implemented during 2015.
Performance of partnership(s)
The project has partnerships at a number of levels:

- Funding partners (Australia, Canada, EU, Sweden and UK): the funding partners have acknowledged the results/progress so far as being significant and are currently planning an extended phase of the HPF beyond March 2016 (HPF2 until March 2018)[13].
  [13] Australia will not participate in HPF2 because of their recent aid policies. They have withdrawn from South Sudan.
- HPF and the MOH: the Project Steering Committee, chaired jointly by the MOH and DFID, has met frequently and provides a forum for project decision-making. The MOH has been involved in important decisions over contract TOR and selecting contractors through an agreed and transparent process. At state level, the State Oversight Committees have also met in all states except Unity.
- A Performance Improvement Plan was agreed between DFID and the fund manager in July 2014 to drive up performance. An assessement by DFID in May 2015 showed that the PIP had its desired effect with improvements made, and hence the PIP was closed.
- Contractual partnerships between HPF and the IPs have largely worked well, with most contracts performing adequately or well and only two contracts performing poorly. The annual review meeting between HPF/MOH/IPs raised numerous issues, where greater contact with, and leadership by, HPF would benefit IP performance.
Asset monitoring and control
Fighting continued in Unity state, where implementing partners (IPs) in Unity state reported the destruction of health facilities and the looting of medicines, supplies and equipment. Initial losses were reported promptly and HPF kept DFID regularly up to date.The value of assets destroyed or looted was valued at £206,350[14].
[14] These losses have been reported to DFID headquarters, however there is no write off in DFID accounts as this is a pooled fund and losses cannot be directly attributed to any individual donor.

HPF has updated the Procedures Manual including a section on asset management. Asset guidelines were finalised in April 2015 and circulated to all IPs. HPF has completed and is maintaining asset registers for both Juba HPF Office and assets purchased by IPs for their use.
Registration of vehicles varies from state to state. In some states it is safer to register the vehicle under GOSS or CHD to allow safe passage within communities. HPF is notified of such instances, however ownership always remains with the project and therefore DFID.
IPs have been notified of the requirement that all vehicles should be insured.

G: Conditionality (½ page)
Update on partnership principles (if relevant)
There are no specific conditionality requirements linked to this programme, which does not channel any funds directly to or through the partner government. However, overall, the Government of South Sudan has a weak and deteriorating commitment to Partnership Principles for South Sudan. At the time of reporting, the relationship between the Government and international community was strained by lack of progress in reaching consensus on transitional security arrangements, which underpin the implementation of the August 2015 Peace Agreement, as well as evidence of ongoing alarming human rights abuses. DFID will undertake a refresh of its partnership principles early in 2016.

H: Monitoring & Evaluation (½ page)
Evidence and evaluation
The Business Case Theory of Change remains valid with project inputs resulting in increased health facility utilisation. There is no evidence yet to demonstrate that this is resulting in an improvement in health status.
Increased health facility utilisation has been equally shared by boys and girls while the strengthening of maternity services has benefitted women and their babies.
The Annual Review noted a number of inconsistencies in the log frame data reported in the annual report. Greater efforts should be made in data cleansing prior to finalisation of the report.
While originally anticipated, no evaluation is currently planned. It is recommended to have a process evaluation of the current phase, possibly tied up with the next annual review. In order to align with the end of the current phase it will be useful to bring forward the next annual review to July 2016 .

Monitoring progress throughout the review period
The review was conducted primarily as a home-based desk review of documents provided by HPF, supplemented by a number of skype discussions with key stakeholders. In addition, the reviewers have used the data collected extensively for the re-design mission for HPF2 in August. It was conducted by two consultants over the period 23rd– 30th October 2015. Both were part of the HPF2 redesign mission. Two field visits were conducted during period covered by the review in Eastern Equatoria and Northern Bahr-el Ghazal involving development partners, implementing partners and MoH personnel. Full reports were written and distributed widely.