Annual Review - Summary Sheet

Title: Security and Risk Management in Hostile Environments
Programme Value: £1,570,000		Review Date: 30 June 2015
Programme Code: 203978	Start Date: 01 July 2013	End Date: 30 Sept 2018

Summary of progress and lessons learnt since last review

An Annual Review was not considered for this programme in Year 1 (Jul 2013 to Jun 2014). As anticipated, only one component of the programme (EISF) was fully operational at that point. However discussions have been convened at regular intervals between DFID and implementing partners, prior to funding and during the initial stages of activity implementation since the programme approval.

Funding will be provided to four partners over the lifetime of this programme. The following chart shows the programme funding timelines and reporting period covered by this review:

This review covers the progress of EISF and INSO for the full period of support (as DFID funding of activities to both partners under this programme has now concluded) and RedR over the first 6 months of funding. Subsequent Annual Reviews will cover DFID funded activities of RedR, ODI, and EISF if further support is provided.

Summary of recommendations for the next Annual Review

- To reconsider the Log frame and remove reference to INSO (as funding to INSO has now concluded) and to include appropriate outputs to cover the activities of RedR, EISF and the ODI.
- Consider an extension of funding to EISF of £100,000 over a two year period.

A. Introduction and Context

DevTracker Link to Business Case:	http://devtracker.DfID.gov.uk/projects/GB-1-203978/documents/
DevTracker Link to Log frame:

Outline of the programme

Humanitarian work is becoming more dangerous with an unprecedented rise in violent attacks (including kidnap) on humanitarian workers - a 177% increase from 1997 to 2008. Kidnap for ransom has become widely used by terrorist and criminal groups and, with wider security threats, there is the potential to impede the work of NGOs on development programmes and humanitarian responses. The Humanitarian Emergency Response Review (HERR), noted the ‘rising security threat’ to aid workers - and its concomitant reduction in humanitarian access and space - as one of the key challenges to be addressed in a contemporary humanitarian response (p.2). The HERR makes a concrete recommendation for DFID to invest in ‘NGO interagency security initiatives where such have proven their worth’ (p.41). And DFID accepted and undertook to implement the HERR recommendations in full.

Inter-agency coordination and collaboration around security and risk management have focused on establishing field level safety platforms – referred to as NGO Safety Offices – which offer safety information, analysis and support to a local network of subscribing NGOs. These platforms have generally proven to be an effective means of improving humanitarian access – and to have a positive impact on the lives of the vulnerable communities accessed. This project will support NGO Safety and Security in three ways:

(i). Improved NGO security management and awareness: The European Interagency Security Forum (EISF) is an independent network of security focal points representing European based humanitarian NGOs operating internationally to encourage stronger security management in humanitarian operations. EISF help NGOs working in hostile environments better to assess risks and strengthen their security arrangements, giving NGOs and their staff more confidence to continue working in such environments. DFID provided £150,000 to EISF over 24 months to support EISF with the capacity to better facilitate NGO dialogue and training focusing on reducing the level of risk to NGOs operating in hostile environments. EISF committed to deliver a NGO membership conference and training events in support of this aim.

(ii). Building global capacity in humanitarian safety: The International NGO Safety Organisation (INSO) has a mandate to establish and operate NGO Safety Offices (NSOs). They have developed an NSO model that engages NGO support and provides a robust operational system in conflict or hostile environments. DFID support provided INSO with the core resources to support and scale up its portfolio of five NGO safety platforms and adding the capacity to establish and operate an additional two platforms a year and respond to further NGO requests. This was intended to ensure that INSO retains programme quality, efficacy and effective oversight, and is able to expand its operational model to support NGO activities in high priority locations. DFID funding of £594,000 over a 12 month period was also intended to allow INSO to develop a sustainable funding strategy based on an expanded donor base and increased country programme revenues.

(iii) Accessible and effective training: A NGO-led partnership between RedR and Digital Training Solutions (DTS) has developed an innovative approach to humanitarian security training using interactive gaming software to challenge learners through immersive learning that will improve knowledge retention. It will be designed to complement existing face-to-face training and maintain the benefits of e-learning approaches in terms of reach and reduced cost per user. It will help teach key skills, such as awareness of personal security, preparedness and planning, security management, personal risk assessments, and travel security. DFID co-funding support (with US OFDA on a 50/50 basis) of £260,000 will support the design and build phase of the training programme (12 months) with basic operation and maintenance support for a further three years. During this time RedR will develop a price banding structure for users to ensure the financial sustainability of the training programme.

Recognition of the risk faced by Humanitarian workers: As another UK measure recognising the risks faced by humanitarian workers we will contribute £61,000 to ODI towards the Annual Humanitarian Aid Worker Memorial and have included this in the EISF/INSO business case.
## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment

EISF now has 70 European NGOs as active members, continuing to raise security awareness and mitigate security risks across the international humanitarian sector.

INSO have established three fully functioning security offices in the Central African Republic (CAR), Iraq and Syria (from the Southern Turkey base). All three countries are DFID priority countries. INSO is now established across two security critical regions, the Levant and West Africa and is being directly funded by DFID country/desk offices.

RedR now has the Mission Ready training platform prepared for triall in September 2015 and are on course to roll this out as per the agreed timeframe. The impact of this will be considered in subsequent Annual Reviews.

Overall output score and description: A

All components of this programme are delivering the planned activities.

Key lessons

EISF should expand its donor-base and work to get other EU donors on board.

RedR is now better prepared to deal with the complexities of working in partnership with commercial contractors.

Key actions

DFID to fund EISF for years 2015 to 2017 (2 years) up to the sum of £100,000 to ensure improved NGO security management and awareness at a time of increased risks for NGOs operating in complex security environments.

DFID can play a leading role in supporting EISF by advocating on NGO safety and security within the World Humanitarain Summit.

DFID/CHASE to consider further funding of INSO in countries where there is no DFID Office, on a case by case basis.

CHASE OT Security Adviser to remain on the RedR Mission Ready Steering Committee.

Has the logframe been updated since the last review?

No changes have been applied to the Logical Framework since conception; the logframe will continually be reviewed and amended as appropriate.

## C: DETAILED OUTPUT SCORING

Output Title	NGO platform for good security and risk management practice established.
Output number per LF		1	Output Score	A
Risk:		Low	Impact weighting (%):	15%

Indicator(s)	Milestones	Progress
1.1 Number of NGO staff reporting better awareness of security and risk issues.	50 members of staff from 40 NGOs receive training and advice; all EISF events scored 80% for quality and relevance (within 1 year).	From the evidence provided, EISF are hitting their 80% ratification targets. 2 Regional workshops (Bangkok and Nairobi) and 3 Europe based workshops held. Bi-annual forum meetings held in Madrid and Brussels (details below).

Regional Workshops
Crisis Management from the In-Country Perspective (Thailand; Jan 2015):
- 27 participants; 4 expert facilitators
- Score: 48% of attendees rated workshop 4/4 and 52% of attendees rated the workshop 3/4.
Crisis Management from the In-Country Perspective (Nairobi; May 2015)
- 52 participants from 41 organizations; 6 expert facilitators
- Evaluation Score: 3.68/4.0 and 3.73/4.0
Europe Workshops
Security Risk Management: Culture, Architecture and Approaches (London; July 2014):
- 23 participants; 3 expert facilitators
- Score: rated Very good by 3 out of 5; fairly good by 2 out of 5.
Abduction and Kidnap Management Workshop (London; Dec 2014):
14 Participants; 1 member briefing paper produced
Humanitarian Access, Negotiation Skills (Paris; March 2015):
- 19 participants; facilitated with Conflict Dynamics
- Evaluation score: overall 3.7/5.0
Bi-annual forum meetings
Madrid; Sept 2014
- 37 member representatives present; 10 external speakers
- Overall Forum rating: 3.3/4.0
Brussels; March 2015
- 39 Member Representatives present; 9 external speakers
- Overall Forum rating: 3.5/4.0

Key points

Overall EISF have met their original targets on Workshops and Forums. Participant numbers on the biannual Forums however were down compared to previous years. Feedback indicates this was because of pressures on member organisation budgets; staff were unable to attend both Forums. EISF is exploring ways in which members can participate in the Forum electronically, for example, recording a Forum session and uploading it into the Members’ Page on the EISF website.

DFID attended the Brussels Forum in March 2015 and saw a high level of engagement from the participants. The quality of external speakers EISF attracted are some of the leaders in their field and this has allowed the NGO community to reach out from their tradition networks. The subject matter covered by external speakers are varied and highly relevant; subjects such as Humanitarian Space and Access, Working in Countries with a Hostile de facto Government, Working in Ebola Affected Countries, Approaches to Risk Management.

Recommendations

DFID to consider further support for EISF over the 2015-17 period.

Output Title	Knowledge and evidence base for humanitarian security established.
Output number per LF		2	Output Score	A
Risk:		Low	Impact weighting (%):	15%

Indicator(s)	Milestones	Progress
2.1 Knowledge and evidence base tools available and being used by NGOs (including website, original research and guides).	3 Good Practice Notes; 2 new researches (each year).	Three new publications and two publications translated into French. / Redesigned website and applications to allow downloads onto handsets.
2.2 Number of external organisations provided with professional advice and support on NGO security and humanitarian issues.	70 organisations requiring support and advice.	135 participants attended five training workshops; 711 downloads of EISF publications; 23 blogs; 1 webinar with 78 participants (75 views on youtube)

Publications issued in 2014/15
New Publication Title
- Security risk management and religion (Aug 2014)
- Communications technology and humanitarian delivery (Oct 2014)
- Opening an Office (Mar 2015)
Translation Title
- Gérer le message (Apr 2015)
- Ouvrir un nouveau bureau : Manuel à l’attention des organisations non gouvernementales (June 2015)
Webinar
Communications Technology and Humanitarian Delivery: Challenges and Opportunities for Security Risk Management:
- 78 Participants; 2 expert speakers
- 75 views on YouTube

Key points

EISF publications are seen by most of the NGO security practitioners as key reference material. EISF research papers come from ideas and requests from its membership. EISF has a full time researcher, but is able to reach out to sector experts as well as academia and industry.

EISF now has the capacity, with the help of DFID funding, to translate these publication into French and Spanish.

The use of web-based technology, such as webinars and social media has allowed EISF to reach a wider audience, especially those based outside of the UK and those working at field level.

Recommendations

EISF to explore further use of innovative technology and social media to allow for the widest audience participation.

Output Title	NGOs voice is heard in debate on humanitarian security and risk management.
Output number per LF		3	Output Score	A
Risk:		Low	Impact weighting (%):	15%

Indicator(s)	Milestones	Progress
3.1 Influence on policy level discussions and debate (including good humanitarian donorship, sector initiatives).	Contributions to policy level discussions and sector initiatives; engagement with key stakeholders.	Attended forum for improving Humanitarian Action (World Humanitarian Summit) ALNAP.
3.2 Coordination between NGO and other security-interested stakeholders (donors, research institutes, consultants).	Linkages in place.	DFID, OFDA, ECHO attended EISF forums 2014/15; SIDA conference on Humanitarian Action; 19 external sector specialists attend EISF forums; 21 events and forums attended.

Key Points

EISF has been working with InterAction on developing a guide for NGOs and Donors on good practice for producing risk plans for inclusion in proposals.

EISF has also been active in promoting security risk management in the debate for the run up to the World Humanitarian Summit. As well as being invited to join the ALNAP WHS “feed in meeting” in New York they are also using the working group on “access” to bring in a safety and security discussion.

As part of the Saving Lives Together Oversight Committee and IASC Task Team for principled humanitarian action, EISF has an opportunity to influence much of the global discussions being held within the NGO and UN community.

EISF has contact with donors and key stakeholders to influence the global debate to improve good security risk management practice in the humanitarian sector. During the reporting period the Executive Coordinator had separate discussions with the French, Swedish and Spanish Governments. EISF is in regular conversations with USAID OFDA, Swiss FDFA as well as DFID.

EISF also works closely with other organisations and consortia to ensure global language and priorities are synchronised to reinforce development of best practice including InterAction, INSSA, Humanitarian Outcomes, Insecurity Insight, SCHR Secretariat and People in Aid.

External experts at events included representatives from the NATO, Chatham House, Insecurity Insight, FRIDE, DFID, Backstage Forensics Ltd, Norwegian Centre for Humanitarian Studies and Portsmouth University and ODI.

Recommendations

EISF to support as appropriate the UK commitment to three high level priorities for the World Humanitarian Summit: Protection of Civilians, Building Resilience and Smarter Crisis Financing. The first priority, a focus on the protection of civilians and International Humanitarian Law, which includes the issues of Humanitarian access, security and security risk management, is a key factor when looking at issues around access. EISF can play a key role in advocating NGO security and risk management and should have a role in bring this to the table at the WHS.

Output Title	INSO will effectively govern their current portfolio, while initiating at least 5 new NGO safety platforms within the funding period.
Output number per LF		4	Output Score	A
Risk:		Low	Impact weighting (%):	20%

Indicator(s)	Milestones	Progress
4.1 Number of staff positions recruited and operational (including ERO)	7 staff recruited (plus ERO)	All 7 position filled including Executive Director; Chief Financial Officer; Info, Comms & Marketing Officer; Admin Assistant; Regional Director Africa.
4.2 Number of NSOs that become operational as result of improved core capacity	5 new NSO in place and operating.	3 new country programmes up and fully functional

Staff positions:
- Chief Financial Officer: renamed as Chief Administrative Officer (CAO) to reflect wider role in HR & Logistics compliance. In the next phase, this post will be upgraded to Director of Finance while HR and Logistic functions will be placed elsewhere.
- Chief Operational Officer: filled & operational up to Dec 2014 when the post was terminated. The functions were then disaggregated back to either the country levels or Section Directors.
- Regional Director Middle East/South Asia: filled and operational since May 2014 but with the title “Mobile Director” to provide flexibility. The mobile director was variably assigned to CAR, Syria & other support roles. In the next project phase, this position will be renamed ‘Section Director’. Each Section Director will oversee up to four country offices.

New country programmes
Within this funding year, INSO established three new NGO safety platforms in Syria (based in Southern Turkey), Central African Republic (CAR) and Iraq:

INSO Syria: this platform started under the Emergency Response Officer (ERO) in April 2014 covering Northern Governorates only Demonstrating a significant value over this period, by September INSO were awarded both ECHO (€450,000) and separate DFID (£954,442) funding to scale up the operation to a full INSO platform. To date INSO Syria has more than 60 organisational members and operates a regional response with 41 members in Turkey, 11 in Jordan, 6 in Iraq and an additional 6 in Lebanon. This approach has been particularly appreciated with INSO Safety Advisors and Director routinely conducting briefings and meetings in Amman & Beirut as well as the INSO Iraq team in Erbil. INSO Syria operates from a main office in Gaziantep, Turkey. INSO are one of the few who succeeded in legally registering in Turkey. INSO has four international and nine national staff based there and a further 41 staff based across all governorates of Syria.
INSO Central African Republic (CAR): established under this project in April/May 2014, the CAR mission presented very differently to Syria in so far as the start-up period required careful and time intensive coordination with the existing safety coordination mechanism which NGOs had found ineffective and wanted to dissolve. The time invested resulted in early commitments from both NGO and donors with full community support backing INSO in August 2014. The project remained funded by ERO over the lifetime of this project, with an additional €300,000 co-funding from ECHO. Just outside the project period (signed in April 2015) INSO CAR was awarded USAID/OFDA funds of $1.2 million to continue the project throughout 2015/16. INSO operates from one main office in Bangui and a field office in Bossanga with another field office planned in Bambari in 2015. There are 4 international and 21 national staff, although recruitment of qualified nationals is proving a challenge as are local logistics and administration.
INSO Iraq: the platform started in mid-September 2015 co-funded by this project and a separate short-term DFID grant (£290,344 for 6 months) issued by DFID Iraq. While initially conceived through a Syria (cross border) lens and thus focused on Erbil and the Northern provinces only, presently INSO has received commitments from ECHO (£360,000) and DFID Iraq (£500,000) for expansion of the platform to cover the country with a new office in Baghdad and staff in most provinces. INSO Iraq now serves upwards of 60 NGO members contributing to the network

Key Points

Staff: the staff scale up has been successful in achieving the primary objective of enabling INSO to effectively govern the existing portfolio and establish new platforms but failed to adequately anticipate the additional capacity that would be required as a result of this expansion itself. INSO underestimated the time and cost of Emergency Response Operations and their readiness for Regional posts. These challenges will be addressed in the second phase of the INSO Strategy, which will aim to introduce more capacity in Human Resources, Finance, IT/GIS and Programme/Operation support, as well as increase capacity of the ERO to sustain longer deployments.

New Country Platforms:
Feedback from DFID Iraq was positive stating that INSO were able to set up in Erbil at an early stage of the crisis of 2014. The CHASE funding allowed INSO to establish an office and start its services to the NGO community. INSO had six months secure funding from CHASE, which allowed them time to reach out to the wider donor community. This included DFID Iraq who are now funding INSO £500,000 for 2015/16. DFID Iraq has reported that INSO’s work has made a major contribution to NGOs’ ability to assess locations and get real time incident reports.

Syria (Southern Turkey) INSO used the CHASE funding to establish its cross border activities. Because of the lengthy NGO registration process for Turkey, INSO was not eligible for donor country funding. CHASE supported the start-up and once INSO were registered they had further funding from DFID Syria and ECHO. Feedback from the DFID team in Turkey is that the INSO information network in Syria is a key information source for NGOs as their own ability to assess areas inside Syria diminishes.

CAR was the third new country INSO set up in using CHASE funds. They have since secured funding form OFDA and ECHO. As there is no DFID office in-country, INSO did not submit a proposal to DFID.

The three countries INSO identified to work in were amongst the most complex emergencies of the last two years.

Recommendations

INSO to continue to link in with DFID country offices.

DFID may wish to consider further funding in countries where there is no DFID office on a case by case basis.

Output Title	To establish and maintain an Emergency Response Officer (ERO) who can deploy rapidly prior to the formation of a new platform, and provide emergency coordination services to NGOs.
Output number per LF		5	Output Score	B
Risk:		Low	Impact weighting (%):	10%

Indicator(s)	Milestones	Progress
5.5 Number of emergencies receiving quality, relevant and timely services from ERO	5 (by end of project)	3 new country programmes up and fully functional under the this grant

Key Points

The target of five was not met. INSO responded to three humanitarian emergencies - Syria, Iraq and Central African Republic.

Overall, the ERO concept has been able to respond to the major crisis that occurred during this reporting period. While INSO set themselves up to respond to five major crises, this turned out to be overly ambitious. The programmes the ERO delivered were very complex and required major resources both in human resources and financial inputs. The need for NGO registration was particularly time consuming for Turkey and Iraq, especially for the ERO director; however DFID was able to support their applications.

INSO have stated that the first year of the ERO was a steep learning curve and it is hoped that future responses will take into consideration the resource required for new start-ups.

Recommendations

On hindsight, this output should have been an indicator for the above output (4) as it covers the same activities.

Output Title	An innovative, online security training system is available to the humanitarian sector through interactive film-based scenarios, based on a series of high quality learning programmes, including documentaries, expert interviews and written content.
Output number per LF		6	Output Score	A+
Risk:		Medium	Impact weighting (%):	25%

Indicator(s)	Milestones	Progress
6.1 Number of scenarios and learning tools made available to the humanitarian sector.	6 scenarios and 100% of learning tools (by Oct 2015)	Six scenarios have been filmed and are in the process of final editing. Trialling will begin mid Sept 2015.
6.2 Number of active users of Mission Ready.	500 (by Oct 15)	With rollout for initial feedback due Sept 15 and the official rollout expected mid Oct 15, it is expected that an initial 30 NGOs will take up the mission ready training and the target of 500 users will be met.
6.3 Participant feedback on quality, relevance and usefulness of online scenarios.	Average user score from 500 users is higher than 4/5 (by end Oct 15)	The feedback for initial users in still on target.

Key Points

For the reporting period October 2014 to July 2015, RedR and DTS made good progress towards achieving the planned project outputs.

A Steering Committee of 13 humanitarian security experts has been established and helped shape the training and target audience. Members represent a number of security positions within leading INGOs, including; Oxfam, War Child, Save the Children and EISF and also included representation form DFID (CHASE OT Security Adviser) and ECHO.

The documentary script, including interview questions were written by RedR, and 13 members of the steering committee based in the UK, US and Kenya agreed to be filmed with more filming undertaken at the EISF conference in Brussels held in March 2015. The filming has now been completed and final editing in underway. Once ready initial trailing will take place with the steering committee taking the first run through. Once the trial is complete Mission Ready will be launched at the British Council in Nairobi.

REDR has come back to DFID and USAID/OFDA for a few budget line amendments. This has been because of the complexity of developing a new style of training and getting it to work with gaming technology. Also working with a commercial contractor, DTS, has been a steep learning curve such as dealing with Intellectual property rights. After some initial delays and the need to re-align some of the budget, the project is now back on schedule and ready to launch on time.

With DFID involved with the development of this project with its seat on the steering committee, this has allowed us to keep a close track of the project development and to support RedR to overcome issues as they arise. During the whole process DFID has kept in contact with USAID/OFDA to make sure we are both working together to help this project come to life.

Recommendations

It is recommended that we continue with the next tranche of funding for Mission Ready. Most of the initial technical hurdles have been overcome and the next phase will be the rollout and testing of the platform.

DFID to remain on the steering committee and to be part of the initial trial of the training product. This can be circulated around the Humanitarian Cadre for testing and for feedback.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

DFID’s funding to EISF and INSO has supplement both organisations core costs and allowed them scope to develop their operations. The key cost driver for INSO was to meet salary costs. These were set at a competitive market rate to ensure experienced and high calibre candidates were recruited and retained. For RedR/DTS specified numbers of days of staff inputs into the programme design and management have been identified. There will also be some additional costs for the purchase of equipment.

For RedR value for money is being achieved through economy and efficiency to deliver effective solutions. Although it won’t replace the need for some face-to-face training, the online interactive training programme will cost as little as £30 per user and be accessible for a year, whereas face-to-face training can cost £450 for a participant to attend one-off course. The programme will also be able to reach a lot more participants than would be possible using other training methods. NGOs and other clients will be able to buy bundles of licences, making it cost effective to give access to large numbers of staff. The project will also benefit from the concept development and pilot scenario work already completed by DTS, and they have utilised RedR’s training expertise and content to develop the training programme and supporting materials.

More widely, VFM can be measured in a number of ways, for example, the ability of NGOs and their staff to prepare and respond to security threats; NGOs being better able to operate in hostile environments and provide vital support to vulnerable populations. The training programme will help to reduce aid worker vulnerability.

Assessment of whether the programme continues to represent value for money

Overall due to the speed and quality of this programme it does represent value for money. This is a relatively small sum of money which can be used to reduce the vulnerability of aid workers through the EISF. The impact on operations of not providing this funding could be hugely costly in terms of humanitarian response and the lives of UK citizens.

DFID funding for one year has provided INSO with the resources necessary to develop a sound governance and management structure, and will also enable it to establish itself on a sustainable financial basis. INSO has developed a robust operational NSO model and has used DFID funding to recruit and deploy key staff, including an Emergency Response Officer. This will help improve INSO management of risks, governance, leadership and oversight, and ensure that standardised operational and administrative policies are further developed.

The RedR/DTS training programme in safety and security will help to lower aid workers’ vulnerability and lead to safer operations. Improved staff capacity to assess risks and prepare contingency plans should lead to more effective humanitarian programming.

Quality of financial management

DFID is working collaboratively with all partners involved in this programme to ensure all funds are disbursed using the correct formal arrangements and in compliance with the DFID SMART Rules. All financial reporting requirements have also been completed for this reporting period.

E: RISK

Overall risk rating: Low

Overview of programme risk

EISF: For EISF the risks are that their work does not make an impact on improving security (security situation worsens, the rate of kidnappings is not reduced) or helps to maintain NGOs’ presence in hostile environments. There is also a risk that other donors reduce funding, which could lead to some activities not being delivered if one of the major funders reduces or withdraws their funding. Their funding beyond the first year was contingent on the delivery of the outputs outlined above. These ouputs have now been assessed in this review and we are assured that Outputs have met the initial conditions and DFID funding for subsequent years (next two years) are approved.

INSO: NGOs continue to request and support establishment of Safety Offices.
- Access to host countries (ie local authorities do not prevent or impede INSO registration in host countries; the ERO is not denied access etc).
- INSO is able to recruit experienced and motivated staff to fill posts.
- Security conditions allow for an NSO to be set up and ERO to be deployed.
- INSO is unsuccessful in attracting funding from other partners.

INSO has produced a Risk Register, outlining the processes and arrangements that are in place to mitigate risks, including providing NGOs with clear information and guidance on how to request a NSO start-up, promotion of INSO charitable status and benefits to cautious governments and others, and establishing robust operational security practices.

RedR/DTS:
- The remaining 50% of funding from OFDA to complete the design and build phase and cover ongoing maintenance are cut. DFID will make its funding conditional on OFDA funding continuing.
- RedR/DTS unable to develop a satisfactory training product. DTS have already invested a significant amount of their own funds and efforts in research and developing the product and testing a pilot version. RedR will be able to draw on its experience of developing and managing training programmes to ensure an appropriate training package and supporting materials are in place.
- NGO interest in the courses does not meet expectations. RedR have surveyed NGOs to gauge interest, which was overwhelmingly positive.

F: COMMERCIAL CONSIDERATIONS

Not applicable; no Direct procurement through a contracted supplier.

G: CONDITIONALITY

Update on partnership principles (if relevant)

Not applicable; no specific conditions apply to this programme.

H: MONITORING & EVALUATION

Evidence and evaluation

Because of the relatively small size of this programme there are no plans for a formal evaluation. A DFID evaluation advisor was involved in assessing the original Business Plan and may provide input to subsequent Annual Reviews.

Monitoring progress throughout the review period

Regular meetings are held between DFID officials and the implementing partners to evaluate activities, identify lessons and needs, as part of the ongoing DFID support.