## Sheet1
PROJECT NAME | Family Planning Outreach Programme in Tanzania Phase II
IMPACT | Impact Indicator 1 |  | Baseline - 2010 | 2014 | 2015: PSI Feb - Dec 2015; MSI Dec 2014 to Dec 2015) | 2016 (Jan to Dec) | 2017 | 2018 | 2019 | Target over 4.5 years assessed in 2019/20
To reduce maternal mortality and improve women's lives by giving them control over their family formation | Maternal mortality ratio - National Level Number of maternal deaths per 100,000 live births | Planned | 454 |  | No survey | 556 | No survey | No survey | No survey | The next Tanzania and Demographic Health Survey will be conducted in 2020/21
Achieved
Source
Tanzania Demographic and Health Survey (TDHS) - surveys conducted in 2010 and 2015/16
| Impact Indicator 2 |  | Baseline - 2010 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | Target over 4.5 years assessed in 2019/20
| Contraceptive prevalence rate (modern methods, married women, national and disaggregated by region and age) | Planned | 27% |  | No survey | 32 | No survey | No survey | No survey | The next Tanzania and Demographic Health Survey will be conducted in 2020/21
Achieved | bar: 2015; 2017 to 2019
Source
Tanzania Demographic and Health Survey (TDHS) - surveys conducted in 2010 and 2015
OUTCOME | Outcome Indicator 1 |  | Baseline | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | Target over 4.5 years assessed in 2019/20 | Assumptions
To increase women's use of comprehensive family planning and availability of comprehensive post abortion care (CPAC) services across Tanzania | A. Couple years of protection delivered by the project [Reset targets for CYPS at end of year 1 based on service delivery breakdown and the value of the commodities] - A: gross CYPs; B: net credited CYPs | Planned | 0 (though other DFID programmes will be providing CYP in the period prior to this programme becoming operational) |  | Aa = 956,030 Ac = 956,030 Ba = 788,438 Bc = 788,438 | Aa = 1,102,565 Ac = 2,058,596 Ba = 921,198 Bc = 1,709,636 | Aa = 1,153,130 Ac = 3,211,726 Ba = 966,105 Bc = 2,675,741 | Aa = 1,162,068 Ac = 4,373,754 Ba = 974,007 Bc = 3,649,747 | Aa=561,996 Ac=3,910,262 Ba = 150,000 Bc = 3,649,747 | Ac = 4,523,754 | There are no major natural disasters, conflicts or political instability. Access and quality of other maternal health services continue to improve.
|  | Achieved |  |  | MSI: 1,168,760; PSI: 99,250 | MSI: 1,095,494 PSI: 267,137 | MSI: 1,151,127 PSI: 336,508 | MSI: 1,173,790 PSI: 336,375 | MSI: 582,854 PSI: 78,118 | MSI: 5,270,097 PSI: 117,498
Source
|  | g | Routine service delivery data
| Outcome Indicator 2 |  | Baseline | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | Target over 4.5 years assessed in 2019/20
| Proportion of clients who are new adopters of family planning [Definition: never used modern contraception] | Planned | 37% |  | 37% | 38% | 39% | 40% | 40% | 40%
|  | Achieved |  |  | MSI: 49.9% PSI: 50% | MSI: 44.4% PSI: 54% | MSI: 45% PSI: 50% | MSI: 46% PSI: 60% | MSI: 46% PSI: 60.4% | MSI: 44% PSI: 55%
Source
Routine service delivery data and exit interviews--use MST 2 questions [Number of exit interviews. MST: 850 PSI: 500 ]
INPUTS (£)22m | DFID (£) |  | Govt (£) | 2015: Other (£); 2016: Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | Target over 4.5 years assessed in 2019/20 | Assumption
FAMILY PLANNING: Private sector family planning outreach services to rural areas (particularly long-acting and permanent methods-LAPM) in consultation with Government public sector services | Number of FP services delivered by the project (long & short term methods/ dissagregated by age) a = annual result, c=cumulative result | Planned | 0 (Note that other DFID programmes will be service FP clients in the period prior to this programme) |  | Aa: 353,925 Ac: 353,925 MSI: 301,071 PSI: 26,427 | Aa: 453,163 Ac: 807,088 MSI: 287,981 PSI: 165,182 | Aa: 489,293 Ac 1,296,381 MSI: 287,981 PSI: 201,312 | Aa: 493,767 Ac: 1,790,148 MSI: 287,981 PSI: 205,786 | Aa: 493,767 Ac: 1,790,148 MSI: 287,981 PSI: 205,786 | MSI: 1,165,014 PSI: 625,132 | Supplies of FP and VCT commodities are consistent and of high quality Adequate support and cooperation from GOT health authorities. No major changes in MOH guidelines for outreach service provision. No significant economic shocks, run away inflation or exchange rate crises that lead to unexpected increases in costs.
|  | Achieved |  |  | MSI: 312,865 PSI: 29,278 | MSI: 295,036 PSI: 74,905 | MSI: 305,030 PSI: 93,082 | MSI: 325,361 PSI: 106,382 | MSI: 170,975 PSI: 28,946 | MSI: 1,417,184 PSI: 312,566
Source
Routine service delivery data & MSD/UNFPA for commodity costs
| Output Indicator 1.2 |  | Baseline | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | Target over 4.5 years assessed in 2019/20
| Proportion of clients classified as poor | Planned | 59% |  | 62% | 63% | 66% | 69% | 69% | 65%
|  | Achieved |  |  | MST: 72% PSI: 60% | MSI: 33% PSI: 62.9% | MSI: 59% PSI: 50.7% | MSI: 69% PSI: 56.7% | MSI: 26% PSI: 57% | MSI: 31% PSI: 55.5%
Source
Exit interview assessments using T2 household budget survey
| Output Indicator 1.3 |  | Baseline | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | Target over 4.5 years assessed in 2019/20
| Cost per CYP (efficiency) | Planned |  |  | MSI: £5.52 PSI: £15.36 | MSI: £4.80 PSI: £7.24 | MSI: £5.31 PSI £5.39 | MSI: £5.16 PSI: £4.94 | MSI: £5.16 PSI: £4.94 | MSI: £5.20 PSI: £6.61
|  | Achieved |  |  | MSI: £4.48 PSI: £13.17 | MSI: £4.89 PSI: | MSI: £2.91 PSI: | MSI: 3.5 PSI: | MSI: £3.5 PSI: | MSI: £2.99 PSI:
Source
|  | DFID consultant calculations, excludes support costs but includes estimated commodity value and estimated value of MoH staff input | [8 empty] | RISK RATING
IMPACT WEIGHTING (%) | Output indicator 1.4 |  | Baseline | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | Target over 4.5 years assessed in 2019/20
50% | Client satisfaction with service they received | Planned |  |  | 90% | 90% | 90% | 90% | 90% | 90%
|  | Achieved |  |  | MSI: 92% PSI: 99% | MSI: 99% PSI: 99.6% | MSI: 91% PSI: 97% | MSI: 97% PSI: 98% | MSI: 99% PSI: 99.1% | MSI: 95% PSI: 98.5
Source
|  |  | Exit interviews | [7 empty] | Low-Medium
INPUTS (£)19,140,000 | DFID (£) |  | Govt (£) | 2015: Other (£); 2016: Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | Target over 4.5 years assessed in 2019/20 | Assumptions
CPAC: Strengthened national comprehensive post abortion care (CPAC) in both public and private sector (including policy work) | MST: 2.1 a) Number of facilities (public and private clinics) equipped and supplied to deliver CPAC 2.1b 'Per cent of facility visits MST makes where CPAC equipment and supplies are monitored and recorded PSI: Number of facilities (public and private clinics) equipped and supplied to deliver CPAC a = annual result, c = cumulative result | Planned | 0 |  | Aa = 820 Ac = 820 MSI: a) 80 b) 80% PSI: 740 | Aa = 120 Ac= 200 MSI: 90% PSI: 120 | Aa = 150 Ac = 350 MSI: 95% PSI: 50 | Aa=50 Ac=400 MSI: 95% PSI: 0 | Aa = 0 Ac = 0 MSI: 95% PSI: 0 | Ac = 400 MSI: 95% PSI: 910 | No changes in government policy on comprehensive post abortion care.
|  | Achieved |  |  | MSI: (a)130 (b)0% PSI: 740 | MSI: (a) 122, Cum 252 (b)76.4% PSI: 392 | MSI: (a) 192, Cum 444 (b) 98% PSI: 464 | MSI: (a) 24 (b)97% PSI: 354 | MSI: 0 PSI: 0 | MSI: 97% PSI: 1351
Source
Routine service delivery data and PSI MAP data; MST verification at facility by outreach teams
| Output Indicator 2.2 |  | Baseline | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | Target over 4.5 years assessed in 2019/20
| Number of public and private health workers trained and certified (at least 80% of those trained) in CPAC using MVA (80% of these will be public sector providers and will include government certification) a = annual result, c = cumulative result | Planned | 0 |  | Aa = 170 Ac = 170 MSI: 160 PSI: 20 | Aa = 230 Ac = 400 MSI: 180 PSI: 50 | Aa = 230 Ac = 630 MSI: 180 PSI: 0 | Aa = 190 Ac = 8200 MSI: 140 PSI: 50 | N/A | Ac = 820 MSI: 650 PSI: 170
|  | Achieved |  |  | MSI: 182 PSI: 20 trained; 16 certified | MSI: 194 PSI: 51 | MSI: 185 PSI: 51 | MSI: 158 PSI: 0 | MSI: 0 PSI: 0 | MSI: 719 PSI: 99 trained, 73 certified
Source
Training statistics provided by NGOs
IMPACT WEIGHTING (%) | Output Indicator 2.3 |  | Baseline | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | Target over 4.5 years assessed in 2019/20
20% | Number of women accessing safe post-abortion care (through this programme of support) a = annual result, c = cumulative result | Planned | 0 |  | Aa = 4933 Ac = 4933 MST: 4670 PSI: 933 | Aa = 7886 Ac = 12,819 MST: 4620 PSI: 3,266 | Aa = 11,299 Ac = 24,118 MST: 5300 PSI: 5,999 | Aa = 11843 Ac = 35,961 MST: 3910 PSI: 7,933 | N/A | Ac = 35,961 MST: 17,830 PSI:18,131
|  | Achieved |  |  | MSI: Work not begun PSI: 725 | MSI: 4941 PSI: 2081 | MSI: 7272 PSI: 1378 | MSI: 5182 PSI: 1598 | MSI: 1357 PSI: 0 | MSI: 18,749 PSI: 5782
|  | Source | [8 empty] | RISK RATING
|  | DHIS-2; routine service delivery data | [8 empty] | Medium
INPUTS (£)860,000 | DFID (£) |  | Govt (£) | 2015: Other (£); 2016: Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | Target over 4.5 years assessed in 2019/20 | Assumption
TRAINING: GOT supported to strengthen its family planning programme, including training of public sector providers | Number of GoURT health providers trained and certified in LAPM/LARCs (with supervision) a= annual result, c = cumulative result | Planned | 0 |  | Aa = 426 Ac = 426 MSI: 300 PSI: 126 | a = 374 c = 700 MSI: 200 PSI: 174 | a = 200 c = 900 MSI: 200 PSI: 0 | a = 50 c = 950 MSI: 50 PSI: 0 | a = 50 c = 950 MSI: 50 PSI: 0 | Ac = 950 MSI: 650 PSI: 300 | GOT cooperates with reasonable health training policies.
|  | Achieved |  |  | MSI:332 PSI: 125 | MSI: 283 PSI: 175 | MSI: 20 PSI: 112 | MSI: 80 PSI: 63 | MSI: 0 PSI: 0 | MSI: 728 PSI: 300 trained and certified
Source
Training reports including cerfificates
| Output Indicator 3.2 |  | Baseline | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | Target over 4.5 years assessed in 2019/20
| Total number of women accessing FP services in public facilities (derived from aggregation of district data) | Planned | TBD |  | Baseline determined: by DHS | 3% increase on baseline | 8% increase on baseline | 12% increase on baseline | N/A | 12% increase on baseline
|  | Achieved |  |  | MSI: 823,551 PSI: 62,903 | MSI: 2,613,275 PSI: 120,708 | MSI: 3,943,477 PSI: 199,587 | MSI: 3,848,256 PSI: 192,096 | MSI: 1,435,499 PSI: 0 | MSI:
IMPACT WEIGHTING (%) |  | Source | [8 empty] | RISK RATING
10% | Output Indicator 3.3 |  | Baseline | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | Target over 4.5 years assessed in 2019/20 | Medium
INPUTS (£)1m | Average QTA score for project teams | Planned |  |  | Score above 90% | Score above 92% | Score above 93% | Score above 95% | Score above 95% | Score above 95%
INPUTS (HR) |  | Achieved |  |  | MSI : 91.5% PSI: 94% | MSI : 91% PSI: 95% | MST: 95% PSI: 95% | MST: 97% PSI: 93% | MST: 100% PSI: 95% | MST: PSI: 94%
Source
NGO QTA scores
| Output Indicator 3.4 |  | Baseline | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | Target over 4.5 years assessed in 2019/20
| All clinical incidents properly investigated and clearly communicated to all levels of Government in a timely fashion (within three days) | Planned | 0 |  |  | Yes or no | Yes or no | Yes or no | Yes or no | 100% Yes
|  | Achieved |  |  | MST: Achieved (1 clinical incident) PSI: None | MST: Achieved PSI: None | MST: Achieved PSI: None | MST: Achieved PSI: None | MST: Achieved PSI: None | MST: Achieved PSI: None
Source
OUTPUT 4 |  | NGO quarterly reports | [8 empty] | Assumptions
| Output Indicator 4.1 |  | Baseline | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | Target over 4.5 years assessed in 2019/20
YOUTH: Young people (<20) reached with family planning (likely to be short term methods) including CPAC, & GBV | Proportion of all services to clients aged under 20 through the outreach teams | Planned | 4% |  | 5% | 7% | 10% | 12% | N/A | 12% | Current trends in economic development continue.
|  | Achieved |  |  | MST: 13% PSI: 7% | MST: 11% PSI: 9% | MST: 10% PSI: 10% | MST: 13% PSI: 24% | MST: 15% PSI: N/A | MST: 16% PSI: 12%
Source
Routine service delivery statistics
| Output Indicator 4.2 |  | Baseline | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | Target over 4.5 years assessed in 2019/20
| Number of (private) programme staff specifically trained to work with or provide information, education or family planning services to adolescents (<20) (No certification here) | Planned | MST: 0 PSI: 3 |  | MST: 55 PSI: 4 | MST: 15% increase PSI: 15% increase | MST: 20% increase PSI: 20% increase | MST: 25% increase PSI: 25% increase | MST: 25% increase PSI: 25% increase | 25% increase on baseline
IMPACT WEIGHTING (%) |  | Achieved |  |  | MST: 72 PSI: 9 | MST: 0 PSI: 35 | MST:19 PSI: 0 | MST: 0 PSI: 0 | MST: 0 PSI: 0 | MST: 91 PSI: 54
10% |  | Source
NGO client records
INPUTS (£) costed with outreach and CPAC | DFID (£) |  | Govt (£) | 2015: Other (£); 2016: Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 5 | Output Indicator 5.1 |  | Baseline | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | Target over 4.5 years assessed in 2019/20 | Assumptions
GBV: Integrated RH services for women who are victims of violence (GBV) in the public or private sectors | Proportion of services to clients that include GBV care | Planned | 0 |  | 4% | 4% | 4% | 4% | N/A | 4% | Government policies remain supportive to women who are victims of violence.
|  | Achieved |  |  | MST: No data PSI: 3904 | MST: 1504 PSI: 5883 | MST: 6301 PSI: 6235 | MST: 6338 PSI: 4331 | MST: N/A PSI: N/A | MST: 17391 PSI: 20353
Source
NGO client records and DHIS-2
IMPACT WEIGHTING (%) | Output Indicator 5.2 |  | Baseline | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | Target over 4.5 years assessed in 2019/20
10% | Number of public (80%) and private providers trained with 80% of these certified in GBV care and treatment | Planned | 0 |  | MST: 50; PSI: 48 | MST: 125; PSI: 92 | MST: 125; PSI: 0 | MST:100; PSI: 0 | MST:0; PSI: 0 | MST:400; PSI: 140
|  | Achieved |  |  | MSI: 71 PSI: 54 | MSI: 122 PSI: 48 | MSI: 124 PSI: 38 | MSI: 100 PSI: 0 | MSI: 0 PSI: 0 | MSI: 417 PSI: 140
|  | Source | [8 empty] | RISK RATING
|  | NGO client records and DHIS-2 | [8 empty] | Medium
| Output Indicator 5.3 |  | Baseline | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | Target over 4.5 years assessed in 2019/20
| Proportion of GBV survivors referred for clinical and non-clinical services | Planned |  |  | 50% | 50% | 50% | 50% | N/A | 50%
|  | Achieved |  |  | MSI: No data PSI: 2,212 | MSI: 483 PSI: 2,032 | MSI: 1705 PSI: 2,003 | MSI: 1291 PSI: 1,037 | N/A | MSI: 17391 PSI: 7,284
|  | Source | [8 empty] | RISK RATING
|  | NGO client records and DHIS-2 | [8 empty] | Medium
INPUTS (£)1m | DFID (£) |  | Govt (£) | 2015: Other (£); 2016: Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
|  |  |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | Target over 4.5 years assessed in 2019/20
Programme Management | Project start-up successful. | Planned | N/A | 2014: Successful tender; two suppliers contracted for two lots; inception meetings conducted | successful project close-out
Achieved
Source
IMPACT weighting: 100% in year one |  |  | Project and procurement documentation and approvals. Meeting minutes
Value for Money Indicators
| VFM Indicator 1 - Effectiveness |  | Baseline 2013/2014 |  | Achieved 2015 | Achieved 2016 | Achieved 2017 | Achieved 2018 | Achieved 2019 | Target 2019
| 1.1 cost/DALY (not currently using) 1.2 cost/maternal death averted 1.3 cost/unwanged pregnancy averted |  | To be determined later
Source
Provider's quarterly reports
| VFM Indicator 2 - Efficiency |  | Baseline 2013/2014 |  | Achieved 2015 | Achieved 2016 | Achieved 2017 | Achieved 2018 | Achieved 2019 | Target 2019
| 2.1 Cost per CYP 2.2 Family Planning continuation rates (not currently using) 2.3 Services delivered/team/year |  | To be determined later
Source
Provider's quarterly reports
| VFM Indicator 3 - Economy |  | Baseline 2013/2014 |  | Achieved 2015 | Achieved 2016 | Achieved 2017 | Achieved 2018 | Achieved 2019 | Target 2019
| 3.1 Cost/team/year 3.2 Amortisation of capital goods |  | To be determined later
Source
Provider's quarterly reports