Project Completion Review

Title: The Queen Elizabeth Diamond Jubilee Trust: UK Contribution
Final Programme Value £ (full life): £50 million matched funding	Review Date: 27 September 2019
Programme Code: 203754	Start Date 25 November 2013	Final End Date: 30 June 2019

Summary of Programme Performance

Year	2014	2015	2016	2017	2018	2019
Programme Score	A	B	A	A	A	A
Risk Rating	Moderate	Major	Minor	Minor	Minor	Minor

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-203754/documents
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-203754/documents

A. Summary and Overview

Description of programme and what it has achieved

The Queen Elizabeth Diamond Jubilee Trust was formally established on 6 February 2012 under the chairmanship of the Rt. Honourable Sir John Major KG CH, former Prime Minister of the United Kingdom. It was set up to celebrate The Queen’s sixty year contribution as Head of the Commonwealth and leave a lasting legacy through programmes on avoidable blindness and youth leadership across the Commonwealth.

DFID provided £50 million in matched funding (November 2013 to June 2019) to support the Trust’s Avoidable Blindness Programme. International efforts are underway to eliminate the main causes of avoidable blindness worldwide, providing a unique moment to join and help progress the global Vision 2020 initiative (a joint programme of the World Health Organization and the International Agency for the Prevention of Blindness).

Through this focus, the programme supported the UK’s contribution to the commitment made by all Commonwealth Heads of Government at the Commonwealth summit (April 2018) to: ‘improve quality eye care for all, including eliminating blinding trachoma by 2020.’ Programme results also contribute towards achieving: (1) the UK’s 2017 commitment to protect 200 million people from the pain and disfigurement caused by treatable Neglected Tropical Diseases (NTDs), including preventing up to 400,000 cases of blindness caused by trachoma; (2) the London Declaration on NTDs;[1] and (3) Sustainable Development Goal 3.3.[2]
[1] The London Declaration on NTDs (January 2012) saw DFID join the World Bank, WHO, USAID, pharmaceutical companies and NGOs to commit to “a new, coordinated push to accelerate progress toward eliminating or controlling 10 NTDs by 2020.” This included committing to eliminate blinding trachoma by 2020.
[2] SDG 3.3 commits to end the epidemics of AIDS, tuberculosis, malaria and NTDs.

Overall, the programme aimed to increase the capacity and access to quality eye health care in targeted areas of the Commonwealth for trachoma, Diabetic Retinopathy (DR) and Retinopathy of Prematurity (ROP) (outcome). Specifically, through its activities the Trust aimed to (i) protect the sight of over 106,000 people and (ii) train and/or retrain over 400 eye health care professionals. The Trust has exceeded expectations by protecting the sight of over 123,605 people and has exceeded expectations in training or retraining 568 eye health care professionals.

The Trust’s Avoidable Blindness Programme comprises four initiatives:
Trachoma[3] management in Africa (£40.6m) and the Pacific (£2m). In Africa, activities were implemented by members of the International Coalition for Trachoma Control (ICTC), with Sightsavers as grant manager, working in 7 African countries to eliminate, or make significant progress towards eliminating trachoma. The Trust’s programmes in Africa provided more than 102,000 people with sight-saving surgery, distributed 26.6 million doses of antibiotics, trained over 61,000 volunteers to locate cases of trachoma, and constructed or upgraded more than 81,000 sanitation facilities. Malawi has reached its trachoma elimination goals. In the Pacific, the Trust worked with the ICTC and the Fred Hollows Foundation to support elimination in four countries; Fiji, Kiribati, Solomon Islands and Vanuatu (the Trust has also supported work in the indigenous communities of Australia but not with DFID funds).Successful mass distribution of antibiotics, reaching more than 80% of the population and 100% of districts where trachoma is endemic, was completed in Kiribati, Solomon Islands and Vanuatu. In Fiji, face-washing messaging has successfully been incorporated into the Ministry of Education school curriculum.
[3] An infectious disease that causes a roughening of the inner surface of the eyelids that can lead to pain in the eyes, breakdown of the outer surface of the eyes, and possible blindness.

Diabetic retinopathy (DR)[4]. Diabetes increases the risk of many eye health problems, with DR predicted to become the leading cause of blindness in adults as rates of diabetes reach epidemic levels globally[5]. The Trust supported a partnership between the London School of Hygiene and Tropical Medicine (£1.4m) and the Public Health Foundation of India (£2.6m) to improve prevention, detection and treatment of DR in India. The Trust also supported the London School of Hygiene and Tropical Medicine (£0.75m) to reduce DR in the Caribbean and the Fred Hollows Foundation to reduce rates of DR in Bangladesh, Pakistan and the Pacific (£1.65m). In total over 160,925 people were screened for DR and over 19,000 people with diabetes were treated. In India, eight of the States supported by the Trust have now committed to domestically funding and expanding programmes tackling diabetic retinopathy. In the Pacific, DR services are coordinated by eye health staff employed by Ministries of Health, ensuring the continuation of screening and treatment activities. In the Caribbean, the DR programmes are now integrated in national eye care plans.
[4] A complication of diabetes which left untreated can lead to irreversible blindness.
[5] As above.

Retinopathy of prematurity (ROP)[6]. The London School of Hygiene and Tropical Medicine (£1.7m) and the Public Health Foundation India (£1.7m) worked with State governments to establish sustainable and scalable services that are integrated into India’s health system. The Initiative developed national guidelines, trained neonatal nurses, introduced new patient record management systems and tested more affordable equipment and methods for identifying babies in need of treatment. Over 13,435 premature babies were screened for ROP and 394 received laser treatment to save their sight. In each of the four Trust focus States, the local government is replicating the model to provide treatment to newborns in more government health facilities. In addition, four additional States are replicating the model to provide screening and treatment.
[6] A condition affecting preterm infants whose retinal blood vessels have not developed before birth. The use of oxygen therapy in neonatal care can severely damage the retina, and lead to irreversible blindness.

Strengthening of knowledge, tools and people to improve eye health care across the Commonwealth through the Commonwealth Eye Health Consortium (CEHC), hosted by the London School of Hygiene and Tropical Medicine (£12.7m). The Consortium supports fellowships to increase eye care expertise in low income Commonwealth countries, provides a knowledge platform to tap into expertise and facilitate learning and information exchange, and supports research and the development of technology to strengthen eye care throughout the Commonwealth. The Consortium has had an impact in every single Commonwealth country. More than 200,000 children in Kenya have had their eyes screened using smartphone app Peek Vision. The app has been downloaded and used 50,000 people in 160 countries. More than 23,000 people from 188 countries have taken the Consortium’s online courses in public health care. 140 eye health professionals from 19 countries have completed training placements in centres of excellence and hospitals across India, Bangladesh, Pakistan, Canada, New Zealand, Singapore, South Africa and the UK.

In addition, the Trust has established The Queen’s Young Leaders Programme delivered in partnership with Comic Relief, the Royal Commonwealth Society and the University of Cambridge. The Programme finds and supports inspirational young people from every Commonwealth country, and awards grants to organizations in selected Commonwealth countries that can demonstrate that they are improving the lives of young people. The Queen’s Young Leaders Programme is not funded by DFID.

The Trust is in the final year of operation and will close once it has delivered its five year programmes. The Trustees have agreed a public closure date of 31 January 2020, with the Trust finally wound down by 30 June 2020.

The UK is the second largest funder of programmes combatting NTDs, and the largest funder on trachoma. DFID will continue to lead these efforts after the closure of the Trust, including through the Accelerating Sustainable Control and Elimination of NTDs programme (ASCEND, £220m 2019-22) which will operate in 25 countries delivering integrated prevention and treatment for 5 NTDs, including trachoma.

Follow up actions required following approval of this report:

All steps required to allow for financial closure will need to be taken. This will include scrutiny of the Trust’s 2019 and 2020 Annual Report and Accounts.

## B: DETAILED OUTPUT SCORING

Output Title	Effective implementation of selected elements of the SAFE (Surgery, Antibiotics, Facial Cleanliness, Environmental Improvements) strategy
Output number per LF		1	Output Score	A
Impact weighting (%)?		45%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
1.1 Percentage (%) reduction in Trachoma Trichiasis (TT) surgery backlog target / Target for specific period shown	Oct 2018 – June 2019 (and end of project status) / Expected reduction: 93% / Kenya 100% / Malawi 100% / Mozambique 100% / Nigeria (Katsina) 40% / Nigeria (expansion) 100% / Tanzania 100% / Uganda 100% / Zambia 100%	Moderately not met / 80% reduction in TT surgery backlog. / Kenya 89% / Malawi 100% / Mozambique 99% / Nigeria (Katsina) 36% / Nigeria (expansion) 73% / Tanzania 97% / Uganda 93% / Zambia 49%
1.2 Percentage (%) of endemic districts achieving >80% coverage of mass drug administration (MDA) in the year / Targets are cumulative	Expected MDA coverage: / Kenya 100% / Malawi 100% / Pacific Islands 100%	Met expectation / Kenya 100% / Malawi 100% / Pacific Islands 100%
1.3 Number of endemic districts benefitting from behaviour change communication activities to increase facial cleanliness and environmental improvement / Targets are cumulative	Kenya 12 / Malawi 17 / Uganda 17 / Tanzania 8	Met expectation / Kenya 12 / Malawi 17 / Uganda 17 / Tanzania 8

Provide supporting narrative for the score

Trachoma is a neglected tropical disease which affects the eyes. If left untreated it can lead to blindness - 1.2 million people are irreversibly blind because of the disease. Elimination of trachoma is possible through the adoption of the World Health Organization’s SAFE strategy (Surgeries, Antibiotics, Facial cleanliness and Environmental improvements).

The Trust’s Trachoma Initiative has been working with its partners towards eliminating the disease as a public health problem through supporting the SAFE strategy in seven African countries as well as in the Pacific. In Kenya and Malawi, the Trust supported all four elements of the SAFE strategy. In the other target countries in Africa the Trust supported one or more element, and worked in coordination with other donors who supported the other elements. In the Pacific, the Trust focused its support on antibiotics, facial cleanliness and environmental improvements, as data indicated low levels of people requiring surgery.

Intensive partnership and collaboration between the Trust and its partners has enabled the seven targeted countries in Africa to significantly progress towards their trachoma elimination thresholds in an efficient and coordinated approach. Malawi has achieved its elimination goals and is currently working on its elimination dossier for submission to the WHO. The other target countries are expected to achieve their elimination targets and submit their dossiers after the lifetime of the Trust.

In addition, the Trachoma Initiative has helped to strengthen country health systems and built knowledge about effective trachoma programming at a global level. For example, the Initiative:
- has helped provide the evidence of how to integrate the four aspects of the WHO SAFE programme. This led to the development of Facial Cleanliness and Environmental Improvement guides adopted and shared by the World Health Organisation (WHO);
- introduced WHO preferred practices to ensure consistent delivery of quality services to all countries;
- was the first programme to adopt the use of dummies for surgical training, which improved surgical outcomes;
- was the leading contributor to the development of approaches to reach full geographic coverage of populations, including the most marginalised;
- helped develop mobile technology to conduct surveys, improve data and track patients in need of surgery;
- developed transition guidelines and guidance on preparing elimination dossiers to help countries move from large-scale elimination programmes to integrating trachoma services into the health system.

Since the start of the Initiative in 2014, 102,405 trachoma trichiasis (in-turned lashes) surgery cases have been managed and more than 26.6 million doses of antibiotics have been distributed to 21.1 million people living in trachoma endemic areas in Africa. More than 900,000 people have been treated with antibiotics in the Pacific. The Trachoma Initiative was focused on ensuring that women within trachoma endemic communities have equal provision, access and uptake of the programme’s eye health services along with other marginalised groups. Over the life of the project 75% of cases managed were female patients. This aligns with the estimated 60% to 85% of all trichiasis cases that are expected to be women.

In the final period of operation (October 2018 – March 2019), four target countries (Malawi, Mozambique, Tanzania, Uganda) met or very nearly met their surgery targets. The three other target countries did not meet their surgery targets. As these countries get closer to elimination and few total cases remain unmanaged, it becomes increasing challenging to identify these last cases. The backlog of cases remaining is based on prevalence estimates from surveys which can have wide confidence intervals. It is therefore increasingly important to ensure that programmes are achieving complete geographic outreach coverage rather than focus solely on the backlog estimate to determine when elimination has been achieved. The initiative implemented an approach of systematic house-to-house sweeping to ensure that no cases were left unidentified.

For those countries where there is significant variation from surgery targets (Kenya, Nigeria and Zambia), further details are provided below:

Kenya
The physical geography and the often-insecure areas have meant that house to house case finding has been more challenging. Work will continue under the DFID-funded ASCEND programme. Insecurity plays a role in achieving 100% coverage, however the health teams are working on different strategies to ensure these marginalised populations have access to health services.

Nigeria
- The Trust initially supported just one State, Katsina, in its surgery work. In the beginning, this programme was hampered by poor adoption of preferred practices, lack of engagement and ownership by the state health care system and continuous insecurity in the north east states, leading to the suspension of the programme in November 2016. This resulted in outputs not meeting targets for the number of cases managed.
- These challenges ended up driving some of the more impactful improvements and learning. After focused engagement and redevelopment of action plans, the work in Katsina has become an example to other states in Nigeria on the best ways to manage the house to house case finding and the advocacy and engagement required at State level – all of which supports the quality delivery of services. Based on this progress, the Nigeria Trachoma Trichiasis Fast Track Initiative was created, helping the country to treat more people more swiftly.
- With the work in Katsina and the subsequent expansion of work, the Trust Initiative has unified all stakeholders to work as one national trachoma elimination programme. The unified approach was a key area highlighted during the meeting between the Trust’s Chief Executive, Dr Astrid Bonfield and the Nigerian Ministry of Health in April 2019.

Zambia
Country-wide, as of March 2019, there are an estimated 765 remaining surgery cases to be managed across 12 districts to reach the WHO trichiasis elimination threshold in Zambia. It is anticipated these districts will be fully and thoroughly covered with case finding, case management and post-operative follow-up by or before December 2019. Zambia is on track to achieve 100% of its target, although this will depend on the availability of incoming trachoma funding from other sources. All district-level supporting documentation to meet the requirements of the national dossier will also be compiled by this time and trichiasis management will be effectively transitioned back into routine domestic eye care services.

Anticipated mass drug administration targets (of 100% of endemic districts achieving >80% coverage) over the programme period were achieved in Malawi and in the Pacific. In Kenya, delays in the release of shipments of antibiotics delayed the planned mass drug administration, but coverage targets were still achieved. The Ateker people regularly move between Kenya, Sudan and Uganda. The Kenyan and Ugandan teams worked together to hold camps along the border to ensure treatment of nomadic populations. This ensured that all of the five counties in this particular district were subject to mass drug administrations and therefore 100% coverage was achieved.

Mass drug administrations also took place in Nigeria and Zambia.

Mass drug administration was successfully completed in Kiribati, Solomon Islands and Vanuatu. Planes and boats were required to reach the populations of these countries due to the long distances between islands and communities. The surveys and activities required to perform these distributions has built a regional network of trachoma health workers in the Pacific, with expertise that is transferrable to other neglected tropical diseases.

Facial cleanliness and environmental improvement activities have been undertaken in 54 districts in Kenya , Malawi and Uganda. 81,288 sanitation facilities have been built or improved to help reduce the prevalence of flies who can transmit the disease. Trachoma education sessions were conducted in schools to teach students the importance of washing their faces. 90 schools in Malawi have also installed new face and hand washing facilities. The Initiative has focused on working with the Water and Sanitation (WaSH) sector, including local WaSH partners, to include face washing in their educational programmes. In Uganda more than 13,000 community workers and volunteers have been trained on the importance of sanitation and hygiene to prevent trachoma.

The Trachoma Initiative worked closely with Ministries of Health and the trust’s partners in the International Coalition for Trachoma Control (ICTC) to ensure that capacity built during the programme was embedded in national health systems to help support the transition of services to the public health system so that they can continue. The Trust has also worked with Sightsavers to help manage the transition from Trust funding to new income sources supporting trachoma elimination. The Trust has encouraged an overlap between the programmes to ensure that there is no shortfall in service delivery. The Trust’s Chief Executive has held meetings with senior government officials in each target country to thank them for their work and to encourage sustained action on trachoma.

Lessons identified this year linked to this output and recommendations for future programmes

A key lesson over the course of the programme was the importance of having strong relationships with local partners and donors in order to be able to identify and address problems that have the potential to impact on the delivery of intended services.

The Trust has also taken proactive steps to ensure the sustainability of the programme, helping its partners to transition and graduate smoothly from the support they have provided and supporting integration of services with national health services.

Africa
In October 2018 the Trust and DFID jointly commissioned a joint learning exercise of both organisations’ trachoma programmes in Africa. The Trust’s Trachoma Initiative and DFID’s SAFE Programme worked with Sightsavers and the ICTC to implement the SAFE strategy, and the two programmes both worked in Nigeria, Tanzania and Zambia. Working in collaboration with Sightsavers and the ICTC, the exercise was intended to identify lessons that would assist countries working to eliminate trachoma and other neglected tropical diseases.

The report was publically released in May 2019 and presented at the World Health Organization Global Elimination of Trachoma by 2020 (GET2020) meeting in Maputo, Mozambique in June 2019. The report is housed on the ICTC website and will remain there after the Trust closes http://www.trachomacoalition.org/sites/default/files/content/resources/files/Trachoma%20Initaive%20Report_Draft%208-compressed.pdf

The report identified 10 key lessons for government and organisations working on trachoma elimination. This included lessons on the delivery of the SAFE strategy, as well as lessons on transition and sustainability once elimination goals had been achieved.

The lessons regarding delivery of the SAFE strategy focused on:
- The importance of agreeing and adopting standardised practices to conduct activities and surveys
- Developing a systematic approach to finding people with trachoma, to ensure equity in coverage
- Using tailored approaches when providing treatment to hard-to-reach populations, such as nomadic communities
- Strengthening relationships with the water and sanitation sector

The lessons regarding sustainability focused on:
- Planning for long-term integration into the health system from the outset
- Transition from a large-scale vertical trachoma programme to ongoing support from a national health system needs to happen over time and cannot only be tackled once elimination goals have been achieved

The report concluded:
“With an unprecedented scale of financial support and a unique and effective partnership model, the programmes have made significant progress towards eliminating trachoma as a public health problem where they worked. This has been made possible by a common, coherent approach to delivery, facilitated by the ICTC’s inclusive partnership model and led by health ministries at the country level. The adoption of standardised guidance and the ICTC preferred practices has been key to progress. Strengthening of health systems was perceived to be an important achievement, with key building blocks put in place to support longer-term health system integration in some contexts. Partnering added value through extending programme reach and sharing learning.”

Pacific
In June 2019 an independent evaluation was completed of the Trust’s Trachoma Initiative in the Pacific. This was shared at a regional conference attended by health officials from Pacific countries. The report concluded:
“The PTI (Pacific Trachoma Initiative) has laid the foundation for the approach to managing trachoma programs across the Pacific through informing policies and practices and capacity development which are also applicable to other NTDs (neglected tropical diseases). It will inform other countries in their approach to eliminate trachoma and has influenced global policy.”

Output Title	Increase in the number of patients with sight threatening retinopathy treated in targeted Commonwealth countries
Output number per LF		2	Output Score	A+
Impact weighting (%)?		15%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
2.1 Number of patients with diabetes screened for diabetic retinopathy annually	Expected cumulative total: 86,300 patients	Substantially exceeded expectations / 160,925 / (India 66,455) / (Bangladesh and Pakistan 30,531) / (Caribbean 21,590) / (Pacific 42,349)
2.2 Number of screened patients with diabetes treated for diabetic retinopathy annually	Expected cumulative total: 11,590 patients	Exceeded expectations / 19,191 / (India 4,020) / (Bangladesh and Pakistan 4,644) / (Caribbean 2,985) / (Pacific 7,542)
2.3 At least one example from each partner of how they have influenced national health policy with respect to integrating diabetic retinopathy models of care into the public health system	India - Government directives issued supporting DR model of care	Met expectations / Government directives issued supporting DR model of care in all ten states in India / Eight states in India have also committed to expanding activities to new districts / DR integrated into national eye care plans in Dominica, Jamaica, St Lucia, Kiribati, Solomon Islands and Vanuatu

Provide supporting narrative for the score

Through its Diabetic Retinopathy (DR) Initiative, the Trust has supported activities that tackle DR in 13 countries across the Caribbean, South Asia and the Pacific. It has supported a partnership between the London School of Hygiene and Tropical Medicine (LSHTM) and the Public Health Foundation of India to improve prevention, detection and treatment of DR in India. It also supported the LSHTM to reduce DR in the Caribbean and the Fred Hollows Foundation to reduce rates of DR in Bangladesh, Pakistan and the Pacific. Through these partnerships, over 160,000 people with diabetes have been screened for DR and 19,191 people have been treated for DR, exceeding targets established for the programme. The Trust has also helped to train 67 health professionals to screen and treat DR; and has assisted partners to embed treatment for DR into government health systems, to ensure access to screening and treatment beyond the life of the Trust’s programmes.

India
In partnership with the London School of Hygiene and Tropical Medicine and the Public Health Foundation of India, the Trust has worked with the Indian Ministry of Health to embed the screening for and treatment of DR. The Initiative in India developed high quality models of integrating control of DR-related blindness in the government health system. The Initiative has improved patients’ knowledge of diabetes and DR, trained health professionals to screen and treat the disease, provided equipment to ensure quality service, and developed national guidelines for good practice. More than 66,000 patients with diabetes have had their eyes screened and more than 4,000 patients have received treatment for sight-threatening retinopathy.

The Initiative began by conducting a situational analysis and holding a National DR Summit in 2014. A National Task Force was established by the Ministry of Health, which then helped to identify key implementation partners in ten states. All ten state governments have issued directives supporting the DR Initiative. A variety of models have been implemented depending upon the characteristics of the state health system and the varying geographical and other accessibility issues that the community faces. In addition, eight of the states have committed to domestically funding and expanding screening and treatment activities to new districts.

The Initiative has highlighted the importance of addressing retinopathy in the care and management of diabetes. Integration of retinal screening at non-communicable disease clinics has ensured that DR care is included in the general health system. Production and dissemination of educational materials to people with diabetes has helped to manage the risk of DR through better diabetes control using lifestyle changes, dietary modification and compliance with medication.

An independent evaluation of the Trust’s DR Initiative in India concluded that “Despite initial teething problems and after overcoming funding challenges, the programme has been able to entrench itself into government systems in a large set of states and facilities... A large volume of scientific evidence has been generated drawing upon programming under the grant. Despite the short period of time in which the pilots have been in operation in several states, they have been able to demonstrate real results that are convincing to state authorities. The grant leaves a lasting legacy in the form of capacity building tools, guidelines and standard operating procedures, equipment and systems that have been transferred to the administration. The national and state governments have indicated their intention to continue the work initiated under the grant and expand it in several cases.”

Bangladesh and Pakistan
The Initiative developed, implemented and evaluated an integrated model of care for diabetes-related vision loss in the divisions of Barisal and Chittagong in Bangladesh, and Lahore and Hyderabad in Pakistan. The high quality model delivered the spectrum of DR care, from routine eye exams for early identification to surgical laser treatment for advanced cases. In both countries, the Initiative helped to incorporate DR care into routine diabetes care within the existing health system.

In November 2018 the Government of Bangladesh officially endorsed a National DR Strategy and Action Plan. The endorsement provides a plan for the continued integration for diabetic retinopathy into the health system and will function as the guidelines for DR management and treatment at the country level. In Pakistan the awareness and screening at community level for diabetes and DR will continue to be delivered by the community health workers and medical officers trained through the Initiative. Partner hospitals are now utilising a new health management information system to track the flow of patients and improve the efficiency of the referral system.

Caribbean (Belize, Dominica, Jamaica, St Lucia)
Between April 2015 and February 2017 the Initiative was administered by the Caribbean Council for the Blind. From March 2017, the Initiative was administered by the International Centre for Eye Health at the London School of Hygiene and Tropical Medicine (LSHTM). Also, from March 2017, the four countries became part of the Diabetic Retinopathy Network (CR-NET) operated through the Commonwealth Eye Health Consortium at the LSHTM through which links to UK hospitals were established.

In Jamaica, St Lucia and Dominica the Governments has assumed ownership of the DR screening and treatment and is integrating it within the relevant directorates. In Belize, the programme is implemented by an NGO but the government took ownership of the capacity-building of primary and secondary health professionals in the public health system.

In Jamaica, for the first time, laser treatment is no longer centralised in the capital and each regional authority is able to provide treatment services. The Ministry of Health now has systems for maintenance and servicing of the equipment purchased with Trust funds. There has been increased coverage of services making the screening and the treatment more accessible to a larger segment of the population. In all the diabetic retinopathy Caribbean countries both the screening and treatment are delivered free of charge to the patients and governments have integrated the delivery of these services into their national health budgets.

Pacific
The Initiative supported Pacific governments to deliver universal coverage and access to specialist diabetic eye care services through delivery of training programmes, improvement of data systems and referral systems, provision of equipment, and the integration of diabetic eye care into country health systems and plans. All staff trained by the Trust’s Initiative are employed by their respective Ministries of Health. People within the Ministries have been identified as ‘DR Coordinators’ to continue stewardship of activities. All countries now have well-equipped eye clinics and appropriate infrastructure to deliver quality care.

In February 2019, an external evaluation of the Diabetic Retinopathy Initiative in the Pacific was completed. “The evaluation has concluded that the Diabetic Retinopathy programme has increased the momentum towards achieving sustainable approaches to addressing diabetic retinopathy in the target countries: Fiji, Kiribati, Samoa, Solomon Islands, Tonga and Vanuatu. Overall, the programme has had a significant impact on strengthening and expanding diabetic retinopathy services through increasing the capability and capacity of the workforce and equipping health workers to provide effective diabetic retinopathy services. The key achievement is a significant increase in awareness and knowledge about diabetic retinopathy and its relationship to diabetes which has increased the demand for diabetic retinopathy services and the expansion of the services to meet the demand.” (p.7)

Lessons identified this year linked to this output and recommendations for future programmes

India
An independent evaluation of the Initiative in India, completed in June 2019, noted several lessons that derived from the implementation of the initiative. This included the importance of working closely with state and national governments and the value of creating a national taskforce. “At the national level, the programme established National Task Forces under the chairmanship of the concerned bureaucrats and eminent scientists, incorporating key functionaries of associations and scientific luminaries. This added much to the credibility of the programme and helped build acceptance of the results of the programme among the decision makers.”

The evaluation also highlighted the need for sharing the skills and knowledge across a wide range of health staff and the importance of raising awareness of the disease: “An area of need has been increasing awareness amongst relevant professional groups and the general community. Awareness among the general practitioner community is critical to funnel patients into the program and awareness in the community is crucial to increasing the footfall of patients… It might also be added that a high footfall was needed to initially create the will among staff to do what is expected. The Diabetic Retinopathy programme helped to do this by providing value-added services at primary health care level which in the opinion of those involved, has led to increasing demand at that level.”

Caribbean
In 2019 a comprehensive evaluation of the Commonwealth Eye Health Consortium was completed, which includes the Diabetic Retinopathy Initiative in the Caribbean. In 2017 the four countries in the Caribbean became part of the Consortium’s LINKS Network, which pairs hospitals overseas with hospitals in the UK. The network facilitates reciprocal training visits and helps to build the capacity of local teams. For example, the eye health team in Dominica was paired with Brighton and Sussex Eye Hospital. This partnership model works well for the Trust’s Caribbean partners. The 2019 evaluation concluded that “…all four countries have now made remarkable progress in both training of screener graders and in achieving buy in from government. The LINKS partnerships are proving fruitful in accelerating progress.”

Pacific
The external evaluation of the Initiative in the Pacific also provided the following recommendations for continued work on diabetic retinopathy:
- Work with governments to strengthen the inclusion of diabetic retinopathy in national plans and strategies; and strengthen partnerships with non-communicable disease unit/department and diabetic services
- Focus on awareness training programmes in areas that have not been covered
- Consider developing training programmes in screening for diabetic retinopathy that are more accessible to nurses who are not specialist eye health nurses
- Increase health promotion activities with particular investment in resources and initiatives that are likely to have the most benefit.

The following lessons were identified as applicable to other integrated programmes in the Pacific and further afield:
- The Pacific is not a case of ‘one size fits all’ and activities need to be tailored to each country
- Building leadership and country ownership takes time, but is critical for sustainability
- Long term success is more likely when activities leverage off established systems and processes
- Activities need to be well-supported by robust monitoring and reporting.

Output Title	Increase in the number of infants treated for retinopathy of prematurity (ROP)
Output number per LF		3	Output Score	A+
Impact weighting (%)?		5%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
3.1 Number of infants screened for ROP in Special Newborn Care Units (SCNUs) in quality improvement programme area annually	Expected cumulative number screened: 12,420	Exceeded expectations / 13,438
3.2 Number of infants treated for ROP in Special New-born Care Units (SCNUs) in quality improvement programme area annually	Expected cumulative number treated: 250	Exceeded expectations / 394
3.3 At least two examples of how the Public Health Foundation of India (PHFI) have influenced national health policy with respect to integrating retinopathy of prematurity models of care into the public health system	Control of ROP is a specific priority in the National Programme for the Control of Blindness, with budgetary provision for screening and treatment / Joint National Neonatology Forum (NNF) and All India Ophthalmological Society (AIOS) National Guidelines for ROP formally adopted by the Ministry of Health	Met expectations / Control of ROP integrated into national Child Health Screening and Early Intervention Services programme. All four states have committed to funding and expansion of screening and treatment / ‘National Retinopathy of Prematurity Operational Guidelines’ adopted by the Ministry of Health and Family Welfare

Provide supporting narrative for the score

As noted under Output 2, the Trust has worked in partnership with the London School (LSHTM) and the Public Health Foundation of India (PHFI) to support the Initiative in India.

Pre-term infants are screened and treated in four States: Telangana, Madhya Pradesh, Odisha and Maharashtra. Persistent advocacy with state governments has helped to secure continued ownership and support of activities beyond the ending of the Trust’s support. These state governments have committed to scaling up work to 30 additional districts. Each district has a population normally in excess of one million people.

During the Initiative, the Trust’s local partner held meetings with states not receiving Trust funding to offer support and technical advice. This has already resulted in four additional states committing to implementing their own retinopathy of prematurity screening and treatment programmes (Delhi, Himachal Pradesh, Kerala and Tamil Nadu).

The Initiative developed ‘National Retinopathy of Prematurity Operational Guidelines,’ for effective implementation of screening and treatment. These guidelines have been integrated into the Child Health Screening and Early Intervention Services led by the national Ministry of Health and Family Welfare. Such national norm setting has been a vital element of the Initiative’s success.

The Initiative has improved the overall quality of neonatal care, rather than just eye care, to help improve the healthy survival rate of pre-term infants. As a result, several neonatal care units have reported increased survival rates and more efficient use of valuable resources such as oxygen and antibiotics.

The Initiative increased the capacity of neonatal teams in the Government sector to improve the care of pre-term infants and increased awareness of retinopathy of prematurity among professional groups, specifically paediatricians, obstetricians and ophthalmologists. The Initiative also developed and implemented an information and education strategy to support parents.

Operational guidelines have been developed and adopted by the Ministry of Health to enable other districts and states to replicate the programme.

The availability of ophthalmologists has been a challenge in some areas. Ophthalmologists have a number of other responsibilities – night duties, cataract targets, glaucoma surgery and administration - which makes it difficult for them to take on additional tasks. In response, the programme has trained ophthalmic assistants or nurses to take photos of the eye, which are then examined by ophthalmologists. The Trust has also highlighted the importance of sufficient capacity in ophthalmology.

Lessons identified this year linked to this output and recommendations for future programmes

An independent evaluation of the Initiatives in India (in 2019) highlighted the value of having a National Task Force to lead on the issue. The Task Force was established in April 2014 by the Ministry of Health to support development of evidence, provide funding advice for policy makers, provide guidance to strengthen screening and treatment services, and advise government on options for better integration of ROP services into the national health system. The National Task Force, which will continue to operate after the Trust’s support has concluded, has representation from the government, ophthalmologists, neonatologists, nurses, and the Trust, Federation of Obstetric and Gynaecological Societies of India, and non-government institutes working in eye health. The evaluation noted: “The National Task Force has been instrumental in turning attention towards retinopathy of prematurity as an issue. The National Task Force has succeeded in making this programme a part of the national agenda, not limited to the states in which pilots are being undertaken.”

The evaluation also noted the value of working closely with senior officials: “Involvement of the top echelons of the national and state administration has been critical to facilitating action.” This often involved multiple meetings over a prolonged period of time, but has helped to more effectively embed the Retinopathy of Prematurity Initiative within the public health system. The evaluation also highlighted the value of investing in training health staff at all levels: “Because so much of the programmes rely on the capabilities of ancillary staff – Special Neonatal Care Unit nurses… optometrists, ophthalmic assistants, counsellors etc., as they do on the capabilities of the doctors and specialists, the programme has highlighted the role that ancillary staff plays. It has made it impossible to ignore the need to upgrade their skills.”

Output Title	Strengthened eye health systems in lower and middle income Commonwealth countries in three key areas of people, knowledge and tools
Output number per LF		4	Output Score	A
Impact weighting (%)?		25%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
4.1 Number of health care professionals trained	Cumulative Total: 180 / MSc students: 30 / Clinical fellowships: 140 / PhD fellowship: 10	Exceeded expectations / Cumulative Total: 191 / MSc students: 42 / Clinical fellowships: 140 / PhD fellowship: 9
4.2 Number of countries with domestic institutions that have agreed and implemented national frameworks for diabetic retinopathy screening and treatment	8 countries have their diabetic retinopathy framework in place and integrated into Ministry of Health services	Met expectations / Frameworks in place in 8 countries (Botswana, Dominica, Jamaica, Kenya, St Lucia, Tanzania, Uganda, Zambia)
4.3 New eye care technologies developed	Botswana school screening trial underway	Met expectations / Botswana school screening trial underway

Provide supporting narrative for the score

The Trust has worked in partnership with the Commonwealth Eye Health Consortium (CEHC), hosted by the London School of Hygiene and Tropical Medicine (LSHTM). Through this partnership the trust has supported a very wide range of activities that include:
- Delivery of Masters in public health for eye care at the London School and the University of Cape Town for eye health professionals from 18 Commonwealth countries. Graduating students return to their countries where they are working in eye care, mostly in leadership roles where they are applying this training to strengthen the delivery of eye services.
- Delivery of seven free online courses covering topics including trachoma, managing eye care services, diabetic eye disease, retinopathy of prematurity and glaucoma. These have been successfully run and completed by 23,500 people from 188 countries, including 13,000 people from 50 Commonwealth countries.
- Award of 140 three-month and one-year clinical training placement fellowships to health professionals from 19 Commonwealth countries who have been able to intensively practice sub-speciality skills that are not widely taught in their home institutions.
- A ‘Training The Trainers’ programme that has significantly improved the training of ophthalmologists across six African Commonwealth countries (Kenya, Uganda, Tanzania, Malawi, Zambia and Rwanda). The Consortium estimates that one million patients per year are treated by health care workers that have benefitted from the training sessions to date.
- Managing the Diabetic Retinopathy Network which has supported 16 Commonwealth countries to develop national or regional frameworks and programmes for the detection and treatment of diabetic eye disease, integrated into the wider health system. National diabetic retinopathy frameworks are now integrated into Ministry of Health services in eight countries (Botswana, Kenya, Tanzania, Uganda, Zambia, Dominica, Jamaica and St Lucia). Over five years the Network has screened an additional 44,097 patients for diabetic retinopathy and treated an additional 6,793 patients (on top of their existing treatment outputs).
- Coordinating the Retinoblastoma Network which brings together partners from four countries to improve treatment and outcomes for this childhood eye cancer.
- Coordinating the Retinopathy of Prematurity (ROP) network which brings together partners through south-south collaboration in seven Commonwealth countries (four African and three Asian), and mentor institutions mostly in India. Ghana and Tanzania have started ROP screening and treatment, already saving the sight of babies who would otherwise have been blind for life.
- Research fellowships at PhD and postdoctoral level. Several of these are generating research that is being utilised in the Trust’s work – such as the Retinopathy of Prematurity Initiative or the use of smartphone device Peek. The PhD fellows have published 22 academic papers, with a further 33 papers in the pipeline. The Consortium has doubled the number of eye health professionals in sub-Saharan Africa who have received formal research (PhD) training.
- Peek Vision smartphone eye health technology is supporting large-scale eye screening programmes. Peek is piloting programmes to demonstrate how teachers can be trained to provide eye screening for students across a country. More than 200,000 children in Kenya have had their eyes screened using Peek. Peek Vision and the Government of Botswana have agreed a programme to screen the vision of every school child in the country and provide them with treatment. Work on site analysis, programme strategy and design has already been completed.
- The Peek Acuity smartphone app has been downloaded and used by about 50,000 people in 160 countries. This simple-to-use smartphone-based test allows the user to reliably test eye sight and has been validated in a peer-reviewed publication. In 2017 it was nominated the “Best Social Impact Application” by Google.

The Trust has agreed to allocate a significant portion of its contingency funds over the 2019/20 period. The last of these funds will be released when the Trust formally closes in mid-2020. This will help the Consortium to transition to new sources of income.

Lessons identified this year linked to this output and recommendations for future programmes

In March 2019 an independent evaluation of the Commonwealth Eye Health Consortium was completed. The evaluation looked at the impact of the individual streams of the Consortium, and examined these streams working together have become more than the sum of their parts. The Consortium brought together 170 eye health experts from 27 Commonwealth countries to hold a week-long series of workshops in March to evaluate progress. The findings from the evaluation were used to generate discussion during the workshops.

Key findings included:
- Eye health professionals who have been involved in the various streams of the Consortium have formed a strong alumni network, which is especially valuable for people who may have few peers working in their local area.
- Several of the Consortium’s streams involved facilitating south-south relationships, for example doctors from Nigeria would spend three months in India working on specific clinical techniques. This structure was beneficial to both the participants and the host institutions, helping them to improve their training capacity and to foster greater links across the Commonwealth.
- Eye health professionals who complete training overseas and return to their home institutions require significant support to help them implement their new skills. It is not reasonable to expect an individual to change a health system by themselves. The Consortium therefore increasingly focused on training teams of doctors and providing ongoing mentorships for participants.
- The disease-specific networks have found increased success when working at the regional, rather than global, level. This helped to create local ownership of approaches and collectively develop appropriate solutions to challenges.

The evaluation concluded:
“The Commonwealth Eye Health Consortium was designed to drive forward progress on addressing avoidable blindness within low and middle-income Commonwealth countries through an integrated approach focused on people, knowledge and tools.

Evidence from across the Consortium shows that this approach is having impact. Individuals have been equipped with research, planning and clinical skills to better design and deliver services in countries and regions in which they are desperately needed and in many cases, where there was previously no provision of specialised services nationally. Tools have bolstered this through the provision of additional training opportunities – supporting both individuals and institutions – and powerful technology to aid planning, screening and referral. Much of this work has been further aided by the development and strengthening of networks, partnerships and collaborations.

Though strong foundations have been developed through the people, knowledge and tools approach and supported through the commonwealth-wide communities of practice that have facilitated it, the CEHC faces challenges to sustaining impact. It will be vital to provide further support to individuals and networks as they develop to ensure they can fully utilise the skills they have attained. In order to strengthen the Consortium structure, opportunities to maximise the application of the tools invested in through this first phase of activity must be fostered.”

Output Title	A robust, responsive and supportive Trust
Output number per LF		5	Output Score	A
Impact weighting (%)?		10%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
5.1 Unqualified audit of accounts received and annual results reporting aligned to common indicators presented in a manner consistent with results-based management principles	Compliant accounts and reporting. Clear lines of communication	Met expectations / Independent auditors have provided an unqualified opinion on Trust’s 2017/18 accounts. The Trust’s 2018 Annual report and accounts were published on the Trust’s website / The Trust’s 2019 Annual Report and 2018/19 accounts will be published by end-2019, with the 2020 Annual report and accounts published in mid-2020
5.2 Proportion of grantees satisfied by implementation and value added by the Trust	90% positive grantee responses to satisfaction question included in reporting to the Trust	Exceeded expectations / 100% positive grantee responses to satisfaction question included in reporting to the Trust
5.3 Development of monitoring indicators and evaluation reports showing capacity building and lessons learned	Evaluations completed	Met expectations / Evaluations completed, with key findings shared and disseminated
5.4 At least two examples of how the Trust has influenced global policy and/or have leverage with respect to scaling up preventable blindness programmes	May 2019 Commonwealth Health Ministers Meeting (CHMM) increases the momentum for meeting the commitments on vision in the CHOGM 2018 communique / Lead the Vision for the Commonwealth coalition to lay the groundwork for a meaningful outcome on vision at the 2020 CHOGM. / Joint evaluation with DFID completed on trachoma and findings disseminated at GET2020 meeting	Met expectations / Presentation of the Trust’s results at the CHMM Ministers’ lunch, including reminder of the commitment and the need for action / The Vision for the Commonwealth coalition is currently discussing the objective of a more focussed commitment on vision for CHOGM 2020, and a roadmap up to June 2020 to secure it / Achieved; presented on behalf of the Trust and DFID

Provide supporting narrative for the score

From its inception the Trust has set itself the objective not only of delivering successful and sustainable programmes to curb blindness from avoidable causes across the Commonwealth, but of using its influence – deriving not least from its association with HM The Queen as Head of the Commonwealth, its mission to create a lasting legacy in her name, and the unusually broad and eclectic donor base supporting it - to raise the issue up the policy agenda and secure lasting change. The aim is always that governments should own and lead the effort, drawing as necessary on the expertise and resources of a range of organisations. The Trust observed that this was not always happening, resulting in uneven patterns of service provision; it also observed that the eye health sector’s advocacy efforts at national and international levels were, with some notable exceptions, lacking co-ordination, with effort expended on talking within the sector at the expense of reaching out to influencers and decision makers beyond its immediate circle. Yet the sector has a compelling message, able to resonate with every nation and individual, and across cultures: 4 out of 5 people who are blind do not need to be and there are simple, low-cost, tried and tested means to change that.

The Trust approached this task in three ways:
- By itself advocating change, using its programmes as examples of what can be achieved;
- By building and leading a coalition of like-minded organisations to advocate change (Vision for the Commonwealth);
- By using its influence as a Trustee of the sector’s umbrella body, the International Agency for the Prevention of Blindness (IAPB), to re-direct and focus the sector’s broader advocacy efforts.

As it prepares to close, the Trust is leaving behind ground-breaking international commitments, and a sector much better placed to gain traction in the future. For example:
- The vision commitments made at CHOGM 2018, with the CHOGM / Commonwealth Health Ministers Meeting (CHMM) review points, provide a basis for continued engagement on the issue at Commonwealth level, including summits;
- The Vision for the Commonwealth coalition is robust and united, continuing under IAPB leadership;
- The IAPB itself has a new strategy, focussing its advocacy efforts on the right objectives in the right places.

In April 2019 the Trust’s Vice-Patron, the Countess of Wessex, visited the Trust’s Retinopathy of Prematurity Initiative in India. She met with patients, health staff, philanthropists and government officials to raise the profile of the Trust’s work and encourage continued investment in this area.

The Trust’s Chief Executive has visited each of the Trust’s target countries in the Caribbean, Africa, Asia and the Pacific to meet with senior government officials. These meetings drew attention to the work supported by the Trust and encourage ministers to continue supporting key activities.

The Trust will publish a legacy book in October 2019 and host a high profile event to showcase its achievements and influence others to continue working in these important areas into the future. It will maintain its website until its formal closure in mid-2020 and transfer key content onto the Royal Family website (https://www.royal.uk/history-queen-elizabeth-diamond-jubilee-trust) to provide a lasting legacy of its work.

Lessons identified this year linked to this output and recommendations for future programmes

In 2019 the Trust commissioned the Institute for Voluntary Action Research (IVAR) to review its approach to the Avoidable Blindness Programme. The purpose of the review was to share the Trust’s experience of working over a relatively short timeframe to achieve strategic focus, deliver impact at scale and to identify learning that may be of value to other independent funders, both in the UK and further afield. The review team met with the Trust team, partners and advisers. The report will be published in September 2019 and shared with funders through a dissemination event that the Trust is hosting. Key extracts from this independent report are provided below.

- “In Avoidable Blindness, [the Trust] identified a strategic focus that spoke to its own needs for: reach, appeal to numerous and diverse stakeholders, demonstrable results and the potential to support sustainable change for the long term…It also offered a distinctive niche, in an issue with support from other funders but no dominant players, creating opportunities for the Trust to work proactively and bring its assets and networks to bear in terms of convening, influencing and advocacy.”
- “Its decision to fund through partnership and collaboration means that the Trust managed some £80 million of funding around Avoidable Blindness through only four substantive grant relationships. This enabled partnership working to ‘operate at the right scale…’”
- “Partners speak very positively about their funding relationship with the Trust: ‘They ask the right questions, of course, but they trust the expertise of partners and rely on their quality control, while really concentrating on the goal.’”
- “The Trust has also taken an advocacy role within the eye care sector itself, seeking to catalyse the actions needed to significantly scale up work to eliminate avoidable blindness.”
- “Overall, there is a real sense that the experience of the last five years has left the eye care sector stronger and more confident – ready to set the agenda for what happens next…”

The report concludes with lessons for other funders in five key areas:

Developing a strategic focus
Learning for foundations interested in framing their work around a tightly defined goal:
- Understanding and agreeing the foundation’s own organisational needs and expectations is a critical first step in identifying an objective that fits its scale, aspirations and appetite for risk;
- Recognising and accepting the importance of complete organisational alignment behind the agreed strategy – ‘achieving strategic focus involves giving up everything else’;
- A fresh pair of eyes can make a big difference – provided they come with respect for the efforts of others and an active interest in learning from both practitioners and authoritative experts, as well as offering challenge and concrete assets to support a new sense of new momentum;
- Building genuine credibility as a contributor ‘beyond the money’ takes time and effort – being present, being interested and being useful all help this process run more smoothly.

Values and attributes
Learning for foundations interested in thinking about how to frame their ways of working to meet the demands of a strategy delivered in close collaboration with others:
- Understanding and developing behaviours that will enable the foundation to work well with others and best support effective collective effort;
- Interrogating the skills needed within the team to add value – creating a culture which enables staff to use their expertise well;
- Welcoming challenge and new ideas, and creating an environment in which these can be most helpfully expressed and acted on;
- Delegating clearly and focusing oversight on ‘mission critical’ concerns.

A partnership approach
Learning for foundations interested in developing effective, trust-based partnerships with grantees:
- Choosing partners carefully and being clear about the different assets that they and the foundation bring to the table – trusting their skills, experience and judgement and being mutually accountable for progress and performance;
- Understanding that much of the funding system drives behaviours that stand in the way of good partnerships and addressing this openly; also understanding that some organisations, and especially government donors, have rules and bottom lines that they do not have the freedom to waive. Working together to find appropriate solutions and compromises;
- Recognising the importance of words matching deeds – of getting into the detail of due diligence, risk management, communication, problem solving, formal reporting and (where appropriate) decisions on future funding – and making sure they support a partnership approach;
Getting the formal partnership structures right, giving particular attention to areas – such as general communications and brand building – where agendas may diverge both within and between organisations;
Investing in relationships – engaging regularly, understanding and sharing opportunities and constraints, chewing over challenges and working together to find solutions; and then building new relationships if key people move on.

Risk and innovation
Learning for foundations considering their risk appetite and their approach to innovation:
- Achieving real clarity and agreement – both internally and with partners – about what risk looks like and where it lies; and then being realistic about potential risks and taking care not to overreact, while being ready to take quick, and hard, decisions where necessary;
- Taking a positive approach to risk management and mitigation, actively seeking access to skills, knowledge and expertise to assist in this task, and deploying these resources effectively;
- Seeking to create relationships with grantees that enable them to contribute their expertise and have the confidence to share “real time” information on challenges and risks so that timely action can be taken to deal with them together;
- In balancing questions of risk and benefit, being conscious of the distinctive freedoms that come with being an independent foundation and being willing to take risks where the potential rewards are sufficiently promising.

Advocacy approach
Learning for foundations interested in making best use of their potential to support effective advocacy for change:
- Rigorously analysing the distinctive skills and assets the foundation is able to bring to bear – and where these may be constrained or curtailed;
- Understanding what it will take to make best of use of these assets and applying sufficient resources to the task. Skilling up where necessary at Board level and by bringing specialist skills into the staff team;
- Recognising that collaboration is key to effective advocacy. Considering how best to build credibility with potential partners and how to attract those best able to increase reach and impact;
- Finding the right style and method to get the message through to those in a position to support sustained change. Talking the cause, not “our programmes”. Being visible and present – there is no substitute for face-to-face contact.

## C: THEORY OF CHANGE AND PROGRESS AGAINST OUTCOMES

Overall assessment of whether the expected outcomes and contribution to target impact(s) were achieved

The overall outcome was defined as ‘Increased capacity and access to quality eye health care in targeted areas of the Commonwealth for Trachoma, Diabetic Retinopathy (DR) and Retinopathy of Prematurity (ROP)’.

Two outcome indicators focused on areas that could be aggregated across the avoidable blindness initiatives:
- Number of people whose sight has been protected as a result of programme activities (cumulative target 106,840); and
- Number of eye health professionals trained/retrained and practicing in targeted countries (cumulative target 402).

In both cases these targets have been exceeded. 123,605 people have had their sight protected and 568 health professionals have been trained or retrained to treat patients for sight-threatening diseases. In particular, the expansion of the Trachoma Initiative to include more work in Uganda, Nigeria and Zambia meant that more surgeons were trained to perform trichiasis operations. The Diabetic Retinopathy Initiative was also able to treat more patients than anticipated. This Initiative often took time to get going in each country, but once the systems were in place the demand for diabetic retinopathy treatment meant that a large number of patients were able to be provided with care. The Trust has supported the training of eye health professionals who are able to provide screening and treatment to save a patient’s sight. This includes surgeons in Africa trained to operate on trichiasis for trachoma patients, and ophthalmologists providing laser treatment for DR and ROP.

The impact was defined as ‘Improved eye health in targeted Commonwealth countries’, with an indicator focused on trachoma elimination:

‘Number of Trachoma endemic Commonwealth countries that have reached elimination targets by achieving their Ultimate intervention Goals (UIGs) <0.1% Trachomatous Trichiasis (TT), <5% Trachomatous follicular (TF)’ .

All countries have made progress towards their targets. Some countries have achieved or exceeded targets, whereas others encountered challenges and were not able to reach their goals.

Malawi, Solomon Islands and Vanuatu have all achieved their Ultimate Intervention Goals (UIGs) and expect to submit their elimination dossiers to the World Health Organisation within the next 18 months. Uganda is expected to take another year to reach its UIGs. Fiji may have achieved its goals, but a further survey will be conducted in 2019 to confirm this situation. Kiribati will conduct a further round of mass drug administration in 2020. Mozambique and Tanzania have exceeded targets and have cleared almost 100% of their targeted surgical backlogs. Zambia has achieved approximately 50% of its backlog while Nigeria has faced multiple challenges and is halfway towards it target.

This variation across the portfolio was expected and the close working relationship between the Trust and its partners has enabled funding to be reallocated in response to changing circumstances.

Beyond achieving country elimination targets, the Initiative has contributed significantly to the global goal of trachoma elimination. The Initiative was the leading contributor to the development of approaches to reach full geographic coverage of populations, new ways to provide surgeon training, official guidelines on transitioning from a trachoma-focused outreach programme back to service delivery by the health system, and guidance on how countries should complete their elimination dossiers for approval by the World Health Organisation. The Trust has been an active member of the donor forum in the fight against trachoma, and has been able to influence and engage other donors, with credibility from its own programme. This has helped the global trachoma community to secure further commitments, particularly from DFID, to ensure that the countries supported by the Trust are able to achieve their elimination targets in the coming years.

Summarise the programme’s theory of change and major changes to it in the past year

The programme’s Theory of Change has envisaged that the combined effects of implementing selected elements of the SAFE strategy, treatment of sight threatening retinopathy and the strengthening of health care systems through improved knowledge and tools (‘the outputs’) will lead to improved capacity and access to quality eye care (‘outcome’) and deliver improved eye care in targeted Commonwealth countries and regions (‘impact’).

The Theory of Change makes a number of assumptions including:
1. The Trust’s programmes can have a measurable impact on avoided blindness across the Commonwealth over a 5 year period;
2. Development and implementation of global/national strategies will create sustainable change across the programmes and help achieve elimination of trachoma/positive change in diabetic retinopathy and retinopathy of prematurity;
3. Selected technological, training and research initiatives will both reinforce (and advance) the three main parts of the strategy and have wider positive impacts;
4. The countries chosen for intervention are those that enable maximum impact;
5. Advocacy will contribute to the achievement of Trust outcomes and reinforce impacts including health system strengthening;
6. Dissemination of learning and best practise will contribute to the achievement of Trust outcomes and reinforce impacts including health system strengthening;
7. The Trust’s work alongside national governments will result in continuation of programmes under local leadership.

The Theory of change shows how the Trust’s avoidable blindness initiatives have worked towards improving access to quality eye care in targeted Commonwealth countries. This is achieved by:
- Increasing demand for eye health services through educational campaigns;
- Technical and technological research to create new development in delivery of eye care;
- Increasing the capacity of health systems by providing resources, training personnel and connecting professionals to global networks;
- Integrating strategies to tackle targeted diseases into national health systems through the development of guidelines, organisation of conferences, dissemination of key lessons and advocacy with Ministries of Health.

No major changes were made to the theory of change since the last annual review in January 2019.

Explain major changes to the logframe in the past year

No major changes were made to the logframe since the last annual review in January 2019.

## D: VALUE FOR MONEY

Assess VfM compared to the proposition in the Business Case, based on the past year and during the lifetime of the programme

The Trust does not directly implement programmes itself but has contracted delivery partners to deliver programmes and services. Value for money has been well understood by the Trust and its implementing partners over the past year and through the life span of the programme.

For instance Sightsavers, who were grant manager for the Trust’s trachoma work in Africa which made up the largest proportion of the spend, have continued to implement a value for money strategy that looks at cost per case managed, cost per mass drug administration treatment and implementation. Close attention has been paid to volume, schedule, cost and quality; and a visual dashboard focusing on key metrics utilised enabling project managers to identify trends in the delivery of project objectives and in the unit costs of achieving these objectives.

The Fred Hollows Foundation, which coordinated several Trust Initiatives, closely monitored their project budget to identify potential areas of underspend in time and redirect the funds to other (existing or new) activities that were higher priority and had more achievable outcomes. For example, savings on equipment procurement in Samoa allowed for more portable screening equipment to be purchased in other target countries and more people to receive eye screening.

Economy

The Trust has ensured economy in its programmes through oversight of costs required to run activities and produce outputs. Key unit costs have been tracked and quality monitored.

Work to eliminate trachoma in Africa has made up the largest area of spend. The cost of surgical interventions and the mass distribution of anti-biotics has been closely monitored. As regards surgical interventions, the average cost per surgery for trachoma was approximately £120. As countries moved closer to their elimination targets, the cost per surgery increased as more resources were required to track down the last remaining cases. The average cost is higher than initially expected as many districts and countries were closer to their elimination goals than anticipated. This required fewer surgeries, but increased cost to locate and operate on the remaining cases. The initiative has also highlighted the importance of improved patient care, follow up checks, surgical supervision and auditing of surgery quality. These activities all increased the cost per surgery but add significant value to the initiative. As regards the mass distribution of anti-biotics, costs were broadly in line with those expected. Unit costs have varied from country to country. In Africa they varied from £0.08 per treatment in Nigeria to £0.33 per treatment in Zambia. The variation was influenced by economies of scale and accessibility. The average cost per treatment was £0.16 per treatment.

The Commonwealth Eye Health Consortium has utilised existing partnerships to reduce costs. For example, they were able to double the number of Masters scholarships provided in London, from 11 to 22, by obtaining co-funding for accommodation from International Students House.

Efficiency

During the course of the programme, outputs have been largely delivered to work-plans and in most cases identified targets have been achieved and, in some cases, exceeded, thereby maintaining the efficiency of output delivery. Overall the Trust’s programmes have exceeded the target number of people whose sight they have protected and also the number of eye health care professionals trained. In particular they have exceeded expectations as regards the number of patients screened for and treated for diabetic retinopathy, and the number of infants treated for retinopathy of prematurity. Where targets have not been achieved, this has been for reasons beyond the control of the Trust.

They have also collaborated closely with other actors. The Trachoma Initiative for example, was delivered by the International Coalition for Trachoma Control (ICTC), a multi-stakeholder membership of non‐governmental, donor, private sector and academic organizations. Working with the ICTC ensured that the Trachoma Initiative coordinated with all actors working on trachoma and avoided unnecessary duplication.

Equity

The Trust’s activities are directly improving the lives and well-being of poor and vulnerable people in at risk communities. Women have been the primary beneficiaries of trachoma trichiasis surgery. In addition, house-to-house searches by case finders have sought to ensure that vulnerable people, or those with accessibility requirements, are not overlooked for treatment. Throughout the course of the project, routine gender disaggregation of all clinical data across all eye care services was maintained, to inform service planning, thereby working towards equity of access to services. The Commonwealth Eye Health Consortium supported smartphone-based eye care system ‘Peek’ to screen people in remote communities. At the heart of Peek’s ethos is to ensure access to eye health services to those least likely to have access, children, women and the elderly as well as those living in remote and often poorer communities. This has been done by bringing the screening for eye health services to these people through facilitating teachers to screen their pupils and community members to screen their communities. Bringing the screening to the people has been shown to improve the percentage of those presenting at triage and attending referrals.

Effectiveness

The original business case envisaged effectiveness largely being measured in terms of the number of disability affected life years averted and the cost per disability affected life year averted. This approach was envisaged to help us understand the cost effectiveness of the interventions targeting trachoma, diabetic retinopathy and retinopathy of prematurity. Whilst directly comparable data was not available at the time this review was completed, there is evidence that indicates the effectiveness of the programme.

In April 2018, PwC completed an economic analysis on the return on investment for tackling avoidable blindness in the Commonwealth, with a specific focus on the Trust’s initiatives. The analysis considered the return on the £25.6 million that had been invested in the Trust’s trachoma, diabetic retinopathy and retinopathy of prematurity initiatives over the period 2014-17. This found an overall return of £12 for every £1 invested. The return on investment was found to vary from £6 for each £1 spent on retinopathy of prematurity and £6.50 for every £1 spent on diabetic retinopathy, to £13.20 for every £1 spent on trachoma. There were also variations by country, The Trust’s investments then to date were considered to have resulted in averted productivity loss of more than £300 million.

As further illustrations of the cost effectiveness of this programme, the original Business Case calculated that as regards retinopathy of prematurity that initiative would break even if only 20 successful interventions were made under the programme. The intervention actually supported 394. And the Commonwealth Eye Health Consortium has provided sub-specialty clinical training for more than 140 ophthalmologists and related eye health workers, mostly from Sub-Saharan Africa. These specialists are now in post and delivering previously unavailable treatment for people with more complex eye problems. The Trust estimates that this will approximately double the number of ophthalmologists with formal sub-specialty training in African Commonwealth countries.

E: RISK

Overview of programme risk (noting the rating from page 1) during the past year and over the life of the programme

There have been no significant changes in the overall risk environment / context since the last Annual Review. The overall risk rating remains Minor. Over the life of the programme, the level of risk having initially increased has progressively reduced as the Trust’s operations matured and results were delivered.

Programme risk (outputs 1-4)

Day-to-day risk management processes were embedded across the Trust through effective implementation of policies and procedures. The Trust maintained a central risk register (covering risks related to reputation, advocacy, programmes, finance, governance and operations) at corporate level and each individual programme and initiative had its own risk register. The corporate risk register is reviewed and updated monthly by the Trust’s Executive Team and it is shared with the Audit Committee. The Board of Trustees formally reviews it and approves it annually. All grantees were required to have their own policies on risk management which were included in their grant agreements. The Trust has conducted due diligence assessments on all grantees.

The overall risk assessment for outputs 1 – 4 is rated as ‘minor’ reflecting the maturity of the Trust’s programmes that had been running for several years with mainly the same key delivery partners. The Trust built strong relationships with its small number of partners and was in contact with them at least once a month which allowed it to monitor performance and risk closely. This has allowed it to deliver effectively against targets even in some countries with difficult operating contexts (e.g. Nigeria) and when working with vulnerable adults and young children.

Organisation risk (Output 5)

DFID conducted a due diligence assessment of the Trust in August 2017, updating a previous assessment carried out in October 2013. Due diligence assessments are intended to obtain sufficient assurance of the implementing partner’s internal control framework, capacity and capability to deliver DFID programmes. The Trust was assessed as being a minor risk in all categories: governance and internal controls; ability to deliver; financial stability and downstream partners. This remains the current risk assessment. With the programme now complete and the Trust due to be wound up in January 2020, the main recommendation from the assessment was ensuring the Trust prepared appropriate exit strategies to build programme sustainability and leave a lasting legacy. It has continued to take appropriate action on both matters.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Performance of partners and DFID, notably on commercial, and financial issues

Delivery: The Trust has supported programmes that have achieved output and outcome targets in line with expectations. The Trust has provided narrative reporting and financial statements to DFID in accordance with the terms of its agreement. It has published Annual Reports and audited accounts, the most recent being for 2017/18 published in December 2018. The Trust’s 2019 Annual report and Accounts (covering the period July 2018 – June 2019) was being finalised by the Trust at the time of completion of this PCR and will be published at the end of 2019. The Trust’s 2020 and final Annual report and accounts will be published in mid-2020.

Financial Management: The Trust is governed by a Board of Trustees who set the Trust’s strategic direction and approved all operational and financial plans. The Audit Committee is a sub-committee of the Board of Trustees and is comprised of two Trustees and four external advisory members. The Audit Committee considered matters relating to financial control, organisational effectiveness and risk management, reporting to the Trustees accordingly.

The final DFID payment to the Trust was made in October 2018. For each payment request the Trust provided a certified letter setting out actual expenditure to date (committed and spent), a forecast of funds to be disbursed or committed during the next 6 months, a statement supporting new funding raised (to which DFID will view as eligible to match) and an explanation (if any) of the disparity between the forecast commitments and disbursements and funding already held by the Trust.

The Trust’s Auditors (Crowe Clark Whitehill LLP) gave a clean audit opinion for the financial period 1 July 2017 to 30 June 2018 and confirmed that there had been no evidence of any financial risk or fraud. The Trust’s 2018 Annual Report and Audited Financial Statements has been countersigned by the Trust’s Chairman and published on the Trust’s website. The Trust’s 2019 Annual Report and Accounts will be published by the end of 2019.

Date of last narrative financial report	June 2019
Date of last audited annual statement	December 2018

G: MONITORING, EVIDENCE & LEARNING

Monitoring

The Trust worked through a small number of partners and closely monitored each of its programmes. Each partner has provided the Trust with monthly updates, as well as longer six-monthly narrative reports and expenditure reports. The Trust held monthly calls with its key partners to discuss any ongoing issues. Targets, indicators and report structure were reviewed on an ongoing basis to ensure that the most appropriate data was collected. The six-monthly reports also provided partners with an opportunity to feed back on their relationship with the Trust and suggest any changes to their way of working. The Trust has produced Annual Reports and Accounts summarising its activities and achievements.

DFID officials held monthly programme meetings with the Trust to discuss programme and financial management issues (including progress against the logframe and a review of risks). In addition, DFID participated in the Trust’s Scientific Advisory Board which received summaries of the monitoring data provided by partners is presented to the Trust’s Scientific Advisory Board and the Board of Trustees at each of their meetings.

The Trust also engaged in field visits to review progress and talk with delivery partners on the ground. This information helped to feed into any funding recommendations put to the Trustees. The Trust has developed a thorough grant closure process with the following objectives:
- To close each grant legally and to meet the reporting requirements of their donors and stakeholders;
- To manage the end of each partnership in a professional and positive way;
- To agree the record of achievements and legacy of the partnership so that there is a clear narrative after we have closed.

Evidence

The Trust’s programmes have helped to generate considerable evidence to improve their own effectiveness and provide guidance for global efforts on avoidable blindness. The scale and speed of the Trachoma Initiative in Africa created new evidence on how to effectively survey populations for disease prevalence using preferred practices, how to reach marginalised populations, how countries can transition back to providing comprehensive eye care, and how they should prepare for submitting information about elimination to the WHO. These have all resulted in new guidelines or guidance documents that will be used by countries still working to eliminate trachoma. In the Pacific, the presentation of trachoma was significantly different to that in Africa and research was required to determine the next course of action. This evidence will help trachoma elimination activities in the Pacific, and other countries with irregular presentation, to become more efficient. The Trust’s Diabetic Retinopathy and Retinopathy of Prematurity Initiatives in India have contributed to the development of guidelines that will aid more effective management and treatment of these conditions. The Commonwealth Eye Health Consortium has produced a significant amount of evidence - 45 academic papers have been published, with a further 33 papers expected to be published by 2020.

Learning

The Trust has commissioned reviews or external evaluations on each of its programmes. These have focused on capturing learning that will be of value to other actors working on avoidable blindness. In each case, the findings have been presented at international or national conferences attended by the target audience and published on the trust’s website. This has raised the profile of the findings and helped to disseminate them more rapidly. For example:

The Trust and DFID jointly commissioned a joint learning exercise of their respective trachoma programmes that was presented at the annual WHO GET2020 trachoma meeting in Maputo, Mozambique in June 2019. This meeting was attended by government officials, technical experts and implementing organisations from across the world.

The evaluation of the Trust’s programmes in India was presented at a national Dissemination Summit in Hyderabad attended by officials from throughout the country who were seeking to replicate the work of the Trust’s model.

Evaluations of the programmes in the Pacific were presented at a meeting in June 2019 attended by officials from across the region. The Commonwealth Eye Health Consortium discussed its evaluation at a week of workshops in March 2019 attended by 170 eye health experts from 27 countries.

Progress on recommendations from annual reviews for this programme

Appropriate action has been taken to follow up on recommendations from previous Annual Reviews. Action taken to the address the most recent set of recommendations is summarised below.

Jan 2019 Annual Review Recommendation	Response/Action
Overall recommendations
The Trust should also work to ensure the sustainability of its programme by supporting its various partners to transition and graduate smoothly from the support they have been receiving.	The Trust has supported partners in transitioning work to new funding or government support. The Trust worked closely with Sightsavers to enable the Trust’s Trachoma Initiative to coordinate and integrate with incoming funding from DFID. The Trust’s Chief Executive has also held meetings with Ministry of Health officials in each of the Trust’s priority countries to promote government ownership of activities.
A key focus for the Trust should be (and is) to ensure the lessons of its programmes are effectively captured and are disseminated widely (both through formal and informal mechanisms) and to ensure that it leaves a lasting legacy from its work.	Independent evaluations have been completed on all of the Trust’s major programmes. These have been proactively shared online and at appropriate national or international forums.
Output 1
The Trust should continue with adaptive programming during its remaining period of operation. It should also continue to help ensure the sustainability of the programme by continuing to support its partners to transition and graduate smoothly from the support they have been providing and supporting integration of services with national health systems.	The Trust’s Board of Trustees has agreed to select Programme Closure Grants for key Trust partners to enable them to continue their work for the next two years after the Trust closes. This extended period will provide them with more time and flexibility to transition to new sources of support.
The Trust should consider with DFID whether the end of programme targets for trachoma trichiasis surgery need to be adjusted to reflect realistic and achievable aims.	Targets could have benefited from review, but this was not possible given proximity to the end of the Project. Variation from surgery targets is explained under Output 1.
The Trust should continue to engage with DFID on the jointly commissioned evaluative learning exercise. Further, it should ensure that once completed the evaluation and lessons learnt are widely shared and disseminated.	The report was completed, released online, and presented and distributed at the World Health Organization Global Elimination of Trachoma by 2020 (GET2020) meeting in Maputo, Mozambique in June 2019. The report has also been shared with the Trust’s trachoma partner in the Pacific and discussed at regional events in Africa. The report was also shared at the Neglected Tropical Disease NGO Network in Liverpool in September 2019.
Output 2
The Trust should continue to highlight the benefits of investing in vision through its engagement with Governments and partners	The Trust’s Chief Executive has met with country Ministries of Health throughout the year. The Trust also engaged with governments at the Commonwealth Health Ministers meeting in May 2019.
Output 3
The Trust should continue to promote the lessons learned through the programme to help ensure that control of ROP is seen as a specific priority in the Indian National Programme for the control of Blindness, with budgetary provision for screening and treatment; and is seen as a scalable model by other Commonwealth countries.	The Trust’s partner in India held a national Dissemination Summit in June 2019 to share learning from the Trust’s Initiative and promote expansion and replication. This meeting was attended by health officials from across the country. / In April 2019 the Trust supported a national ROP meeting in Pakistan. Personnel from India shared their experience of the Trust’s programme to help Pakistan to develop a similar model.
Output 4
The Trust should continue to provide the support, advice and access it has been able to offer to the development and take-up of the Peek smartphone software. Lessons and recommendations from the ongoing evaluation will be an important aspect of the Trust’s legacy.	The Trust has continued to work very closely with Peek in ensuring that their technology and services continue to develop. / The Commonwealth Eye Health Consortium held a week-long workshop in April 2019 to discuss learning from the evaluation and plan for future services.