Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.
Title: Saferworld Public Partnership Agreement
Programme Value: £8,695,800 – Lifetime spend over 5 years		Review Date: July 2015
Programme Code: 202709	Start Date: 2011	End Date: 2016

Summary of Programme Performance
Year	2011/12	2012/13	2013/14	2014/15
Programme Score	A+	A+	A+	A+
Risk Rating	Medium	Medium	Medium	Medium

Summary of progress and lessons learnt since last review

Saferworld has far exceeded targets in its logframe. Significant progress has been made at the output levels and there is evidence this is leading to outcomes. Targets in the extension logframe (2014-16) were revised to reflect increased capacity and expansion of programmes. Saferworld attributes exceeding these targets to (i) the ability to leverage funds over the past three years, using the foundation of the PPA, (ii) consistent and sustained work through partners in-country, and (iii) a robust theory of change that combines work at local, national and international levels to contribute to positive changes in people’s lives. There is evidence to support this. Sustained engagement over time on thematic issues and in focus countries appears to be bearing results. However, consideration should be given to whether the structure of the logframe - with a primary focus on quantitative stakeholder targets – and the similarity between some of the outcome and output indicators helps or hinders conveying a clear sense of outcomes on conflict and security issues. Some of the quantitative targets could be re-focused to improve their quality.

PPA funding appears to be used strategically to help deliver results and support organisational strengthening. Investments in human resource, financial management and monitoring, evaluation and learning systems are having a positive impact on country programmes. There is an impressive commitment to organisational learning and staff are reflective about their work. There appear to be good two-way vertical linkages between country work and international policy and advocacy. PPA funding has played a vital role: filling funding gaps, expanding into new regions; supporting innovation, leveraging funding and underpinning institutional development.

Summary of recommendations for the next year

Summary of recommendations for the next year

1. Saferworld should consider if the logframe as currently structured helps to convey the outcomes of their work and if it should be revised. This is important in the context of next years’s Project Completion Report (PCR).
2. Quantitative targets in the logframe should not be increased for 2015-16. The focus for 2015-16 should be firmly on the qualitative aspects of Saferworld’s work and ensuring that outputs help to deliver outcomes.
3. Saferworld should continue to develop theories of change (ToCs) for all its focus countries that make explicit the theory for the community security work. These should include a greater focus on engaging sub-national authorities, influencing state planning processes and developing partnerships for scaling up.
4. Saferworld considers engaging in the public health approach to violence prevention as a natural extension of its gender and community security work.
5. Saferworld considers how the outcomes identified through its work on outcome harvesting (a M&E approach that identifies what has changed and whether and how an intervention has contributed to this) can be clearly communicated to DFID.

A. Introduction and Context
DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-202709/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-202709/

Outline of the programme
Saferworld believes that everyone should be able to lead peaceful fulfilling lives, free from insecurity and violent conflict. They work directly (and through local partners) with communities affected by instability and conflict to enable them to articulate their safety concerns and improve their sense of security. They challenge national and international actors to listen to the views and priorities of those living with insecurity, and seek to influence and support civil society, governments and international agencies to respond in a sensitive and accountable fashion. They document lessons from their work, and the work of others, and gather evidence to inform policy and practice.

## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment
Saferworld’s numerical outcome indicators have all been significantly exceeded. 95 community action groups (27 new ones this year) have been trained, who implemented 86 community security action plans. 211 CSOs have been trained in 10 countries, many of whom are accompanied or mentored regularly, to influence authorities. 31 authorities, 9 at national and 22 at subnational level, in 8 countries, have developed or implemented new approaches/policies in part as a result of SW and partners’ technical input. 34 external actors have taken up SW and partners’ recommendations, at least 14 of which have a global impact. Five SW country programmes have included gender analysis in their planning. There are qualitative examples of outcomes being achieved including enhancing legislation on policing in Kyrgyzstan, improving police accountability in Kenya, enabling women to report security concerns in Yemen and including security issues in the Sustainable Development Goals. The challenge is that a number of the outcome and output indicators are similar. For example, Outcome indicator 1 - the number of community groups that have the capacity to act to address security issues - would arguably be more appropriate as an output indicator with the Outcome indicator focusing on the improvements in security these groups have brought about, or the percentage of issues in community safety plans that have been implemented by citizens and local authorities. SW’s achievements in improving conflict and security outcomes do not always come through clearly in reporting. The way in which the logframe is structured around stakeholders rather than issues seems to inhibit this.

Overall output score and description

A+ Outputs moderately exceeded expectation: Saferworld is perfoming very well at the output level and has significantly exceeded all targets in the logframe.

Key Lessons

Saferworld conducted three evaluations this year which identified important lessons:
1. SW’s work on the Arms Trade Treaty (ATT) since 1993/4 highlighted the importance of: (i) a consistent strategic organisational commitment to the issue, (ii) access to flexible funding to ensure consistent financial support, (iii) trusted expertise and long-term commitment of staff, (iv) coherent programming that links multiple entry points at different levels of policy-making, and (v) continued engagement with the issue after ratification of the treaty.
2. SW’s partnership with the Kosovo NGO Forum for Civic Initiatives showed the importance of long-term mentoring and support, and the trust required for sustainable capacity-building.
3. SW’s work on police reform in Kenya highlighted the value of combining work to influence national policy with civil society capacity building and local community security work. It also identified the importance of a scaling up strategy for community work and clarifying if this is primarily intended as a pilot to prove a concept for others to mainstream and replicate, or if the main aim is to improve local safety in those areas.

Key actions

1. Saferworld should consider if the logframe as currently structured helps to convey the outcomes of their work and if it should be revised. There are understandable reasons not to change it at this stage in the PPA cycle and there would be transaction costs for both SW and DFID. However, the risk of not changing it is that the outcomes of their work may not be fully reflected in next year’s Project Completion Report (PCR). The important investment in outcome harvesting is giving SW the information to improve outcome reporting. Now is the last opportunity in the PPA cycle to change logframe indicators. It would make sense to align logframe indicators to the strategic objectives in SW’s Strategic Plan 2014-17.
2. Quantitative targets in the logframe should not be increased for 2015-16. A focus on increasing targets year on year risks encouraging a focus on the numbers of groups formed rather than on what these groups do. The focus for 2015-16 should be firmly on the qualitative aspects of Saferworld’s work and ensuring that outputs help to deliver outcomes. Some of the quantitative targets could be re-focused to improve their quality.
3. Saferworld should continue to develop ToCs for all its focus countries that make explicit the theory for the community security work. These should include a greater focus on engaging sub-national authorities, influencing state planning processes and developing partnerships for scaling up.
4. Saferworld considers engaging in the public health approach to violence prevention as a natural extension of its gender and community security work.
5. Saferworld considers how the outcomes identified through its work on outcome harvesting can be clearly communicated to DFID against the conflict and security objectives in its strategic plan to feed into next year’s Project Completion Report.
6. Saferworld should continue to be proactive in harvesting good VFM indicators and feeding these back to DFID. With increased scrutiny on the aid budget and security and justice work this is more important than ever.
7. Saferworld should consider if further strategic benefit could be got from some of its partnerships, particularly in its community security work.

Has the logframe been updated since the last review?

No. Not since the last review with PPA managers in October 2014.

## C. DETAILED OUTPUT SCORING : DETAILED OUTPUT SCORING
Output Title	SW and local partners provide support to community members in identifying and addressing their community security and justice needs in collaboration with local authorities (Y2011-2014 in Caucasus, Kenya, Kyrgyzstan/Tajikistan, Nepal, Pakistan and South Sudan; 2014-2016 in Bangladesh, Caucasus, Kyrgyzstan/Tajikistan, Nepal, South Sudan and Yemen)
Output number per LF		1	Output Score	A++
Risk:		Medium	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress	Disagggregated data
1.1: Number of action-oriented community groups formed (and continually supported) by members of conflict-affected communities - with SW support - through which communities can identify their security related needs and priorities, and develop a shared purpose and vision for change (see notes below)	15 action-oriented community groups formed	27 action-oriented community groups newly formed	Total number of women (all groups) / 465	Total number of men (all groups) / 1514
			Country	Newly formed
			Kyrgyzstan/Tajikistan	4
			Nepal	15
			South Sudan	8
1.2: Number of groups that successfully implement community security action plans, in dialogue with authorities, with support from SW and partners	30 groups successfully implement plans	86 groups successfully implement plans	Country	Action plans
			Caucasus	10
			Kenya	7
			Kyrgyzstan/Tajikistan	9
			Nepal	15
			Bangladesh	16
			South Sudan	28
			Yemen	1

Key Points
The numbers of community action groups both newly formed and implementing community security action plans far exceeds the milestones (almost 2x and 3x respectively). There are numerous examples of the achievements of these groups given in the self-assessment report and in interviews with staff. The community security handbook was cited by country staff as being very helpful. For example, the evaluation of SW’s policing work in Kenya showed that due to the establishment of Community Safety Forums 100% of community respondents in the pilot communities said they felt safer in their local areas. Inter-communal conflicts have been successfully mediated by local groups in Nepal and South Sudan.

The indicator used is not high quality. It focuses on the number of groups formed but without having a sense of the population size and geographical area covered by the groups it is hard to determine the value of this. Also, in many contexts community governance mechanisms and sub-national development plans will already exist and it may be more sustainable to work to integrate citizens’ security issues into these than form new parallel groups or plans.

The community security work gives SW credibility as an actor in target countries by giving them insights into local security challenges and barriers to reform. This provides evidence for advocacy and an opportunity to test new approaches to enhancing security. However, the level at which the community security work is targeted and the linkages community groups have with state actors seems to vary considerably between countries. Saferworld is developing country-level ToCs which is welcome as in some countries the ToC for this area of work should be made more explicit. For example, the Kenya policing evaluation is very complimentary about Saferworld’s work and achievements but highlights that in terms of coverage Saferworld was working in 2.85% of the police stations nationwide. It also questions whether the target sites were intended as pilots to test approaches for replicating and scaling up, or as projects in their own right to improve the security situation in that specific location.

Recommendation: Saferworld continues to develop explicit national ToCs for all its focus countries that place greater emphasis in its community security work on influencing sub-national authority planning processes, integrating security issues into these rather then developing SW-specific project plans. The continued development of partnerships with local and national authorities, donors and NGOs will be critical to scaling up.

Output Title	In Bangladesh, Kenya, Kosovo, Kyrgyzstan/Tajikistan, Nepal, Pakistan, Somalia, Sudan, South Sudan and Yemen, local civil society organisations receive support from SW to develop the skills and capacities required to play an effective role in addressing conflict-related issues in their contexts.
Output number per LF		2	Output Score	A++
Risk:		Medium	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

The numbers of CSOs trained and mentored on advocacy and community engagement far exceeds milestone targets (almost 3x and over 7x respectively). This indicator has a qualitative element to it which is welcome. SW measures this through beneficiary feedback and tracking the skills learnt, uptake and use of information, and changes in relationship between actors in-country as a result. This is excellent practice but again highlights the similarity between output and outcome indicators (the Outcome 2 indicator is the number of NGOs that have increased capacity). There is evidence of capacity building support having contributed to partner organisations and networks achieving results, for example legislative change in Kyrgyzstan. Saferworld also reports that in Yemen, members of youth partner organisations have not become involved in the conflict which might indicate a possible increased resilience as a result of engagement. There is also evidence in Yemen and Pakistan of the sustainability of capacity building support as local community organisations have continued to function in the absence of direct support.

A noticeable trend is that the political space for civil society organisations is significantly closing in a number of countries where SW works. SW is responding well to this by finding innovative solutions such as supporting networks (to prevent individual organisations being picked upon), increasing transparency and linkages with government officials to help increase trust, and where necessary moving from local programming to advocacy. Saferworld’s presence can help increase the space for local civil society to operate and provide some protection and solidarity. This is a good example of the benefit of PPAs to INGOs working on conflict/S&J.

Indicator(s)	Milestones	Progress	Disagggregated data
2.1: Number of local CSOs that receive targeted and tailor-made high-quality training / capacity-building from SW on how to effectively advocate for improved approaches and / or greater accountability from authorities and policymakers, building on the view of their constituents (in Kyrgyzstan/Tajikistan, Kenya, Kosovo, Somalia, Sudan and Yemen)	High quality, tailor-made training / capacity-building provided to 23 CSOs	64 CSOs provided with high-quality training	Country	Numbers
			Kyrgyzstan/Tajikistan	4
			Sudan	21
			Somalia	3
			Egypt	31
			Uganda	5
			Kenya	3
2.2: Number of local CSOs that receive training and mentoring from SW on how to support communities to identify and address their conflict / security related needs and problems (in Bangladesh, Kyrgyzstan/Tajikistan, Nepal, Pakistan, South Sudan and Yemen)	20 CSOs have received training and mentoring from SW	147 CSOs have received training and mentoring from SW	Country	Numbers
			Kyrgyzstan/Tajikistan	23
			Pakistan	85
			Bangladesh	4
			South Sudan	8
			Caucasus	9
			Nepal	12
			Egypt	6

Output Title	National and/or subnational authorities receive support from SW and partners to assist them in developing effective policies and practical approaches for building peace, justice and security
Output number per LF		3	Output Score	A+
Risk:		Medium	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress	Disagggregated data
3.1: Number of formal / informal governing authorities that receive quality technical input and/or support from SW and partners at the national level, in the development of new policies and practices related to conflict prevention and security and justice (including but not limited to: Caucasus, Kenya, Kosovo, Kyrgyzstan/Tajikistan, South Sudan, Uganda and Yemen)	SW has provided quality technical input and/or support to 6 authorities at the national level	9	Country	Numbers
			Kyrgyzstan/Tajikistan	5
			Yemen	1
			Caucasus	1
			Kenya	1
			South Sudan	1
3.2: Number of formal / informal governing authorities that receive quality technical input and/or support from SW and partners at the sub-national level in the development of new policies and practices related to conflict prevention and security and justice (including but not limited to: Bangladesh, Caucasus, Kenya, Kyrgyzstan/Tajikistan, South Sudan, Uganda and Yemen)	SW has provided quality technical input and/or support to 14 authorities at the subnational level	22	Country	Numbers
			Kyrgyzstan/Tajikistan	3
			Bangladesh	10
			South Sudan	1
			Caucasus	2
			Kenya	1
			Uganda	3
			Somalia 5	2

Key points
Saferworld has a strong track record in influencing change in policy and practice. The milestone targets of national and sub-national governing authorities that have received input and support from SW has been exceeded by 50% at both levels. Most progress seems to have been made on policing issues. Examples include the piloting of a new reporting mechanism on crimes against women in Yemen, in which referrals are made from the Ministry of Human Rights to the Ministry of Interior and an increase in reporting from police stations to the women’s department at the MoHR. This led on from two workshops that Saferworld held in late 2014 on gender and conflict with the MoHR and MoI. Prior to this there was no formal relationship between MoHR and these police stations. In Kenya, SW’s support has helped to enhance accountability for policing. For example the Case Intake Committee recommended that of 610 cases in the first half of 2014, 125 be referred to the Police Internal Affairs Unit and 66 be referred to the National Police Service Commission.

Output Title	External actors (incl. donors, external governments, and / or relevant multilateral agencies) receive SW analysis, policy options and training aimed at influencing and strengthening their policies and approaches for engaging in fragile and conflict-affected countries
Output number per LF		4	Output Score	A+
Risk:		Medium	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress	Disagggregated data
4.1: Number and quality of research papers and policy briefings / reports published or electronically circulated by SW and disseminated to external actors	42 briefings, papers / reports have been published or electronically circulated	64	Thematic area		Numbers
			Arms Control (4), Rising Powers (18), Security and justice (8), Gender (7), Conflict sensitivity (27)
4.2: Number of external actors (disaggregated by gender) receiving relevant, high quality training from SW, or participate in relevant and productive SW-facilitated seminars / roundtables, on engagement in fragile and conflict-affected countries	1,850 external actors have received training or participated in SW-facilitated seminars / roundtables	1632	Thematic area	Numbers
				Total		Men	Women
			Security and justice	245		214	92
			Gender	251		189	61
			Conflict sensitivity	287		215	72
			Rising Powers	302		200	102
			China	307		231	76
			Arms Control	240		165	75
4.3: Number and quality of products (including briefings and submissions) provided to the UK Government by SW, which build on evidence and lessons learned from SW programme implementation	The UK Government has received 6 products building on evidence and lessons learnt from SW's programming	14 including briefings, for example on ‘Beyond Aid’, the Conflict, Stability and Security Fund, and the role of security and justice sector reform in addressing sexual and gender-based violence.

Key points
The milestone target number of research reports and briefings has been exceeded by 50%. The number of products provided to the UK government was exceeded by over 100%. Saferworld’s policy and advocacy work on the ATT and SDGs appears to have been highly effective and had a significant impact on international agreements. There appear strong two-way connections between country programmes and policy/advocacy with the former providing evidence for the latter and the latter providing new thinking and technical support to the former.

The work on gender issues has been welcomed by country and regional teams and opens up a potentially new area of work for SW: moving from addressing conflict and violence issues through processes (e.g. enhancing state-society relations and civil society capacity building) to dealing directly with perpetrators and victims. This is an important organisational development. Consideration should be given as to whether this necessitates the development of new partnerships or the development of new in-house capacity. There may be useful lessons to learns from other organisations that combine capacity-building with case work and advocacy (e.g. those combining legal aid and advocacy like Advocats Sans Frontiers and the International Centre for Transitional Justice).

Recommendation: Saferworld considers engaging in the public health approach to violence prevention as a natural extension of its gender and community security work. This focuses on identifying and addressing the factors that make communities and individuals at risk to becoming perpetrators and victims of violence and may help to enhance the focus of community security plans.

Output Title	SW incorporates new elements into its Monitoring Evaluation and Learning (MEL) system including an Outcome Mapping, Monitoring and Harvesting approach and trials a more systematised beneficiary feedback mechanism
Output number per LF		5	Output Score	A+
Risk:		Medium	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
5.1: Number of teams collecting and reviewing outcomes on a quarterly basis	50% of SW teams are collecting and reviewing outcomes on a quarterly basis	70% on a bi-or tri-annual basis
5.2: The number of partners and community action groups that participate in setting outcomes for their work and provide feedback on the changes they are seeing as a result of working with Saferworld.	At least 12 community action groups are participating in setting outcomes for their work, monitoring them and reporting on them.	89 groups participate in setting outcomes and monitor them
		Country	Number
		C Asia	19
		Nepal	15
		Kenya	7
		South Sudan	27
		Caucasus	5
		Bangladesh	16

Key points
Saferworld has done significant work on strengthening institutional systems (e.g. financial management, human resources and M&E) under the PPA but this indicator only focuses on the M&E aspect. As currently structured, the logframe does not capture some significant work that SW has done which should help enhance programme outcomes. There also appears a disconnect between Output 5 (M&E) and Outcome 5 which focuses on integrating gender analysis into country programmes. The other outputs and outcomes are directly related.

The work on outcome harvesting (a M&E approach that identifies what has changed and whether and how an intervention has contributed to this) seems to be having a positive impact on the way in which country programmes identify desired outcomes, collect evidence of progress and use this to review strategies to achieve outcomes. Teams must do this minimally twice a year, before biannual reports are written. 70% of teams in Saferworld conducted full outcome harvesting sessions that fed into staff learning (Community Security Learning and Practice Group), programme reviews (MTR on Community Security Programme in South Sudan, Yemen and Bangladesh), and evaluations (Kenya, Sudan). Outcome harvesting is being implemented in a participatory way with partner organisations which is having benefits. To support this effort, Saferworld has recruited two MEL staff in Kenya and South Sudan, and has dedicated focal points in all teams.

Saferworld is ahead of many organisations in its adoption of outcome harvesting as a valuable MEL methodology. The challenge now is to ensure that this internal work translates into improved external reporting on outcomes. The full benefit of this investment is not yet being communicated to DFID.

Recommendation: Saferworld considers the benefit of broadening output and outcome 5 to focus on organisational development. Saferworld also considers how the outcomes identified through the outcome harvesting work can be clearly communicated to DFID against the conflict and security objectives in its strategic plan to feed into next year’s Project Completion Report.

Summary of responses to issues raised in previous annual reviews (where relevant)
The 2013-14 Annual Review’s recommendations focused on articulating the qualitative aspects of SW’s work and the need to clearly explain the outcomes of the work done under each of the five outputs. This echoes similar comments in previous annual reviews. Some progress has been made on this in the 2014-15 self-assessment report which does include examples of changes as a result of SW’s work. But the reporting sometimes feels like a long list of individual achievements without always a clear sense of whether these are more than the sum of its parts. The extent to which combined work on different outputs in a country contributes to outcomes does also not come across clearly in reporting. The way in which the logframe is structured around stakeholders rather than issues seems to encourage this.

Recommendations have also been made to increase numerical logframe targets year on year. This has been done and Saferworld has comfortably exceeded these successively. The view of this reviewer is that increasing the number of targets may be counter-productive though, as it could encourage a focus on numbers whilst the overall drive should be to focus more on outcomes. There is one previous recommendation which does not appear to have been actioned which is to test the extent to which the community-based approaches to security advocated by Saferworld have strengthened communities and made them more resilient to broader conflict and insecurity.

Recommendations
Saferworld should consider if the logframe as currently structured helps to convey the outcomes of their work and if it should be revised. There are understandable reasons not to change it at this stage in the PPA cycle and there would be transaction costs for both SW and DFID. However, the risk of not changing it is that the outcomes of their work may not be fully reflected in next year’s Project Completion Report (PCR). The important investment in outcome harvesting is giving SW the information to improve outcome reporting. Now is the last opportunity in the PPA cycle to change logframe indicators. It would make sense to align logframe indicators to the strategic objectives in SW’s Strategic Plan 2014-17.

Quantitative targets in the logframe should not be increased for 2015-16. A focus on increasing targets year on year risks encouraging a focus on the numbers of groups formed rather than on what these groups do. The focus for 2015-16 should be firmly on the qualitative aspects of Saferworld’s work and ensuring that outputs help to deliver outcomes.

Saferworld should continue to develop theories of change (ToCs) for all its focus countries that make explicit the theory for the community security work. These should include a greater focus on engaging sub-national authorities, influencing state planning processes and developing partnerships for scaling up.

Saferworld considers engaging in the public health approach to violence prevention as a natural extension of its gender and community security work.

Saferworld considers the benefit of broadening output and outcome 5 to focus on organisational development, and how the outcomes identified through its work on outcome harvesting can be clearly communicated to DFID against the conflict and security objectives in its strategic plan to feed into next year’s Project Completion Report.

Saferworld should continue to be proactive in harvesting good VFM indicators and feeding these back to DFID.

Saferworld should consider if further strategic benefit could be got from some of its partnerships, particularly in its community security work.

## D: VALUE FOR MONEY &FINANCIAL PERFORMANCE
Date of last narrative financial report	1.7.14
Date of last audited annual statement	October 2014 (2014/15 statements audited and signed off in October 2015)

Key cost drivers and performance

Saferworld staff demonstrate a good awareness of cost drivers and the new financial management system (funded through PPA resources) is helping track expenditure more systematically . Their main driver is staff costs and by working through partners (especially in Sudan) SW has reduced its proportion of staff costs from 43% in 2013/14 to 38% last year. Core costs drivers remain, with the following breakdown: Staff costs are £4.72m, 38% of total costs (2013/14: £3.85m, 43%), accommodation and meeting hire costs are £1.40m, 11% of total costs (2013/14: £0.83m, 9%), travel costs are £0.85m, 7% of total costs (2013/14: £0.60m, 7%), per diems for staff, partners and programme participants are £0.72m, 6% of total costs (2013/14: £.5m, 6%), and consultants are £0.48m, 4% of total costs (2013/14: £0.34m, 4%). The total value of costs shown above is 67% of total costs (2013-14 was at 70%) of the total. Staff costs as a prominent driver are closely monitored by: (i) having a performance management system to support effectiveness and efficiency, and (ii) conducting annual reviews of salaries in all countries by:
1. assessing financial and salary conditions and local inflation to review payscales, and
2. an annual Board-level review of proposals for recruitment in each country that is based on local market conditions,
SW’s travel costs (second largest cost driver) are largely paid via two London-based preferred suppliers. Both suppliers are reviewed annually.

VfM performance compared to the original VfM proposition in the business case
DFID’s original business case proposes three reasons why SW is considered value for money: (i) SW’s theory of change is aligned with its results framework, (ii) SW scale up impact through influencing approaches and leveraging resources, and (iii) PPA investment will enable SW to significantly increase the scale and breadth of its impact. All three conditions are still being met. The evaluation of the ATT work shows the significant impact of SW’s policy work using a VFM lens from a fairly modest financial investment c.£1million over a 20 year period. The work on Goal 16 of the SDGs also shows SW helping to leverage policy change for fairly small cost. Organisationally, Saferworld has used PPA funding strategically as a pump primer to attract project funds from other donors.

Assessment of whether the programme continues to represent value for money
The programme continues to represent VFM and Saferworld is making ongoing efforts to demonstrate this through (i) tracking key cost drivers, (ii) integrating a VFM lens into evaluations, and (iii) introducing a new financial management system to better track finances. An organisational commitment to invest PPA funds to fill a funding gap in South Sudan in 2012 has resulted in attracting new donor funds and scaling up of operations from 12 community groups in 2013/14 to 28 in 2014/15. VFM approaches can also be seen in how the largest development organisation in the world – BRAC – has started using Saferworld’s M&E and conflict sensitive programming.

Recommendation: Saferworld should continue to be proactive in harvesting good VFM indicators and feeding these back to DFID.

Quality of financial management

Financial management remains on track in terms of forecasts. Saferworld have provided satisfactory financial reporting and annual audited statements. The Finance Director reports to the Board on the performance of the organisation against budget. An annual budget is approved by the Board in April each year and formally updated twice a year. All management staff review monthly financial data and explain their performance to their teams, line managers and the finance department.The UK audit of the SW charity covers all entities around the world and, by value, around 75% of donor funding also receives project audits. Financial management capacity has improved during the year with the development of a new world-wide finance performance system (implemented to plan and budget in time for 2015-16 FY).

E: RISK

Overall risk rating
Low	Medium	High
	M

Overview of programme risk

The overall level of programme risk is still judged to be medium although the level of risk has increased in certain countries such as Yemen where there is active civil war. It has also increased on certain issues such as civil society capacity building with a reduction in political space in many countries and regions where Saferworld is working (e.g. East Africa, Middle East, Central Asia and South Asia). This should continue to be carefully monitored.

Saferworld demonstrates an excellent understanding of risks and its risk management approach has been consistently strengthened to respond to changing risks in its focus countries. For example, maintaining work in Yemen is an achievement in the current context. In Bangladesh, weekly political/security updates are sent to London. The Kenya policing evaluation highlighted the iterative and adaptive style of programming in response to the changing political and security context. In South Sudan, SW has reviewed its engagement with the South Sudan Police Service in the wake of reports of human rights abuses and developed a considered strategy to adapt its approach. There are regional (and where relevant country) risk management teams in place with a revised set of Standard Operating Procedures. SW’s OSJA is regularly updated with the latest review completed in June 2015 and it appears comprehensive and up to date, capturing risk assessment for an HMG audience. SW also mainstreams risk assessments during strategic planning processes at the country-level. These risks are reviewed quarterly, with more substantial risks addressed at the head office in London.

Outstanding actions from risk assessment

There are no outstanding actions.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe
Saferworld is on target to and has already met most of the targets set in the logframe. The emphasis in the remaining period should be on evidencing qualitative outcomes.

Performance of partnerships
Partnerships are crucial to the delivery, impact and sustainability of Saferworld’s work. Saferworld has developed strong and effective partnerships at different levels (international, national and local) which have helped achieve its results. Saferworld has a strong relationship with DFID overall but there are aspects which could be strengthened. For example, by DFID improving the coordination between centrally-managed programmes and country offices.

Recommendation: Saferworld should consider if further strategic benefit could be got from some of these partnerships, particularly in its community security work. For example, it has developed an effective partnership with BRAC in Bangladesh but could this now be extended to BRAC’s work in other countries? Saferworld reports that the community security handbook is being used as a training resource by UNDP, the Netherlands, Conciliation Resources and Danish Demining Group. Could partnerships now be developed to jointly implement community security work in target countries?

BRAC – a huge organisation in Bangladesh - have adopted our M&E and conflict-sensitivity approaches; our influence therefore reaches beyond specific projects where we partner with them. Our partnership with CAMP (Pakistan) provides access to local CSOs and communities in areas where it is extremely difficult to bring about change directly. Our work to influence national authorities, including police, is undertaken alongside local networks such as Civic Union in Kyrgyzstan and Usulama in Kenya. This ensures our approach and recommendations are relevant and have strong potential for sustainability. At the global level, we collaborate with INGOs, donors and multilaterals, thereby increasing the weight of our influence within high level processes such as the ATT and post-2015 SDG development.

Asset monitoring and control

As part of standard financial management, London and local accounting staff monitor the use of fixed assets, working capital and cash. Saferworld has few fixed assets due to the nature of its work. All environments hold fixed asset registers and additional controls for the type of assets, e.g. mileage logs for vehicles. Working capital balances comprise largely partner balances which are monitored monthly and regularly reconciled. SW policy is to pay partners monthly and further advances are contingent upon adequate financial reporting. Only experienced partners who have demonstrated good financial management receive flexibility in this approach.

G: CONDITIONALITY

Update on partnership principles (if relevant)

The partnership principles have not been updated in the review period.

H: MONITORING & EVALUATION

Evidence and evaluation

SW has a specific output (5) on MEL (see above) and demonstrates an impressive commitment to organisational learning. This year, it piloted a bespoke Programme Review and Improvement process (PRIMP), the first of five scheduled over three years, reviewing its work in Kosovo/ Western Balkans. A 20 year retrospective of SW’s policy, advocacy and programming work on the ATT was conducted. A Mid-Term Review of community security in South Sudan, Yemen and Bangladesh, and an evaluation of police reform in Kenya were also undertaken and provide significant evidence and learning for Phase 2 of each project.

Saferworld’s investment in outcome harvesting and training of staff to implement this approach is sound and should help to improve programme effectiveness and reporting on outcomes.

Monitoring progress throughout the review period

This Annual Review was drafted by a Senior Security and Justice Adviser from the Stabilisation Unit, drawing on Saferworld’s self-assessment report, interviews with SW and DFID staff in headquarters and country offices, and a review of relevant documentation. A draft of the report was shared with SW, DFID and SU for comment and then a revised version produced.

SW uses its intranet, Karacel, with a linked project database, monitoring data, reports on all outcomes and activities, and input data used for biannual reporting, to produce bespoke reports filtered by programme, actor category, and donor. There is a new area covering all its work at community level, which reportedly enables reports on specific communities, including regular perception data. A publication quality review process for randomly selected publications was piloted across several categories, using external reviewers. Each team undertakes a 6-monthly outcome harvesting session, to assess the changes in practice, behaviour and relationships between key target actors, which feeds into the biannual reports and outcome documentation on Karacel. Activity reporting, disaggregated by actor and gender, links to organisational performance indicators, agreed across the organisation during the year. How-To Guides produced this year include: Evaluation ToRs, Outcome Harvesting for Teams and Partners.

I: DISABILITY

Does your organisation consider disability in it’s policies and programmes: Y/N. If yes, please outline your approach

Yes. Saferworld makes an organisational commitment to equal opportunities, including disability rights in the Global Handbook (sections 2 and 3). Saferworld works with vulnerable communities in fragile and conflict-affected states according to the equity principle, including all who are fundamentally vulnerable.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessmen
Key points
Summary of response to iprogrammessues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process