Annual Review – September 2019

Title: Accelerated Reform Facility (ARF)
Programme Value £ (full life): £ 15m		Review Date: 30 September 2019
Programme Code: 203601	Start Date: 16 August 2012	End Date: 31 December 2020

Summary of Programme Performance
Year	2013	2014	2015	2016	2017	2018	2019
Programme Score	A	A	A	A	A	A	B
Risk Rating	Low	Low	Medium	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-203601/documents
DevTracker Link to Log frame:	The revised logframe will be reflected in the DevTracker in a few weeks.

A. Summary and Overview (1-2 pages)

Description of programme (1/2 page)

The DFID Myanmar’s Accelerated Reform Facility (ARF) was set up to provide up to £5 million between September 2012 and April 2014 for DFID Myanmar to respond quickly to opportunities, created by the reform process, to support interventions that catalyse, foster and deepen reform in Myanmar.

The ARF has been extended several times. In 2014 the Minister of State (MoS) approved (Vault no 4322226) a further £10m and extended the ARF until the end of the December 2016 based on the success of the initiatives funded under the ARF and the further opening of reform space, particularly in relation to the peace process. In 2016, the DFID Myanmar Head of the Office approved an extension of the project on a no-cost basis to the end of 2020. In July 2016, the MoS approved the reallocation of £5m earmarked in the 2014 extension for supporting the peace process for use under any of the ARF’s focus areas (EDRM 5514046). In November 2017, a new approval processes for the ARF projects was agreed which provided delegated authority back to the Head of Office (It was agreed in July 2016 that Ministers would approve them initially) as decisions on small, opportunistic spending were best made at the country level.

The ARF was established to focus on six strategic pillars to create a better governed, more peaceful & prosperous Myanmar that uses its increased wealth to reduce poverty. Project bids under ARF should not duplicate wider programmes DFID implements. They must focus on strategy, policy, influencing and donor/aid effectiveness, complementing the wider DFID Myanmar portfolio with the ability to respond swiftly to opportunities and challenges. Specific interventions for support under these six themes are based on a set of policy and strategic criteria.

The six strategic pillars of the ARF are:

1. Good governance and public financial management
2. Promoting responsible investment
3. Improving transparency, accountability and the rule of law
4. Strengthening the work of Parliament
5. Helping the process of ethnic reconciliation
6. Better coordination and aid effectiveness

Following the Rakhine crisis of 2017, the use of the Fund has been reviewed and updated. We recognise that Myanmar’s transition is not straightforward and that we need to be realistic about opportunities for change – but that nonetheless opportunities do exist. The overall ARF results framework was reviewed in April 2018 to respond to the four shifts in the overall portfolio. This has meant placing a stronger focus on inclusion, the needs of displaced people and those affected by conflict and engaging with government on the needs of the most vulnerable. The use of the ARF is aligned with the Smart Rules and the Gender Equality Act 2014.

A further review of the ARF will be carried out following the completion of the new DFID Myanmar business plan and theory of change (expected end 2019/20). This will ensure the ARF programme remains relevant and appropriate, is sufficiently flexible to respond swiftly to the changing context and includes a stronger focus on deepening our knowledge and understanding.

This annual review only assesses performance of the outputs and indicators that were live this year (see Annex 1). These are better governance and public financial management, helping the process of ethnic reconciliation, and better donor coordination and aid effectiveness.

Summary supporting narrative for the overall score in this review (1/2 page)

The overall output score is B (Output moderately did not meet expectation). The ARF continues to be an effective vehicle for supporting change in Myanmar and for working with key reformers. It has played a useful role in piloting successful strategic and policy interventions that are low-cost but high-impact. Some of interventions have also evolved into larger sectoral support, notably the earlier English for Education College Trainers project which provided the basis for DFID’s new nationwide education programme, and the Project Management of Restoration and Reinvigoration of Rangoon General Hospital and Transforming Medical Education” (RGHT) which built the foundations for the transition to DFID Myanmar’s new Access to Health programme. The additional value add for DFID has been the RGHT’s capacity to influence and foster space for strategic engagement with the government authorities including Myanmar State Counsellor, Aung Sang Sui Kyi.

In this reporting cycle, the Rakhine strategic engagement fund has helped to provide entry points for policy dialogues and influence with local stakeholders. DFID has provided support to all communities in Rakhine State through our aid programmes. However, there remains a perception among ethnic Rakhine that little is being done for them. The international community including the UK has been poor at engaging with the ethnic Rakhine population and has done little to counter this narrative. This is risky for our development portfolio and our operations in Rakhine. The strategic engagement fund was designed to help us engage with a broader range of stakeholders in Rakhine, working in a coherent manner with our larger programme interventions to provide visible, swift, low cost - quick impact projects in response to needs identified by communities. The fund has implemented timely small-scale projects in response to the Rakhine crisis. For example, funding was used for small scale infrastructure to promote education and provide improved water and sanitation for girls in monastic schools. These projects were responsive to needs expressed by the Rakhine community around Sittwe.

Through support to the Rangoon General Hospital implemented by the Rangoon General Hospital Trust (RGHT), a UK based charity with the Rangoon Hospital authorities, the ARF has provided an entry point to work on the health system reform in Myanmar. Since the last Annual Review, the ARF successfully concluded the 1st phase of support. The RGHT delivered a masterplan for the Hospital and presented it to Myanmar’s Minister for Health and Sport, U Myint Htwe. The masterplan has recommended critical implementation proposals to make the hospital building safe that DFID is considering funding and aspects of the masterplan is being implemented. RGHT is reshaping the landscape of Myanmar medical education (e.g. the University of Medicine has reformed its medical curriculum, helped to generate a cadre of human resources for health, and guaranteed that essential infrastructure is present in which to teach such a programme). This was made possible by the project bringing key British health sector expertise to deliver substantive and lasting change. The project is continuing to build stronger relationships between the UK and Myanmar.

DFID Nay Pyi Taw Liaison Office has been critical in expanding UK’s understanding of government and parliament, and fostering closer engagement with the government departments DFID supports through our wider portfolio and programming. It has also begun to strengthen donor coordination, which is still someway from being fully effective. Further direct engagement at NPT will be needed across donors as they and the UK plan to slowly move to the new capital over the coming years.

The ARF has also provided a financial contribution to the Cooperation Partners Group (CPG) this year to enhance donor co-ordination. The CPG was established in July 2016 as the main coordination mechanism for international development partners operating in Myanmar with over 80-member agencies. UK support allows the CPG to act on its mandate to enhance effective development cooperation in Myanmar in collaboration with multiple stakeholders including government, civil society, INGOs, academia and the private sector.

The CPG is supported by a Secretariat which is hosted administratively by UNDP and which performs various roles to support strategic priorities determined by the CPG including by the CPG Facilitators and Alternate Facilitators, and by selected Cooperation Partners (CPs) who on a rotational basis guide and lead the collective endeavours of the CPG. DFID are Facilitators for the Rakhine State Development Work Stream and the Nexus Work Stream. A key result from this project has been the creation of a Communications Strategy for Rakhine which sits under the Secretariat and provides instrumental communication guidance in Rakhine to CPs. This is in line with the recommendations that have been set out by research and studies conducted on how the international community communicate with communities in Rakhine State.

At a time when the country is facing new and growing development, humanitarian and conflict challenges, ongoing additional strategic insights and coordination from the international community will be essential. We expect ARF programme of support to continue provide additional value for Myanmar, for DFID and wider development partners.

Recommendations for the year ahead (1/2 page)

Strategic:

A strategic review of the ARF approach is recommended to ensure that DFID continues to deliver strategic interventions and policy work through the ARF pillars and approach. Key components of the review will be to:
- Ensure that the pillars are still relevant and appropriate to current context and needs, and to recommend any changes that maybe required;
- Refresh the original logframe output indicators to ensure relevance of interventions and build in robust mechanisms to collect evidence under each output, with clear indicators being developed for any new interventions and a workplan;
- Determine whether, given the change in context, we should place a stronger focus on efforts to support learning for DFID and our national and international partners;
- Given the change in context from the time ARF was originally designed, refine the results framework and funding approach required to drive value for money;
- Ensure the criteria and consistent approach for approval is maintained by thematic leads drawing on the ARF funds so that the fund remains strategic and programme management complexity does not grow out of proportion;
- Consider and make a recommendation on where the programme best fits within DFID Myanmar.

The strategic review should also consider future funding options. There are 4 options: (i) the ARF BC could be extended beyond 2020 Dec for a further two years; (ii) it could be extended for a further 2 years with additional costs approved; (iii) it could be replaced with a new mechanism under a new BC; or (iv) it could be closed and not replaced. This will depend on the strategic direction and budget planning recommended above. If no additional cost is required, a time extension is needed in order to help ensure sustainable impact of the existing projects.

The ARF logframe must capture new activity indicators in a timely manner and set out a workplan. Without this it is hard to assess progress as highlighted for the CPG or the Rakhine areas of work. The team should work quickly with thematic leads and SMT to address this urgently as this is a cross-office programme.

Strengthen programme management and consistency for ARF and across the thematic pillars. The programme management suffered in this reporting cycle due to sudden changes of SRO midway – an interim SRO was designated on a temporary basis and there has not been consistent programme management capacity, with no support at present. The interim SRO has now initiated a recruitment for a new Programme Manager who is expected to quickly take on programme cycle management responsibilities.

Select fewer, but impactful activities that maximise VFM for the entire portfolio. It is also recommended that bids should include a risk matrix for project approval process to ensure the overall ARF risk framework is managed. These elements are even more critical as there are increasing bids on the ARF funding. In addition, it is essential that the DFIDM programme teams who draw on funding from ARF continue to comply with ARF funding criteria and SMART rules to ensure bids do not make the ARF too complex to manage.

Output Specific Recommendations:

Rangoon General Hospital Trust
The established relationship and trust between UK and Myanmar through RGHR program has taken significant effort and represents an opportunity to continue support to the hospital, RGH improvements, medical education reform, improving clinical practices as well as wider health system reform.

DFID Myanmar should continue to draw on the RGHT as a tool for supporting reformers and continue support implementation of master plan that plays a central part of the reform process of the Rangoon General Hospital and medical education in Myanmar. The last review recommended continuing DFID’s support to implement RGHT master plan recommendations and allow flexibility in the activities and outputs for which the funding is used, providing it continues to contribute to the overall outcome of the reinvigoration of the hospital. This recommendation remains appropriate.

There is a current gap in funding which has been covered by the RGHT from their own resources while DFID follows up with RGHT on the delays in the submission of the independent audit, and the response to the enhanced due diligence. DFID should continue to follow up with RGHT trustees for speedy conclusion of this issue. RGHT should commit to further strengthening of project management for the next phase of work, if DFID approves it.

Strategic Engagement in Rakhine
- This annual review notes that support for high visibility projects will stop, but recommends that continued assistance is needed to develop a more coherent and strategic stakeholder engagement plan and an influencing strategy for Rakhine (to be tasked and delivered by the Rakhine Working Group) which identified strategic entry points and opportunities, and looks to draw capacity from across the broader DFID portfolio. A working paper should be developed and agreed as soon as the annual review is approved.
- The engagement plan should build in evidence-based performance measurement. During this reporting cycle it was not possible to measure impact as we would have wanted. A key lesson is the need for a more coherent stakeholder engagement plan (this has now begun) and influencing strategy as well as a log frame refined to clearly set out what we wish to achieve and how we will measure success. It is very difficult to measure influence and how this affects changes in attitudes and policy, but a methodology is possible and necessary.
- It is important that the Rakhine Working Group is involved in any approach (including FCO to judge political risks). We need to be wary of a stop/start approach which could lose goodwill which will be difficult to get back. The review team recommends that the support to Rakhine is reviewed along with the overall strategy of the new business plan. Accordingly, logframe indicators to be refined with clear performance expectations and measurement approaches for future strategic funding.
Improved donor coordination
- Thematic leads to review impact of existing support and agree scaled up support to CPG and aid effectiveness for a more effective and sustained impactful outcome as soon as possible in co-ordination with other donors and the CPG Secretariat.
- A refinement to the logframe indicators or a more appropriate approach to reporting needs to be agreed for the Nay Pyi Taw Liason Office as soon as possible led by the thematic lead and SRO with the SMT and FCO based on the draft strategy developed. This should also fit with the review of the overall ARF approach.
Lessons

Strong programme management is critical to ensure that the ARF projects fit together as a strong portfolio. The programme team suffered due to change in the SRO midway through this year, and through constrained programme support. Quality assurance of the implementation of a cross office programme needs dedicated time to provide vision and direction.

The situation in Rakhine continues to be very complex and sensitive. The UK needs to continue to deepen its understanding of the issues and context while supporting the most vulnerable. It is extremely difficult to do this through a remote presence; DFID staff need to directly experience and understand the situation first hand in order to make the best informed decisions. Setting up a quick impact flexible fund under ARF provided an opportunity to swiftly respond to urgent and critical needs. Building on this foundation, going forward we expect interventions should be through our larger funding instruments and adhere to the Principles for Engagement in Rakhine (developed by DFID and adopted by the international community) in a more joined up manner.

More generally, management of small ARF projects can be time consuming and resource intensive, but benefits can outweigh the costs when projects are carefully selected. Value for money is gained by having DFID directly engage in critical areas where we need deeper understanding of context (e.g. Rakhine State which changes so rapidly), from creating platforms for larger scale work (e.g. work on health sector institutional linkages), and from filling critical gaps. However, if not planned well, and we don’t remain strategic with future interventions, we may end up with too many small projects that will increase complexity and programme management burden. Therefore, a timely, effective and strategic approach is recommended through wider office discussion on the appropriate use of the ARF going forward.

## B: DETAILED OUTPUT SCORING (suggest 1 page per output)

Output Title	Better Governance and Public Financial Management
Output number per LF		Output 1: 1.7	Output Score	B
Impact weighting (%):		68%	Impact weighting % revised since last AR?	Yes

Output Indicator: 1: 1.7	Progress
Rangoon General Hospital development Masterplan is agreed and implemented	Masterplan developed and agreed; key elements of the plan implemented.

Describe the output and provide supporting narrative for the score (1/2 page)

DFID started the current phase of the support to RGHR project since 01 June 2014 to Dec 2018. DFID partnered with RGHT through an Accountable Grant and provided the following support during this period:

Undergraduate Medical Education Situation Analysis
Supported an expert Professor Catherine D. DeAngelis to work with Ministry on Curriculum Blueprinting (26th Oct to 9th Nov 2018)

Visiting Professorship Programme
- Pathology Training and Laboratory Services Improvement Meeting (8th and 9th November 2018)
- Liaison psychiatry training was provided by Dr. Min Min Latt from UK on 28th Oct 2019

Ongoing implementation of Masterplan Recommendations
- Launched a programme to clean and survey sewage and surface water systems, the first step in a major renewal for improving utilities
- Completed a Safety Evaluation of the newly completed Cancer Care buildings. Presented guidance on fire safety for the whole site, and specific key buildings.
- Finalised a Brief for a new mortuary, repurposing existing heritage buildings to new functions.
- Proposed a new Management Team and submitted to the office of the State Counsellor and the Ministry of Health.

The key achievement has been the completion of the masterplan of the hospital. This plan has received support from the Minister and hospital authorities who are keen to support the implementation proposals although the output indicator of the masterplan to be also implemented in this period was over ambitious in the time-frame. Therefore overall the output scores as B.

The programme also made important progress on undergraduate education. RGHT assembled a team of international experts with a proven track record to continue the Undergraduate Medical Education Situation analysis, share skills and mentor a Burmese design team, and to provide further support for delivering medical expertise across the University and Hospital campus through the Visiting Professorship Programme. The RGHT team supported colleagues from the University of Medicine i) to unlock a national improved undergraduate medical education curriculum, the design of a new Skills Training simulation ii) Research Centre iii) and the delivery of a Visiting Professorship Programme to support clinical improvements while the broader work of the curriculum reform continues. This is delivering world class UK expertise to deliver on a strategic situation analysis that will unlock a curriculum and medical education reform process appropriate to the needs of Myanmar and its people. It will focus on University of Medicine 1 and its associated Hospital, which is the largest in the country.

As recommended in the 2018 AR, DFID has worked with RGHT to strengthen programme management, getting dedicated support from the UK to supplement the team in Yangon. RGHT has completed an independent audit, but DFID has not yet received the final report. The delay has been caused by the auditor needing to make additional detailed checks of rules and procedures as RGHT is registered under Jersey Law. The DFID Head of Office and SRO has raised the delay in audit submission with the Board of Trustees. In response to the delay, DFID has carried out an independent enhanced DD review to seek additional assurance from the RGHR Trustees. Recommendations from this enhanced DD review have been actioned. DFID has assessed that, on this basis, it has sufficient assurance to move forward with funding for phase II.

The political situation in Rakhine provided some concerns to British experts who were due to carry out technical visits to sites. This delayed some activities (e.g. International experts postponed their technical support visit to avoid travel risks to Myanmar - although RGHR doesn’t operate in Rakhine). DFID and RGHR colleagues intensified strategic engagement with British experts clearly communicating and messaging around the safety of project sites and working environment in Yangon helped RGHR colleagues to carry out planned activities without severe delay.

Lessons identified this year, and recommendations for the year ahead linked to this output. (1/2 page)

The established relationship and trust between UK and Myanmar through RGHR program has taken significant effort and represents an opportunity to continue to support to the hospital, RGH improvements, medical education reform, improving clinical practices as well as wider health system reform.

DFID Myanmar should continue to draw on the RGHT as a tool for supporting reformers and continue support implementation of master plan that plays a central part of the reform process of the Rangoon General Hospital and medical education in Myanmar.

There is a current gap in funding which has been covered by the RGHT from their own resources while DFID follows up with RGHT on the delays in the submission of the independent audit, and the response to the enhanced due diligence. DFID should continue to follow up with RGHT trustees for speedy completion of the audit process. RGHT should commit to further strengthening of project management for the next phase of work.

Output Title	Helping the process of ethnic reconciliation: increased understanding of key actors in Myanmar on the strategic stakes and the mechanisms by which peace and reconciliation can be negotiated.
Output number per LF		5	Output Score	B
Impact weighting (%):		19%	Impact weighting % revised since last AR?	N/A / (New)

Indicator(s)	Milestone(s) for this review	Progress
5.1. Key leaders from the main target groups to participate in senior leadership programs and exposure visits	N/A – too early	N/A will be reported next AR
5.2 Feedback from targeted leaders on how they value project research and see its relevance to upcoming policy decisions	N/A – too early	N/A will be reported next AR
5.3 Evidence of increased understanding of approaches to sectarian conflict during democratic transitions in an international context	Improved DFIDs relationship and by association the broader international humanitarian/ development community’s with local political stakeholders. / Deepened understanding for the work of the international community and that of DFID. / Key stakeholders more open to meet with DFID, as well as other donors, to discuss grievances giving us the opportunity to explain how our assistance is for all communities in needed and people affected by crises. / Space for open dialogue in the conflict context.	Met. This funding has begun to deepen our understanding of deep rooted complex context. / Some evidence that the engagement has increased access with the state government and stakeholders. Limited evidence of increased scope for open dialogue. / Projects responded to the need raised by the community and state government applying demand driven approach. / Systematic measurement planned to be in place.

Provide supporting narrative for the score

The complex situation in Rakhine was exacerbated by the 2012 violence which further intensified in 2017 when over 700,000 Rohingya fled to Bangladesh. The remaining Rohingya population believed to be 600 thousand are now either living in camps in central Rakhine or confined to their villages across the central and northern part of the state. DFID has provided support to all communities in Rakhine State through our aid programmes and spent approx. £20 million from DFID Myanmar’s annual budget of £100m on a range of interventions last FY. The vulnerable muslim populations became the focus of an international humanitarian effort which scaled up with a number of UN and INGO agencies providing much needed urgent humanitarian assistance. In addition the wider Rakhine population are also supported through our larger specific programmes. These interventions complement each other well in the field. However, there remains a perception among ethnic Rakhine that little is being done for them despite the fact that DFID’s development assistance is also targeted to the ethnic Rakhine population. This strand of work was intended to engage with a range of stakeholders in Rakhine using visible, swift, low cost - quick impact projects to counter the narrative that the international community does not listen to the requests of communities, and by doing so build understanding of the situation and stakeholder perspectives.

Under this workstream DFID held discussions with a wide range of stakeholders, such as INGOs, local government officials, parliament members, town elders, civil society and the public. In these engagements, discussions highlighted three priority areas of water, roads and solid waste management. This project is administered and implemented by DFID directly. The fund identified and implemented small scale activities. These have included the funding of classroom spaces, and water and sanitation activities. There is no formal limit to how much each project can, or should cost, but the fund is intended to work across a range of activities and so we have worked on the basis that each project should not cost more than £50,000.

This approach has complemented the longer-term funding provided by DFID in Rakhine State e.g. it is in line with the Principles of Engagement for Rakhine agreed by donors in Myanmar. It has not sought to replicate funding from larger instruments such as LIFT and the Access to Health Fund but to identify where there are gaps in support across a range of issues identified by communities.

In order to better show that the international community was supporting people across Rakhine, DFID funded the production of a communications strategy. This strategy is now being implemented on behalf of the wider international community via LIFT funding.

The following are the results to date:
- Strengthened engagement with the ethnic Rakhine population, proactively engaging with a number of local political stakeholders to discuss mutual beneficial projects that demonstrably show the international community’s endeavours to provide assistance to all communities across Rakhine.
- Implemented low cost, small but high visibility projects within the peri-urban area of Sittwe. This helped improve reach of health interventions; provided education support (e.g. materials for poor families); computer literacy, classroom, dormitory and sanitation block and adjoining water trestle construction (especially for girls).

The output is scored as a B as there is not robust evidence to make a judgement of the milestones set out in the M+E plan and the impact is also too early to judge as this requires longer timeframe.

In August 2019 DFID Myanmar Senior Management decided to complete support for the current round of high visibility projects, but not to fund further projects. This decision reflects our learning, high management costs of ensuring strong direct project management of a portfolio of small projects in a high-risk context. It also reflects the need to have a strong strategic framework to drive decision making on small projects.

Lessons identified this year, and recommendations for the year ahead linked to this output
The UK and the international community need to continue to deepen understanding of the issues and context, as we continue meaningful support to the most poor and vulnerable in Rakhine. In a fairly limited period of time, this project has improved our knowledge of the situation on the ground and allowed us to listen to the voices of communities to respond directly, quickly and effectively, which we would not otherwise get.
Having DFID funded staff resource in Rakhine on a permanent basis has led to not only a better understanding of the situation on the ground but also raised our profile with the UN, INGOs and others as additional value. This has also enabled us to influence the UN strategy. However, this presence has to be taken forward with correct risks analysis and risk mitigation approaches; and embed scale up or down approaches accordingly.
This annual review notes that support for high visibility projects will stop, but recommends that continued assistance is needed to develop a more coherent and strategic stakeholder engagement plan and an influencing strategy for Rakhine (to be tasked and delivered by the Rakhine Working Group) which identified strategic entry points and opportunities, and looks to draw capacity from across the broader DFID portfolio. A working paper should be developed and agreed as soon as the annual review is approved.
The engagement plan should build in evidence-based performance measurement. During this reporting cycle it was not possible to measure impact as we would have wanted. A key lesson is the need for a more coherent stakeholder engagement plan (this has now begun) and influencing strategy as well as a log frame refined to clearly set out what we wish to achieve and how we will measure success. It is very difficult to measure influence and how this affects changes in attitudes and policy, but a methodology is possible and necessary.
It is important that the Rakhine Working Group is involved in any approach (including FCO to judge political risks). We need to be wary of a stop/start approach which could lose goodwill which will be difficult to get back. The review team recommends that the support to Rakhine is reviewed along with the overall strategy of the new business plan. Accordingly logframe indicators to be refined with clear performance expectations and measurement approaches for future strategic funding.

Output Title	Better donor coordination and aid effectiveness
Output number per LF		6	Output Score	A
Impact weighting (%):		13%	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestone(s) for this review	Progress
Better donor coordination and aid effectiveness	Processes for CPG engagement in support of national development priorities and Sustainable Development Goals (SDGs) are transparent and effective	Met / CPG meetings with Government entities such as the Development Assistance Coordination Unit (DACU) and Foreign Economic Relations Department (FERD), as well as with other Government Ministries, coordination bodies / Relationship management
	Strengthened oversight for effective cooperation and partnerships for development solutions. Mechanisms are in place to generate and share knowledge about effective development cooperation	Met / Support to CPG-related meetings / Information management / Support to CPG Work Streams / Retained strategic overview of the work streams and attended work stream meetings on an ad hoc basis to ensure coherence across the work streams
	People in Myanmar live in a more peaceful and inclusive society, governed by more democratic and accountable institutions, and benefit from strengthened human rights and rule of law protection	Set up funding coordination mechanisms – donors can effectively prioritise development needs and areas of cross-over.

Provide supporting narrative for the score

The first purpose of the funding was to ensure the CPG Secretariat could continue its work to coordinate development donors. This has been achieved for this year. As mentioned above systems were put in place (agendas, monthly meetings, readouts, sector updates etc.) to ensure coherent information sharing. The following activities completed in this reporting period:

- Produced materials for CPG monthly meetings, including agendas, talking points, pre-meeting briefs, meeting summaries, updates on sector coordination groups and work streams and action points.
- Facilitated bimonthly meetings with the CPG Facilitators to plan and track CPG work.
- Collated and shared aid and development cooperation information for the benefit of the CPG, including strategies/policies, studies, assessments, records of meetings and contact lists. In collaboration with MIMU shared knowledge on, and promoted understanding of, development cooperation with other key stakeholders, including Government, parliament, INGOs, CSOs and the private sector
- Although work streams are self-managing, the CPG Secretariat helped ensure overall updates of strategic progress made under the work stream are regularly provided to all CPG members
- Set up donor co-ordination mechanisms for effective development in Rakhine and coherence

The second purpose of this funding was to support the DFID Liaison office in Nay Pyi Taw. Assessment of this component is limited by the fact that a specific output indicator was not established for the work. However, significant activities have been undertaken with the continuation of the NPT office. The logframe needs to be urgently rectified for the upcoming period, with either an indicator developed to cover the Nay Pyi Taw office operations; the output eliminated as a separate workstream and instead integrated through other outputs; or, depending on the outcome of ongoing central approval processes, the office instead consider this under other operational budget mechanisms.

DFID has continued implementation of the Liaison office as a trial since late 2017, having moved from co-location with the Australian Department for Foreign Affairs and Trade. The intention of the move was to enhance capacity and engagement with local partners and the government and ministries based in Nay Pyi Taw in order to strengthen coordination and development effectiveness. Locating the office in a hotel was identified as the most cost-effective mechanism for delivering a Liaison Office in the capital. Other donors, including the US and World Bank, have taken a similar approach. The office is staffed by three full time DFID representatives.

The Liaison office provides a stepping stone to a UK office which would allow the UK to gradually scale up staffing over the medium term in Nay Pyi Taw. As we move beyond the trial phase, management for the process will pass from DFID to FCO with decision-making under the One HMG umbrella. This approach is consistent with enhancing overall HMG presence with a view to a future Embassy move eventually. There remain challenges for scaling-up this approach and key risks need to be considered around, for example, the viability and sustainability of the model, and the expectations of the Government of Myanmar (which is pushing for formal commitments to Embassy moves).

The office has delivered impact in three main ways: i) supporting programme delivery by driving forward engagement on specific workstreams with implementers/beneficiaries based in Nay Pyi Taw (e.g. parliamentary strengthening); ii) facilitatory, enabling visits from high-level representatives engaging on behalf of HMG in NPT; and, iii) thematically, providing a platform for DFID staff to drive forward specific agendas with counterparts in the capital and the international community.

Lessons identified this year, and recommendations for the year ahead linked to this output

DFID have identified the significant need for a coordination mechanisms amongst the CPs in Myanmar in order to ensure greater development effectiveness. This includes supporting CPs in engaging with Government through joint strategic approaches at a critical time when the Government has taken steps towards articulating its development priorities in a formal Sustainable Development Plan (MSDP) around which CPs will increasingly orient themselves. And also, at a time when the country is facing new and growing development and humanitarian challenges, which require additional strategic coordination from CPs, in collaboration with other members of the international community.

Should there be a funding gap, the CPG Secretariat would have to operate at a reduced level of ambition. The continued and uninterrupted support from the CPG Secretariat is essential for the functioning of the CPG including its monthly meetings, work stream activities, regular follow-up on government policies and initiatives etc. The sustainability of the Secretariat is entirely dependent on donor funding.

In recent years there has been a broadening of donors contributing to the CPG in order for effective donor co-ordination and implementation to take place. DFID’s contribution represents an equitable burden share although it is also our aim to widen the number of donors contributing in future years. This approach will also complement the UN Reform agenda. Our funding will enable international partner priorities to be taken forward in Myanmar.

Over the last year the liaison office team has made important progress in supporting the FCO to develop NPT delivery options. It will be critical to develop indicators to measure the contribution of the liaison office and its transition to a longer term model. This needs to be properly considered for the upcoming reporting period in the context of other workstreams under the ARF. The team has already developed the outline of a formal engagement strategy for use x-HMG, and this is an important step towards better strategic engagement leading to both enhanced delivery but also more robust monitoring of outcomes.
- Thematic leads to review impact of existing support and agree scaled up support to CPG and aid effectiveness for a more effective and sustained impactful outcome as soon as possible in co-ordination with other donors and the CPG Secretariat.
- A refinement to the logframe indicators or a more appropriate approach to reporting needs to be agreed for the Nay Pyi Taw Liason Office as soon as possible led by the thematic lead, SRO and Strategy and Results Adviser in consultation with SMT and FCO based on the draft strategy developed. This should also fit with the review of the overall ARF approach.
## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES (1-2 pages)

The ARF was set up to enable DFID Myanmar to respond quickly to opportunities to support interventions that catalyse, foster and deepen reforms and our strategic understanding of context. Given the nature of the reforms and the need to respond quickly to positive change, the ARF strategic and policy focus are on 6 broad themes:
- Good governance and public financial management
- Promoting responsible investment
- Improving transparency, Accountability and the Rule of Law
- Strengthening the work of Parliament
- Helping the process of ethnic reconciliation
- Better coordination and aid effectiveness.

The experience of the ARF to date validates its original theory of change. The reform process in Myanmar is dynamic and very unpredictable. Across the nation, there are complex conflict issues that are expected to rise. The lead up to the general election in 2020 is likely to be particularly challenging. Opportunities to back important reforms and increase DFID’s own in-house understanding of the complexities can present themselves at short notice. The ARF has enabled DFID to be agile in backing these opportunities. So the rationale of the ARF is still relevant.

There are no major changes to the original theory of change, but the projects funded under the ARF programme have adapted to the four shifts in the overall portfolio, seeking opportunities to focus more on inclusion, conflict areas and focused engagement on policy reform. More recently, we have strengthened engagement on aid effectiveness in order to maximise CPG support to reforms.

The ARF approach and theory of change will be reviewed when DFID Myanmar has finalised its new business plan,

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead (1/2 page)

The purpose of this intervention is to opportunistically finance interventions that arise in the fast-paced context to maximise the potential benefits opened up by political reform. The expected outcome of the ARF is “short term results that strengthen long term reform in the ARF focus areas.” With the change in context since 2017, the ARF approach has evolved to include responding to both opportunities and challenges in the policy space.

The increased awareness of the complexity of Myanmar’s reform process, the short time frame of the projects, and the high levels of strategic risk, mean that it is difficult to make an overall judgement of progress against at the outcome level. Some current and recent areas of work show good potential on a trajectory towards sustainable policy impact (for example the ARF interventions in teacher training and in Rangoon General Hospital) or towards establishing new ways of working (the support to the CPG and the DFID Liaison Office), while for others progress at the outcome level looks likely to be more challenging (e.g. the work in Rakhine), Additional work is required to strengthen the M&E framework for the ARF to help make these judgements on a more empirical basis.

Going forward DFID SMT should take stock of how best to deploy resources under the ARF backed by a more effective strategic approach. This would involve ensuring that the strategic and catalytic interventions funded can be more clearly linked to a single outcome. Results will come from both the activities in areas directly covered by the projects, by supporting learning and indirectly by supporting and influencing. Refreshing the logframe will increase clarity of the impacts in the various output areas.

Overall output score and description

Output	Description	Impact Weight (%)	Output performance
1	Better Governance and Public Financial Management	68%	B (Output moderately did not meet expectation)
2	More Responsible Investment	0%	(No activity under this output since the last Annual Review)
3	Improving Transparency, Accountability and the Rule of Law	0%	(No activity under this output since the last Annual Review)
4	Strengthened Parliament	0%	(No activity under this output since the last Annual Review)
5	Helping the process of ethnic reconciliation	19%	B (Output moderately did not meet expectation)
6	Better donor coordination and aid effectiveness	13%	A (Outputs met expectation)

Explain major changes to the logframe in the past year (1/2 page)

The overall logframe was updated in April 2018 as the Technical Assistance for Public Private Partnership (PPP) Framework and the English for Education College Trainers (EfECT) projects ended.

Describe any planned changes to the logframe as a result of this review (1/2 page)

The SRO and Thematic leads will work with the Result Adviser and SMT to review the ARF approach and the theory of change in the light of the new DFID Myanmar Business Plan. Following this review they will need to review and update the logframe and embed more evidence based performance measures. This will include ending old outputs that will no longer be relevant and refining output level indicators to include appropriate milestones for all current activities.

## D: VALUE FOR MONEY (1-2 pages)

Assess VfM compared to the proposition in the Business Case, based on the past year (1 page)

The ARF BC Value for Money proposition remain valid and the programme has provided additional benefits below:

Economy:
- DFID’s Liaison Office at Nay Pyi Taw represents positive value for money having undergone significant analysis by both FCO and DFID over the last year to ensure that this continues to represent the most beneficial model for the office moving forwards. This has involved cost comparisons with similar office accommodation as well as other options of HMG investing in upgrading and maintaining a standalone office. For the staff based in the office full-time, the cost-per-desk remains excellent value for money considering wider benefits of inclusive service provision. Without this, there would be higher additional costs in terms of necessary estates functions to be performed.
- The platform which the office provides has enabled a series of High-Level visits to meet Myanmar government and stakeholders, without which there would have been a necessity to hire additional and ad-hoc venues for meetings. This would cost DFID more and much frequent travel of essential staff back and forth Yangon and NPT. Further, it provides a useful base to enable visiting core staff and HQ colleagues to maintain productivity when visiting the capital for meetings.
- The cost of the RGHR work is discounted with pro bono support and reduced fees by engaging interested participants through Imperial College and RGHR contacts. For every £1 of DFID support, RGHR add additional financial value through the support of partners to the programme. RGHR also keeps overheads to a bare minimum e.g. the office space in Jersey, from which all activities are coordinated, costs a mere £210 per month.
- The Sittwe Strategic Fund projects are implemented at low cost, with high visibility community improvement initiative. This has enabled development of local services/environment in Sittwe and its immediate surroundings which benefit the urban population. Utilising delegated procurement for education support in Rakhine has also concluded on time in a complex area.

Effectiveness:
- DFID’s earlier grants to RGHR supported a team with strong links through the Hospital, University and Ministry. This same team is committed to delivering this programme. The support provided by DFID to RGHR will help the Ministry of Health and Sports to target its own money more effectively.
- Funds were made available in the Government budget year for infrastructure which is a huge success; and government engagement in the renewal of a system that needs substantial further investment is positive. Lead architect Robin Cross is already working with Ministry officials to support the improved effectiveness of this budget. This kind of reform will allow for better engagement with private sector providers of health services.
- DFID’s grants to RGHT continued to support a team with strong links through the Hospital, University and the Ministry including the State Counsellor. This created important space for dialogue with government on reforms through the RGHT. The relationships built with government and stakeholders through the activities, and our increased space and ability to engage with non traditional stakeholders have provided good credibility for the UK. This is difficult to measure but is certainly proving effective and adding value to our ability to influence the government.
- The M&E mechanism embedded in the discrete activities have ensured that our interventions are used effectively for the intended purposes. However, the annual review has made a recommendation to further enhance performance measurement approaches to build empherical evidences for hard to measure components.
- The Sitwee strategic funds has facilitated, working in co-operation, and in parallel, to our larger programme interventions to provide some assistance. But also through visibility and speedy response, has countered the narrative that the international community does not listen to the requests of the local community. It has complemented the longer term funding through other instruments. It has successfully demonstrated to the local communities that DFID can be flexible and demand driven in its approach, creating a good space for building trust amongst communities and stakeholders and smooth implementation of our wider programmes in the conflict affected state.

Efficiency:
- In recent years there has been a broadening of donors contributing to the CPG in order for effective and more efficient donor co-ordination and implementation to take place in Myanmar. DFID’s contribution represents an equitable burden share although it is also our aim to widen the number of donors contributing in future years. This approach seeks to complement the UN Reform agenda in country and UK funding will enable international partner priorities to be taken forward in Myanmar.
- The RGHR program is a long term programme that DFID has supported. It will require further levels of investment to bring the Programme to fruition and DFID has committed to additional funding to continue critical aspects of the masterplan. The Programme developed through this proposal will support further fund raising in targeting further partnerships and investment opportunities that will drive longer term efficiency and sustainability for the hospital and its beneficiaries.
- The Sitwee projects has brought about immediate benefits to the urban population. These are aimed to show the benefits provided by the international community and the UK specifically in a visible, demand driven fashion.

Equity:
- Value for money is gained by having DFID directly engage in critical areas where access is difficult and we need even deeper understanding of context and complexities (e.g. Rakhine State which changes so rapidly), and creating platforms for larger scale work (e.g. work on health sector institutional linkages), and from filling critical gaps to ensure that no one is left behind.
- The RGHR programme has produced a masterplan for improvements of the Rangoon general hospital to provide better services for all the public and enhance efficient management of the hospital infrastructure. The government are ready to implement the improvements that will provide an overall positive benefit to all the people of Myanmar, much needed health care services.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio (1 page)

Yes. The original theory of change remains valid in the context of the wider portfolio and the complexities in Myanmar. The ARF programme is set up to respond swiftly to strategic and policy interventions at an opportune time that will continue to complement and add value to not only DFID’s wider portfolio but also influence wider donor collaboration and joined up working influencing the UN reform agenda such as agreeing on one joined up communication strategy for Rakhine. Deepening understanding of the context, strategic analysis and in depth insights into the conflict, political and economic areas will continue to be needed as we need to directly deepen our understanding, which this programme will allow. The vfm gains will be provision of influence and strategic direction to our wider programming and the donors working together on reform agenda and specifically in Rakhine.

In terms of specific interventions, the RGHR program is a long term, complex and innovative project that requires continued high level engagement including with the State Counsellor Daw Aung San Sui Kyi and hospital authorities which the programme has enabled. It will require a second phase funding to bring the Programme to fruition with concrete results that DFID and RGHT has already agreed. The Programme developed through this proposal has strong support from the government as it will help the Myanmar public at large. Our funding is also expected to leverage further fund raising in targeting new partnerships and investment opportunities for the RGHT and the hospital. Similarly, other existing projects such as NPT and CPG will need to continue to ensure the development gains achieved thus far are cemented fully providing long term results. CPG support may also need more scaled up support for longer term sustained impact.

Overall the ARF should continue to deliver on its original goals that remain relevant and sustainable within the next few years. So the cost and time extension should be considered which this annual review recommends. Ending the programme by Dec 2020 will not provide longer term VfM for DFID and the investments we will make, e.g. the RGHT second phase activity may take longer than expected and new challenges need to be addressed and responded on time in Rakhine and other contested and complex areas. The aid effectiveness reform agenda is also long term to see any meaningful results.

E: RISK (½ to 1 page)

Overview of programme risk (noting the rating from p.1) and mitigation

The ARF programme’s net risk rating is: moderate

The key risks identified for this overall programme are external context, operational, and delivery. The SRO monitors overall risks and mitigation actions on a regular basis with thematic leads. An updated risk matrix is attached [Annex 2].

ARF risks are reviewed regularly by the ARF team and mitigation actions updated. However, project risks assessment should be strengthened for future bids on ARF with a full risk matrix required for the HoO approval process.

Operation in Rakhine remains the key driver of context, delivery and reputational risks due to the conflict in the region and the fast changing situation. Perceptions that the UK and development partners are not supporting the wider Rakhine populations are being mitigated by the ARF work in Rakhine and it is recommended that the joint communication strategy is effectively implemented and linked to the wider DFID programmes. The reputational/delivery context in Rakhine needs to be closely monitored and any risks above risk appetite will be escalated. This includes the misuse of any assets provided by the ARF – all of which are covered by an assets management policy.

As noted above we are still awaiting the delivery of the independent annual audit report on RGHT. In response to the delay, DFID has conducted an independent Due Diligence Peer Review and sought confirmation from the UK auditors that that audit presents no issues or risks. The auditors have responded that they have not identified serious issues, but that as RGHT is registered under Jersey Law, additional work has been required to understand the rules and procedures in order to complete the final certified audit statement. This process has taken longer than expected.

Since the last annual review RGHT has also provided an Anti-Bullying  and Anti-Harassment Policy and has reaffirmed complete commitment to ensuring that all those who are employed by RGHRCT or act as consultants for RGHT will deliver a safe and trustworthy environment in which all can work without fear of exploitation or abuse. This was in response of DFID’s letter to partners on safeguarding.

Update on partnership principles [if relevant. If it’s not – delete this section, but only having read the text in the Smart Guide at the end] (1/2 page)

The partnerships principles were reviewed, and the ARF is operating within the framework set out by the partnership principles. The discrete projects are implemented in a manner that meets DFID’s requirements and UK’s commitment to the overall funding approach. DFID will not provide direct financial aid to government and will continue to implement small projects based on stakeholder consultation and engagement as appropriate. Any risks to partnerships principles will be looked at during the risk reviews.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE (1-2 pages)
Performance of partners and DFID, notably on commercial, and financial issues (1-2 pages)

ARF BC Budget Allocation / £15,000,000.00		Total spend to date / £10,736,119.41	Actual disbursement in review year	Balance to date (f.y. 19/20) / £4,263,880.59
203601-106	Joint Liaison Office in Nay Pyi Taw	313,733.43	5,800.00	130,489.19
203601-118	Establishment of a small fund for low cost high visibility Projects in Sittwe	102,784.57	102,000.00	197,215.43
203601-119	Additional Funding for the Cooperation Partners Group (CPG) Secretariat	60,000.00	-	1,000,000.00
203601-116	Funding project management of restoration and reinvigoration of Rangoon General Hospital and transforming medical education	1,975,000.00	361,452.00	1,000,000.00

In the last review, DFID has had some concerns about the depth of the programme management in the RGHT. and recommended strengthening in country support. This is now in place. The RGHR trust reports to DFID on a 6 monthly basis which includes a full Programme and Financial analysis of the expenditure and budgets.

Reporting

Date of last narrative financial report(s)	RGHR / 5 Mar 2019 (Vault ID 46383292)
Date of last audited annual statement (s)	RGHR / 10 May 2019 (Vault ID 48411201) / Auditor’s assurance letter received and awaiting full certified annual audit report

Commercially, the programme uses a mix and balance of instruments to procure goods and services under the programmes that provide value for money. We have used the local market to procure locally available goods for the Sitwee project and use of local organisation in the supply chain has provided low cost and speedy implementation under the delegated procurement threshold. For our agreements with partners we use accountable grants and MOUs as direct procurement channel that provide the best comparative advantage such as working with the RGHT and the CPG under the UNDP umbrella which have proved beneficial.

G: MONITORING, EVIDENCE & LEARNING (1-2 pages)

Monitoring (1/2 page)

The programme components have good monitoring mechanisms in place. The ARF programme interim SRO is the Senior Programme Manager who works closely with cross office thematic leads on the output areas. At the ARF BC level, monitoring is done through this joint team. We plan to strengthen this further following the review of the ARF strategy and approach to maximise impact and learning.

ARF discrete projects have embeded programme monitoring mechanism (e.g. for the RGHT where they have a small and efficient team made up of leaders and trustees in their respective fields). Regular meetings and dialogue is led by DFID’s thematic lead for RGHR by way of visits and stakeholder meetings.

For the Sitwee project, we have an officer based in Sittwe who provides strong monitoring of the context, stakeholder engagement and reporting back to the team in DFID Yangon. Until recently we had also fielded a CHASE OT adviser based in Sittwe to manage implementation of the programme. Staff (with the support of the Rakhine issues Coordinator) SRO in Yangon visit project sites once a week, for regular monitoring during the implementing period. The team also conducted pre and post assessment on construction infrastructures and provision of educational materials during August or September 2019. Post construction phase, the monastic schools supported will submit monthly attendance registers for the first twelve months.

DFID ARF SRO, Rakhine Issues co-ordinator and Head of Office in Yangon made a field visit to Sitwee to monitor first hand progress and provide support to staff based there. The made a visit to the project sites as well as the Rohingya camp to monitor the impact of our work. They also met the key stakeholders and conducted a partners meeting. We also learnt about the safeguarding training being provided to field based partners in this remote area by our key Humanitarian Assistance project to all the downstream partner leads.

CPG is represented by a team of DFID officials, mainly the Head of Office, (and the DEFT team and the Rakhine Issues Coordinator) participate in development partners meetings. Head of Office and team leaders also visit the NPT office and engage in monitoring, influencing key meetings with government and departments to maximise value for money for our wider portfolio as well as pushing reforms.

Evidence (1/2 page)

The key learning from this review is that the ARF programme needs to embed a more effective and strategic approach to capture evidence and performance. Concrete results have been achieved, but indicators need refinement to generate real evidence of impact for all the projects across the strategic fund. Therefore a revision to the logframe as a monitoring tool and setting up a refreshed results framework is recommended.

However, in terms of specific projects, there is anecdotal evidence of impact through evidence and learning. For example RGHR is playing a key role in supporting the national Medical Curriculum Reform Programme. The relationships held with the Permanent Secretary and others close to the Union Minster of Health and Sports have generated valuable. Another example comes from the fact that the Union Minister requested RGHR to engage with Sittwe General Hospital in Rakhine; which commenced through the access project via UNOPS. The experience we have gained in Yangon should help UNOPs provide a workable masterplan implementation for Sittwe.

Learning (1/2 page)

Our support to strategic interventions, though small has demonstrated influence through strategic learning. For example, DFID’s support to RGHR program unlocked the comprehensive renewal of the medical curriculum and associated infrastructure of Burma, bringing British expertise to deliver substantive and lasting change as part of the wider work of the Burmese government to transform the health and wellbeing of its people. The program transferred world class UK expertise and knowledge to the Myanmar leadership. Building on existing relationships between UK and Myanmar to support delivery of health system reform fit for the needs of people. DFID should continue to apply RGHR program as an instrument to strengthen relationship and trust for achieving wider health system reform.

A Key learning for DFID has been the importance of project management in the delivery of programmes and a criteria based approval mechanism within this programme to ensure quality and strategic focus. We need to continue strengthen this for ARF to ensure that more bids on this BC are consistent, and avoid complexity. The SRO has been messaging this with the use of standardized templates and criterial for approval of projects by the HOO.

Progress against recommendations from last Annual Review

The major recommendation from the last review was to continue DFID’s support to implement RGHR masterplan activities and allow flexibility in the activities and outputs for which the funding is used, provided it continues to contribute to the overall outcome of the reinvigoration of the hospital. This has been actioned.

The review also recommended RGHT strengthening it’s programme management capacity which has been actioned with delegated RGHT programme manager who now supports the local team. The trustees also regularly meets with DFID officials. The audit report has not been submitted by RGHT.

A quick review of the logframe review was undertaken against the DFID results commission work with support from the Results advisor but further work is needed to refresh this soon after the review as this is a working tool.

Annex 1:

Table 1: The ARF Results Chain
Impact: A better governed, more prosperous Burma that uses its increased wealth to reduce poverty.
Outcome: Short term results that strengthen long term reform in the ARF focus areas.
Outputs: / Better governance and public financial management / More responsible investment / Improving transparency, accountability and the rule of law / Strengthened Parliament / Helping the process of ethnic reconciliation / Better donor coordination and aid effectiveness.