Annual Review - Summary Sheet

Title: Support to the World Bank project ‘Enabling the Business of Agriculture’
Programme Value: £4,900,000 total (£4,425,000 disbursed)		Review Date: October 2018
Programme Code: 204123	Start Date: 18/11/2013	End Date: 30/11/2020

Summary of Programme Performance
Year	2014	2015	2016	2017	2018
Programme Score	A	A	A	A	A+
Risk Rating	Medium	Medium	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	Business Case
DevTracker Link to Log frame:	Logframe

A. Summary and Overview

Description of the programme

The ‘Enabling the Business of Agriculture’ (EBA) programme is a multi-donor, multi country programme housed in the World Bank. It collects data on 10 indicators that measure legal and policy barriers for businesses operating across agricultural value chains, and the transaction costs in dealing with government regulations. The EBA is the Doing Business Index for the agriculture sector. Indicators cover regulations in the areas of seeds, fertilisers, mechanisation, land, water, livestock, transport, finance, information communication technology (ICT), gender, climate and markets and data is gathered in 80 countries. The evolution of EBA since its inception in 2012 is shown below:

Supporting narrative for the overall score in this review

EBA programme score for this year is A+ reflecting strong performance against all outputs. The indicator set has been further refined, geographic reach extended and evidence of influencing regulatory reforms is emerging. During the next year, close monitoring of the new approach to CSO engagement is needed to ensure that EBA continues to reflect the interests of a broad range of stakeholders.

On indicators and countries, EBA has extended the number of countries covered by the 2019 report to include 80 countries and will fully apply all 12 thematic indicators for the first time. The extended geographic coverage reflects the interests of the wider donor group, improves the comparability of data between countries and increases the footprint of the EBA in middle and lower income countries.

On uptake, following the launch of the 2017 report, EBA has undertaken a significant range of dissemination and engagement events (see Annex 2) and has developed an engagement strategy which prioritises key countries and channels for policy influencing. During the year, EBA targeted 32 priority countries of which 15 have expressed interest in using EBA data for policy analysis, 6 (Rwanda, Zimbabwe, Malawi, Vietnam, Lao PDR, Ghana) have begun the process of reform based on EBA policy analysis and 3 have completed such reforms (Sudan, Ghana and Vietnam).

During the year, DFID commissioned an independent review of EBA which focused on EBA’s communication, engagement and influencing activities. The findings of this review are discussed in Section H but overall the review found that EBA is widely regarded by governments, donors and NGOs as a credible tool for measuring compliance with good practice. The review recommended a more strategic approach to dissemination and engagement which has been adopted by EBA and more proactive use and dissemination by EBA’s donors.

EBA is well-positioned to capitalise on the rigorous dataset it has gathered from three data gathering cycles and on the relationships it has established with a range of stakeholders to accelerate regulatory reform that will increase investment in agriculture in low and middle income countries.

Recommendations for the year ahead

R1. DFID should seek the inclusion of Indonesia, Somalia and South Sudan into future data gathering exercises in order to improve the coverage of DFID countries for which agriculture is a critical economic sector and consider the extent to which EBA geographies can be improved to reflect emerging priorities on strategic directions and building markets. Responsibility: DFID SRO by March 2019

R2 The output indicators for 2019 should be changed in order to reflect the revised CSO engagement strategy incorporating increased CSO involvement at national level and increased virtual engagement of international CSOs. Responsibility: DFID SRO by December 2018

R3. DFID should develop a comprehensive engagement strategy to promote the uptake and use of EBA 2019 data by country offices and centrally managed programmes. This will help to further improve the value for money effectiveness of the programme. Responsibility: DFID SRO by December 2018

R4. EBA and its donors should identify a small number of priority countries in which to intensify collaboration on uptake in order to demonstrate the potential impact that the use of the indicators can have and to use this to promote wider uptake across relevant donor networks. Responsibility: World Bank EBA outreach team by March 2019

R5. EBA should develop a series of shorter, less technical reports and engagement documents and social media communications to promote broader engagement with EBA data and increase web traffic. This should form part of the EBA 2019 communications plan. Responsibility: World Bank EBA core team by March 2019

R6. In order to fully communicate the development impact potential of EBA, the EBA team should further develop the outcome/impact elements of the theory of change and the pathways through which EBA’s work and data can lead to positive policy reform and pro-poor, inclusive growth. Responsibility: World Bank EBA core team by March 2019

R7. DFID needs to determine its long-term engagement with EBA beyond the current phase which ends in 2020. Responsibility DFID SRO by March 2019

## B: DETAILED OUTPUT SCORING

Output Title	Comprehensive and inclusive data collection in a reflective range of countries where agriculture is an important sector
Output number per LF		1	Output Score	A
Risk:		Moderate	Impact weighting (%):	33%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones1	Progress
1.1 Number of countries covered; and number of EBA indicators developed	1. 12 indicators fully developed / 2. Data collection in 80 countries initiated / 3. Sub-national data collection in India initiated	1. 12 indicators now fully developed, with gender and environmental sustainability incorporated across the 10 core topics. / 2. Data collection initiated in 82 countries / 3. Subnational data collection in India initiated
1.2 Effective CSO engagement and partnership	1. Working Group consultation working document finalised and circulated; / 2. First EBA-CSO WG in person meeting organised to discuss how to incorporate CSOs feedback into the next EBA report; / 3. 2 in-country CSO events organised. / 4. 1 major CSO conference joined.	1. New Working Group approach in place, targeting CSO involvement at i) working group level and ii) via a virtual consultation network. / 2. Targeted CSO events were held in Uganda, Nigeria and Nepal since the launch of the EBA 2017 Report, which brought together a total of 24 CSOs to discuss EBA. Going forward, CSOs will be included in country level EBA-based policy discussions, as has been in 8 countries to date: Tanzania, Ghana, Nigeria, Mozambique, Kenya, India, Nepal, Cambodia. No major CSO conference was joined.
1.3 Targeted research on effectiveness and impact of EBA indicators	2 research outputs covering the impact of regulation in agricultural development	2 policy notes produced: / • “The role of ICT regulations in agribusiness and rural development”, October 2017 / • “Anchoring water demand management”, June 2018

Key Points

Overall EBA has delivered fully against indicators 1.1 and 1.3 and has substantially delivered against indicator 1.2, although the approach to this indicator has changed slightly.

  1. Countries and Indicators
EBA has extended its footprint to now consider the legal barriers for businesses operating in 82 economies. The addition of 20 extra countries has led to the inclusion of three new DFID countries (Democratic Republic of the Congo, Afghanistan and Iraq) and means that almost 80% of countries where DFID is currently working bilaterally are covered by the programme. Only Indonesia, Lebanon, occupied Palestinian territories, Somalia, South Sudan, Syria, and Yemen remain excluded.

R1. DFID should seek the inclusion of Indonesia, Somalia and South Sudan into future data gathering exercises in order to improve the coverage of DFID countries. Responsibility: DFID SRO by March 2019

EBA measures 10 core indicators (seed, fertiliser, land, livestock, markets, water, ICT, machinery, transport, finance) and 2 crosscutting indicators (gender and climate). EBA has extended the data gathering for the additional topics of livestock and land which were piloted during 2017 in a subset of countries to now cover all countries. The crosscutting indicators of gender and climate have been further refined during the period and are integrated into the 10 core indicator sets.

1.2 CSO engagement
The approach to CSO engagement has changed from operating through a single CSO working group to i) incorporating CSO input into the topic level advisory groups for each indicator, ii) increasing engagement with CSOs in country on the dissemination and use of EBA findings and iii) consulting with CSOs through a virtual network.

1. CSOs participate in the Topic Advisory Groups for 6 topics: seed, fertilizer, land, water, livestock and markets
2. A CSO engagement strategy has been developed to involve CSOs more systematically in EBA outreach, by targeting national, regional and global CSOs and CSO networks. The strategy includes actions such as
  1. Targeting CSO participation in technical discussions in many of the 32 priority countries (in addition to inclusion in advisory working groups)
  2. Developing a CSO section on the EBA website to provide information and customised material on the use of EBA that links to CSO concerns
  3. Participating in online platforms with high CSO traffic
To date CSOs have been included in country level EBA-based policy discussions in 8 countries (Tanzania, Ghana, Nigeria, Mozambique, Kenya, India, Nepal, Cambodia) and targeted CSO events were organized in Uganda, Nigeria and Nepal since the launch of the EBA 2017 Report, which brought together a total of 24 CSOs to discuss EBA findings.
EBA’s CSO strategy also includes the creation of virtual meeting (such as webinars) to discuss and explore how EBA data can drive an improved enabling environment for agribusiness. These are expected to begin after the 2019 data publication.

As part of the revised approach EBA has organised more national CSO events (3 instead of 2) and increased CSO engagement in advisory working groups. It has not organised the face to face CSO working group or virtual meetings for international CSOs. The independent evaluation noted the need for EBA to do more to engage collaborative international CSO’s in the overall evolution and outputs of EBA. Whilst this has not happened during the year, the revised CSO engagement strategy includes a number of measures that will address this concern including virtual meetings, tailored materials and CSO sections of the EBA website, alongside greater national level engagement.

R2 The output indicators for 2019 should be changed in order to reflect the revised CSO engagement strategy incorporating increased CSO involvement at national level and increased virtual engagement of international CSO’s. Responsibility: DFID EBA SRO by December 2018.

1.3 Research Outputs
This year has been a heavier year for data collection in preparation for the 2019 report which has meant that there are fewer research outputs planned and delivered compared to 2017 (in which five research outputs were produced). EBA has produced policy notes and policy briefs based on Research Outputs as follows (which are all publicly available for download via the EBA website http://eba.worldbank.org/):

The Role of ICT Regulations in Agribusiness and Rural Development: This research looks at how Information and Communication Technology (ICT) supports farmers by facilitating access to markets through real-time data on market prices, weather forecasts, information on pests, seed varieties and planting techniques. In particular, it focuses on the type of regulatory environment that is conducive to ICT development.

Anchoring water demand management: This research looks at how reform to the legal framework for water usage is one possible tool that can be used to support the sustainable water resources management practices. In particular, the research looks at how regulatory reforms can contribute to water demand management by creating mandates that provide support to (a) water information systems, (b) inclusive planning, (c) permits for water abstraction, (d) strong and context-appropriate enforcement, and (e) in highly-developed systems, economic incentives to reduce or reallocate water.

Output Title	Technically robust indicator development
Output number per LF		2	Output Score	A+
Risk:		Moderate	Impact weighting (%):	33%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
2.1 Development of gender indicators	1.Gender indicators' methodology tested in 4 countries / 2. New EBA gender indicators developed	1. Questions on gender piloted in 4 countries in December 2017 / 2. EBA gender approach reformulated to embed gender questions in indicators where relevant, and to use data from the Women Business and the Law indicator programme where applicable
2.2 Development of the efficiency index	1. Efficiency index methodology tests in 4 countries / 2. Efficiency index methodology refined	1. Efficiency data questions tested in 4 countries in December 2017 / 2. Efficiency note on proposed data points developed
2.3 Updates and revision to the EBA indicators based on ongoing consultation	1. EBA refined methodology tested in 4 countries and analysed 2. Technical consultation on EBA 2018 indicators methodology 3. Assessment of EBA indicators and scoring methodology refinement 4. New questionnaires developed 5. 5,000 contributors consulted	1. EBA methodology refinements tested in 4 countries data collection in late 2017 / 2. All topic teams formed technical advisory groups to consult on methodology / 3. Methodology refinement took place in late 2017 and early 2018 / 4. New questionnaires developed for data collection in 2018 / 5. Approximately 10,000 contributors consulted from June 2017 to June 2018

Key Points

EBA has met or exceeded all the indicators in this output, particularly as regards consultation with contributors on the technical nature of indicators.

2.1 Gender Indicators
The EBA 2017 report included a chapter on gender and data was gathered for a number of gender related sub-indicators. This data has been further refined and piloted and aligned with the data gathering undertaken by the World Bank’s Women Business and the Law (WBL) indicator work (also part funded by GRD). The final indicator set for the 2019 report is shown in Annex 3 and data gathering has begun against these indicators in all 82.

2.2 Efficiency Indicators
Efficiency indicators look at the practical implementation of reforms and assess the extent to which binding constraints for each indicator are being addressed as well as the technical legal basis of reform. In many cases, efficiency indicators look at the time and cost of complying with regulations, for example, the number of procedures and the time and cost associated with following a process such as certifying seed.

During the year EBA has developed further efficiency measures for indicators which look at a range of factors affecting compliance with regulations that go beyond time and cost, for example on seeds the efficiency indicator looks at the existence of agencies and public expertise to enable the registration of new varieties and not just the time and cost involved in complying with the law.

2.3 Indicator refinement
EBA has continued to update and refine the core indicator set during the period by working with advisory working groups and consulting practitioners in each country. The programme has exceeded the number of contributions to this process (over 10,000 as opposed to the target of 5,000). Contributions come from individuals that have engaged with EBA through surveys, meetings and workshops. During 2017 EBA undertook a comprehensive piloting of new indicators (on gender, climate and efficiency indicators) which led to further refinements prior to the commencement of the data gathering cycle for the 2019 report.

Output Title	Dissemination and uptake of the EBA
Output number per LF		3	Output Score	A+
Risk:		Moderate	Impact weighting (%):	34%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
3.1 Events organised and attended where the EBA is effectively presented to relevant participants	EBA17 report dissemination during data collection year: / 1. Targeted events to reach policy makers, private sector, civil society, multilateral organisations and academia to entice them to use data in analysis and to promote change: / - methodology workshops, including at least one presentation event in one of the countries identified as successfully changing legislation, and 1 regional dissemination event / - topic specific webinars / - industry conferences / 2. Revised dissemination engagement strategy and update framework as needed	EBA17 report dissemination plan implemented: / 1. Country-level outreach events and activity held in 23 countries leading to 15 expressions of interest for policy engagement and 6 countries where reform has been initiated. / EBA was presented at 2 regional events, in Tanzania and Tajikistan. / Three topic webinars were held on the EBA water topic area. / A partnership has been developed with AGRA for joint dissemination and discussions leading to reform programmes in 9 African countries. / 2. Revised 2018 Engagement Strategy produced for 2019 Report dissemination
3.2 Effective use of social media and website to disseminate information on and about the EBA	1. 4 quarterly newsletters published / 2. 6 by-monthly data highlights published / 3. 10% average monthly increase in page views / 4. 36,000 page views / 5. 6,000 unique visitors	1. EBA updates integrated into departmental newsletter, two were sent out by EBA in August and December and EBA was featured in two further departmental newsletters / 2. Website updated 6 times during the year, including a complete website redesign in November 2018 / 3. Page views varied month by month, and the average increase was 2%. However, there were increases following the quarterly newsletter increase of 44%, 29% and 25%, showing that engagement drives website visits. / 4. 54,530 Page views during Oct 2017-Oct 2018 / 5. 17, 587 unique visitors

EBA has met or exceeded the Logframe targets for this output and is therefore scored A+.

3.1 Engagement Events and Strategy
The EBA engagement and dissemination team have conducted a considerable number of events during the year as outlined above and in Annex two, including two regional events in Tanzania (the East African Annual Agriculture Policy Conference) and Tajikistan, and has met or exceeded the logframe targets. In line with EBA’s strategy of bringing stakeholders together with policymakers, no separate industry events have been held and the private sector has, instead, been actively involved in country level dialogue meetings with governments. A revised engagement strategy has been in place since the start of 2018 and focuses on following core approaches:
Outreach events – events in 18 countries have taken place/are planned for 2018. These events are organised in conjunction with local partners such as World Bank Agriculture Practice or AGRA (see below for more details on work with AGRA). The independent evaluation noted the “impressive amount of direct engagement with stakeholders” conducted by EBA in 2017 and the progressive increase in engagement activities over the years (see Figure 2 below) but identified a need for a more strategic approach to engagement which has been adopted in the 2018 engagement strategy.

Engagement events (including global, regional and country) (Source ITAD)

Outreach partnerships with donors – EBA is working in collaboration with EBA donors and partners (World Bank, Gates, USAID, DFID) on joint activities to advance the uptake and use of EBA in priority countries for these donors and partners. With the World Bank, EBA has been used to analyse weaknesses in the regulatory frameworks in Honduras, Iraq and Uzbekistan. With DFID, EBA has supported country offices on local policy issues (e.g. Fertiliser in Tanzania) and has begun close collaboration with some DFID projects (e.g. workshop has taken place with the Montpellier-Malabo Panel identify areas for collaboration). However, the independent evaluation also identified the opportunity for DFID in particular to make more of the outputs and research of EBA and to support greater uptake and use of these in DFID country office learning and influencing work.

Outreach partnerships with other organisations – EBA is working with CSOs and other third parties to influence local uptake and use of EBA data. This reflects a key recommendation in the independent evaluation around the need for EBA to identify and collaborate with local influencers in order to drive uptake. This approach involves engagement with CSOs, technical working groups involving donors and other local organisations. EBA has formed a partnership with AGRA through the Micro-Reforms for African Agribusiness (MIRA) initiative, to use EBA findings to guide policy discussions and drive reforms in 11 African countries. Joint EBA-MIRA missions funded by AGRA are underway to hold technical workshops on EBA and to develop policy recommendations with a number of key stakeholders (government, private sector, and technical and academic experts) which MIRA can then finance and push forward.

R3. DFID should develop a comprehensive engagement strategy to promote the uptake and use of EBA 2019 data by its country offices and centrally managed programmes. This will help to further improve the value for money and overall effectiveness of the programme. Responsibility: SRO by December 2018

R4. EBA and its donors should identify a small number of priority countries in which to intensify collaboration on uptake, in order to demonstrate the potential impact that the use of the indicators can have, and to use this to promote wider uptake across relevant donor networks. Responsibility: EBA outreach team by March 2019

3.2 Social Media and Website Use

EBA updates are now included in the quarterly external briefing from the World Bank’s Indicators Group which covers the Doing Business Indicators and the Women in Business and the Law Indicators. This enables the information to reach a large audience.

EBA has met or exceeded all the indicators for this output, with the exception of the rate of achieving a steady increase in the number of page views. With 54,000 page views and over 17,000 unique visitors the core website is being well used and data gathered by the independent evaluation reveals that a reasonable proportion of these visitors are from Africa (18%) and Asia (14%) showing promising global reach which can be built on further. Most interest related to the indicators of seed, finance and fertilisers.

Page visits peak during the period when the EBA index and report are published (see Figure below). No report was published during the period under review therefore in this context, the achievement of 54,000 page views is considerable. However, the evaluation found that “overall, the web presence of the EBA is not rising, with page views and report downloads both falling slightly in 2017” [compared to previous years].

EBA page views 2016 – 2017 (Source ITAD)
The evaluation also reported that many interviewees hoped that in future the EBA would produce more short, technically simple information products and more translations of materials into the main languages of countries covered by the index. The evaluation noted that EBA’s critics reach broader audiences by sharing brief products and videos rather than detailed analytical reports. It is therefore recommended that EBA develop shorter communications and makes great use of social media in order to attract more visitors to its core product, the EBA report, and to increase website traffic.

EBA is undertaking a number of actions that will increase its web presence and footprint. Firstly, the website will be updated in November 2018, to incorporate a cleaner web design, graphics and to make it more mobile friendly. Secondly, the website will include new visualisation tools that will allow the core EBA data to be presented more flexibly and dynamically. Finally, EBA has appointed a social media consultant to improve the use of social media by across all aspects of EBA’s work.

R5. EBA should develop a series of shorter, less technical report and engagement documents and social media communications to promote broader engagement with EBA data and increase web traffic. This should form part of the EBA 2019 communications plan. Responsibility: EBA core team by March 2019

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change and any major changes in the past year

The ultimate aim of DFID’s support to EBA is to promote smart regulations that support thriving agribusinesses and, by doing this, to provide opportunities for smallholders and workers and to promote long term inclusive economic development and transformation. In this way, the index supports the monitoring and delivery of Global Goal 2 of ending hunger, achieving food security, improving nutrition, and promoting sustainable agriculture, and also contributes to Goals 1 (ending poverty), 5 (gender equality) and 8 (economic growth) amongst others. It contributes to the delivery of DFID’s strategic framework on economic development as well as DFID’s conceptual framework on agriculture.

During the year, the independent evaluation team prepared a revised theory of change (see below) which captures this intended impact and incorporates the existing intended outcomes.

DFID has asked EBA to expand the impact level of the theory of change in order to clearly define the different potential impacts of reforms (e.g. higher productivity, safer food, secure land rights, increased trade, increased private sector investment etc) and to clarify the links to relevant SDGs on incomes, jobs and food security.

R6. In order to fully communicate the development impact potential of EBA, the EBA team should further develop the outcome/impact elements of the theory of change and the pathways through which EBA’s work and data can lead to positive policy reform and pro-poor, inclusive growth. Responsibility: EBA core team by March 2019

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead

The programme appears to be on track to deliver the logframe outcomes relating to improvements in regulatory reform that reduce transaction costs for agribusiness firms and smallholders and improved perception of regulatory forms that are implemented. The EBA team has provided some evidence of regulatory reforms which have come about as part of the conversation that was stimulated by EBA - pointing to examples where policy reforms have followed engagement on EBA analysis in 4 countries, with 15 countries out of a targeted 32 expressing an interest in exploring reform. The independent evaluation noted that although “it is still too early to say whether the EBA has had a substantial influence on reform occurring…it has become an effective tool in policy dialogue in a third of countries covered. It is seen as credible, even by its critics, even if it is not yet seen by them as addressing a poverty agenda”.

It is worth noting that these results have been achieved despite the fact that EBA has been in existence for a relatively short period of time and only 10 countries have had 3 sets of data reported (the pilot countries from year 1). As EBA becomes further established across 82 countries and its indicator sets continued to be further refined it provides a powerful tool from which to engage with governments and advocate for further policy reform.

Logframe

There have been no changes to the logframe in the last year. The logframe indicators for 2019 relating to CSO engagement should be updated in line with the revised CSO engagement strategy as noted above.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Assess VfM compared to the proposition in the Business Case, based on the past year

The overarching VFM proposition in the Business Case was that costs would be controlled, resources allocated to value-adding activities and that research and reports would be used to influence policy.

Costs/economy:
The UK contributed £3m to Phase 1 of the EBA pilot against a total project budget of $17.6m, equalling a burden share of approximately 22%. The UK will disburse an additional £1.9m for the three-year extension, against a total project budget of $6.8m which is less per year but reflects an increased burden share to approximately 36% due to the withdrawal of the governments of Denmark and the Netherlands from the project.

During the period under review, DFID disbursed £950,000 ($1,235,000) which includes funding for costs incurred and costs committed by the Bank. During the period to July 2018, the EBA Trust Fund spent the following:

Expense Categories	Total FY18 TF Disbursement	Proportion of spend
Staff Costs	2,315,294	81%
Consultant Fees	378,193	13%
Associated Overhead Costs	2,227	<1%
Travel expenses	57,846	2%
Equipment Costs	-	-
Media Workshop	1,345	<1%
Contractual Services	104,000	4%
Total	2,858,905

Table 1: EBA disbursement by component (July 2017 - June 2018)

The overall costs of running the EBA project are in line with expectations. Staff costs follow standard World Bank salary scales, and the mixture of senior versus junior staff appears to be reasonable with a ratio of 3.5 senior staff to 7.5 junior staff. Consultants are used for research, data collection, data processing, topic technical expertise and certain specific tasks such as communications and translation. Consultants are appointed using standard World Bank terms which provide some comfort relating to value for money. EBA has been successful in involving a large number of pro bono advisers, academics and others in helping to define the project’s indicators and to gather appropriate data. In addition to this, EBA makes use of the World Bank’s country office network, Agriculture Global Practice and Global Indicators group in order to support the delivery of EBA.

Efficiency

Efficiency is measured in terms of the cost of delivering key outputs such as the EBA report and data rankings and the dissemination and engagement events and activities. During 2018, EBA’s costs were split 76% on data gathering and 24% on dissemination but the biannual publication of EBA reports makes it difficult to assess the efficiency of EBA’s work over a single year.

Given that EBA is on track and on budget it is possible to look at the overall expected efficiency of the programme extension during its three-year lifespan. During this period $6.8 million is expected to deliver a significant set of outputs as outlined in the section above, including 2 biannual EBA reports (2017 and 2019), covering 80 countries in 2019 across 10 sets of indicators and drawing on the contribution of 10,000 contributors and disseminating the results through more than 20 national, regional and global events.

On dissemination, the recent independent evaluation noted that “dissemination activities clearly take value for money into account, with the EBA team taking advantage of existing high-profile events to directly reach a large (often international) audience without the costs of convening an event”. By taking advantage of existing events and existing World Bank channels and infrastructure EBA is able to deliver a good level of efficiency.

Effectiveness

Effectiveness of EBA relates to delivering the intended outcomes of reducing the time and cost involved in key regulatory procedures and improving the perception of regulatory reforms that are made. In order to measure this it is necessary to look at the extent to which EBA has succeeded in influencing reforms that reduce time and cost and improve public perception. This annual review has not reported on outcomes, however, achievements at the output level and findings from the independent evaluation suggest that this is on track.

Equity

The ultimate intended beneficiaries of the EBA programme are farmers and agriculture-related businesses that will benefit from an improved enabling environment which promotes agricultural productivity and attracts investment into agriculture.

As discussed above, it is difficult to identify a causal link between EBA’s activities, regulatory reforms and, ultimately, improved farm incomes due to the multiplicity of factors affecting each stage in this causal chain. However, it is possible to consider the extent to which the things that are measured by EBA are relevant to farmers, particularly those on low incomes in developing countries. EBA has been criticised by a small number of international NGOs for measuring indicators which are of perceived interest to larger, commercial farmers or agribusinesses and of less relevance to poorer smallholder farmers. DFID does not share this opinion and believes that the indicators include a range of measures relevant to smallholders and local communities aiming to participate in markets, such as:

- Markets: Establishment and operations of producer organizations: covers the legal requirements relating to the establishment of agricultural cooperatives, including registration, share capital requirements, membership, and government participation. This indicator also covers obligations on cooperatives to comply with the principle of non-discrimination.
- Land: Customary land: measures issues such as legal recognition of customary land, ownership rights of customary land, registration procedures on customary land and compensation rights on (registered and unregistered) customary land in case of expropriation
- Gender: the inclusion of sub- indicators on gender across the range of core indicators.
- Seed: Additional data points are now collected on legal practices that contribute to the conservation and circulation of diverse seeds in the market. In EBA19 the Seed indicator is scoring legal practices that promote coherence between formal seed production and the local/informal production relevant to smallholder farmers. For example, data will be included on the farmer’s right to save, use, exchange varieties submitted to protection at the community level, and the availability of affordable quality control frameworks for producers of low value seed. By doing so, the indicator promotes a development of the seed sector that is pluralistic and includes public, private and community-based stakeholders.
- Finance: Access to credit and financial services is important in promoting agricultural development. Farmers and agribusinesses need working capital to expand operations, and payment services to support production activities. Ensuring the stability of finance institutions who are key providers of rural and agricultural finance while simultaneously promoting new channels of delivering financial services to unbanked population is essential for agricultural finance. EBA finance indicators measure regulations on non-bank lending institutions such as microfinance institutions (MFIs) and financial cooperatives which are important providers of rural and agricultural finance. EBA finance indicator also measures branchless banking channels which are important for farmers who live in rural areas and can benefit from the convenience of accessing financial services through bank agents and their mobile phones. Finally the indicator captures the ability to use movable collateral such as warehouse receipts which can create opportunities for farmers and agribusinesses to use their crops as collateral against a loan.
- Transport: Strong food transport systems help farmers to deliver goods to markets more safely and efficiently, with minimum loss or spoilage. This increases marketing opportunities and can help farmers to transform into more commercially viable agribusinesses
- Water is fundamental for crop production. Farmers must have access to enough good-quality water, at the right time and location. However, this need must be balanced with the needs of other water users and the environment.

The mix of indicators has been developed in consultation with governments, academia, the private sector and CSOs and it is felt to be an effective basket of measures to promote agribusiness investment and improved agricultural productivity, safety and quality control. All of these are essential to driving inclusive economic growth and therefore the potential equity of EBA’s results is considered to be positive.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio

Based on the analysis above, plus the evidence from the independent evaluation, it is considered that EBA continues to represent good value for money and should continue.

DFID can increase the effectiveness of the EBA by taking an even more proactive, strategic approach to uptake with country offices and centrally managed programmes and recommendations on this are included elsewhere.

EBA supports DFID’s wider inclusive and sustainable economic development portfolio in a number of ways:
- EBA indicators provide an objective starting point for engagement with governments on enabling environment reform. They therefore support country office engagement with governments and support central programmes promoting regional reform, such as the Food Trade and Resilience programme.
- The focus on investment climate reform is intended to facilitate investment and supports the objectives of programmes on agribusiness investment such as through AgDevCo, CASA and GAFSP.
- EBA’s coverage of middle-income countries positions it well to support DFID’s building markets agenda and the broader objective of shared prosperity.

Quality of financial management

The EBA Multi-Donor Trust Fund (MDTF) is managed in accordance with standard World Bank procedures for Trust Funds, including fees and staff salaries. DFID’s £950,000 contribution for this financial year was disbursed in December 2017 and October 2018 and the final £475,000 is due to be disbursed in December 2018. The World Bank provided an unaudited trust funds financial report and a budget breakdown prior to the request for disbursement. Although the Trust Fund is not subject to independent audit, it is part of the single audit that the World Bank undertakes for all of its core Trust Fund Operations. As of the 30 of June 2018 the EBA (MDTF) and Parallel Trust Fund had a combined balance of $2,023,872 available for allocation.

Date of last narrative financial report	n/a
Date of last audited annual statement	n/a

E: RISK

Overall risk rating: Moderate

Risks are monitored and discussed with EBA as part of regular monitoring calls, and risks rated moderate-severe are actively managed through ongoing programme management. For example, the DFID-commissioned independent evaluation helps to define and manage the risk of not delivering regulatory change. EBA-donor conference calls take place on a quarterly basis and also provide a vehicle for managing certain risks e.g. the risk that the programme will not be financially sustainable over the long term.

An update against each of the programme risks is shown in Annex 4:

The majority of risks to the project’s ability to deliver results remain relevant. One risk, “The programme is not financially sustainable over the long term”, has been raised to severe as the project period is due to end at the end of 2019 and no firm commitments for future funding have been made by any of the existing donors, nor have any other sources of funding been discussed as yet. Donors are meeting in December to address this issue.

R7 DFID needs to consider its long-term engagement with EBA beyond the current phase which ends in 2020. Responsibility: DFID SRO by March 2019

F: DELIVERY, COMMERCIAL AND FINANCIAL PERFORMANCE

Performance of partners and DFID, notably on commercial and financial issues

The EBA team have delivered against their milestones. The 2019 report will be published in April 2019 rather than February/March 2019 in order to accommodate a Bank-wide review of the data and content prior to publication. This leaves a remaining 18 months during this phase for dissemination and engagement activities through to November 2020.

Performance of partnership
The EBA team have remained responsive to the donors in the multi-donor trust fund. They have kept donors up to date on progress and informed the group on proposed changes as well as the process to make decisions. The multi-donor trust fund met face to face in June 2018 in Washington. Other MDTF meetings have been via teleconferences.

H: MONITORING, EVIDENCE & LEARNING

Evidence and evaluation

During 2017/18 ITAD was appointed by DFID to conduct a review of EBA’s activities with a particular focus on the effectiveness of its engagement and dissemination activities. The evaluation found that overall EBA is a well-regarded credible tool for measuring compliance with good practice in the agribusiness policy and regulatory environment. It recommended that EBA invest more in strategic engagement and explore options for supporting regimes to implement the policy reforms which the data have highlighted. Key findings and recommendations were:

- The EBA biannual report is widely acknowledged as highly relevant and of high quality. The programme would benefit from shorter, more technically simple products and products tailored to different audiences. EBA should rely more heavily on local, national actors to drive change and influence national government policy, as well as international influencers.
- Engagement approach with a range of stakeholders has improved and needs to become more strategic in its nature. Private sector engagement has been strong but there is a need to find ways to engage international NGOs and smallholder groups more effectively.
- Donors, including DFID, could do more to make use of the outputs of EBA in their programming and policy engagement with national governments.
- EBA’s donors should consider making available additional funds to support implementation by national governments of policy reforms which emanate from the findings of the EBA’s work. Governments have requested help to take action based on the EBA findings and to develop a roadmap for the implementation of reforms in their countries.
- EBA should seek to evaluate the impact of its policy recommendations and the reforms that are undertaken on the basis of these recommendations.

The findings of the evaluation were presented at the 2018 annual donor meeting and were broadly accepted by EBA and donors. In particular, donors agreed to more actively share approaches and successes relating to uptake and dissemination within their organisations and a quarterly meeting between donors and EBA was instituted. EBA has produced a more strategic dissemination and outreach work plan which includes a prioritisation of countries for dissemination work and clearly defines the criteria for the selection of these countries. Donors did not support the proposal to create an additional fund to support implementation of government reforms in response to EBA’s findings on the basis that these funds should be made available at a national level rather than through a global vehicle. The World Bank agreed to publication of the evaluation in response to DFID’s requirements on transparency.

Monitoring progress throughout the review period

The programme has continued to be monitored on a quarterly basis through calls with the EBA implementation team and reviews of progress against milestones. This work is supplemented by an annual EBA meeting and quarterly phone calls of all donors and EBA to review areas of joint interest (e.g. engagement in dissemination activities) and address significant risks (e.g. future funding).

Recommendations from the 2017 annual review (and actions/responses)

EBA to continue to keep donors apprised in terms of the development of the methodology to assess environmental sustainability indicators and potentially engage with donors on discussions relating to methodology options and approaches.

EBA has completed the development of indicators to assess environmental sustainability which were piloted with a small number of countries in December 2017 and are now fully built into the 2019 data collection cycle. The indicators are captured under a number of different headings rather than us part of a separate section on environmental sustainability, reflecting the crosscutting nature of this subject.

Review and release gender background note for external access.

EBA has produced a gender note which compares the data gathered by EBA and the Women in Business and the Law indicator set and draws out comparisons and key trends. This note has been peer-reviewed and is in the process of being published as part of a new type of communications activity which summarises technical findings into more accessible, short outputs and makes use of social media. The note and other communication materials are scheduled for launch in November 2018.

EBA and DFID to engage closely in using these indicators for the development of the new CASA (Commercial Agriculture for Smallholders) Programme, in terms of establishing effective monitoring and embedded in programme design.

The log frame for CASA is under development and will seek to use EBA indicators to assess regulatory reforms in Nepal, Uganda and Malawi. In addition to this, ARD’s Food Trade and Resilience Programme is looking at using EBA indicators on market access to track progress on regional trade reforms.

EBA to develop the evidence links between indicator dissemination and legal and regulatory reform. DFID to buy into and support this process and analysis.

EBA has been actively tracking the links between its dissemination activities and legal and regulatory reform and reported this in it 2018 uptake report. It has also contributed to The Africa Agriculture Status Report 2018 sharing findings and evidence on successful approaches to driving regulatory reform, including evidence highlighting the correlation between countries with strong regulatory regimes on paper and strong de facto implementation of those regulations.

Improve use of social media for dissemination of methodology and results of EBA work

EBA has hired a social media consultant to develop a social media communications strategy and is using this to support the launch of the tender information note referenced above. EBA intends to increase the amount of social media communications around the launch in 2019 and other stand-alone outputs on issues such as fertiliser and irrigation over the next year.

It is recommended in future years that EBA disaggregates financial reporting on different stages of programme activities to show the specific comparative costs of data collection, report preparation and dissemination.

This has been done and is reported in the VFM section.

It is recommended that the ongoing process of using World Bank feedback mechanisms to inform and fine-tune World Bank operational policy and approach is further developed in the coming year clearly demonstrating the link between dissemination of EBA indicators, operational impact and regulatory reform.

EBA, as a World Bank led project, has strong links with World Bank country office teams and has worked closely with them to identify the links between dissemination activities and regulatory reform. Each EBA country has an agriculture focal point in one of the World Bank institutions that provides support on data gathering and report dissemination. The independent evaluation reviewed the link between dissemination activities and regulatory reform - see above for further information.

The EBA team could do more to demonstrate the effectiveness of the report and engagement activities to ensure that the research continues to inform strategies, policies and operations.

The independent review conducted by DFID and the Report on Dissemination Engagement Activities from EBA during 2018 clearly highlight the effectiveness of the EBA indicators on stimulating dialogue on regulatory reform and initiating the process of policy change. The revised Engagement Strategy with its clear focus on a limited number of countries serves as a strong basis on which to further influence reform.

Acronyms

AfDB	African Development Bank
AGRA	Alliance for a Green Revolution in Africa
AGRF	Africa Green Revolution Forum
BBA	Benchmarking the Business of Agriculture
BMGF	Bill and Melinda Gates Foundation
CAADP	Comprehensive African Agricultural Development Programme
CSO	Civil Society Organisation
CSPF	Civil Society Policy Forum
DANIDA	Danish International Development Agency
DBA	Doing Business in Agriculture
EBA	Enabling the Business of Agriculture
FAQ	Frequently Asked Questions
IFPRI	International Food Policy Research Institute
IMF	International Monetary Fund
MDTF	Multi-Donor Trust Fund
MM	Market Metrics
SRO	(DFID) Senior Responsible Owner
VfM	Value for Money
WBG	World Bank Group
WG	Working Group

Annexes

Annex 1: Summary of Impact to date

Dissemination
Activity
Operational
Support
COUNTRIES WHERE INTEREST AND DIALOGUE HAS BEEN GENERGATED
COUNTRIES WITH IMPROVED AGRIBUSINESS REGULATIONS
Ownership operational teams
COUNTRIES WHERE ACTION HAS BEEN INITIATED
COUNTRIES WHERE AWARENESS HAS BEEN RAISED
Discussions
& Dialogue

The team has set target for results in each of the aforementioned categories, as follows:

        AWARENESS	EXPRESSION	INITIATION	IMPROVED
RAISED	OF INTEREST	OF REFORMS	REGULATIONS

Target

6 countries

Target

15 countries

Target

32 countries

Target

4 countries

Expression of interest

Of the 32 priority countries targeted, a few have already expressed interest in using EBA for policy analysis and planning: Vietnam, Sudan, Rwanda, Cambodia, Zimbabwe and Malawi. Others – Kenya, Tanzania, Uganda, Zambia and Cote d’Ivoire – have expressed initial interest, to be followed up on, deepened and formalized. Once dissemination activity is carried out in Ghana, Nigeria, Kazakhstan, Cameroon, Mali, Liberia, Mozambique, Myanmar, India, Sri Lanka, Egypt, Jordan and Nepal, an initial assessment of interest in the use of EBA for their policy work will be made.

Initiation of EBA-based reform

Of the priority countries, there is one where a reform has already taken place: Vietnam. In several others, projects financed by the WBG have incorporated evidence provided by EBA, which is expected to lead to a reform.
Rwanda (Programme-for-Results)
- Cambodia (Investment Project Financing)
- Zimbabwe (Technical Assistance)
- Malawi (Policy and technical dialogues)
- Lao PDR (Investment Project Financing)
These projects, and the WBG operational teams driving them, will require continuous support from the EBA team if they are to include and implement plans that lead to a reform related to EBA findings.

Improved agribusiness regulations

In three of the priority countries, there have been regulatory improvements reported: Vietnam, Ghana and Sudan. In two of them, improvements have been made in the following areas and reflected in reforms:
- Vietnam – seed, fertilizer and machinery
- Ghana – seed, machinery and finance (branchless banking)
Improvements in Sudan remain to be assessed in the EBA 2019 Report.

Annex 2 - Outreach and dissemination events

Enabling the business of Agriculture (EBA) events Nov 17-Oct 18
Month	Title of Event	Where	Audience
Nov-17	Launch of the EBA 2017 Report	Beijing, China	Government officials, Academia
Feb-18	Joint AGRA-WB EBA Technical Workshop	Accra, Ghana	Public sector, the private sector, civil society organizations, and the research community – including representatives from the relevant Ministries.
	Joint AGRA-WB EBA Technical Workshop	Ouagadougou, Burkina Faso	Public sector, the private sector, civil society organizations, and the research community – including representatives from the relevant Ministries.
	Joint AGRA-WB EBA Technical Workshop	Abuja, Nigeria	Public sector, the private sector, civil society organizations, and the research community – including representatives from the relevant Ministries.
	High-level discussions on EBA17 findings	Abidjan, Cote d’Ivoire	Department of Planning, Programming and Finance of the Ministry of Agriculture and Rural Development
	CSO Discussion on EBA	Abuja, Nigeria	CSOs
	4th Annual Agricultural Policy Conference	Dodoma, Tanzania	High-level Government officials, including Parliamentarians, private sector, academia
April-18	Launch of the EBA 2017 Report	New Delhi, India	Government officials, private sector representatives, CSOs, research organizations and multilateral development agencies
	Launch of the EBA 2017 Report	Kathmandu, Nepal	Public sector, private sector, multilateral development agencies
	CSO Discussion on EBA	Kathmandu, Nepal	CSOs
	High-level meeting with Ministry of Agriculture	Nairobi, Kenya	Minister of Agriculture, Ministry Permanent Secretaries, and Director Generals
May-18	Joint AGRA-WB EBA Technical Workshop	Lilongwe, Malawi	Government officials (Representatives from Ministry of Agriculture, Ministry of Industry and Finance), Seed companies, fertilizer associations, financial entities, farmer service firms and commercial agriculture initiatives, and CSOs
	Joint AGRA-WB EBA Technical Workshop	Bamako, Mali	Public sector, the private sector, civil society organizations, and the research community
	Investors Round Table session at Astana Economic Forum / Second Kazakhstan Competitiveness Forum	Astana, Kazakhstan	Private sector representatives, Government officials, academia
	High-level discussions on EBA 2017 Report findings for Nepal / Technical workshop on EBA 2017 Report	Kathmandu, Nepal	Government officials (Agriculture, Land Management and Cooperatives, Ministry of Finance and the National Planning Commission), private sector- input companies, financial institutions, investment firms, development agencies, CSOs
June-18	Joint AGRA-WB EBA Technical Workshop	Maputo, Mozambique	Public sector, the private sector, civil society organizations, and the research community – including representatives from the relevant Ministries.
	Launch of Report: Closing the Potential-Performance Divide in Ugandan Agriculture	Kampala, Uganda	Government officials, private sector, CSOs, academic and research community
	High-level meeting with Ministry of Finance and Ministry of Agriculture / Private sector Roundtable	Tegucigalpa, Honduras	Government officials, private banks, agriculture input companies, research institutes, universities, CSOs and donor agencies
Oct-18	Technical Discussion Workshop with Min of Ag Taskforce	Astana, Kazakhstan	Government representatives from the Ministries of Agriculture, of Finance, and of Information and Communication
	EBA Introductory Workshop	Tashkent, / Uzbekistan	Government representatives and donor organizations
	El Nino Southern Oscillation and Enabling the Business of Agriculture Dissemination and Consensus Building Workshop	Phnom Penh, Cambodia	Government representatives, academic and research community, private sector
	Work sessions with Vietnamese Government policy institutions	Hanoi, Vietnam	Policy experts and government representatives
	El Nino Southern Oscillation and Enabling the Business of Agriculture Dissemination and Consensus Building Workshop	Vientiane, Lao	Government representatives, academic and research community, private sector

Annex 3 – Gender Indicators in EBA

Annex 4 – Progress against risks

Risk Description	Mitigation Strategy	Residual Risk	Update since last AR
The programme is not financially sustainable over the long term	The EBA team needs to fundraise money from sources other than donors. This should include country governments financing data collection for the indicator in their own country. It is appreciated that this takes time but needs to be part of their strategy from early on. Further, the team should explore if there is interest in the private sector or with CSOs to finance the EBA, possibly through a ‘black box’ fund.	Severe	Risk raised to severe due to the short timeframe remaining (programme ends December 2019). USAID have expressed some willingness to continue funding provided that other donors participate, Gates have confirmed they are unlikely to fund beyond this pilot phase. Donors have asked the World Bank to look at internal sources of funding. Donors agreed to discuss the issue in the next quarterly call (Dec 2018).
Programme activities do not lead to regulatory changes.	EBA team will work closely with operational colleagues in the World Bank, and in other institutions, to translate findings into policy dialogue and actions that trigger changes in the regulatory environment related to the project’s interventions. DFID to develop and implement its own dissemination plan with country offices and government facing programmes.	Major	This risk was the overriding evaluation question of the recent DFID funded review. Evidence of successful influencing a regulatory change has already been identified. An enhanced dissemination plan is underway targeting a core group of 30 countries. Mitigation strategy has been adjusted to include enhanced DFID focus on building EBA into programmes which engage with national governments.
The programme narrowly focuses on indicators that measure the status of laws and regulations in the books and does not reflect the experience of businesses in reality.	EBA is expanding its indicator set to capture the practice and efficiency of processes to comply with laws and regulations.	Moderate	Efficiency Indicators are now firmly established within the EBA framework and will be measured in the 2019 data (as they were in 2017)
Indicators produced are not considered to be relevant and/or rigorous.	A broad group of experts and stakeholders (including researchers and target users) have been consulted and their advice is informing indicator selection and subsequent refinements.	Moderate	No further update necessary - indicators are still based on the same group of experts and advisers input.
Lack of government buy-in	Governments of countries covered by the EBA are being targeted for dissemination and consultation. Proper interpretation and understanding of the evidence provided by EBA indicators will be fostered through dissemination events and technical workshops.	Moderate	Results reported in Annex 1 indicate positive progress on government buy in.
Pressure over regulatory indicators and country rankings lead to a pushback on the EBA.	EBA should carefully consider pros and cons before proceeding with country rankings.	Moderate	Ranking of countries has been determined to not be appropriate due to the destruction of competition between countries. Instead regional comparisons and global comparisons are made between each country and subsectors of the countries sampled.
Unintended consequences	The programme will devise a way to model the expected policy responses from the indicators to ensure against negative outcomes.	Moderate	EBA continues to monitor these consequences during National country dissemination and engagement. Recent evaluation did not identify any significant unintended consequences.
The process of agreeing to policy changes is not sufficiently inclusive and consultative at country level.	The programme is paying attention to not only encouraging policy reforms, but how they have been achieved, particularly in terms of including key stakeholders in the discussions that EBA indicators generate.	Moderate	EBA has continued to engage private sector, civil society and academia in country in order to support them to use the EBA data to influence change
Significant variations between the regulatory frameworks for different agricultural commodities limit the comparability of EBA indicators.	Indicators will use a standardised case study to allow comparison across different countries.	Minor	No change since 2017
Governments narrowly target their reform efforts to trigger EBA indicators only.	Besides broadening EBA indicators to measure practice-related elements of the regulatory framework, the team will work with other World Bank units to support their programmes providing technical assistance to client governments that go beyond what is measured by the indicators.	Minor	No evidence of this was identified by the recent evaluation. EBA reform date is used as a means of starting a discussion on a range of potential policy improvements. EBA scope of implementing and pursuing these changes is limited - they are primarily a data and information distributor.
Confusion over or misinterpretation of what the indicators do and don’t measure.	EBA to continually communicate the range and limits of the data.	Minor	Level of EBA continues to engage a wide number of stakeholders in order to ensure that the data is properly understood at a national and international level e.g. CSOs, companies, donors and governments
Countries selected are not aligned to programme objectives.	The World Bank will consult donors on the country selection process. A geographically diverse set of countries at different stages of agricultural growth will be selected to allow for sub-comparisons.	Minor	Addition of new countries reflect the interests of the donor group.
Insufficient attention given to gender and environmental sustainability	Integration across relevant topic areas such as land, financial access and water	Minor	Gender and environmental sustainability were integrated into the 2017 report and will also be part of the 2019 report