## ERKP LF (Aug. 2015 update)
PROJECT NAME | ANNEX H: Log frame, Enhancing Resilience in Karamoja
IMPACT | Impact Indicator 1 |  | Baseline (Start) | Milestone 1 (Year 1) March 2014 | Milestone 2 (Year 2) March 2015 | Milestone 3 (Year 3) March 2016 | Milestone 4 (Year 4) March 2017 | End of Programme Target (March 2017)
Increased resilience of the population of Karamoja to climate extremes and weather events | Number of people indirectly supported to cope with the effects of weather and extreme climate events through early warning and preparedness systems (ICF indicator 1) | Planned | tbd | Early Warning (EW) & preparedness systems partly operational at local level across Karamoja | EW fully operational at local level across Karamoja. Preparedness systems operational in selected districts | EW & preparedness systems operational at local level with enhanced support from the national level. | - | EW & preparedness systems operational at national and local level across Karamoja (Population coverage 1.2 million)
|  | Achieved |  |  | Early warning analysis and reports are supporting all districts. 42% of targeted householdsare responding to DEWS messages. District contingency plans are not yet reviewed and supported (due October 2015)
Source
FAO & UN agencies monitoring & evaluation reports
| Impact Indicator 2 |  | Baseline (Start) | Milestone 1 (Year 1) March 2014 | Milestone 2 (Year 2) March 2015 | Milestone 3 (Year 3) March 2016 | Milestone 4 (Year 4) March 2017 | End of Programme Target (March 2017)
| Extent to which the Programme has a transformational impact (ICF indicator 15) . | Planned | Qualitative indicator to be desinged during inception phase | tbd | tbd | tbd | tdb | tbd
|  | Achieved |  |  | Baseline report due in October 2015
Source
Qualitative scorecard (tbc) against DFID methodology, can be independently assessed and triangulated
| Impact Indicator 3 |  | Baseline (Start) | Milestone 1 (Year 1/2) | Milestone 2 (Year 1) |  |  | Target (End Year 2)
| Strong evidence base identifies ways of increasing resilience and defines options for future investment [IFC] | Planned
Achieved
Source
| Impact Indicator 4 |  | Baseline (Start) | Milestone 1 (Year 1/2) | Milestone 2 (Year 1) |  |  | Target (End Year 2)
| Sustainable reduction in livestock mortality through government programmes | Planned
Achieved
Source
OUTCOME | Outcome Indicator 1 |  | Baseline (Start) | Milestone 1 (Year 1) March 2014 | Milestone 2 (Year 2) March 2015 | Milestone 3 (Year 3) March 2016 | Milestone 4 (Year 4) March 2017 | End of Programme Target (March 2017) | Assumptions
Increased resilience of targeted communities to climate extremes and weather events | Number of people directly supported to cope with the effects of climate change (disagregated by progamme and gender) (ICF indicator KPI 1 ) | Planned | 0 | 255000 | 300000 | 145000 | 173,807 | 873807 | UN & local partners able to work effectively with GoU The DPs can be persuaded to harmonise their support projects with the DDPs and national priorities. All partners {LG, OPM, Line Ministries, DPs (including NGOs)} are willing and able to reach agreement on reporting and coordinating outlines & processes and the office of the CAO has the capacity to monitor and oversee the process.
|  | Achieved |  | 273,760 (male - 118,758 and female - 155,000) | 272582
Source
|  |  | UN agencies monitoring reports | [5 empty] | Coordination at the national and local level enables effective programme development
| Outcome Indicator 2 |  | Baseline (Start) | Milestone 1 (Year 1) March 2014 | Milestone 2 (Year 2) March 2015 | Milestone 3 (Year 3) March 2016 | Milestone 4 (Year 4) March 2017 | End of Programme Target (March 2017) | Capacity to respond to 'spikes' in malnutrtion (MoH / UNICEF)
| Stabilisation in prevalence of Global (GAM) & Severe Acute Malnutrition (SAM) in children aged 6-59 months in Karamoja | Planned | GAM 13.1% SAM 3.9 % (May 2012 FNSA) | per baseline | GAM <11-12% SAM <2-2.5% | GAM <10-11% SAM <2.0% |  | GAM <10% SAM <2.0 % | Current levels of food security and access to health services are maintained
|  | Achieved |  | GAM 13.4% SAM 2.8% | GAM 12.8% SAM 3.2% |  |  |  | Weather or other shocks do not create another emergency situation in Karamoja
Source
UNICEF SMART Surveys / FSNA surveys : Marc 2015 EoY result from Dec 2014 FSNA
|  |  | Baseline (Start) | Milestone 1 (Year 1/2) | Milestone 2 (Year 1) |  |  | Target (End Year 2)
| Local government and partners using coordinated early warning systems | Planned
Achieved
Source
| Outcome Indicator 5 |  | Baseline (Start) | Milestone 1 (Year 1/2) | Milestone 2 (Year 1) |  |  | Target (End Year 2)
| Climate resilience integrated by Local Government into District Plans [IFC] | Planned | None integrated | CR entry points identified | 3 CR inclusions into DP |  |  | 6 CR inclusions into DP
Achieved
Source
| Outcome Indicator 6 |  | Baseline (Start) | Milestone 1 (Year 1/2) | Milestone 2 (Year 1) |  |  | Target (End Year 2)
| Increased evidence base on building resilience is used by expanded donor investment plans | Planned
Achieved
Source
INPUTS (£) | INPUTS (£) |  | Govt (£) | Other (£) | Total (£) |  |  | DFID SHARE (%)
| 34500000 |  | 0 | 0 | 34500000 |  |  | 100%
INPUTS (HR) | DFID (FTEs)
1.5
OUTPUT 1 | Output Indicator 1.1 |  | Baseline (Start) | Milestone 1 (Year 1) March 2014 | Milestone 2 (Year 2) March 2015 | Milestone 3 (Year 3) March 2016 | Milestone 4 (Year 4) March 2017 | End of Programme Target (March 2017) | Assumption
Increased access to high impact nutrition interventions | Number of VHT members actively engaged in nutrition screening, referal and follow up of children with SAM . Numbers are cumulative | Planned | 0 | 500 | 1000 | 3000 | _ | 3000 | Security situation allows access to agencies to implement
|  | Achieved |  | 1174 | 1908
|  | Source | [6 empty] | Health and community workers are motivated to implememt programme
UNICEF coverage and evaluation assessments. March 2015 - EoY - Data from UNICEF Dec 2014 progrep
| Output Indicator 1.2 |  | Baseline (Start) | Milestone 1 (Year 1) March 2014 | Milestone 2 (Year 2) March 2015 | Milestone 3 (Year 3) March 2016 | Milestone 4 (Year 4) March 2017 | End of Programme Target (March 2017) | Commodity pipeline fully funded and implemented without breaks
| Number of SAM children enrolled in the therapeutic feeding programmes (gender disaggregated) | 2015 | 0 | >65% ( 4,794; of the total SAM burden) | >70% (12,530 ; of the total SAM burden) | >75% (13,425 ; of the total SAM burden) | 0 | 37590
|  | Achieved |  | 4556 (oct 2013 - Mar 2014) | 9692 (Apr 2014 - Mar 2015) (60% of caseload)
|  | Source | [6 empty] | Implementing agencies perform to quallity standards
UNICEF reports, mid term reviews, and evaluations
| Output Indicator 1.3 |  | Baseline (Start) | Milestone 1 (Year 1) March 2014 | Milestone 2 (Year 2) March 2015 | Milestone 3 (Year 3) March 2016 | Milestone 4 (Year 4) March 2017 | End of Programme Target (March 2017) | Commodity pipeline fully funded and implemented without breaks
| Number of moderatly malnourished children (GAM), pregnant & lactating women enrollled in the programme. (women, children,gender & age disaggregated ) |  | 0 | 50000 | 100000 | 25000 | _ | 175000
|  | Achieved |  | 44,413 (6 months Oct 13 - Mar 14) | 66,876 (April 2014 - Mar 2015) Under 5s and P&L women
|  | Source | [6 empty] | Implementing agencies perform to quallity standards
WFP PRRO reports, mid term reviews, and evaluations
| Output Indicator 1.4 |  | Baseline (Start) | Milestone 1 (Year 1) March 2014 | Milestone 2 (Year 2) March 2015 | Milestone 3 (Year 3) March 2016 | Milestone 4 (Year 4) March 2017 | End of Programme Target (March 2017) | Implementing agencies have technical capacity to deliver improved programmes
| Dietary diversity: % of children 6-23 months who received foods from 3 or 4 food groups (Cummulative %) | Planned | 30-50% ( FNSA, May 2012) | per baseline | 5% increase | 5% increase | _ | 15% increase
|  | Achieved |  | 42% MMF and 1.5% MDD | 3.1% MMD and 36.5% MMF - based on Dec 14 FSNA
IMPACT WEIGHTING (%) |  | Source | [6 empty] | RISK RATING
25% |  | UNICEF SMART surveys | [6 empty] | Low / Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  |  | DFID SHARE (%)
| 10850000 |  | 0 | 0 | 10850000 |  |  | 100%
INPUTS (HR) | DFID (FTEs)
0.35
OUTPUT 2 | Output Indicator 2.1 |  | Baseline (Start) | Milestone 1 (Year 1) March 2014 | Milestone 2 (Year 2) March 2015 | Milestone 3 (Year 3) March 2016 | Milestone 4 (Year 4) March 2017 | End of Programme Target (March 2017) | Assumptions
Increased food and livelihoods security | Household (HAS) and community asset scores (CAS) - WFP PWP | Planned | HAS 6.2 (Oct 2013) | HAS increased in at least 80% of the targeted households | HAS increased in at least 80% of the targeted households | HAS increased in at least 80% of the targeted households | _ | HAS / CAS increased in targeted households / communitiies | Security situation in Karamoja permits food security and livelihoods programmes to be continued
|  | Achieved |  | progress report showed overall HAS Score of 3.7 and CAS of 3.6 . For HAS this is an increase of 16% on the baseline in 80% of HH. | collected in the November 2015 survey
|  | Source | [6 empty] | Commodity pipeline fully funded and implemented without breaks
WFP NUSAF 2 monitoring reports & baseline assessments
| Output Indicator 2.2 |  | Baseline (Start) | Milestone 1 (Year 1) March 2014 | Milestone 2 (Year 2) March 2015 | Milestone 3 (Year 3) March 2016 | Milestone 4 (Year 4) March 2017 | End of Programme Target (March 2017)
| Number of women & men participating in Public Works Programmes (PWPs) | Planned | 0 | 160000 | 20000 | 20000 | _ | 200000 | Implementing agencies have technical capacity to deliver improved programmes
|  | Achieved |  | 189,615 (april 2014 prog rep) | 196,014 (based on the reach of the 1st distibution - rep in Dec 14 prog rep
Source
WFP NUSAF 2 baseline & monitoring & evaluation reports
| Output Indicator 2.3 |  | Baseline (Start) | Milestone 1 (Year 1) March 2014 | Milestone 2 (Year 2) March 2015 | Milestone 3 (Year 3) March 2016 | Milestone 4 (Year 4) March 2017 | End of Programme Target (March 2017)
| Number of cattle, sheep and goats vaccinated against epidemic diseases. | Planned | 0 | 0 | 40,000 (fmd vaccines) | 1,500,000 (500,000 cattle, 400,000 goats, 600,000 sheep) | _ | 1,540,000 | Implementing agencies perform to quallity standards
|  | Achieved |  | no action this year - budget moved out to 2014/15 & 2015/16 see QN. 4952927 | 0 | 40,000 cattle for FMD (april - June 15)
|  | Source | [6 empty] | No incidence of any serious cattle epidemic occurs
FAO baseline & monitoing & evaluation reports - veterinary services
| Output Indicator 2.4 |  | Baseline (Start) | Milestone 1 (Year 1) March 2014 | Milestone 2 (Year 2) March 2015 | Milestone 3 (Year 3) March 2016 | Milestone 4 (Year 4) March 2017 | End of Programme Target (March 2017)
| Number of agro-pastoralists and pastoralists with improved access to improved animal nutrition (sex disaggregated). | Planned | 0 | 0 | 4000 | 2000 | 5400 | 11400
|  | Achieved |  | no progress | 0 - field schools started in Jan 2015 data not yet available on the participants
Source
FAO baseline & monitoring & evaluation reports - animal nutrition
| Output Indicator 2.5 |  | Baseline (Start) | Milestone 1 (Year 1) March 2014 | Milestone 2 (Year 2) March 2015 | Milestone 3 (Year 3) March 2016 | Milestone 4 (Year 4) March 2017 | End of Programme Target (March 2017)
| Number of women and men agro-pastoralists trained in climate resilient animal husbandry techniques. | Planned | 0 | 0 | 3500 | 1900 | - | 5400
|  | Achieved |  | no progress | 0 field schools started in Jan 2015 data not yet available on the participants
IMPACT WEIGHTING (%) |  | Source | [6 empty] | RISK RATING
25% |  | FAO baseline & monitoring & evaluation reports - Agro-Pastoralist Field Schools | [6 empty] | Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  |  | DFID SHARE (%)
| 16400000 |  | 0 | 0 | 16400000 |  |  | 100%
INPUTS (HR) | DFID (FTEs)
0.35
OUTPUT 3 | Output Indicator 3.1 |  | Baseline (Start) | Milestone 1 (Year 1) March 2014 | Milestone 2 (Year 2) March 2015 | Milestone 3 (Year 3) March 2016 | Milestone 4 (Year 4) March 2017 | End of Programme Target (March 2017) | Assumption
Strengthened early warning and response systems | % of Communities, GoU and development partners reporting use of EW information in their planning of development and/or emergency response activities. | Planned | 20% of partners and 60% communities reported having implemented emergency activities (EA) according to Drought Bulletin (DB) recommendations (End-user survey, September 2012) | NA | 40% of partners and 70% communities reported having implemented EA according to DB recommendations | NA |  | 60% of partners and 80% communities reported having implemented EA according to DB recommendations | Government and partners agree on form of integrated early warning & response system
|  | Achieved |  |  | From Dec 2014 Prog Rep - Agronomic responses: 52%; Food stocking / economy: 39%; Livelihood diversification: 64%; Livestock husbandry responses: 67%; Physical measures: 32%; Public health responses: 59%; Soil & water conservation measures: 47%; Overall average: 49%
Source
ACTED DEWS Appraisal, Monitoring, and Evaluation Unit Assessment Reports
| Output Indicator 3.2 |  |  | Milestone 1 (Year 1) March 2014 | Milestone 2 (Year 2) March 2015 | Milestone 3 (Year 3) March 2016 | Milestone 4 (Year 4) March 2017 | End of Programme Target (March 2017) | Security situation in Karamoja permits EWS programmes to be continued Agencies involved in various EWS in Karamoja are supportive of coordination process
| Chronic and acute IPC food security analyses conducted |  | 0 | 1 Acute | 3 (2 Acute & 1 Chronic) | 2 (1 Acute & 1 Chronic) |  | 6 (4 Acute & 2 Chronic)
|  |  |  | 2(1 acture and 1 chronic) | 3 Chronic – Feb 2015 Acute – August 2014 November 2014 |  |  |  | Capacity is developed for implementation of effective preparedness and response plans
Source
|  | FAO monitoring reports - food security analysis | [6 empty] | Political will and stability remains adequate
| Output Indicator 3.3 |  |  | Milestone 1 (Year 1) March 2014 | Milestone 2 (Year 2) March 2015 | Milestone 3 (Year 3) March 2016 | Milestone 4 (Year 4) March 2017 | Target (March 2016)
| Community Animal Health Workers trained in participatory surveillance. |  | 0 | 0 | 220 | 200 |  | 470
|  |  |  | 0 | 60 CAHWs (22 Females and 38 Males )
IMPACT WEIGHTING (%) |  | Source | [6 empty] | RISK RATING
20% |  | FAO monitoring and evaluation reports - disease surveillance and diagnostics | [6 empty] | Low
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  |  | DFID SHARE (%)
| 1850000 |  | 0 | 0 | 1850000 |  |  | 100%
INPUTS (HR) | DFID (FTEs)
0.3
OUTPUT 4 | Output Indicator 4.1 |  | Baseline (Start) | Milestone 1 (Year 1) March 2014 | Milestone 2 (Year 2) March 2015 | Milestone 3 (Year 3) March 2016 | Milestone 4 (Year 4) March 2017 | End of Programme Target (March 2017) | Assumptions
Improved development co-ordination | Number of Local Government District Development Team members trained in DRR & climate awareness (ICF Indicator 13) | Planned | 0 | Capacity needs assessment conducted | 140 | 140 | 50 | 280 | DRR and climate awareness package agreed with districts
|  | Achieved |  | 0 | 0
Source
|  | FAO monitoring reports | [6 empty] | Response plans and triggers agreed at district level
| Output Indicator 4.2 |  | Baseline (Start) | Milestone 1 (Year 1) March 2014 | Milestone 2 (Year 2) March 2015 | Milestone 3 (Year 3) March 2016 | Milestone 4 (Year 4) March 2017 | End of Programme Target (March 2017)
| No. of district teams trained on contingency planning, preparedness and response for nutrition. Numbers are cummulative | Planned | 0 |  | 4 | 7 |  | 7
|  | Achieved |  | 0 | 0 - activities were due to commence in Q1 2015 - report due in August 2015
Source
UNICEF monitoring reports
| Output Indicator 4.3 |  | Baseline (Start) | Milestone 1 (Year 1) March 2014 | Milestone 2 (Year 2) March 2015 | Milestone 3 (Year 3) March 2016 | Milestone 4 (Year 4) March 2017 | End of Programme Target (March 2017)
| Number of updated disitict level contingency plans with response options (ICF Indicator 13) | Planned | 0 | Review of status of district contingency plans done | 70% update of district contingency plans in 7 districts | 30% update of contingency plans in 7 districts |  | 7 districts have fully updated contingency plans
|  | Achieved |  | 0 | 0 | status review completed for Aug 2015. Work on updating plans due.
Source
FAO partner monitoring reports
| Output Indicator 4.4 |  | Baseline (Start) | Milestone 1 (Year 1) March 2014 | Milestone 2 (Year 2) March 2015 | Milestone 3 (Year 3) March 2016 | Milestone 4 (Year 4) March 2017 | End of Programme Target (March 2017)
| Two catchment management plans developed and being implemented | Planned | 0 |  |  | • Rangeland management plan for two watersheds; Water Risk and Sustainability Assessment | Catchment Management Plan for Lokok and Lokere | 2 operational plans developed and being implemented
|  | Achieved |  | 0 | 0
IMPACT WEIGHTING (%) |  | Source | [6 empty] | RISK RATING
15% |  | FAO and GIZ reporting against Water Addendum | [6 empty] | Low
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  |  | DFID SHARE (%)
| 1340000 |  | 0 | 0 | 1340000 |  |  | 100%
INPUTS (HR) | DFID (FTEs)
0.15
Footnote 1:
OUTPUT 5 | Output Indicator 5.1 |  | Baseline (Start) | Milestone 1 (Year 1) March 2014 | Milestone 2 (Year 2) March 2015 | Milestone 3 (Year 3) March 2016 | Milestone 4 (Year 4) March 2017 | End of Programme Target (March 2017) | Assumptions
Increased evidence and learning | No. of evidence / knowledge (ICF Indicator 14) areas identified, defined, researched and analysed. Numbers are cumulative. | Planned | 0 | 2 | 4 | 8 | 8 | 16 | Forum developed for coordinated approach by implementing partners, GoU ministires, and other partners
|  | Achieved |  | 2 | 4
|  | Source | [6 empty] | Political will exists or is generated to influnece policies and programmes
Programme management monitoring reports - innovation fund & specific research studies
| Output Indicator 5.2 |  | Baseline (Start) | Milestone 1 (Year 1) March 2014 | Milestone 2 (Year 2) March 2015 | Milestone 3 (Year 3) March 2016 | Milestone 4 (Year 4) March 2017 | End of Programme Target (March 2017)
| ``````` | Planned | 0 | Study-plan & contracting finalised | Initial feasibility study conducted & results disseminated | Follow-up research conducted, training materials developed, training conducted |  | Watershed management feasibility study fully developed
|  | Achieved |  | changed | -
Source
FAO monitoring reports
| Output Indicator 5.4 |  | Baseline (Start) | Milestone 1 (Year 1/2) | Milestone 2 (Year 1) |  |  | Target (End Year 2)
|  | Planned | 0 | Feasibility assessed Plan finalised | Water sources review completed |  |  | Field monitoring completed | Community Based Integrated Watershed Management is found to be an appropriate model for Karamoja
Achieved
| Output Indicator 5.4 |  | Baseline (Start) | Milestone 1 (Year 1/2) | Milestone 2 (Year 1) |  |  | Target (End Year 2)
| Baseline survey conducted (of what?) | Planned | 0 | Plans developed | Survey 50% complete |  |  | Survey complete, data analysed
Achieved
Source
FAO Component 1.1 Assessments
IMPACT WEIGHTING (%) | [8 empty] | RISK RATING
15% | [8 empty] | low
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  |  | DFID SHARE (%)
| 1860000 |  | 0 | 0 | 1660000 |  |  | 100%
INPUTS (HR) | DFID (FTEs)
0.35
Non Output Costs | 1) Advisor & M&E costs | 1200000
| 2) Contingency fund | 1000000
| Total non output costs | 2200000