Project Completion Review – Cover Summary Sheet

Review Date:	30 June 2015

Title: United Kingdom International Search and Rescue (UKISAR) Deployment Support Programme
Programme Code: 203423	Start Date: 01 Nov 2012	End Date: 31 March 2015

Summary of Programme Performance

Year	2013
Programme Score	A
Risk Rating	Low

Financial Position

Original Programme Value	£519,681
Total programme spend	£462,102.91
Log-frame revisions	Impact weightings have been revised slightly for all Outputs in line with DFID revised guidance that Impact weightings can no longer be less than 10%: / Output: Initial weighting: Revised: / 1 (UK ISAR) 29% 30% / 2 (UK ISAR) 29% 30% / 3 (UK ISAR) 14% 10% / 4 (UK ISAR) 14% 10% / 5 (UK ISAR) 9% 10% / 6 (Fire AID) 5% 10% / Following the recommendations the 2013 Annual Review, Output Indicator 4.4 has been amended. The target milestone on number of operational canines available for immediate response has been reduced from 14 to 12, to reduce costs and to align to the 3:1 ratio principle between personnel and canine. / All other Outputs, Indicators and Milestones remain the same.

Follow up actions required following closure

This programme ended on 31st March 2015, however DFID has renewed the programme to ensure the UK retains its existing search and rescue capability to meet international development commitments.

The formal agreement between DFID, the Cabinet Office (CO), the Department for Communities and Local Governments (DCLG) and the Chief Fire Officers Association (CFOA) known as the ‘Memorandum of Understanding Concerning UK Fire and Rescue Sector Support to HMG for Emergency Response Operations Overseas’ which underpins this DFID Project will also be updated, agreed and signed by all participants.

A. Introduction and Context

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-203423/
DevTracker Link to Log frame:

Outline of the programme
The UK provided £434,681 over a 28 month period (Nov 2012 to Mar 2015) to support the training and standby costs of UK International Search and Rescue (UKISAR) teams provided by UK Fire and Rescue Services (former fire brigades). This support ensured that UKISAR was ready to deploy for sudden onset emergencies, providing lifesaving support in the immediate aftermath of major disasters.

This funding was critical to provide 24/7 availability of a trained, experienced UKISAR team, equipped to the necessary international standards. UKISAR wil be able to continue to draw on 260 fully trained responders, along with a medical support team, to deploy teams of between 45 and 68 personnel in response to sudden onset emergencies.

To complement UKISAR activities the UK provided an additional £85,000 over two years (June 2013-Mar 2015) to support Fire AID activities overseas. They work with local government agencies, communities and fire & rescue services to provide much needed equipment, accompanied by training for trainers and assistance with emergency response strategies. This UK funding formed part of a sustainable local initiative, involving civil society and local policy makers to have maximum impact.

What the programme achieved:

UKISAR are trained and remain certified to the highest international standards, as overseen by the International Search and Rescue Advisory Group (INSARAG). They are equipped and ready for very rapid deployment; enabling DFID to rescue people affected by overseas disasters, help to co-ordinate local rescue efforts and to contribute to wider international rescue capacity.

The retention size of such a UKISAR deployment Team remains up to 60 to 70 personnel drawn from the 15 Fire and Rescue services. The UKISAR deployment teams continues to include rescue dogs, and the teams are equipped to provide a “Heavy” rescue response (as classified by the UN) with the capability to rescue people from collapsed buildings constructed from steel framed or steel-reinforced concrete across two separate worksites. If necessary, the UK also has the capacity to provide a “medium” search and rescue deployment, with the capability to rescue trapped people from collapsed buildings – at one worksite or multiple smaller scale sites. UK support will continue to enable a “medium”, or if necessary “heavy” deployment to be drawn from the 15 UK Fire and Rescue services; staffed, trained and equipped to the necessary standards of expertise with a 6 hour response time and a continuous 24/7 standby rota.

Fire AID: The results of UK support to Fire AID has been to strengthen and extend their network to make best use of expert volunteers and trainers; to establish a website to recognise UK donations and encourage wider membership; together with a database to track good quality redundant UK equipment available for donation to fire & rescue services in DFID target countries. This assistance will help support preparedness for fire and other risks, vital for preventing and responding to disasters and conflict.

## B: PERFORMANCE AND CONCLUSIONS

Overall Outcome Assessment
UK ISAR have retained and enhanced their capacity and remain certified to the highest international standards.

As the UK ISAR deployment to the Bosnia floods demonstrates, the niche assistance met critical humanitarian needs, the UK fire service water rescue team assisted the BiH national government in the immediate search and rescue phase and to restore power lines and infrastructure. The most recent deployment to Nepal following the devastating Earthquake reaffirms the critical importance of this UK capacity (the deployment to Nepal falls outside of this programme, however it will be reviewed and evalutated during the initial Annual Review under the new funding).

The 2010 independent Humanitarian Emergency Response Review (HERR) chaired by Lord Ashdown, concluded that; DFID should retain its existing search and rescue capability, this remains the case. DFID support to UKISAR is needed to ensure the personnel are staffed, trained and equipped in a state of readiness for rapid and effective deployment for the UK’s international response to sudden onset emergencies. These international requirements are additional to those required by for domestic UK response, and cannot be covered by national/county level Fire and Rescue Service budgets.

Output Score and Description (UK ISAR)
Output number per LF	Output Score	Impact weighting	Output Description
1	A++	30%	(UK ISAR) Current frameworks and processes are used to develop and deliver operational training to ensure the competence of all operational staff. This will include acquisition, developmental and maintenance of competence training.
2	A+	30%	The UK ISAR heavy equipment cache is maintained at a constant state of mission readiness and complies with general requirements as determined by the INSARAG guidelines. This includes planned and agreed maintenance, R&D and asset refresh programmes.
3	A	10%	UK ISAR makes an effective contribution to the development of INSARAG governance and methodologies to improve international urban search and rescue assistance.
4	A	10%	All UK ISAR personnel and canines on request are fully prepared to deploy overseas and operate in austere environments for up to 14 days.
5	A	10%	UK ISAR has effective management, and administration functions in place to support the operational elements of the team.

Output Score and Description (Fire AID)
Output number per LF	Output Score	Impact weighting	Output Description
6	TBC	10%	Fire AID better able to track availability of UK equipment for donation and match to applications for assistance from target countries.

Lessons and how these have been shared

UK ISAR: There is currently one structural engineer as part of the UK ISAR platform, given recent deployments and nature of assistance, the number of structural engineers may need to be increased to build in flexibility and rotational capacity. It is particularly important to avoid exhaustion during emergencies when the team is required to operate for extended durations.
## C: DETAILED OUTPUT SCORING

Output Title	Current frameworks and processes are used to develop and deliver operational training to ensure the competence of all operational staff. This will include acquisition, developmental and maintenance of competence training.
Output number per LF		1	Output Score	A++
Risk:		Low	Impact weighting (%):	30%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Yes

Indicator(s)	Milestones	Progress
1.1 No. of staff completing technician acquisition and maintenance course.	260 staff (by Project Completion date of 31 March 2015)	249 of the UK ISAR team have achieved these baseline standards. / In addition 240 staff have completed further courses cultural awareness, safety and security, international operations, personal preparedness, health and hygiene, media and DVI awareness. / 264 staff complete maintenance of competence courses on a regular basis with delivery achieved through a mixture of national and “in house” programmes.
1.2 No. of staff completing specialist and technical support acquisition and maintenance courses.	120 staff (by Project Completion date of 31 March 2015).	114 staff have undertaken various National Resilience USAR specialist courses including hot cutting, confined spaces supervisor, timber shoring, and chainsaw operator; / All team members consistently received international deployment modules via series of weekend workshops and continuous professional development modules.
1.3 No. of national training exercises completed that include full deployment cycle.	6 x national exercises completed including the 2014 IER.	UK ISAR personnel have regularly attended national-scale exercises as well as participating in international exercises in excess of the milestone (some examples listed below).

Key Points
Output exceeded as UK ISAR predominantly recruits personnel from Fire and Rescue Services (FRSs), with exception of Scotland; Manchester; Cheshire, who are also currently serving whole time or retained USAR technicians. These staff members are required to complete basic acquisition and maintenance of skill courses, for the following durations USRT1 (1 week), USRT2 (2 weeks), line access and casualty management (3 days), confined space operator, (2 days) and safe working at height (2 days).

Indicator 1.2
Additional specialist and technical support acquisition and maintenance courses undertaken:
- 1 x UK ISAR structural engineer completed EU Technical experts and FEMA structural specialist courses;
- 6 x USAR Medical Team & sector medic courses; attended by an average of 30 personnel;
- 4 x team medics completed FEMA medical specialist courses (in the USA);
- Trauma Risk management course (delivered by Military trauma specialist) attended by 23 personnel.
- 6 x specialist slinger/signaller and appointed persons courses delivered and attended by 64 personnel.
- 2 x command support communications course delivered to 24 personnel.
- 48 personnel completing Union Civil Protection Mechanism courses (8 different courses available), delivered across EU participating states;
- 57 Instructors have been nominated by FRSs to deliver International SAR training and capacity building;
- 12 personnel completed hostile environment security awareness courses;
- 12 personnel completed exchange programmes focussed on trauma management with the Cape Town Ambulance Service;

Indicator 1.3; the following represents some of the national and international exercises completed:

Exercise type	ISAR Personnel (And duration)	Interaction with international teams
Exercise Tusker, UK / November 2012	100 / (4 days)	Full field exercise alongside B-FAST (Belgium) medium team.
EU field exercise, Denmark 2013	38 / (6 days)	Earthquake scenario with teams from Iceland, Estonia, and Czech Republic
UN earthquake simulation, Poland, 2013	10 / (6 days)	Earthquake scenario with teams from Germany, Spain, Poland, Russia, Belarus
INSARAG earthquake simulation exercise Switzerland 2013, and 2015	6 / (4 days)	Table top exercise 12 countries represented. UK ISAR management team participation
EU field exercise, Italy 2013	70 / (4 days)	Heavy deployment with Estonia, Hungarian and Austrian USAR teams.
Exercise Poacher, UK / 2014	70 / (4 days)	Full heavy deployment exercise in preparation for INSARAG external classification.
EU field exercise 2014	67 / (5 days)	Full heavy deployment to Venice, Italy

Output Title	The UK ISAR heavy equipment cache is maintained at a constant state of mission readiness and complies with general requirements as determined by the INSARAG guidelines. This includes planned and agreed maintenance, R&D and asset refresh programmes.
Output number per LF		2	Output Score	A+
Risk:		Low	Impact weighting (%):	30%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Yes

Indicator(s)	Milestones	Progress
2.1 The UK ISAR Medical Team (UMT) is able to deliver the required level of effective medical care in support of UK ISAR deployments. Includes charges applied for maintenance, logistics, drug turnover and staff costs.	Equipment needs addressed and readiness maintained.	A review of medical equipment levels, type and suitability completed. As a result the weight and volume of the medical equipment has seen a reduction of approximately 60%. Furthermore UKISAR have renegotiated deployment, training and servicing costs based on the new equipment scales. This equates to an annual saving of £10,000. / DFID funds has ensured the financing of replacement medical equipment, servicing, turnover of drugs, storage and management costs. The team have also procured 2 x medical lite giving sets, 2 x medical training packs, 1 x medical manikin, 3 x electro medical kits, 3 x defibrillators which has allowed us to align the equipment to our medical concept of operations.
2.2 The UK ISAR team has a mission ready complement of logistical support, coordination, administration, IT, communications, sanitation, accommodation, showering, food, and water, with appropriate maintenance and storage arrangements.	Support arrangements and equipment readiness maintained.	UK ISAR has established a specific logistical and equipment working group to carry out continuous reviews of all equipment used for deployments. / Funding has also been used to support an upgrade to the ICT infrastructure including 5 x satellite phones, 6 x laptops, 2 x VHF radio masts and antennae in order to improve the range of communications and options.
2.3 The UK ISAR team has a mission ready complement of operational equipment including, shoring, breaking, confined space, hot cutting, working at height, technical search, lifting and moving and hydraulic rescue components.	Equipment readiness maintained.	All operational equipment is stored within West Sussex with maintenance undertaken by Babcock Ltd under the DCLG long term capability maintenance programme. Any equipment outside of the national contract is maintained by the hosting service, therefore guaranteeing mission readiness status.

Key Points
Information and communications technology (ICT) equipment is stored and maintained by West Midlands Fire Service ICT department and is asset refreshed and maintained as part of normal business continuity programmes.

Equipment has been procured to reduce weight and volume but maintaining operational effectiveness and capability. This included lighting, generators, toilet facilities and water purification kits. In addition the command support, logistics and medical tents for rapid deployment inflatable structures that are able to operate in extreme conditions have been upgraded, as well as the procurement of single tents which reduces the risk of spreading illnesses amongst team members.

Medical equipment is owned and maintained by the Events Medical Company with the DFID funding contributing towards storage, maintenance, electrical testing and drug turnover costs. New arrangement with the Event Medical Company has allowed us to pay an annual leasing fee, gives us the most cost effective way of delivering high quality medical equipment and support when deployed.

Consumables such as ration packs and bottled water have a defined shelf life and are procured in staggered batches to ensure that they do not go out of date at the same time, and are used when approaching end of life on exercises and training events (if the team has not deployed). This ensures full value for money can be achieved from these items.

Output Title	UK ISAR makes an effective contribution to the development of INSARAG governance and methodologies to improve international urban search and rescue assistance.
Output number per LF		3	Output Score	A
Risk:		Low	Impact weighting (%):	10%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Yes

Indicator(s)	Milestones	Progress
3.1 UK ISAR make effective contributions to international, regional, national and technical meetings, that leads to improved guidance and processes.	Continued improvement of INSARAG guidance and governance processes.	The following summarises the meetings and INSARAG External Classifications/Re-classifications and other events attended by UK ISAR personnel:

Key Points

Meeting Type	Year	Frequency of attendance
INSARAG Training Working Group	2012/15	Attendance at 6 meetings
INSARAG Operational Working Group	2012/13	Attendance at 4 meetings
INSARAG Medical Working Group	2012/15	Changed MWG Leads and attended 4 meetings
INSARAG Regional Group meetings	2012/15	Attended 2 meetings
INSARAG Guidelines Review Group	2013	Attended 3 meeting
UK ISAR National Working Group	2012/15	15 meetings held for strategic delivery team
UK ISAR National User Group	2012/15	15 meetings held for tactical delivery team
UK ISAR Training sub group	2012/15	12 meetings held for training delivery team
UK ISAR Medical sub group	2012/15	6 meetings held for the development of medical doctrine and procedures
UK ISAR Logistics sub group	2013/15	5 meetings held for the development of equipment and logistics policy/procedures
IEC Belarus	2014	IEC Team member
IEC Saudi Arabia	2015	IEC Team member
IEC Finland	2012	IEC Team Leader
Mentorship for Turkish USAR prior to IEC	2012	IEC Mentor
SWIFT Sweden IER	2012	Mentor
IEC Jordan	2013	IEC Team Leader
IEC Turkey	2013	Assessor
IER Iceland	2013/14	Mentor
UAE Abu Dhabi	2013	Capability building
India x 2	2013	Capability building
Pakistan x 2	2013/14	Capability building
Lebanon x 3	2014	Capability building for Syrian first responders
Poland (POLEX) exercise	2013	Test of ASR methodology
IER Poland	2014	IER Team Leader
IER Norway	2014	IER Team Leader

Output Title	All UK ISAR personnel and canines on request are fully prepared to deploy overseas and operate in austere environments for up to 14 days.
Output number per LF		4	Output Score	A
Risk:		Low	Impact weighting (%):	10%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Yes

Indicator(s)	Milestones	Progress
4.1 Number of canines available for immediate response.	12 canines available.	The UK ISAR management team took the decision to reduce the operational canines available for international response from 14 to 12, in order to reduce costs, reduce the impact on UK national resilience and align to the 3:1 ratio principles. Due to retirements and reduction in numbers two vacancies currently exist across the rota groups, which will be augmented with 2 dogs currently in training and subject to successfully passing the grading process.
4.2 Number of personnel who are fully vaccinated and prepared for immediate response.	240 personnel.	UK ISAR currently has an overall team strength of 259 personnel that are fully vaccinated with a predefined list of inoculations to allow travel to all parts of the world. This includes all fire fighters, Medical staff, veterinary staff and the structural engineer. / Each Fire and Rescue Service takes responsibility for ensuring that vaccinations are kept up to date through their respective Occupational Health Departments, with non FRS staff taking responsibility for their own inoculations. Receipts from non FRS staff are passed through the UK ISAR business center to be refunded when possible from the DFID budget. / It should be noted that each FRS receives a contribution of £2300 towards the costs however the real costs are somewhat higher, depending upon team size and booster frequencies.

Output Title	UK ISAR has effective management, and administration functions in place to support the operational elements of the team.
Output number per LF		5	Output Score	A
Risk:		Low	Impact weighting (%):	10%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
5.1 Management, administration and reporting functions are effectively undertaken in the appropriate timeframe.	All financial and reporting data submitted as per timeframes in the operational guidelines.	Since the transition of UK ISAR into the governance arrangements of CFOA National Resilience Limited (13 April 2014) the team have been able to operate in a more structured and professional manner. / The team currently has a National Coordinator (funded by CFOA with a contribution of £10,000 by DFID towards management costs associated with ISAR work). The coordinator is responsible for chairing and managing the National User Group and for reporting progress to the National Working Group and National Resilience Boards as well AS financial reporting through the CFOA National Resilience Ltd Board. Progress and issues are also reported through the National Resilience and Assurance team meetings and to supporting Fire and Rescue Services. / Working within the CFOA structure allows access to a range of support functions (finance, procurement, documentation support, legal advice, centralised training, IT, and transport resources). These arrangements have undoubtedly improved the support given the 15 FRS, Government Departments and to the overall performance of the team when responding to disasters.

Recommendations for future programmes
We may consider removing this output or amending the Indicator as performance for financial reporting is now covered under the ‘Quality of financial management’ in Section D below of the revised DFID Annual Review and Programme Completion Review Template.

Output Title	Fire AID better able to track availability of UK equipment for donation and match to applications for assistance from target countries.
Output number per LF		6	Output Score	A
Risk:		Low	Impact weighting (%):	10%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Key Progress
6.1 Amount of equipment available for donation matched to target country needs.	Equipment donated delivered to target countries.	Republic of Moldova 2014-2015: Equipment donated during the grant period: 12 fire engines*; 2 ambulances; 20 sets of hydraulic cutting gear; 1 rescue boat; Tools for maintenance. / Nepal, March 2015: 200 disaster relief kits and large quantities of firefighting PPE, rescue lines, harnesses and equipment. / Zimbabwe, 2014: FIRE AID member Operation Florian delivered 3 containers of equipment and 7 fire engines - 2 for Bulawayo Fire and Ambulance Service, 2 for Harare Fire Brigade, 2 for Gweru Fire Brigade and 1 for Victoria Falls Fire Brigade. This was accompanied by 5,884 student hours of training in Breathing Apparatus and Road Traffic Collision, Trauma Care, Incident Command, Fire Investigation.
6.2 Equipment and training lead to improvements in local capacity in target countries, and the speed and effectiveness of rescues and response times.	Rescues and response times improved.	Republic of Moldova: training in basic firefighting, trauma care, road traffic collision response, pumps and ladders, driver training and water rescue. Data and testimonials from internal evaluation (Nov 2014) indicate response times improved and equipment in use and maintained. In the town of Ialoveni in Moldova, 7 people were saved using the hydraulic cutting equipment – the firefighters stated this wouldn’t have been possible previously. further evaluation due in Nov 2015. / Pakistan, Feb 2015: FIRE AID member the Asian Fire Service Assoc (AFSA) held series of meetings and r workshops to further develop their work in the region. A key activity was the opening of AFSA’s first international office at the newly established Emergency Services Academy in Pakistan from where collaboration between Rescue 1122 (the Punjab Emergency Service) and AFSA will be managed.

Key Points
This funding has enabled Fire AID to build and develop a bespoke database to track equipment, process equipment donations and track donations both past and present. Fire and rescue aid will now be better coordinated and recorded centrally- a key need identified by those working in this area. Closely allied to the development of the database has been the drafting and adoption of an Ethical Donation Policy, Anti-Bribery Policy and Project Handbook to ensure potential equipment donors can be assured donations will not be wasted or misused. The database was built during the grant period and is now running with user guides being produced in April 2015. Fire AID have started to apply historical data to the database.

*A breakdown of how 4 of the fire engines to Moldova have been used during May-Nov 2014:
Number of interventions				Distance Travelled km	Fire Station (location)
RTC	Fire Response	Others	Total
	18	16	34	518	Chisinau TC
3	86	28	117	2298	Ialoveni
4	24	44	72	2381	Floreşti
		5	5	144	Sîngerei

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance (UK ISAR)
The main costs associated with this project related to the maintenance of equipment and training levels. The equipment required for training and for maintaining effective readiness and 24/7 deployable capacity has to be stored, maintained and replaced (if necessary). These activities were all costed in the project budget and expenditure has been in line with those forecasted.

Cost drivers not included in the project budget were the salary and related costs of UK Fires and Rescue Service personnel, which were met by individual services. Also not included in the budget were the costs of equipment required for training and deployment. These costs were significant and would have had to be met by DFID if the UK FRS was no longer able to fund these services. If this was to happen, DFID would have had to reconsider the cost-benefit of the provision of such a service.

VfM performance compared to the original VfM proposition in the business case (UK ISAR)
VfM Performance measures remained as specified in the business case. UKISAR can be assessed in terms of DFID’s three components of humanitarian value for money; cost, quality and speed:
- the speed at which UK ISAR teams deployed from Britain to the disaster zone and become fully operational in the affected area;
- the 24/7 availability of an optimum number of trained and experienced search and rescue experts to comprise ideally sized functional UKISAR teams of 60-70 persons;
- the quality of UKISAR liaison and coordination with INSARAG, other search and rescue teams, authorities and rescue teams in affected country and UN coordination mechanisms;
- the quality of procedures undertaken in the transfer of survivors rescued by UKISAR for follow up medical care;
- he quality of internal UKISAR coordination and command and control in training and deployments, and in functional operational relationships with DFID CHASE;
- the cost of search and rescue preparedness set against the above benefits.

Assessment of whether the programme represented value for money (UK ISAR)
The recent deployments of the UK ISAR team to Bosnia & Herzegovina in May 2014 in response to severe flooding in the Balkans is considered below and demonstrates successful operational performance. In terms of preparedness, staff training has been in line with agreed levels, equipment has been maintained at a constant state of readiness in line with INSARAG guidelines and personnel are fully prepared to deploy rapidly.

The added value of this programme lay in providing an additional layer of international capacity to an existing UK service and as needs demand, rapidly deploying a high quality search and rescue team into a disaster zone to support and supplement a rapid local and international response.

Quality of financial management during programme (UK ISAR)
The risks of funds not being used as intended were very low. The project was subject to double controls, by both DFID and the UK Fire and Rescue Service through CFOA, and fully accountable under UK Government guidelines, procedures and legislation.

Within DFID, the CHASE Humanitarian Response Group manages expenditure. Audit, accounting and reporting/monitoring arrangements have been clearly specified in the MOU with CFOA and the Accountable Grant arrangement with Fire AID. DFID requires partners to provide a copy of their certified Annual Audited Accounts (AAA) and that they clearly show DFID funding as a distinct line of income.

E: RISK

Quality of risk management over the life of the programme

UK ISAR: The risks to this tested arrangement not being able maintain equipment, training and readiness to deploy a specialist team are currently low. This facility and capacity have been managed for more than ten years, and management and administration of this project have been strengthened by the new management and oversight provided by CFOA National Resilience. This arrangement worked well.

The effects of the 2010 Comprehensive Spending Review have meant most UK Fire and Rescue Services have reduced staffing levels, and instigated savings across all levels of service delivery. There was a risk that cost savings could have prevented staff from attending training and development events, and logistical and maintenance support might also be reduced. To mitigate risks, budget lines where FRSs contributions were no longer available, such as vaccinations, were fully costed in the project budget and be met by DFID (if required). In view of these funding pressures, risks were monitored on a regular basis throughout the project, and if necessary were reassessed.

Fire AID: The Fire AID component was also seen as low risk, the database and website development proposed was considered to be within their capabilities to deliver.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe (UK ISAR)

Performance of partnership(s)
Search and rescue deployments promote good inter-departmental relations and co-operation between DFID, the FCO, the Department for Communities and Local Government (DCLG) and the Cabinet Office, all of which are involved in the UK’s search and rescue deployments.

Asset disposal and value obtained by DFID
Equipment costs charged to DFID were minimised by utilising existing fire and rescue service equipment wherever possible. DFID contributed to the maintenance and replacement of this equipment, as well as meeting some standing charges. For equipment used on deployment, DFID and UKISAR have agreed criteria for when equipment replacement costs were to be reimbursed or not.

Following the recommendations from the 2013 Annual Review, UKISAR provided a comprehensive list of equipment for deployment at least once a year for audit purposes, even if there were no deployments.

G: CONDITIONALITY

Not applicable; no specific conditions apply to this programme.

H: MONITORING & EVALUATION

Evidence and evaluation
Due to the relatively small size of this programme there are no plans for a formal evaluation. A DFID evaluation advisor was involved in assessing the original Business Plan and subsequent Annual Reviews.

Monitoring progress throughout the programme (UK ISAR)
Regular meetings were held between DFID officials and the Search and Rescue Team to evaluate deployments, identify lessons and the equipment and training needs, as part of the ongoing DFID support.

UKISAR were also monitored following the deployment of their fire service water rescue team of 33 people with four rescue boats in response to the severe floods in the Balkans in May 2014. The team were deployed within 48 hours of request from the Bosnian authorities, to work under the coordination of the local Emergency Management Agency. They went into action at midnight on Sunday 18 May 2014 and were released from rescue duties on 21 May 2014.

During their mission they:
- surveyed and assessed flooded areas on behalf of the government;
- rescued 45 stranded people (including 18 elderly women and some children);
- led 58 other people to safe areas;
- provided transportation and other support to local engineers repairing electrical supply between the power station and villages – a priority task;
- delivered food, water and medical supplies to approximately 500 homes as well as to stranded livestock;
- transported military personnel (assisting with the disaster) by boat to inaccessible areas.

The UK ISAR moderately exceeded expectation for this deployment; their effective participation of the in this emergency response through their rapid deployment to provide essential supplies and services to vulnerable groups was recognised and commended by both the local authorities and the British Embassy in Sarajevo.