Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: UK Aid Direct: Phase II of the Global Poverty Action Fund (includes the Global Poverty Action Fund 2010 - 2018)
Programme Value: £290 million / £140m for GPAF (originally £120m for funding rounds 2010 – 2013, plus an additional £20m for Jobs & Livelihoods round in November 2013). GPAF grants will be in implementation until 2018. / £150m for UK Aid Direct to be allocated through competitive funding rounds between 2014 – 2020, with grants in implementation until 2025. / Note: these are total values and include funding allocated to all aspects of the implementation of the Funds, including grants to CSOs, fund management, monitoring and evaluation costs.		Review Date: August / 2015
Programme Code: 202035	Start Date: Sept 2010	End Date: March 2025

Summary of Programme Performance
Year	2011	2012	2013	2014	2015
Programme Score	X (too early)	A	A	A	A
Risk Rating	M	M	M	M	M

Summary of progress and lessons learnt since last review
The key achievements of UK Aid Direct/GPAF this year (August 2014 – August 2015) include:
1. Effective management of the 142 GPAF grants in implementation by Fund Manager (as of 30 June 2015).
2. Fund Manager implementation of learning strategy including capacity building webinars and workshop with GPAF grants holders in Tanzania.
3. The development and approval of the business case for UK Aid Direct as a second phase of the GPAF, with a minimum investment of £150 million in funding rounds between 2014 – 2020 (with grants potentially in implementation until 2025).
4. Completion of first UK Aid Direct Funding Round, focused on the off track health MDGs and SRHR. Launched in October 2014 and 23 grants awarded[1] in April 2015.
  [1] These are provisional grant awards and will be confirmed following the completion of due diligence.
5. Procurement of UK Aid Direct Fund Manager.

Conclusions of this Annual Review and lessons learnt:
A: Outputs met expectation [the GPAF log frame is being used to assess performance at this Annual Review]

This Annual Review concludes that UK Aid Direct and the GPAF is meeting expectations. As well as the effective management of the 142 grants in implementation by the GPAF Fund Manager, this year’s activities have focused on the development of the second phase of the Fund, UK Aid Direct. UK Aid Direct will continue and extend the impact and reach of the GPAF and build on the evidence and lessons learnt, whilst introducing additional flexibility that will ensure the Fund is able to respond to the priorities coming out of the recently agreed Sustainable Development Goals (SDGs), DFID’s Single Departmental Plan (SDP), and the conclusions of the Civil Society Partnership Review (CSPR).

Action on previous recommendations:
1. The log frame has been revised based on the recommendation from the 2014 Annual Review, however, due to the development of the business case for UK Aid Direct during the last year, this log frame does not reflect the revised theory of change nor demonstrate performance against the overall objectives of the Fund. [This Annual Review recommends that DFID and the UK Aid Direct Fund Manager work together during inception to prepare a new log frame based on theory of change and indicative log frame proposed in the business case].
2. Standard indicators have been introduced and piloted through the GPAF Jobs and Livelihoods round and UK Aid Direct. Future funding rounds should consider introducing standard indicators at the call for proposals stage.
3. Although there has been no formal response from the Fund Manager to the Coffey Mid Term Evaluation, the findings have been discussed and reflected in changes to Fund Management processes.

Summary of recommendations for the next year
1. A priority action is for DFID to operationalise the UK Aid Direct Fund Manager through the completion of the procurement process.
2. DFID and the UK Aid Direct Fund Manager to use learning and evidence from GPAF and broader experience and sector engagement to design UK Aid Direct grant management systems and practices.
3. DFID and the Fund Manager should then work to develop a new log frame for UK Aid Direct that encompasses the ambition of UK Aid Direct (as set out in the business case documents) and the existing GPAF portfolio, and can demonstrate the performance of the Fund.
4. DFID team to feed in learning into, and ensure that UK Aid Direct can respond to conclusions of, the Civil Society Partnership Review.
5. DFID and Fund Manager to strengthen engagement with stakeholders and communications on the achievements of UK Aid Direct.
6. DFID to plan the next evaluation by Evaluation Manager (Coffey) and evaluation for UK Aid Direct.
7. DFID to use the KPIs for the UK Aid Direct Fund Management contract as a measurable performance framework for the work of the Fund Manager.
8. UK Aid Direct Fund Manager to review and implement findings of BOND Grant Holder survey and agree priority follow up actions with DFID. DFID to include annual Grant Holder survey in BOND accountable grant to enable this to become a routine part of the monitoring of the performance of the Fund Manager.
9. UK Aid Direct Fund Manager to review process of agreeing grant holder log frames to ensure that all projects have an agreed log frame by 3 months.
10. UK Aid Direct Fund Manager to review learning carried out in the Fund to date and develop a new learning strategy for the Fund going forward in discussion with DFID.
11. UK Aid Direct business case outlines a desire to introduce a portfolio risk management approach. UK Aid Direct Fund Manager to propose how to introduce this system.
12. DFID team to ensure that the risk appetite for each Funding Round is established with Ministers when agreeing the focus and criteria for grant award.
13. DFID team to review and revise risk matrix in Delivery Plan, in particular to address the risks around managing the transition between GPAF and UK Aid Direct Fund Manager.
14. UK Aid Direct Fund Manager to integrate learning from the GPAF Beneficiary Feedback pilot into the design, implementation, monitoring and reporting of the Fund.
A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-202035/documents/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-202035/documents/

*UK Aid Direct Business Case is pending publication on DevTracker – it is exempt from publication until procurement of the UK Aid Direct Fund Manager is complete.

Outline of the programme
The Global Poverty Action Fund (GPAF) is a demand-led fund that has awarded 182 projects to Civil Society Organisations, focused on poverty reduction in pursuit of the Millennium Development Goals (MDGs) by delivering tangible changes to poor people’s lives, in the 28 DFID priority countries and bottom 50 Human Development Index countries.

The Fund started awarding grants to projects in 2011 and has been DFID’s central mechanism for funding small and medium sized international and national Civil Society Organisations (CSOs) working to reduce poverty. The GPAF has supported a diverse portfolio of projects that demonstrate a 'clear line of sight' to poverty reduction. 36 grants have completed implementation (as of 30 June 2015), 142 GPAF grants are in implementation, and 4 are still to commence activities.

The GPAF was established to contribute to DFID’s priorities from the 2010 Structural Reform Plan. The GPAF completed its allocation of grants through 11 funding rounds from 2010 – 2014. The Fund has now transitioned into a new phase as UK Aid Direct.

The GPAF’s intended Impact, Outcome and Outputs are as follows:
Impact: Improved poverty reduction and the achievement of the most off-track MDGs in poor countries
Outcome: A diverse range of CSOs with the capacity (resources) to improve the well-being (services, livelihoods, voices) of poor women, men, girls and boys in GPAF target countries.
Outputs:
1. CSOs supported (through funding and Fund Manager) to improve (access and quality) delivery of basic services to poor people in GPAF target countries (55% impact weighting).
2. CSOs supported (through funding and Fund Manager) to increase livelihood/economic opportunities for poor people in 25 countries (25% impact weighting).
3. CSOs supported (through funding and Fund Manager) to consult with and represent the views of citizens to national, regional and/or local governments on services, accountability, peace and justice (5% impact weighting).
4. Flexible and responsive fund management (10% impact weighting).
5. The Fund generates useful learning (5% impact weighting).

Across the lifetime of the GPAF, the fund has:
- Awarded 182 grants, totalling £114.5 million
- Provided development benefits to people across 36 countries in Sub-Saharan Africa, Asia and - Middle East, including fragile states
- Supported 6,139,397 beneficiaries (2,412,037 men/boys, 3,727,360 women/girls, 352,495 disabled beneficiaries).
- Received 3,737 concept notes and assessed 2,544
- Invited and assessed 723 full project proposals
- Leveraged an additional £64.3 million through match funding

The GPAF allocated funding through:
- 4 Impact windows (giving grants of between £250,000 - £4 million to medium/large UK or international CSOs[2], who have secured a minimum 25% match funding). Impact grants form 90% of GPAF funding. The purpose is: “Poverty reduction linked to Millennium Development Goals (MDGs). Projects focused on off-track MDGs are prioritised”.
  [2] PPA agencies are not eligible to apply
- 4 Innovation windows, then succeeded by 3 Community Partnership windows (giving grants of up to £250,000 to small UK based CSOs with an annual income of less than £1m for the last three years). The purpose is: "To support initiatives focused on delivering results at community level which will achieve benefits for men, women, girls and boys".

UK Aid Direct has been designed as the second phase of the GPAF and is now establishing and financing a flexible programme of support to small and medium sized national and international CSOs to reduce poverty through service delivery, livelihoods, empowerment, accountability and peace, security and justice. The business case for UK Aid Direct was approved in September 2014 and the continuation of the Fund, with a focus on support to small and medium sized UK and international CSOs, confirms DFID’s on-going commitment to the role of civil society in poverty reduction.

The design emphasis on flexibility and the ability to adapt means that the Fund can be deployed to respond to the UK development priorities that are being established through the recently agreed Sustainable Development Goals (SDGs) and the strategic objectives for DFID, which will be articulated through the Single Departmental Plan (SDP) currently being finalised.

The intended impact of UK Aid Direct is the decline in poverty in target countries through achievement of MDGs/SDGs, through financing civil society programmes.
The outcomes are:
I.	The achievement of the outcomes of all projects funded by UK Aid Direct in the areas of service delivery, empowerment and accountability, changing social attitudes and economic empowerment;
II.	Effective civil society organisations.

The first UK Aid Direct competitive funding round, focused on the off-track health MDGs and particularly welcoming projects working on SRHR, was launched in October 2014. The Secretary of State approved 23 grants in March 2015, committing a total of £16.61 million over three years. To date 2 UK Aid Direct grants have started implementation. The others are in the final stages of grant set up (including due diligence, log frame confirmation) and should all commence by 1 January 2016.

The business case sets out an annual strategic investment decision cycle that will determine, with Ministerial guidance and approval, key investment decisions for the UK’s work with civil society. These may include thematic areas for concentration and results achievement, managing varying volumes of financing, opportunities for action, modalities for providing finance and geographical emphases. This approach will now align with the post-election decision to carry out a Civil Society Partnership Review (CSPR), to define DFID’s objectives, approach and instruments for a partnership with civil society in order to deliver more for the world’s poorest. This review being carried out between July – November 2015, will look at the objectives of UK Aid Direct and will make recommendations for future strategy through the line of enquiry on Effective Approaches.

The GPAF Fund Manager (appointed in 2010), Triple Line Consulting in a joint venture with Crown Agents, acts on behalf of DFID to manage the application process, disburse funds and manage performance, reporting and result measurement procedures of grant holders, and for reporting on portfolio results and impact to DFID. The GPAF Fund Manager contract has been extended to manage the first funding round of UK Aid Direct, whilst a procurement process is undertaken to appoint a Fund Manager for UK Aid Direct (which will include the management of the GPAF grants still in implementation).

DFID has also appointed a joint Evaluation Manager for GPAF and the PPAs (Coffey International). Due diligence for GPAF grant holders was carried out by KPMG through a separate contract. For UK Aid Direct due diligence will form part of the Fund Manager’s responsibilities.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

Outcome: A diverse range of CSOs with the capacity (resources) to improve the well-being (services, livelihoods, voices) of poor women, men, girls and boys in GPAF target countries.

Indicator	Target FY14/15	Achieved
1a: Number of ongoing and completed GPAF projects demonstrating positive outcomes in health, education and WASH	96	94 / (2 not yet reporting)
1b: Number of people benefitting from improved access to health, education and WASH service delivery as a result of GPAF supported projects	Total: 4,882,142 / M:1,679,916 / F:3,202,226 / D[3]:122,014	Total: 4,962,032 / M: 1,911,303 / F: 3,050,729 / D: 309,570
2a: Number of ongoing and completed GPAF projects demonstrating positive outcomes in terms of improved production and/or income	56	49 / (7 not yet reporting)
2b: Number of people benefitting from improved access to livelihood/economic opportunities as a result of GPAF supported projects	Total: 735,546 / M:339,934 / F:395,612 / D:4,724	Total: 623,536 / M: 269,698 / F: 353,658 / D: 20,586
3a: Number of ongoing and completed GPAF projects demonstrating positive outcomes in CSOs capacity to consult with and represent the views of citizens in relation to services, accountability, peace and justice	17	16 / (1 not yet reporting)
3b: Number of people benefitting from improved CSO capacity to represent their views in relation to services, accountability, peace and justice	Total: 480,021 / M:198,347 / F:281,674 / D:16,353	Total: 554,009 / M: 231,036 / F: 322,973 / D: 24,429
4: Portfolio analysis provides examples of GPAF projects demonstrating the potential for scale-up or replication	Yes	Yes
5: Portfolio analysis demonstrates diversity of applicants	Yes	Yes
[3] Number of disabled beneficiaries

The assessment of progress against outcome indicators is based on data gathered from the annual reviews of the 115 GPAF grants reporting to the Fund Manager on 31 March 2015.

GPAF grants in numbers, as of 30 June 2015…
    In total, 182 grants have been awarded
        36 have completed activities
        115 submitted annual reviews this year on 31 March 2015*
        142 are in implementation**
        4 grants are still to start activities
*grants that have been in implementation for less than 3 months do not submit annual
 Reviews, grants with less than three months submit an interim report
**17 Jobs and Livelihoods grants started implementation on 1 April 2015

The Fund Manager annual reviews include all aspects of project implementation and achievement, learning and reflection, and financial reporting. Full analysis of achievements at outcome level can be found in the ‘Overview analysis of the GPAF portfolio’ prepared by the Fund Manager (quest document: 5079892), which is summarised below.

The Fund Manager analysis shows that the objective of funding a diverse range of CSOs, that possess the resources to deliver positive changes to the lives of poor women, men, girls and boys, has been achieved.

The diversity of the CSOs being supported through the GPAF can be seen in the range of organisations that have been awarded grants:
- 115 organisations implementing projects in 36 countries
- 98 grants awarded to UK based CSOs (91 in England, 4 in Scotland, 2 in Northern Ireland and 1 in Wales)
- 17 grants awarded to CSOs based overseas (1 organisation in Ghana, Liberia, Malawi, Nepal, Nigeria, Pakistan, Sierra Leone, South Sudan, Tanzania and Zimbabwe, 2 in South Africa and Uganda, and 3 in India).
- 60 projects being implemented by organisations with an annual income of less than £1 million
- 55 projects being implemented by organisations with an annual income of more than £1 million
IMP: Impact grants
INN: Innovation/Community Partnership grants
The capacity of CSOs (grant holders) to deliver positive development results is demonstrated by results of the 2014/15 Fund Manager Annual Reviews of GPAF projects (undertaken based on the Smart Rules and DFID Annual Review processes). The scores of these annual reviews are outlined in the table below:

The majority of GPAF grants (64%) have been assessed as meeting or moderately exceeding expectations (53% score A and 11% A+). The 33% that did not meet expectations have received specific feedback and follow up actions from the Fund Manager, in consultation with DFID, to support them to take the necessary actions to get the projects back on track; this includes focused one to one meetings, quality assurance visits and more intensive grant management. The Fund Manager analysis of the annual reviews, show that the reasons that projects did not meet expectations include:
- grants operating in fragile and conflict affected environments
- grants affected by natural disasters (such as Ebola, floods in Malawi and earthquake in Nepal)
- start-up activities took longer than anticipated
- partner changes caused delays to project activities
- insufficient evidence and weak reporting
- over ambitious log frame targets
- issues with project design and/or delivery
This learning will be acted on and applied to on-going management.

Analysis by the Fund Manager shows a similar capacity to deliver across organisation size, with CSOs at both ends of the spectrum of income sizes moderately exceeding expectations.

Thirty-one GPAF projects completed activities during 2014/15. The table below shows the Fund Manager analysis of the project completion reports (PCRs) of the thirteen that had reported by 31 March 2015 (projects have three months after their end date to submit their PCR) and the 5 projects that completed last year. The majority (11) are meeting or exceeding expectations, with seven not meeting expectations. Similarly to the annual reviews, the learning from these grants and PCRs is being fed back into the management of current grants.

In total, the 182 GPAF grants awarded will deliver results across 36 countries to 6,139,397 beneficiaries (2,412,037 men/boys, 3,727,360 women/girls, 352,495 disabled beneficiaries). The table below shows the breakdown of beneficiaries reached according to the thematic focus of GPAF projects.

The portfolio analysis also provides nine examples of GPAF projects that are demonstrating the potential for scale-up/replication, including an innovation grant where learning from this project has led to the integrated secondary health care model being replicated by three other regions of Uganda, and an impact project, where support to community members to engage local authorities in Zimbabwe, resulted in utility water pipes being extended into another settlement. Based on the viable approach demonstrated by this project, the Council has started work alongside the community to bring water to three other neighbouring settlements.

Overall output score and description

A: Outputs met expectation
Based on the milestone data provided by the annual reviews of 115 GPAF projects, the majority of outputs (three of five) have met expectation this year. Three outputs (1, 4 and 5) are scored A, meeting expectation. Outputs 2 and 3 are scored B, moderately did not meet expectation.

Two of the Outputs (3 and 5) have a 5% impact weighting. Guidance states that impact weighting should be no less that 10%. This should be considered as part of the review of the log frame and the new log frame should ensure that the guidance is followed.

Key lessons
1. The lessons from last year’s Annual Review on the challenge of assessing the overall performance of the Fund are still relevant. There are still a number of output indicators that would benefit from being linked to a measure that can demonstrate quality and relates to the theory of change of the Fund.
2. Lessons from the introduction of standard indicators should be reviewed throughout the implementation of the GPAF Jobs and Livelihoods and UK Aid Direct Round 1 (Health) grants.
3. Lessons from implementing the first funding round of UK Aid Direct were captured in a reflection session after the completion of the funding round (summarised in the Fund Manager’s Annual Report).

Key actions
DFID and UK Aid Direct Fund Manager
As recommended above, a priority activity for DFID and the UK Aid Direct Fund Manager is to establish a new log frame for 2015/16 onwards that encompasses the ambition of UK Aid Direct (as set out in the business case documents) and the existing GPAF portfolio and relates to the UK Aid Direct Theory of Change (as outlined in business case). This work should be undertaken collectively by the DFID team and UK Aid Direct Fund Manager. The new log frame should be clear on quality measures and responsibilities.
DFID
1. Ensure UK Aid Direct can feed into and respond to the conclusion of the CSPR.
2. The DFID team have worked to strengthen the involvement of, and relationships with, DFID Country Offices during the course of the year, particularly on coherence between central funds and country office programmes. This is an ongoing piece of work that will continue in the next year.
UK Aid Direct Fund Manager
1. Consider moving annual reviews of grants to the year anniversary of the start date (rather than all grant holders being requested to report by 31 March each year) to allow grant holders to report annual achievements and balance annual review work throughout the year.
2. When establishing UK Aid Direct systems, consider how grant management processes be more tailored to the needs of specific grant holders and how the criteria for funding rounds will impact on the diversity of CSOs being supported (including what is achieved from distinction between Impact and Community Partnership grants).

Has the logframe been updated since the last review?
Yes, the logframe was updated following the recommendation from the 2014 Annual Review. The impact and outcome level objectives remain the same but the outputs have been revised. The aim of the revisions was to identify appropriate milestones and targets by which to monitor progress against output indicators. Although the new outputs go some way to demonstrating the breadth of activities and achievements of the Fund, a new log frame for UK Aid Direct should be prepared, which includes indicators that are measurable and provide an assessment on the quality of work carried out.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	CSOs supported (through funding and FM) to improve (access and quality) delivery of basic social services to poor people in GPAF target countries
Output number per LF		1	Output Score	A
Risk:		Medium	Impact weighting (%):	55%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones	Progress
Number and percentage of on-going EDUCATION focused projects that are meeting or exceeding expectations	8 of 13 (66%)	10 of 13 (77%)
Number and percentage of on-going HEALTH focused projects that are meeting or exceeding expectations	33 of 50 (66%)	33 of 48 (69%)
Number and percentage of on-going WASH focused projects that are meeting or exceeding expectations	5 of 7 (66%)	4 of 7 (57%)

Output Title	CSOs supported (through funding and FM) to increase livelihood/economic opportunities for poor people in 25 countries
Output number per LF		2	Output Score	B
Risk:		Medium	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones	Progress
Number and percentage of ongoing projects that are focused on improving AGRICULTURAL production and/or incomes which are meeting or exceeding expectations	11 of 17 (66%)	12 of 17 (71%)
Number and percentage of on-going projects that are focused on providing finance and support for INCOME GENERATION, which are meeting or exceeding expectations	11 of 16 (66%)	9 of 15 (60%)
Number and percentage of on-going projects that are focused on addressing ENVIRONMENTAL issues, which are meeting or exceeding expectations	2 of 3 (66%)	1 of 3 (33%)

Output Title	CSOs supported (through funding and FM) to consult with and represent the views of citizens to national, regional and/or local governments on services, accountability, peace & justice.
Output number per LF		3	Output Score	B
Risk:		Medium	Impact weighting (%):	5%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones	Progress
Number and percentage of ongoing projects that are focused on BUILDING CAPACITY of CSOs to represent the views of citizens, which are meeting or exceeding expectations	9 of 13 (66%)	7 of 12 (58%)

Key Points
The first three outputs of the log frame all relate to the Fund Manager annual review scores of GPAF grants working in the areas of: i) provision of basic social services; ii) improving livelihoods and increasing economic opportunities; and iii) supporting citizens to represent their views to governments, accountability, peace and justice. The progress against milestones is based on the number of projects meeting (scoring A) or exceeding expectations (scoring A+).

Output 1 has met expectations, with two of the indicators (education and health focused projects) moderately exceeding the milestone target and the third indicator (WASH focused projects) moderately not meeting expectations (with only 4 rather 5 projects meeting expectations).

Outputs 2 and 3 have moderately not met expectations. For output 2, whilst the first indicator (projects focused on improving agricultural production and/or incomes) has moderately exceeded expectations with 12 (1 above the milestone target) meeting or exceeding expectations. The other two indicators (projects focused on income generation and addressing environmental issues) have moderately not met expectations with fewer projects than expected meeting or exceeding expectations in these areas. Similarly for Output 3, only 7 (rather than the milestone target of 9) projects have met or exceeded expectations in the area of building capacity of CSOs to represent views of citizens.

Summary of responses to issues raised in previous annual reviews (where relevant)
- Clear targets and milestones have been included in the revised log frame.
- Webinars have been undertaken to support grant holders to strengthen their understanding of theories of change, knowledge of quality of evidence, sustainability, and reporting requirements.
- Grant holders have received their annual review scores for the first time in feedback letters.
- The Fund Manager has carried out further analysis of the underperformance of WASH and Governance programmes (quest document: 5123321). Further action to be taken to follow up on the findings presented.
- Standard indicators have been introduced for Jobs & Livelihoods and Health projects.
- The Fund Manager developed a Learning Strategy for 2014/15 based on a survey of grant holder needs and focused on capacity strengthening.

Recommendations
1. DFID and UK Aid Direct Fund Manager to consider how to demonstrate the relevance of these projects to the target beneficiaries and the positive development results that they are delivering in the development of the new log frame.
2. UK Aid Direct Fund Manager to consider the introduction of portfolio quality scores to demonstrate the performance of the Fund.
3. UK Aid Direct Fund Manager to review process of agreeing grant holder log frames to ensure that all projects have an agreed log frame by 3 months.
4. UK Aid Direct Fund Manager to review how grants affected by humanitarian emergencies can be supported to respond and adapt to the change in context where they are operating.

Output Title	Flexible and responsive fund management.
Output number per LF		4	Output Score	A
Risk:		Medium	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones	Progress
DFID confidence in Fund Manager services (services include capacity strengthening, financial management, risk management, facilitating learning, performance management etc.).	High	Meeting expectations
GPAF grant holder surveys and feedback demonstrate satisfaction with support provided by Fund Manager (services include capacity strengthening, financial management, risk management, facilitating learning, performance management etc.).	Yes	Yes
UK Aid Direct Health round completed (round launched; CN/proposals appraised; recommendations to DFID; annexes prepared; SoS approval; new contract submission etc.)	Yes	Yes

Key Points
DFID is satisfied that the Fund Manager is delivering work that ensures that the GPAF meets expectations. However, there is no framework by which to measure the quality of Fund Manager outputs and it is therefore difficult to score the first indicator. Whilst grant holder feedback on capacity strengthening workshops and webinars is captured in the BOND grant holder survey and shows a good level of satisfaction, other areas such as the financial and performance management of the Fund have been more challenging.

The findings of the Grant Holder survey, carried out by BOND in June 2015, show a good level of satisfaction with the support provided by the Fund Manager. 46% of respondents who have worked with the Fund Manager for more than a year consider that there has been an improvement in their experience in the last 12 months, with half of these (23%) describing this improvement as ‘significant’. Further detail where provided suggests that there is a better mutual understanding, improved communications and better support. 18% of respondents also felt that the support offered in terms of training, webinars and workshops on financial management, M&E and annual reporting requirements offered specific value. 80% talked about the positive longer term implications of working with fund managers in terms of changing the way their grants run. An area highlighted for strengthening in terms of the Fund Manager, is to clearly communicate the role and responsibilities of the Fund Manager from the offset and to look for ways to improve reporting processes. [Full analysis of the survey results by BOND in quest document: 5065690].

UK Aid Direct was approved by the Secretary of State in September 2014 and announced at the first Regional Roadshow to promote DFID funding opportunities to small and medium Civil Society Organisations (CSOs) throughout the UK. The first UK Aid Direct funding round was launched in October 2014, focused on the off-track health MDGs and welcoming projects working on SRHR. 491 concept notes were received, 288 were assessed (i.e. were eligible) and 64 projects were invited to submit a full proposal.

The funding round was completed in 5 months to ensure that the recommendations could be considered by the Secretary of State prior to the end of the last government. This compressed timeline of was achieved by detailed resource planning between the Fund Manager and DFID. The assessment process was also strengthened in a number of ways including, webinars for applicants to strengthen the quality of proposals submitted, consulting with country office colleagues at the concept note stage, reducing the number of projects invited to submit a full proposal, not using the ‘queried recommended’ category for Impact proposals and only using selectively for Community Partnership proposals, and improving the quality of the documentation submitted to the Secretary of State (which received positive feedback from Private Office).

The Secretary of State agreed 23 provisional grant awards in March 2015. These grants are now completing due diligence. All organisations have participated in a welcome webinar with the Fund Manager and are finalising grant set up processes. Two grants have started implementation activities.

The procurement of the UK Aid Direct Fund Manager, following the European Union directives (OJEU) started in December 2014 and is expected to be finalised shortly.

Recommendations
1. DFID will use the key performance indicators that will be agreed with the UK Aid Direct Fund Manager, to develop a framework by which to measure DFID confidence in Fund Manager services. The UK Aid Direct contract will also contain an element of performance related payments which will relate to the payment of 10% of the total fund management fees, which will be reviewed quarterly.
2. UK Aid Direct Fund Manager to review and implement findings of BOND Grant Holder survey and agree priority follow up actions with DFID. Including whether any of the compliance and reporting processes can be made more proportionate.
3. DFID to include an annual Grant Holder survey in the BOND accountable grant to enable this to become a routine part of the monitoring of the performance of the Fund Manager.
4. UK Aid Direct Fund Manager to follow up on the key areas of learning that came out of the reflection session on round 1, particularly on reducing the number of concept note applications that were ineligible.
5. The UK Aid Direct business case outlines the ambition for an enhanced focus on communications, outreach and evidence. It is important to communicate the objectives and achievements of the Fund to stakeholders and also ensure a broad range of eligible organisations are aware of the opportunities the Fund is offering. DFID and the Fund Manager should review and implement the proposed approach to stakeholders and communications in the next year.

Output Title	The Fund generates useful learning
Output number per LF		5	Output Score	A
Risk:		Low	Impact weighting (%):	5%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones	Progress
Qualitative examples of how learning from GPAF has improved design, implementation and performance within: a) Civil Society; b) DFID; c) the Fund Manager	Examples provided	Yes

Key Points
In terms of the work of the Fund Manager, useful learning has been generated in a number of different areas during the course of the year, including:
- Funding rounds – a useful reflection exercise was carried out following the completion of the first funding round of UK Aid Direct. Action was also taken on learning from past funding rounds by introducing webinars for interested applicants covering proposal writing, log frames, vfm, financial management and gender.
- Grant set up and due diligence – learning has been generated from the new process of incorporating the log frame review at grant set up stage which should lead to stronger M&E by grant holders and the introduction of awardee workshops. A lot of learning was also generated from the due diligence of UK Aid Direct provisional grant awards, which was undertaken by the Fund Manager for the first time.
- Project start up – learning from the introduction of standard indicators is being generated. Also webinars on log frames and how to improve quality of evidence were introduced based on learning from existing grant management.
- Grant performance – learning from previous years meant a more smooth and streamlined appraisal at annual review point. Other learning to consider, is the involving grant holders in the design of the reporting template. The capacity assessment questions incorporated into the template for the first time should be used to inform Fund Manager capacity building support going forward.
- Risk management – A lot of learning on managing risks has been carried out this year. Grant holders have been encouraged to share experiences and lessons learned in this area also. A particular example of this is the session at the workshop with grant holders in Tanzania, which also gave grant holders reassurance that they would be supported to tackle fraud. A review of the QAVs which took place between January – March 2015 has been carried out and the findings will be used to strengthen procedures and design of future QAVs.
- Gender and social inclusion – learning from current grants, and the results of the learning survey, has led to the specific support to grant holders in the area of gender and inclusion. In particular, a lot of learning and information sharing on grant holders own gender policies has been generated this year.
- Financial management – there has been a strong focus on strengthening financial management this year based on the learning from previous years.
- Value for money – thematically focused rounds have provided opportunity to strengthen vfm analysis through the introduction of standard indicators and the use of relevant cost effectiveness measures. The ability to make more direct comparisons of vfm of project designed to deliver similar outcomes.
This learning is fully outlined in the Fund Manager Annual Report

In terms of programme learning, in response to the recommendation of the last Annual Review to prepare a proposal for capacity building training events for grant holders, the Fund Manager carried out a survey of grant holders in December 2014. The findings of the survey were used to agree a Learning Strategy for 2014/15 which included:
- A Results and Learning Seminar in January 2015 – a one day event held twice over two days to accommodate the number of grant holders who wanted to attend (over 45 each day). Key sessions focused on gender mainstreaming and preparation for the annual report process.
- Financial management capacity strengthening – quarterly workshops run by the Fund Manager covering the claims process, forecasting, exchange rates, local partner engagement, budget revisions, annual reporting and value for money. This training has been turned into a webinar to give access to GPAF grant holders overseas. Separate sessions have also covered IATI and AAA.
- Webinars and working groups for new grant holders on log frames
- Workshop with GPAF grant holders in Tanzania in April 2015 - to share learning between grant holders, (and with the Fund Manager and DFID) and increase capacity to manage grants effectively. The report of the visit details the approach and outcomes.
- Round table in UK to follow up on Tanzania visit and share learning with UK based grant holders and those managing GPAF grants in similar sectors and the same region.
- Webinars on Quality of Evidence (44 participants)
- Pilot Thematic Knowledge Network on Education – to encourage grant holders working in the same thematic area to connect and share experiences and learning. The Fund Manager has established a DGroups platform. The network has 38 members.

Recommendations
UK Aid Direct Fund Manager to review learning carried out in the Fund to date and develop a new learning strategy for the Fund going forward in discussion with DFID.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
The principal cost drivers of UK Aid Direct is the number of projects being funded. Projects are challenged on their costs through the proposal assessment and grant set up stages.
Associated with that are the Fund Management costs and the cost of running funding rounds, assessing concept notes and proposals, the cost of grant set up, grant management, learning and closure.

VfM performance compared to the original VfM proposition in the business case
The business case outlines four areas for driving value for money through UK Aid Direct:
  1. The vfm potential of UK Aid Direct’s flexibility
  2. Vfm of the Fund Manager
  3. Vfm at project selection
  4. Vfm through the life of projects

UK Aid Direct has been designed to be able to respond flexibly to priorities and opportunities. This approach will offer improved vfm by allowing decisions to be taken at the appropriate time and based on evidence of where a central funding mechanism to CSOs can deliver the best results. This area will be realised when the UK Aid Direct Fund Manager is in place and the Fund can operate as intended. The vfm of the Fund Managers ability to work flexibly was assessed through the UK Aid Direct procurement process and was part of the evaluation criteria.

Vfm of the Fund Manager has always been a key consideration. The UK Aid Direct Fund Manager has been selected through a competitive tender. Based on learning from the GPAF Fund Manager contract and other DFID experiences, the contract has been designed to ensure maximum value for money through output based payments. Payment of 10% of the management fees will also be based on performance against an agreed set of key performance indicators. Vfm will be assessed across the lifetime of the contract and in particular at the four break points built into the contract.

The decision of which projects to fund has and will always be made on the basis of vfm. All proposals are assessed on the vfm of their impact on poverty (effectiveness and efficiency) and management arrangements (economy) and the relative balance of these areas. Vfm at project selection has been further strengthened through the first UK Aid Direct funding round. Questions related to the analysis of key cost drivers and how vfm would be managed throughout the lifetime of the proposed project were included in the proposal form. Moreover, for the first time, proposals were assessed on cost effectiveness using a measure related to the health focus of the proposals (DALYs). This approach could be applied to future thematic rounds and can be used to measure and track cost-effectiveness and impact during the life of the project. The thematic focus of GPAF Jobs and Livelihoods round, and first UK Aid Direct funding round, has also allowed standard indicators to be agreed for the log frames. This should allow for comparisons across similar projects for the first time.
Vfm is assessed through the life of projects awarded grants by the Fund Manager. In particular through the Annual Reviews, where grant holders are required to demonstrate how they are delivering vfm and report against the agreed log frame indicators. The Fund Manager also proactively manages grants with high risk ratings and which are underperforming. As a number of GPAF grants reach project completion, learning and evidence is being gathered on what worked and is being used to support and build the capacity of other grants holders, as well as to inform the criteria and appraisal of new grant proposals.

Assessment of whether the programme continues to represent value for money
In terms of the reach, results, and performance, this programme is assessed as still representing good value for money. As UK Aid Direct is implemented this will continue to be monitored and value for money will be a key consideration in the design of all future funding rounds.

Quality of financial management
Overall £139.4 million has been committed in grant funding through GPAF and UK Aid Direct grant awards and will be spent over the lifetime of grants. A total of £97,318,309 has been disbursed to date.
- £88,816,117 in grant funding
- £6,826,626 in Fund Management costs
- £858,446 for the Evaluation Manager
- £817,120 on the GPAF Beneficiary Feedback pilot.

For effective financial management of GPAF and UK Aid Direct, it is important to understand the complex spending profile which commits funding for grants over 3 years through funding rounds. It can also take up to a year for some grants to start implementation activities from the point of provisional grant award.

DFID and the Fund Manager have been working collectively to strengthen financial management over the last year, in response to a significant underspend against the 2014/15 budget for the GPAF (approximate £2.5m). The assumptions underpinning the 2015/16 forecast have been revised and new processes relating to financial management have been introduced, including more detailed monthly reporting from the Fund Manager, and quarterly meetings to review the financial performance of the Fund. The Fund Manager should use their knowledge and experience to strengthen their critical appraisal of project forecasts from grant holders. A move to quarterly invoicing (between the Fund Manager and DFID) could also assist stronger financial management performance of the Fund Manager.

The ability of grant holders to manage their forecasting and budgets is also crucial for accurate financial management. At grant level, the Fund Manager has carried out workshops and webinars on forecasting and financial management to strengthen grant holder capacity in this area.

Date of last narrative financial report	July 2015[4]
Date of last audited annual statement	N/A[5]
[4] GPAF and UK Aid Direct Fund Manager Annual Report to DFID
[5] The Fund Manager’s contract does not require sending DFID annual audited accounts. However, all grant holders are required to submit their accounts to the Fund Manager on an annual basis and these are monitored closely.

E: RISK (½ page)

Overall risk rating: Medium
The overall risk rating for UK Aid Direct in assessed as medium. The UK Aid Direct business case considered financial and fraud risk to be medium to low based on the types of projects and organisations that the GPAF had funded to date.

Overview of programme risk
Risk in UK Aid Direct is managed at (i) grant level by the Fund Manager and (ii) programme level by DFID and the Fund Manager.

Grant level risk
- The Fund Manager works closely with grant holders to manage, address and reduce risk grant level. (The Fund Manager Risk Management Strategy can be found in quest: 5123337).
- The assessment of risks affecting each grant begins at the application process and is a key consideration when recommending projects for grant award. All projects are classified as low, medium or high risk, and this risk action rating (based on technical performance, risk management capacity, financial management capacity and operating context) determines how the project is managed by the Fund Manager. Grants classified as medium or high risk are likely to have more intensive management and receive projects visits.
- When a provisional grant has been awarded, a due diligence assessment is undertaken, any issues it raises must be addressed before the grant is confirmed (and could lead to the grant not proceeding).
- The Fund Manager deploys a number of tools to actively manage and mitigate risks to each grant once in implementation:
  - PMON – high risk tracker which is reviewed in fortnightly meetings with DFID
  - Annual Reviews – grant holders are asked to review risks through the annual review assessment which is then appraised by the Fund Manager. This year’s Fund Manager annual review process assessed 38 projects as not meeting expectations and thirteen projects as high risk. The Fund Manager feedback to grant holders will require immediate actions to address these concerns. The Fund Manager will also use one-to-one meetings and risk management processes identified here to ensure that the projects get back on track and address the identified risks.
  - Quality Assurance Visits – QAVs are undertaken to respond to serious concerns and involve visiting a project to assess the issues and support the grant holder to address them. Twelve QAVs were undertaken in 2014/15.
  - Audits – to manage financial risk a minimum of 15% of grants receive a light touch (level 1) audit per quarter. These are selected though a combination of random sampling and risk based selection. The level 1 audit can escalate to a more in depth audit if the findings of the audit raise concerns. The table below show the 91 audits undertaken in 2014/15. The findings of the audits have been used to inform Fund Manager processes and grant holder capacity building. Also for the first time this year QAVs and audits have been aligned so that there is insight into all areas of the grant and it can be managed holistically.

- Any instance of fraud or alleged fraud is reported by the Fund Manager to DFID immediately. There have been 10 allegations of fraud in GPAF projects this year. These cases are dealt with based on advice from DFID’s Counter Fraud and Whistle Blowing Unit, in line with DFID’s zero tolerance approach.
- The workshop with GPAF grant holders in Tanzania included a comprehensive session on managing fraud and included a very comprehensive presentation by a grant holder who had experienced partner fraud and provoked a good discussion and learning between partners.

Programme level risk
- The risk matrix from UK Aid Direct business case was reviewed and revised when the delivery plan was drafted.
- Risk management is guided by Inclusive Societies Department’s Anti-Corruption and Fraud Strategy (quest document: 5062661).
- Financial and fraud risk is considered different for different components of the programme. Risk associated with the Fund Manager is assessed to be low, as the contract is subject to a full pre-contract due diligence process. There is a higher financial and fraud risk relating to the grants to CSOs and their partners and the management and mitigation measures outlined under the grant level risk are in place in recognition of this.
- There will be inherent risks to transitioning between the GPAF and UK Aid Direct Fund Manager contracts which will require additional time and resources from DFID to manage.

Outstanding actions from risk assessment
- DFID team to review and revise risk matrix in Delivery Plan and ensure risks associated with the transition between GPAF and UK Aid Direct Fund Managers are captured and management/mitigation strategies in place.
- UK Aid Direct business case outlines a desire to introduce a portfolio risk management approach. UK Aid Direct Fund Manager to propose how to introduce this system.
- DFID team to ensure that the risk appetite for each Funding Round is established with Ministers when agreeing the focus and criteria for grant award.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
UK Aid Direct is on track against planned timeframes. The allocation of GPAF funding is now completed and UK Aid Direct has been approved as the second phase of the Fund. The first funding round of UK Aid Direct has been also carried out according to planned timeframes and the grants were awarded by the end of March 2015. Two UK Aid Direct grants have started activities and the others are expected to commence between now and 1 January 2016.

The procurement of the UK Aid Direct Fund Manager is slightly behind schedule. The OJEU procurement process started in December 2014, following the approval of the business case and launch of first funding round. It is about 1-2 months behind schedule, due to the decision to invite potential suppliers to presentations. The submission requesting approval to contract is currently with Ministers. The GPAF Fund Manager contract has been extended to ensure continuity of services to grant holders and DFID until the UK Aid Direct Fund Manager is in place. The delay could affect the timing of the next funding round.

Performance of partnership (s)
The partnership with the GPAF Fund Manager is managed through fortnightly meetings and frequent communication on project issues including the management of high risk grants and the management of the Fund as a whole. The Fund Manager delivers the activities required for the Fund to meet expectations and the grant holder survey shows an increasing degree of grant holder satisfaction with the Fund Manager. However, the absence of a performance framework makes it difficult to assess the level of DFID satisfaction in the partnership and the current reporting framework does not assess quality of Fund Management outputs. Learning from this, the UK Aid Direct Fund Manager contract will manage performance through an output based payment plan. The quality of Fund Manager outputs will be determined through a set of key performance indicators that will be reviewed quarterly. Performance against these will determine 10% of management fee payments.

Other key partners include the Evaluation Manager, Coffey, however due to the nature of the joint Evaluation contract for the PPAs and GPAF there has not been a significant amount of work on the GPAF during this year. A further evaluation of the GPAF will be carried out in 2015/16.

Asset monitoring and control
Grant holders asset management policies are checked through the due diligence carried out before the grant is confirmed. The Grant Arrangement terms and conditions require all grant holders to maintain an asset register, which is checked during audits and visits. At the end of a project there is a formal asset transfer process.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant) Not relevant for this programme.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
The review and discussion of the Theory of Change presented in the UK Aid Direct business case will be central to the inception phase for the UK Aid Direct Fund Manager. It will also influence the systems and processes they establish to manage and monitor the performance of the Fund.

Due to the nature of the joint Evaluation contract (with Coffey) for the PPAs and GPAF there has not been a significant amount of evaluation work on the GPAF during this year (the Mid Term Evaluation was delivered in early 2014). Support has been provided to grant holders nearing project completion (through a seminar) to ensure a good understanding of how to commission evaluations and respond to the findings. A further evaluation of the GPAF will be carried out in 2015/16, and the evidence gathered through this work will be used to shape the direction of UK Aid Direct and determine future evaluation plans for the Fund, which should also be aligned with the Inclusive Societies Department Evaluation, Learning and Evidence Strategy.

Evidence and learning generated by the CSPR, particularly on why DFID works through CSOs and how to build effective partnerships, will also be important for UK Aid Direct and should be built into future decision making on funding rounds and grant management.

Monitoring progress throughout the review period
Grant Holders self-report progress against their agreed log frames by the end of March each year, which are appraised by the Fund Manager. The grant holder annual review process requires grant holders to report on how they are seeking feedback from primary beneficiaries and to share the information they are receiving, and how they have acted on the feedback. As well as the challenges they face in collecting and acting on beneficiary feedback. The Annual Review of the GPAF Beneficiary Feedback Pilot (quest: 5063762), highlights the opportunity to integrate learning from the pilot into the design, implementation, monitoring and reporting of the Fund. The GPAF Fund Manager sits on the Steering Group and has already begun following up on this recommendation.

Due to the large number of grants it is not possible to carry visits to all projects. Projects visits by the Fund Manager are prioritised according to need as can be seen through the QAV process outlined above. The DFID team also had the opportunity to visit projects in Tanzania this year as part of the workshop with grant holders there.

DFID has also commissioned a second grant holder survey by BOND as part of this Annual Review process to ensure that views of the grant holders are reflected in the performance assessment of the Fund (this is an indicator in output 3). The views of grant holders influence DFID and Fund Manager decisions and processes, as can be seen from the response to the first BOND grant holder survey. The results of the first grant holder survey were also presented to all suppliers interested in bidding for the UK Aid Direct Fund Manager contract to inform the design of their proposals.

Review process
This Annual Review has been undertaken as an internal desk based exercise by DFID’s Civil Society Team. The assessments and conclusions are based on the analysis of:
- GPAF portfolio analysis prepared by the Fund Manager (quest document: 5079892)
- GPAF Fund Manager’s Annual Report to DFID 2014/15 (quest document: 5079908)
- GPAF Fund Manager’s Quarterly Report 1 April – 30 June 2015 (quest document: 5079880)
- GPAF Fund Manager’s Quarterly Report 1 January - 31 March 2015 (quest document: 4998557)
- GPAF Fund Manager’s Quarterly Report 1 October – 31 December (quest document: 4881562)
- GPAF Fund Manager’s Quarterly Report 1 July – 30 September (quest document: 4796429)
- BOND Grant Holder Survey 2015 (quest document: 5065690)
- Information on the Aid Management Platform and ARIES

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessment
Key points
Summary of response to iprogrammessues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process