## Template
Please refer to the Smart Guide for advice on completing the various fields in the logframe.
Smart Guide
PROJECT TITLE
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
Negotiated outcome enabling a viable, contiguous and democratic Palestinian state, alongside a secure and prosperous Israel | Proportion of population who are satisfied with the way that the PA is managing its affairs. | Planned | 53% (West Bank 63%, Gaza 32%) 2011 | 65% (West Bank 70%, Gaza 55%)
Achieved
Source
Jerusalem Media and Communication Centre (www.jmcc.org). The target as been drafted by DFID for the state building Grant log frame, but will be replaced with a PA owned target once the DFID polling project starts with the PA.
| Impact Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| World Bank Voice and Accountability score for the OPTs. | Planned | -0.85 2010 | -0.8
Achieved
Source
World Bank Worldwide Governance indicators: (http://info.worldbank.org/governance/wgi/index.asp)
| Impact Indicator 3 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| World Bank Control of Corruption score for the OPTs | Planned | '-0.31 2010 | -25%
Achieved
Source
World Bank Worldwide Governance indicators: (http://info.worldbank.org/governance/wgi/index.asp)
OUTCOME | Outcome Indicator 1 (new) |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
Palestinians are better able to hold their authorities to account | No of policy changes as a result of Tajaawob activities | Planned |  |  |  | 4 | DFID/BC continue to be allowed to operate in Gaza. Unity government continues to operate. PNA receives funds to pay officials and continues to be able to provide some services. Security tensions remain at a level where Tajaawob operations can continue.
Achieved
Source
British Council quarterly reports
| Outcome Indicator 2 (new) |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| Percentage of Tajaawob participants actively using knowledge and skills gained through Tajaawob | Planned |  |  |  | 60% (40% women)
Achieved
Source
Annual survey of committees and CALP participants
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone 2014 | Milestone 2015 | Target 2016 | Assumptions
Strengthened advocacy skills in Palestinian CS through the delivery of Tajaawob advocacy cycle with individuals and communities | No.of advocacy cycles which have reached: Stage 1 (definition & capacity building) Stage 2 (advocacy design & delivery) Stage 3 (Advocacy Action) | Planned | 0 | 6 advocacy cycles | 6 completed advocacy cycle Stage 1 (0) Stage 2 (3) Stage 3 (6) | 6 new completed advocacy cycles Stage 3 (6) | Community Committee model continues to inspire volunteer activism and committee maintain interest in working with Tajaawob. Authorities continue to cooperate with Tajaawob campaigns. There is continued access to Gaza for training.
|  | Achieved |  | Stage 1 (3) Stage 2 (3) | Stage 2 (5) Stage 3 (8)
Source
British Council
IMPACT WEIGHTING (30%) | Output Indicator 1.2 (new) |  | Baseline | Milestone 2014 | Milestone 2015 | Target 2016
| % of particpants who have completed specialised Training and who are satisfied (of which women) | Planned | 0 | 0 | 0 | 80% (50% women)
Achieved
|  | Source |  |  |  |  | RISK RATING
|  | British Council Annual surveys |  |  |  |  | Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
Governance Advisor 0.1 - Programme Officer 0.25
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone 2014 | Milestone 2015 | Target 2016 | Assumptions
Authorities able to understand and engage with communities and CSOs through new and improved mechanisms | No. of engagement mechanisms1 presented by Tajaawob to authorities | Planned | 0 | 3 Mechanisms | 5 Mechanisms | 2 Mechanisms | MOSA, MOE, MOLG and OPM/MOF are available and willing to cooperate across all Tajaawob communities. Citizens and communities continue to be interested in improving social accountability through these tools and spaces.
|  | Achieved |  | 3 | 5
Source
British Council
IMPACT WEIGHTING (25%) | Output Indicator 2.2 |  | Baseline | Milestone 2014 | Milestone 2015 | Target 2016
| No. of engagement mechanisms presented to authorities receiving quality feedback 2 from public | Planned | 0 | 1 mechanism | 3 mechanisms | 5 Mechanisms (aggregate)
|  | Achieved |  | 1 | 3
|  | Source |  |  |  |  | RISK RATING
|  | British Council |  |  |  |  | Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
Governance Advisor 0.1 - Programme Officer 0.25
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Milestone 2014 | Milestone 2015 | Target 2016 | Assumptions
Strengthen capacity of Palestinian media to reflect community lead issues of margenalized voices, including women and youth. | No. of training sessions on outreach to marginalised communities delivered to media houses | Planned | 0 | 2 | 4 | 0 | 24FM continues to operate and PNA officials continue to cooperate with their media discussion shows.
|  | Achieved |  | 5 | 4
Source
British Council
| Output Indicator 3.2 |  | Baseline | Milestone 2014 | Milestone 2015 | Target 2016
| No. of discussions and debate shows between CS and authorities broadcast on radio and TV on community issues | Planned | 0 | 5 radio debates broadcast by the trained radio stations | 20 radio debates broadcast by the trained radio stations. 1 TV show which reaches 10% of the Palestinian population | 24 radio debates broadcast
|  | Achieved |  | 2 broadcast radio shows | 38 radio shows 2 TV shows
Source
British Council
IMPACT WEIGHTING (15%) | Output Indicator 3.3 (new) |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| To ensure monitoring and follow up of commitments made as a result of the debate shows: 1. No. of government authority representatives participating in media programs | Planned |  | 0 | 0 | 1. (15) 2. 70%
| 2. Percentage of commitments made by Palestinian authority representatives systematically followed up by Tajaawob. | Achieved
|  | Source |  |  |  |  | RISK RATING
Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
Governance Advisor 0.1 - Programme Officer 0.25
OUTPUT 4 (New) | Output Indicator 4.1 |  | Baseline | Milestone 2014 | Milestone 2015 | Target 2016 | Assumptions
The evidence of the project captured and disseminated. | Number of lessons captured through: 1. Case studies 2. Policy briefing 3. Research paper | Planned | 0 | 0 | 0 | 1. (6) 2. (1) 3. (1) | Partners cooperate in gathering data and participating in analysis. Tajaawob generates sufficient quality information from which to generate analysis and policy briefs. There is academic/think tank interest in Tajaawob's evidence.
Achieved
Source
British Council: Quality assured by the DFID
| Output Indicator 4.2 |  | Baseline | Milestone 2014 | Milestone 2015 | Target 2016
| Disseminating the evidence3 through: 1. Effectively functioning website. 2. Social Accountability Expo 3. Presentations | Planned | 0 | 0 | 0 | 1. (1) 2. (1) 3. (2)
Achieved
Source
British Council: Quality assured by DFID
IMPACT WEIGHTING (30%) | Output Indicator 4.3 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
Planned
Achieved
|  | Source |  |  |  |  | RISK RATING
Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
Governance Advisor 0.1 - Programme Officer 0.25
Footnotes
1. Engagement mechanisms are platforms where Civil Society and communities can engage with government bodies or authorities responsible for the devlivery of services to the people (e.g. the Citizen Report Card under 2.2.)
2 Quality feedback: Quality feedback is any form of feedback that is communicated from citizens to authorities through accountability and engagement mechanisms, that meets the following criteria: a) Written or documented in the form of memos, letters, minutes of meeting, etc… b) Addressed to particular authorities or decision makers c) Specific in the issues or policies the feedback is focused on, and on the desired outcome, as opposed to general and broad issues d) Well evidenced with information, data, and figures where relevant
3. For example, Tajaawob accountability tools to be made publicly available on the website

## Smart Guide
Smart Guide
Teams should use the guide below to complete the logframe template.
PROJECT TITLE
A meaningful, easily understood (plain English) Project Title.
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from DFID and partners to achieve the impact, ie is your project nested within a broader undertaking?
OUTCOME
The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Millenium Development Goals (MDGs) or Climate Change.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
l | Promote a more considered approach to the choice of Outputs at project design stage; and
l | Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by DFID and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The DFID share at Outcome Level is a simple, pro rata calculation of DFID’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual DFID Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
l | Specific – what will be measured? And how?
l | Measurable - data can be collected
l | Relevant - to the results chain
l | Useful – for management decision making
l | Does not include any element of the target
l | Can be disaggregated if relevant
l | Good mix of qualitative and quantitative
l | Already defined e.g. DRF, OP, ICF KPIs, MDG indicators
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Results Chain and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your SRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality eg use data from national statistical systems / MIS.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets dissaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the logframe are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed ie consider its validity, reliability and availability.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same.
RISK RATING
Risk ratings are recorded as Low, Medium or High and are supported by a robust analysis including a risk matrix.