Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: / CHASE Urban programme
Programme Value: 3,539,487		Review Date: 15/09/2015
Programme Code: 204273	Start Date: 07/10/2014	End Date: 31/12/2017

Summary of Programme Performance
Year	2015
Programme Score	A
Risk Rating	Mid

Summary of progress and lessons learnt since last review

Both IIED and IRC have demonstrated significant progress over the first year of the programme, and are largely on track to meet or surpass milestones. The two partners have established an excellent working relationship. This began in the inception phase with the development of a joint theory of change and impact statement, and agreement over plans for the first co-hosted learning event/practitioners’ workshop. This fruitful collaboration has continued in to the implementation phase, particularly with the recruitment of the Urban Learning Manager at IRC, whose role is most closely linked to IIED’s contribution to the overall programme.

Both partners have experienced some minor challenges during the first year – IRC have had delays in filling key posts related to the programme; IIED has had prolonged negotiations over the formation of a Learning Partnership. This has resulted in some delays to implementation, but has not had any major impacts on milestones or deliverables.

IRC has had some notable successes in its policy engagement at the international level, and is reporting early progress towards intended outcomes. The innovative partnership with DFID that allows IRC, through the DFID secondee, to draw on a range of different networks, is proving successful.

Summary of recommendations for the next year
IRC should scale up its policy engagement with Europe-based institutions and organizations.

As both partners begin to draft and/or commission knowledge and learning products, they should ensure that these are complementary, and that overlap in content or proposed audience is minimised. They should further ensure that each partner takes the opportunity to disseminate these products through their own networks.

IIED must take the necessary steps to ensure that the Learning Consortium is inaugurated on a positive note, and in the spirit of true collaboration. This may require further facilitation to ensure the members of the two mini-consortiums are maximising the synergies between their work and making the most of each other’s networks. Given IRC’s leadership of one of the consortiums, and their implementation of the other component of the overall programme, there may be a role for them to facilitate greater interaction. This should be discussed further once a final decision has been made on consortium members.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:
DevTracker Link to Log frame:

Outline of the programme
This programme responds to the Humanitarian Emergency Response Review’s identification of urban areas as increasingly frequent locations of crises, and the widespread lack of confidence and capability within the humanitarian system to operate in urban environments. The main purpose of this programme is to increase DFID’s, its partners’, and the humanitarian system’s capability to respond to urban crises.

This business case has 2 components. Component 1 is an advocacy and learning partnership with the International Rescue Committee (IRC). Component 2, managed by the International Institute for Environment and Development (IIED), is a capability fund that will make grants to support documentation of and learning from good practice, and the development of practical tools.

Total value of project is £3.5m over the period October 2014 to December 2017.

Component 1
IRC’s contribution to the programme is an innovative learning and advocacy ‘co-production’ partnership with DFID, in which IRC acts as convenor and catalyst in support of an enabling policy environment for improved response to urban crises by government, humanitarian and development actors. IRC’s contribution to the programme has two outputs:

1. IRC’s advocacy focused output is working to broaden the range of actors involved in responding to urban crises and encourage key stakeholders to develop, review and enhance their policies on urban contexts and their implementation. To this end, IRC is implementing a programme of policy engagement focused on the World Humanitarian Summit (WHS) and Habitat III, both in 2016, as well as contributing to other international forums and conferences..

2. IRC’s learning output is working to improve humanitarian and other actors’ understanding of how crises impact urban contexts and how to programme effectively in towns and cities. With a particular focus on working with local authorities and on cash and livelihoods programming, the partnership will generate evidence-based knowledge products that draw on IRC’s and other organisations’ operational experience in crisis-affected towns and cities, and will disseminate lessons learned and good practice

Component 2
IIED’s contribution to the programme aims to strengthen understanding and improve practice among national and international humanitarian actors, local and national governments, and donors, with regard to approaches to humanitarian response in urban contexts. It seeks to do this by addressing gaps in knowledge, technical capacity and skills in order to provide a better basis on which to prepare for and respond to humanitarian crises in urban areas. The work by IIED has three mutually reinforcing outputs:

1. Coordinating a ‘learning partnership’ of leading international organisations (including NGOs, multilateral agencies, and academic institutions) working in the field of urban humanitarian response, in order to document best practices, generate tools, and develop innovative operational working methods.
2. Managing a ‘learning fund’ and ‘responsive small scale research and documentation fund’ to support innovative thematic and regional research on key issues shaping humanitarian responses in urban areas.
3. Coordinating learning events and networking activities in order to disseminate best practices, discuss policy changes, and build the capacity of key actors. This output also includes an efficient and accountable project- and grant-management process to create and coordinate a Strategic Steering Group (SSG); undertake monitoring, evaluation and learning (MEAL) activities; and disburse funds.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

Both partners are delivering on the outputs as set out in the logframe, and are on target to meet the outcomes for the programme. IIED has begun commissioning research and is in the final stages of establishing the learning consortium, that will deliver a number of products critical for the success of the programme. IRC has demonstrated early progress towards creating a more enabling policy environment for urban crises programming, and its learning component is underway. The two partners are working well together, as demonstrated by the success of the first joint workshop, held in Istanbul in September 2015.

Overall output score and description

Overall, the Urban Crises Programme scored an ‘A’. Outputs are meeting expectations, and the programme is on track to achieve its outcomes.

Key lessons

The programme has clearly benefitted from close interaction between the two partners organisations, in the inception phase and in the initial stages of implementation. This looks set to continue over the coming year, and is likely to increase, as IRC will be leading one of the two mini-consortiums that will make up IIED’s Learning Partnership. IRC should consider how it can use its unique position within the overall Urban Crises Programme to ensure that the most is made of DFID funds invested in the Learning Partnership. Both IIED and IRC should give significant consideration to how the tools, evidence and learning generated by the two consortiums, as well as by their own research and learning activities, are widely disseminated and taken up by as broad a range of organisations as possible.

Key actions

- IRC should scale up its policy engagement with Europe-based institutions and organizations.
- Partners should ensure complementarity between the knowledge and learning products that they are producing or commissioning, so as to minimse overlap in content or proposed audience.
- IIED must take the necessary steps to ensure that the learning partnership/consortium begins on a positive note, and in the spirit of true collaboration. This may require further facilitation to ensure the members of the two groups are maximising the synergies between their work and making the most of each other’s networks.
- Partners should ensure a joint web presence that provides details of the Urban Crises Programme as a whole, and provides a platform for outputs from both partners.

Has the logframe been updated since the last review?

Yes. The IRC components of the logframe were revised after the end of the inception phase, submitted with the most recent quarterly report (June 2015) and approved by DFID. The timeframe was corrected as the previous logframe had mistakenly extended the IRC components of the programme until October 2017, when they are in fact due to end in December 2016. The planned targets and deliverables up until December 2016 remained the same. IRC’s milestones were altered to better reflect the different phases of the project, and to ensure they were clear and sufficiently ambitious. Impact weighting and risk rating were added. Finally, the revised logframe was simplified, so as to have one outcome for each of IRC’s areas of focus – learning and advocacy – and a clear set of outputs under these outcomes.

IIED have indicated that they would like to alter the milestones for their Output 2.
## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Advocacy: Key stakeholders are encouraged to develop, review and enhance their policies on urban contexts and better operationalise them
Output number per LF		(IRC) 1	Output Score	A
Risk:		Medium	Impact weighting (%):	33%
Risk revised since last AR?		NA	Impact weighting % revised since last AR?	NA

Indicator(s)	Milestones	Progress
Number of advocacy products produced with actionable policy recommendations that address how humanitarian, development and urban stakeholders can improve response in urban contexts and disseminated at regional and global advocacy and policy events and through online downloads.	By 02/15: 1 paper linked to Ditchley Park event / By 12/15: 3 papers (Dec 2015) / By 12/16: At least 6 advocacy products (papers, reports and briefings) have been published or electronically circulated over the course of 2 years	The following papers have been prepared since the start of the programme, surpassing the Dec 2015 milestone. / 1. ‘How far have we come?’ Paper prepared for Ditchley Park event October 2015. (http://www.alnap.org/resource/19863) This met Milestone 1. / 2. Humanitarian Action in a New Urban World (Prepared for Budapest consultation, February 2015, and rewritten with Middle East content for Amman side event, March 2015) (https://www.worldhumanitariansummit.org/node/493298) / 3. Position Paper - The Urbanisation of Emergencies (Submitted to ALNAP’s Global Forum, June 2015) (http://www.urban-response.org/resource/20281) / 4. Area-based approaches to programming and coordination – the way forward? Paper disseminated at ECOSOC HAS side event.
Number of events at which evidence based advocacy messages are shared (side events, high-level panel events).	By 02/15: 1 Ditchley Park event / By 12/15: 4 events / By 12/16: At least 6 events where advocacy messages are shared	The programme has met milestone 2, and is on track to surpass it, with further events planned for the last quarter of 2015. The following events have been organised to date: / 1. The Ditchley Park event was held in October 2014. This contributed to Milestone 1. / 2. A side event was hosted by IRC in Amman in March on urban displacement to coincide with the Regional Consultation for the MENA region. / 3. A side event was hosted at the ECOSOC Humanitarian Affairs Segment in Geneva in June on Area-based approaches and bridging the humanitarian-development divide in urban areas. / 4. IRC co-convened the WHS Urban Consultation in Barcelona in June.
Number of targeted stakeholders (including humanitarian, urban and development) briefed by IRC on the specificities of urban crises and key recommendations.	By 02/15: 75% of Group A organisations exposed to key messages at Ditchley Park event or through bilateral meetings with IRC. / By 12/15: All Ditchley Park attendees in Group A have had at least 2 follow-up meetings and 30% of Group A have sent representatives to other IRC events. Initial meetings held or other forms of institutional engagement with Group B stakeholders / By 12/16: Engagement maintained with all Group A organisations and follow-ups with Group B. Briefings extended to five additional high-level stakeholders (donors, international multilateral agencies or INGOs)	The programme is on track to meet the target. All US-based stakeholders that attended Ditchley Park have had at least one follow-up meeting. 50% of Group A have already sent representatives to IRC events in Amman and Barcelona. The programme has engaged with the majority of Group B stakeholders. / It should be noted that most of this engagement in the period since the end of the incepation phase in March 2015 has been with US-based stakeholders. This is due to restructuring and staff changes in the UK office which has limited European engagement.

Key Points

IRC’s advocacy and policy engagement over the past year have generated significant progress towards the outcome for the programme: Humanitarian and development actors have improved understanding and enhanced policy and operational commitment to respond to the challenges and opportunities presented by urban crises, to meet the immediate needs of the city and its inhabitants, foster recovery and encourage sustainable development.

Two UN stakeholders in Group A are taking the first steps in the development of new urban policies or internal guidance, and have either requested support directly from the IRC partnership, or have stated that they plan to incorporate key messges developed by the Urban Expert Group in to their internal policy.

Having the flexibility to align the programme with the urban expert group for the World Humanitarian Summit, and being linked in to this network has allowed IRC to get considerable value for money, in terms of leverage in New York and engagement in international consultations and events. Without these alliances, the significant rise in profile of the urban crises agenda over the past year would not have been possible. As a result of intensive engagement with the ‘Urban Coordination Cell’ (that convenes the expert group), the synthesis report for the WHS has considerable coverage of urban crises. Further engagement is required to ensure that the Summit itself gives adequate attention to the urban crises agenda, but high-level statements from senior staff engaged in the Summit are, since September 2015, making reference to the urbanisation of emergencies.

IRC has taken a ‘two-track’ approach to influencing the WHS agenda, externally through publications, written submissions and side events, and internally through its membership of the Urban Coordination Cell. The successful engagement with the WHS secretariat is likely to be repeated with the Habitat III secretariat (also in New York), as the DFID secondee has been selected as an urban expert and will join one of the 10 policy units for the conference. Habitat III will be an excellent forum for reaching a wide variety of stakeholders, including municipal actors and the urban planning community, who are critical for the overarching goal of the Programme.

The project has also recently initiated a new front in the advocacy work, cultivating an interest in crisis response in urban settings among urban experts with a view to creating a demand for greater engagement with humanitarians for improved response. This is in early stages, but IRC have begun to place articles in this sector’s publications; an article by the Urban Advisor/ DFID Secondee was recently published in Citiscope on this issue (http://citiscope.org/habitatIII/commentary/2015/08/learning-language-cities-crisis) and a second article is under consideration by the Guardian for its Cities page.

Restructuring of IRC and staff changes have led to delays in filling vacancies for the programme in the London office. This has meant that the level of policy engagement in New York and Washington DC has not been matched with Europe-based stakeholders. However, WHS processes and enagement have to date been concentrated in New York, and the focus has been on WHS consultations and the drafting of the synthesis report. As such, the project targets have not been overly affected. With the publication of the synthesis report in Sept 2015, the time is ripe for dissemination of advocacy messages with European donors and multilateral agencies based in Geneva, Brussels and other European capitals. An increase in programme staff in the UK office from the final quarter of 2015 will address the imbalance and allow for reengagement in Europe.

Summary of responses to issues raised in previous annual reviews (where relevant)

N/A

Recommendations

As mentioned in Key Points, a recommendation for the next phase of the project is to increase dissemination of advocacy messages with European donors and multilateral agencies based in European capitals.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Learning: Humanitarian and other actors supported to have greater understanding of how urban contexts are impacted by crises and how to programme effectively for the urban context.
Output number per LF		(IRC) 2	Output Score	A
Risk:		Medium	Impact weighting (%):	17%
Risk revised since last AR?		NA	Impact weighting % revised since last AR?	NA

Indicator(s)	Milestones	Progress
Number of knowledge products produced on how urban contexts are impacted by crises and how to programme effectively for the urban context.	By 02/15: Plan for 3 knowledge products with timings and proposed focus of each / By 12/15: 1 knowledge product produced / By 12/16: At least 3 knowledge products produced based on evidence and lessons learnt from IRC urban programming and other non-IRC urban humanitarian and development programming over life of project.	The Urban Response Learning Manager (Learning Manager) has made progress towards the completion of 3 knowledge products by December 2016, with the first scheduled for December 2015. The Learning Manager has conducted several qualitative interviews with IRC’s technical units and country offices, particularly those that practice livelihood programming in urban areas – the topic of the first knowledge product. The Learning Manager has also conducted interviews around other possible topic areas, such as protection in urban areas. In addition to interviewing IRC colleagues, the Learning Manager has had conversations with peer organisations, municipal actors, and UNHCR in an effort to have a fuller conversation and generate lessons that touch on multiple perspectives.
Number of Regional Practitioner Workshops delivered independently or jointly with IIED on how urban contexts are impacted by crises and to promote exchange of knowledge on how to programme effectively in urban areas.	By 02/15: Plans for Regional Practitioner Workshop to be delivered jointly with IIED. / By 12/15: 1 Regional Practitioner Workshop delivered by IRC in collaboration with IIED. / By 12/16: 3 Regional Practitioner Workshops delivered by IRC or jointly with IIED.	The Learning Manager worked jointly with IIED in preparing for and hosting the first regional practitioner’s workshop on “Meeting Needs in a Context of Urban Displacement in the Middle East/North Africa.” Practitioners from international and local NGOs, as well as municipal actors, and development specialists, participated and shared their ideas as to how various sectors and organisations may better collaborate to meet the needs of urban residents living in crisis. IIED has posted a blog about IRC’s presentation on urban planning principles in humanitarian action.

Key Points
Delays in recruitment for the Learning Manager position have impacted on progress towards the learning-related aspects of IRC’s outcome statement. However, the post is now filled, and progress towards milestones is on track. IRC’s decision to temporarily hire a more senior programme coordinator with in-depth knowledge of the IRC and extensive humanitarian experience has helped the Learning Manager to navigate the organisation and make the right connections quickly. This is key to IRC’s aim to generate lessons learned from its own programming and promote exchange with stakeholders at country level. The Learning Manager has also been able to capitalise on participation at the IIED/IRC practitioners’ workshop in Istanbul to travel on to Jordan and Lebanon and begin interviewing municipal stakeholders and gathering data from urban programming in the region.

Initial interviews have confirmed the interest of practitioners in involving municipal actors in the delivery of services and of their need for further support on how to design programmes to be more inclusive in diverse urban settings. It is also clear that practitioners have an incomplete understanding of what constitutes an “urban context,” even though most of their programming takes places within an urban setting, and have yet to consider long-term resilience or city planning goals when implementing programs. These preliminary findings confirm the relevance of the learning component of IRC’s programme for IRC and other humanitarian organisations.

While literature on the need for the humanitarian sector to improve its urban response is vast, it lacks clear and actionable lessons to guide this improvement, Given this, future knowledge products will be based on case studies, so as to draw lessons and recommendations from empirical evidence. The majority of the case studies for the first knowledge product will come from the Syria regional response.

Summary of responses to issues raised in previous annual reviews (where relevant)

NA

Recommendations

Collaboration between IRC and IIED on the practitioners’ workshop in Istanbul was excellent, led to a well-attended event covering five countries in the Middle East affected by the Syrian conflict, and including both humanitarian and city/national authorities. This collaboration looks set to continue in to the second year of the programme. As both partners begin to draft and/or commission knowledge and learning products, they should ensure that these are complementary, and that overlap in content or proposed audience is minimised. They should further ensure that each partner takes the opportunity to disseminate these products through their own networks. IRC should also take advantage of its offices in Europe to organise events where lessons emerging from the learning component of the programme can be shared with an audience of donors, multilaterals and NGOs.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Effective practices documented, tools generated and innovative operational working methods developed by the learning consortium
Output number per LF		(IIED) 1	Output Score	A
Risk:		Medium	Impact weighting (%):	20
Risk revised since last AR?		Y/N	Impact weighting % revised since last AR?	Y/N

Indicator(s)	Milestones	Progress
Number of tools and knowledge products co-produced by more than one consortium partner	Consortium formed and workplan for production of knowledge products (of different types) and tools developed	On track: Consortium members identified and contracting to be completed in November
Number of learning events jointly delivered by consortium partners.	Workplan developed for learning events co-organised and independently organised by consortium members	On track: the two ‘teams’ in the learning consortium have a clear workplan

Key Points

Nine Expressions of Interest were received, in response to IIED’s call for proposals for a Learning Consortium in April 2015. Following IIED’s anaylsis of the proposals, and consultation with the Strategic Steering Group (SSG) the idea emerged to consider funding more than one consortium with a smaller allocation of money for each (in the light of the overall budget, and the proposed activities). Involving more agencies in the consortium would engender greater convening power and enhance the visibility of the findings, and open up more avenues for influence in both the humanitarian and research sphere. Additionally, greater value for money would be achieved by combining the two consortia, as well as improving the coverage of a broader range of humanitarian crises – both conflict and natural disasters.

IIED proposed that the two frontrunner proposals be combined in to a single consortium of up to eight organisations. These two proposals, led by IRC and Habitat for Humanity GB respectively, complemented each other geographically and in terms of their greater level of focus on conflict and natural disasters respectively. The IRC proposal was more focused on developing operationally relevant tools and guidance whilst the Habitat approach had a balance of operation and academic/policy-oriented research. The SSG supported this proposal, and the two consortia also signalled their willingness to collaborate.

Negotiations are ongoing to revise budgets, activities and geographical focus areas, with the aim to begin activities in November 2015. There will be two streams of work, with each consortium separately funded but with joint events to facilitate complementarities in the findings and shared learning across the two groups. In light of the larger number of organisations involved, and the feedback of the two consortia, IIED intends to increase the total budget available for the consortium to a total of £1.1 million (from £900,000). This will be allocated as £500,000 per consortium, plus £50,000 per consortium for discrete research outputs. In addition, IIED will play a role in convening regular programme alignment meetings and mutual learning meetings bringing together all actors in the consortia.

The process of setting up the Learning Consortium/Partnership has demonstrated the value of the expertise and guidance of the Strategic Steering Group. The process has demonstrated to IIED the importance of taking the time to build consensus when setting up a large partnership.

Feedback from the organisations involved highlighted that the original term ‘consortium’ carried a certain baggage and therefore we renamed it the Learning Partnership, reflecting also the revised model of shared learning across parallel streams of work.

Summary of responses to issues raised in previous annual reviews (where relevant)

N/A

Recommendations
IIED’s proposal to combine two proposals in to a single consortium or partnership has the potential to offer greater value for money, and to extend the influence of the programme and the findings generated by partnership members to a wider network of stakeholders. However, consortium members have had to spend additional time to rework their proposals with a much reduced budget and concerns have been shared informally with DFID. IIED must take the necessary steps to ensure that the partnership begins on a positive note, and in the spirit of true collaboration. This may require further facilitation to ensure the members of the two groups are maximising the synergies between their work and making the most of each other’s networks. Given IRC’s leadership of one of the consortiums, and their implementation of Component One of DFID’s urban crises programme, there may be a role for them to encourage the successful commencement of the partnership.This should be discussed further once a final decision has been made on consortium members.

Output Title	Innovative thematic and regional research produced through a learning fund and small scale research and documentation fund.
Output number per LF		(IIED) 2	Output Score	B
Risk:		Medium	Impact weighting (%):	20
Risk revised since last AR?		Y/N	Impact weighting % revised since last AR?	Y/N

Indicator(s)	Milestones	Progress
Number of research grants allocated through the learning fund and the small-scale research fund	First round of 15 research grants allocated	The first thematic call for proposals will be launched in autumn with contracting to be done by January 2016 – though fewer than 15 grants will be made; a further two research proposals commissioned through the responsive fund
Number of knowledge products produced from both funds and disseminated at events and through online downloads	15 knowledge products in progress; accurate assessment of forums for dissemination identified (including workshops, seminars, conferences and other events) and dedicated IIED webpage created for knowledge products	2 knowledge products published, 1 in progress, 2 proposals under discussion; forums for dissemination used (e.g. ALNAP webinar, IREC conference); IIED webpage created, ALNAP also hosting products
Effective and relevant knowledge products are produced (including products with particular focus on needs of different groups and gender relations)	A framework for assessing effectiveness and relevance of the knowledge products is produced jointly with IRC	To be discussed at the October meeting of the Strategic Steering Group – to identify criteria for effectiveness and relevance

Key Points

The ‘responsive’ research fund has produced 2 knowledge products:

Brown D, Johnson C (2015). Setting a new research agenda for urban crisis and humanitarian response
pubs.iied.org/17301IIED.html

Parker E, Maynard V (2015). Humanitarian response to urban crises: a review of area-based approaches
http://pubs.iied.org/10742IIED.html

IIED are disseminating hard copies of these papers and have posted them on IIED’s website and submitted them to ALNAP’s urban response portal. IIED’s approach to solicit calls for expressions of interest has been to put these out via ALNAP’s urban response community of practice and through their own networks. This has helped to disseminate the calls widely, and to identify the best-placed researchers to work on these pieces.

The two finished papers have generated a high level of interest. Between July and September, the review of area-based approaches was downloaded 414 times; while the new research agenda briefing was downloaded 256 times between June and September. One of the authors of the area-based approaches paper was involved in an ALNAP webinar on the topic

The first thematic call for proposals under the Learning Fund will be launched in Autumn 2015 with an aim to complete contracting by early January 2015. IIED will launch further calls in February 2016, May 2016 and September 2016, each with a pot of £150,000, with the intention of funding 4-5 research pieces per call. This represents a change in IIED’s approach. The original aim had been to fund 15 separate initiatives per call, but IIED has decided that it wishes to fund more in-depth and analytical research based on effective partnerships between practitioners and researchers.. It is anticipated that each phase of research should last between 6-9 months and lead to substantial working papers which provide an authoritative discussion of the issues being addressed as well as briefing papers which are targeted more explicitly at policy audiences.

ALNAP’s webinar series, and the Development Planning Unit’s International Reconstruction conference have so far served as opportunities to discuss and disseminate published research.

Summary of responses to issues raised in previous annual reviews (where relevant)

N/A

Recommendations
Indicators 2.1 and 2.2 currently state that 15 research grants will be allocated by December 2015 and that 15 knowledge products associated with those grants will be in progress. However, following IIED’s revised approach, and desire to fund more in-depth research, IIED is likely to have allocated a total of 10 research grants by the December 2015 milestone. While this means that IIED has not met the milestone, they have requested a revision to the milestones to ensure they reflect the new approach outlined above.

The decision to focus on more in-depth research for the thematic calls is appropriate for the Urban Crises programme as a whole. IIED is already commissioning shorter pieces of work and rapid reviews through its responsive window, and the IRC is also producing short advocacy briefs. There is a need within the humanitarian and development sectors for greater evidence on how best to programme in urban areas. Generation, documentation and dissemination of this evidence will require more extensive research, and will be achieved by providing researchers and practitioners with slightly longer timeframes.

Output Title	Best practices disseminated, policy changes discussed and capacity of key actors built through learning events, networking, and effective project management.
Output number per LF		(IIED) 3	Output Score	A
Risk:		Medium	Impact weighting (%):	10
Risk revised since last AR?		Y/N	Impact weighting % revised since last AR?	Y/N

Indicator(s)	Milestones	Progress
Number of different types of events organised (webinars, workshops) and number of participants atttending the events, with feedback from participants indicating that they plan to make use of workshop content in their work	Workplan for key events of different types prepared; Target audience for events and network identified; 1 event held with at least 20 participants.	On track: workplan and target audience to be discussed with IRC and Comms teams; / 1 event held (September, Istanbul) jointly with IRC
Number of events at which research outputs shared	Mapping of key events prepared	IRC and IIED Comms teams in contact
Chances of reaching the most relevant people are maximised and information that is most useful to them is shared to them	Mapping of key target audiences and their information needs prepared	IRC and IIED Comms teams in contact

Key Points

In conjunction with IRC, the first Learning Event/Practitioners’ Workshop was held on September 7-8 in Istanbul. This brought together 22 participants from humanitarian agencies and local and national government from the MENA region to discuss key issues around the increasingly urban nature of refugee crises, with a focus on service provision. The event was well received by participants and enabled IIED to gather feedback on areas of perceived research gaps. As the first international event organised under this grant it was an opportunity to understand in more depth the nuances of the humanitarian crisis in the MENA region, and responses being applied by both humanitarian and state actors. It has also led to a core group of actors in the region being identified as contacts for potential future research and as avenues for dissemination. A blog was published on the website in the days following the workshop: http://www.iied.org/why-urbanisation-matters-responding-humanitarian-crises

The event also demonstrated the capacity for successful collaboration between IIED and IRC, with the two organisations effectively working together to identify participants, set the agenda, and facilitate the workshop.

The IIED Comms team and the IRC Comms team are in contact and will be able to work together to identify key events and opportunities for targeted dissemination. We will begin planning for the World Humanitarian Summit, identifying opportunities for media engagement around the event, as well as a side event (if this is possible). It is likely that future learning events will focus on Asia and Africa respectively.

Summary of responses to issues raised in previous annual reviews (where relevant)

N/A

Recommendations
IIED and IRC have explored opportunities to increase the visibility of the Urban Crises programme on the internet, and are in discussions with ALNAP on an opportunity to have a page on ALNAP’s Urban Response portal that would summarise the programme and provide links to partners’ outputs. This would be a good way to publicise the work of both partners, as ALNAP’s site is the principal repository for research and learning on urban crises, and receives considerable traffic from those interested in urban response. Having a page on ALNAP’s site will allow IIED and IRC to direct interested people to one site that explains the whole programme. However, a final decision has yet to be made by ALNAP on what the website pages for current ‘urban initiatives’ will look like. Once this decision has been made, IRC and IIED should decide jointly whether this provides the necessary profile for the Programme. If it does not, they should rapidly seek an alternative solution.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

IRC

Key cost drivers and performance
The cost drivers for this project, comprised predominantly of staffing, travel, events and publications, have not changed.
Two budget realignments have been submitted, one at the end of the inception phase and a second with the most recent quarterly report (ending June 2015). This budget realignment used funds made available by a late hire of the learning manager and the London-based advocate coming back from maternity leave on a part-time contract to hire a coordinator position. The coordinator is a more senior post and contributes to both the learning and the advocacy components of the project. This post is in addition to the advocate based in London.

VfM performance compared to the original VfM proposition in the business case

IRC is a pre-qualified RRF member, and has passed due diligence for this process, which included an institutional assessment of VFM. Moreover, the IRC is driving programme efficiencies by leveraging its technical expertise and experience, as well as its business processes. In 2014, the IRC went through a systematic process to define the biggest challenges that humanitarian actors face. IRC generated ideas for how to respond to these challenges and how to maximise the impact of funds contributed by donors to make meaningful improvements in the lives of the people IRC serve. During the implementation of this project, IRC is doing so in a number of ways, which include the following;
(1) IRC reviews its salaries against the local markets to ensure they are competitive in each country;
(2) IRC hires the best candidates on the market, who will be more efficient in the implementation of their work;
(3) IRC has outsourced functions to actors that can deliver them at an economy of scale; and
(4) IRC is working in synergy with other internal departments and external stakeholders to share and document lessons and challenges.

The outputs of this project will help equip humanitarian actors and other stakeholders to confront the increasing scale and complexity of crises in urban settings, creating savings for humanitarian response in the future.

Assessment of whether the programme continues to represent value for money

The project continues to represent value for money for two reasons:
1) the overarching argument that the money invested in this advocacy and learning to improve crisis response in urban settings will save much more money in actual crisis response over time remains valid; 2) the savings in actual expenditure by the project created by the late hire of the learning manager has been transformed into an opportunity to deploy more human resources to the project. In total, there is an increase of half a position in human resources working on achieving the project’s results. Moreover, the Coordinator is a senior post supporting the two workstreams. The reduction in time of the learning manager on the project will not harm the quality of the expected outputs because their nature has changed from academic studies to practical case studies and lessons learned, which is deemed more useful and appropriate to achieving the project’s stated objectives.

Quality of financial management

The financial management of the project meets IRC’s standards, which have been evaluated and approved by DFID. Financial reports, showing budget versus actuals, are reviewed on a monthly basis during grant management meetings.
Although the project has faced difficulty in hiring a financial officer on a part-time basis, the organization has made the human resources available to uphold its standards of financial management and accountability.
Date of last narrative financial report	31 July 2015
Date of last audited annual statement	N/A

IIED

Key cost drivers and performance
Cost drivers behind the production and the quality of IIED’s research deliverables are the following:

- Staff costs (salaries and enabling costs such as travel expenses)
- Co-production of knowledge, evidence and processes (engaging directly and early with policy makers and beneficiaries)
- Research partnerships with leading experts (grants and consultancies)
- Communication and dissemination
- Project management (including planning, monitoring and evaluation)

The majority of budgeted costs are pass through funds, 73% in grants and consultancies, and IIED has taken a careful approach to the selection of recipients, with value for money as a key test. IIED has negotiated with the two consortia selected to be part of the new Learning Partnreship, to ensure best value and best financial management practices.

Research value depends in large part on whether the findings are communicated effectively to the different stakeholder groups who are affected by them, or who are in a position to act upon them. To achieve this requires both a theoretical and practical understanding of what different audiences need, and how those needs might be met. This requires thinking about effective communication from the very beginning of a research project, hence IIED’s inclusion of communications staff time.

VfM performance compared to the original VfM proposition in the business case

The Steering Group is closely involved in decisions over the large pass through funds to the Learning Partnership. IIED has recently undertaken a due diligence review for the DFID funded Forest Governance, Markets and Climate programme and are awaiting the outcome which we expect shortly, from which we will comply with all recommendations.

Assessment of whether the programme continues to represent value for money

In line with ongoing practices and recent due diligence review, IIED continues to represent good value for money. At this early stage of the project, evidence is limited, so this will be assessed fully in the next review once more publications have been disseiminated and the work of the Learning Partnership and Learning Fund is well underway.

Quality of financial management

IIED processes:

- Quarterly financial reporting of actual costs with revised budget
- Budget planning on a quarterly basis, with revision against actual costs each quarter
- Staff time, grants and consultancies, travel and meeting costs are recorded in a multi-year budget, phased by quarter, providing the basis for accurate forecasting and monitoring
- Use of timesheets to record staff time against each project
- Costs per publication are recorded to provide comparison and guidance when budgeting for the next period

Date of last narrative financial report
Date of last audited annual statement	6th July 2015

E: RISK (½ page)

IRC
Overall risk rating: Medium

Overview of programme risk

Each project component was evaluated for risks to its achievement.

The anticipated risks to the advocacy component are a lack of traction for change in the UN system and the agenda of the World Humanitarian Summit being drawn to other thematic areas. It is too early in the project to assess the first. The second one has been mitigated by the involvement of the Urban Advisor/ DFID Secondee in the Urban Coordination Cell managing the Urban track of the World Humanitarian Summit, the project members’ participation in the WHS consultations, and the project’s convening of side events at WHS consultations to keep urban crises on the agenda.

The anticipated risk to the learning component is that humanitarian space in the Syria region is further limited reducing the project’s scope for research and learning. The Learning Manager will be traveling to the affected region this month to collect lessons, good practices, and learning. Therefore, so far, this risk has not affected the project’s implementation.

Moreover, the IRC has developed a One Syria Approach, a multi-country-access programme, which will focus on ensuring that IRC’s response to the Syrian crisis is efficient, effective and accountable to ourselves, to our partners, to our donors, and to the people we assist. By doing so we will increase the responsiveness and relevance of our programming. Through this flexible and responsive approach we will maintain strategic access to the region as much as possible, and will be able to shift our learning component in a conflict sensitive way depending on the security situation.

Outstanding actions from risk assessment
None.

IIED
Overall risk rating: Low/Medium/High

Medium

The programme is dependent on certain external events. As IIED is working with operational humanitarian agencies to develop tools and document existing practice, there is a risk that a new large-scale humanitarian crisis may reduce organisational focus on the activities supported by IIED, or cause Learning Partnership members to divert human resources away from these.

Setting up the Learning Partnership requires effective collaboration between members and ability of consortium members to recruit as per their plans

Overview of programme risk

The lead organisations of the Learning Partnership, who will be managing the budgets for their teams, will be assessed through a pre-engagement questionnaire, following IIED procedures. This will ensure any potential risk factors are identified before contracting starts and can be addressed as required.

IIED has minimised any potential for conflict of interest in the selection process of the Learning Partnership by ensuring that members of the Strategic Steering Group from any of the organisations applying were not involved in the selection process.

IIED has a range of policies and procedures which mitigate the risk of engagement with third parties:

- All relationships with new partners (grantees) are subject to pre-engagement assessment of the relationship internally within IIED and to internal checks by IIED’s Finance department.
- IIED’s Procurement policy requires assessment of capacity and value for money of service providers
- IIED’s Anti-Fraud and Bribery policy requires declaration of interests
- IIED conducts due diligence on new partners over certain thresholds (risk assessment over £40K, more detailed questionnaire and assessment over £100K).
- External contracts are based on deliverables and paid in staged instalments
- Contracts include provisions drawing the attention of partners to requirements under the UK Bribery Act
- Staff training is provided on transparency and anti-corruption
- Any incidence of failing partnerships is monitored and declared to the Board of Trustees

Outstanding actions from risk assessment

N/A

F: COMMERCIAL CONSIDERATIONS (½ page)

IRC
Delivery against planned timeframe

The delivery of all outputs is on schedule and in line with the updated logframe, approved by DFID in September 2015.

Delivery against the planned timeframe has been delayed by the hiring of the Learning Manager. This post was initially planned from the beginning of the project and was not filled until July 2015. However, the tasks assigned to this post were changed for programmatic reasons, independent of the delay. In the initial planning stage, the project intended to undertake academic studies of urban programming. As the project got underway, it was recognized that a great deal of academic literature exists and what the project needed to focus on and deliver were actionable learning products that programmers in the field could easily use. These learning products build on existing academic literature and field experience, and they are not as time consuming to produce. Therefore, the reduced timeframe for the learning component will not negatively affect the quality of the products.

Performance of partnership (s)

The partnership between IRC and DFID is unique in that it is a co-production. As such, the deployment of a DFID staff member into the team is a new experience for both organisations and has been a significant asset for the project. This is due in large part to the secondee’s knowledge, experience and skill set that she brings to bear on the project, as well as her position within DFID. For example, she has ably served as one of three experts on the Urban Coordination Cell for the World Humanitarian Summit, has recently been appointed as an expert on a policy unit for Habitat III, and has been accepted to hold a side event at the 32nd International Conference of the Red Cross and Red Crescent. Through these leadership roles in major international fora where debates and decisions on the future of humanitarian assistance are made, we have a greater chance of influencing the agenda and persuading key stakeholder of the criticality of urban-specific crisis response.

The partnership between IIED and IRC has been productive thus far. IIED and IRC have a full understanding of each organisation’s role in the partnership, with IIED focusing on high-level, conceptual ideas around urban response and IRC focusing on more specific evidence and lessons from case studies on IRC’s programming in urban areas. Most recently, the organisations worked collaboratively to plan for and host the first practitioner’s workshop on “Meeting Needs in a Context of Urban Displacement” in September 2015. Leading up to the workshop, staff from each organisation worked together to decide on the workshop’s themes and direction, and to make sure that it helped to identify areas for future research. The immediate feedback from the participants was very positive. Attendees were excited about the discussions held on multiple sectors and benefited from insights from national and municipal level actors, humanitarians, and city planners.

The success of the partnership and the nature of cooperation established will help ensure that the deliverables of each organization are complementary and that they share messaging to promote a coherent international discourse.

Asset monitoring and control
NA

IIED
Delivery against planned timeframe

The inception phase was carried out in the time period envisaged by the business case, and the IIED programme remains on track to be carried out in the 3 year time period originally agreed upon.

Performance of partnership (s)

IIED has strong partnerships with a number of development and academic actors working in the field of urban risk, and has deliberately invested time in building relationships, particularly in the formation of the Learning Partnership, to develop trust. IIED has ensured that the Strategic Steering Group was composed of key individuals representing a cross-section of urban crises work, from conflict to disasters to resilience, and has received valuable support and guidance from the Group. The Strategic Steering Group is comprised of:

- Roger Zetter, Emeritus Professor, Refugee Studies Centre, Oxford
- Jo da Silva, Director, ARUP International Development
- Maggie Stephenson, independent
- Irina Mosel, Research Fellow, ODI
- Lucy Earle, DFID / IRC

IIED’s collaboration with IRC is on a strong footing following the recruitment of the Urban Learning Manager and a successful workshop in Istanbul, jointly organised and hosted by both organisations.

Asset monitoring and control

Close control is maintained by a strong oversight from the IIED Chief Operating Officer, Head of Finance and Head of Strategy and Learning with regular reviews of spend and budget monitoring.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

H: MONITORING & EVALUATION (½ page)

IRC
Evidence and evaluation

Evidence gathering by IRC is in early stages. It is clear that there is a demand for greater evidence by humanitarian and other actors on how best to operate in urban contexts. The theory of change for the programme remains robust.

No evaluations are planned for IRC’s contributions to the programme,, given the long-term nature of its efforts to influence the policy environment and the delivery of humanitarian assistance.

Monitoring progress throughout the review period

IRC’s component of the programme has a monitoring plan that draws on the ‘Outcomes Mapping’ approach and integrates the joint Theory of Change, Logframe, and an ‘Alignment, Interest, and Influence Matrix’, which maps the targeted stakeholders. Additional tools supporting the monitoring plan are the project work plan and an outreach tracker.

During the review period, baseline assessments were undertaken for both the learning and the advocacy aspects of IRC’s contribution to the programme. The assessments serve as progress markers: stakeholders can be re-interviewed over the course of the initiative to measure change in position, engagement, and commitment to the urban crises issue. The learning baseline undertook interviews with five IRC country offices and three peer organisations. The advocacy baseline undertook interviews with five institutions, representing about 29% of the targeted primary stakeholders.

Weekly team meetings and monthly grant management meetings are held to ensure the project is on track to meet its planned results and identify solutions for challenges confronted in implementation.

IIED
Evidence and evaluation

Research and knowledge production by IIED and its grantees are in early stages. It is clear that there is a demand for greater evidence by humanitarian and other actors on how best to operate in urban contexts. The theory of change for the programme remains robust.

Plans for monitoring and evaluation have been established, and will include a key role for the SSG to assess progress, relevance and effectiveness of activities.

Monitoring progress throughout the review period

IIED plans to implement a Monitoring, Evaluation and Learning (MEAL) process, and has been discussing this both with IIED MEAL staff and a specialist and market-leading MEAL organisation with experience in the humanitarian sector.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessmen
Key points
Summary of response to iprogrammessues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process