Annual Review - Summary Sheet

Title: Support to the World Bank project ‘Enabling the Business of Agriculture’
Programme Value: £4,900,000 total (£3,000,000 disbursed)		Review Date: October 2017
Programme Code: 204123	Start Date: 18/11/2013	End Date: 30/11/2020

Summary of Programme Performance
Year	2014	2015	2016	2017
Programme Score	A	A	A	A
Risk Rating	Medium	Medium	Moderate	Moderate

Summary of progress and lessons learnt since last review

This is the fourth annual review of the Enabling the Business of Agriculture project (EBA),originally a 3-year programme commencing in 2013 which had a cost and time extension approved in 2016 , extending the project for another three years to the end of 2019/20. This funding is expected to deliver biannual data collection and publication of the EBA indicators, the fulfilment of a dissemination and uptake strategy, development of an implementation efficiency index and further refinement of the methodology, gender and environmental sustainability aspects of the index.

The EBA is now firmly established in data collection in 62 countries across 10 main thematic areas and two over-arching themes (gender and environmental sustainability). Data collection and report preparation has been moved to a biannual cycle with no data collection in 2017, the next round in 2018 and the next report due in 2019.

The 2017 Annual Report was published in January 2017 and is available for public download.
The logframe was substantially reviewed and amended from the previous version and this Annual Review assesses progress against the new outputs and milestones (3 outputs compared to 2 previously). As a result there is some inconsistency in relation to previous annual reviews which assessed against prior, now redundant or substantially amended milestones.

The EBA is on track according to progress against the new agreed outputs and milestones. The Annual Report (2017) details data collection methodology, and explains how gender and environmental sustainability themes are addressed as overarching theme in addition to the focus on the 10 main thematic areas (seed, fertiliser, machinery, finance, markets, transport, water and ICT, land and livestock). The report clearly presents the data that assesses and measures the legal barriers for businesses operating in those 62 countries (which are a mix of low, middle and higher income countries). The EBA team has made substantial progress in developing analysis on gender as an overarching theme. The team however has made less progress on developing analysis on environmental sustainability in the last year, having chosen a gender focus but have prioritised this for the upcoming year.

Dissemination of EBA methodology, approach and findings has been broad, across multiple events and fora including good CSO engagement at various levels. As a result EBA is becoming recognised as an important World Bank initiative easing the barriers to the development of agribusiness across many countries.

Lessons Learned:

- Biannual data collection eases off the pressure to collect data from so many countries each year and allows effective dissemination in intermediate years.
- Good progress made on developing overarching gender indicators. Similar effort required to address overarching environmental sustainability indicators this year.
- Importance of effective feedback mechanisms from events has been recognised as critical to further developing and fine-tuning the indicators.
- The development of the EBA indicators is an effective relatively low-cost approach to opening up markets in agribusiness across many countries. It should be an integral element of any support for the commercialisation of agricultural production (at all scales) in low and middle income countries.

Summary of recommendations for the next year

EBA to continue to keep donors apprised in terms of the development of the methodology to assess environmental sustainability indicators and potentially engage with donors on discussions relating to methodology options and approaches.

Review and release gender background note for external access.

EBA and DFID to engage closely in using these indicators for the development of the new CASA (Commercial Agriculture for Smallholders) Programme, in terms of establishing effective moni-toring and embedded in programme design.

EBA to develop the evidence links between indicator dissemination and legal and regulatory re-form. DFID to buy into and support this process and analysis.

Improve use of social media for dissemination of methodology and results of EBA work

It is recommended in future years that EBA disaggregates financial reporting on different stages of programme activities to show the specific comparative costs of data collection, report preparation and dissemination.

It is recommended that the ongoing process of using World Bank feedback mechanisms to inform and fine-tune World Bank operational policy and approach is further developed in the coming year clearly demonstrating the link between dissemination of EBA indicators, operational impact and regulatory reform.

The EBA team could do more to demonstrate the effectiveness of the report and engagement activities to ensure that the research continues to inform strategies, policies and operations .

Recommendations from the 2016 Annual Review (and actions/response)

The programme should move to a biannual publication cycle following the publication of the 2017 report. This gives time for the team to focus on uptake of the report’s content to create more opportunity for impact, e.g. for reforms to take place.

The programme has moved to a biannual cycle with next data collection in 2018 and next report due in 2019.

The EBA team should strengthen and deepen indicators and analysis on gender and environmental sustainability across topics. Data should be presented in two standalone chapters on gender and environmental sustainability in the 2017 report

The EBA team has made substantial progress in developing analysis on gender as an overarching theme. The team has made less progress on developing analysis on environmental sustainability.
These were presented as two standalone chapters in the 2017 report.

The EBA team should develop an implementation efficiency index for data collection in 2018, to improve understanding of policy practice and implementation of laws and regulations which are needed to create an enabling environment for agribusiness.

The EBA team has made progress in developing an efficiency index. In the first instance this index is based on cost and time. Further work is in progress to develop this index further for the legal barriers.

The EBA team should further strengthen collaboration and feedback mechanisms with other World Bank staff, in particular operational staff providing technical assistance to governments in country as well as Washington based policy and programme teams. Progress should be reported in the next annual review.

The EBA team has conducted an internal quality check to determine and advise how feedback mechanisms can be improved, particularly from events targeting World Bank operational teams. WB country teams are normally actively integrated in country level dissemination events and the feedback mechanism is being continually developed and improved so that dissemination can be shown to lead to operational impact. It is recommended that this process is further developed in the coming year clearly demonstrating the link between dissemination of EBA indicators, operational impact and regulatory reform. (new Recommendation 7)

The SRO should work with the EBA team to ensure DFID focus countries are included in the index as far as possible

This is still pending. Some preliminary discussions were had but there is a disconnect between some of DFID priority countries, which are highly fragile, such as South Sudan, and what the Bank deemed realistic and practical in terms of doing business. Afghanistan was noted as a potential addition though. This concern is valid and for highly fragile states the EBA indicators are not applicable until a suitable level of stability is reached.

A. Introduction and Context

DevTracker Link to Business Case:	Business Case
DevTracker Link to Log frame:	Logframe

The ‘Enabling the Business of Agriculture’ (EBA) programme is a multi-donor, multi country programme housed in the World Bank. It collects data on indicators that measure legal barriers for businesses operating across the agricultural value chain, and the transaction costs in dealing with government regulations. The ultimate aim is to promote smart regulations that ensure safety and quality control as well as efficient regulatory processes that support thriving agribusinesses. The intended impact is to provide opportunities for smallholders and workers through these agribusinesses and promote long term economic development. In this way, the index supports the monitoring and delivery of Global Goal 2 of ending hunger, achieving food security, improving nutrition, and promoting sustainable agriculture, and also contributes to Goals 1 (ending poverty) and 8 (economic growth) amongst others. It contributes to the delivery of DFID’s strategic framework on economic development as well as DFID’s conceptual framework on agriculture.

Three years on, the index is starting to become a trusted source of information for governments, including in DFID focus countries. The EBA measures regulations, policies and transaction costs that affect the emergence and sustainability of agriculture-related businesses. The project aims to provide policy-makers with an evidence-backed tool that can be used to inform policy reform, for example improve regulation around certifying and importing fertilizers. In the past year, the EBA started to show direct impacts on policy reforms in agriculture. For example in Vietnam, regulations related to Tractor import, Tractor operations and Tractor testing/standards have been addressed in a policy reform, as reflected in EBA indicators scores. Sixteen other regulatory reforms are in process in Vietnam, Sudan, Rwanda and Ethiopia following on from EBA dissemination.

The first phase of the EBA aimed to develop two components: (i) Regulatory indicators and (ii) Deep-dive policy and practice assessments, known as Market Metrics (MMs).

1. Regulatory indicators: these indicators focus on the laws and regulations that are the most important for agricultural productivity in countries around the world – developed and developing. The indicators will be consistent and comparable across economies, enabling benchmarking to take place.
2. Market Metrics (MMs) multi-country studies: these metrics will examine a broader range of factors affecting agricultural productivity, market access, and the policy environment for agriculture. MMs will bring new benchmarks to the attention of policymakers and will provide a number of important new metrics to better enable policy-makers to establish their country's position in relation to their neighbours and countries at a similar stage of agricultural development.

The EBA started with 6 indicators, which have been scaled up to 10 indicators this year including the following topics: seeds, fertilisers, mechanisation, land, water, livestock, transport, finance, information communication technology (ICT), and markets. Other topics, such as contracting agricultural production, were considered at an earlier stage, however the comparability of data across countries has led to the project settling on the 10 topics selected. In addition indicators focussing on gender and environmental sustainability were integrated across a number of topics.

The Market Metrics as they were named have been removed following work by the Technical Advisory Committee and Donor Committee which found the methodology unable to deliver sufficiently robust information. Whilst the aims of the market metrics remain relevant, the programme is adapting so that it will deliver these outcomes in different ways, for example by creating country specific profiles or regional analysis, developing partnerships and feedback mechanisms and focussing on policy relevance and uptake.

The EBA indicators were developed over three years, starting with a pilot phase of data collection in 10 countries in 2013, scaling up to 40 countries in year 2 and 62 countries in year 3, including a range of DFID focus countries. The chosen countries represent a range of geographic regions at different stages of agricultural development so that comparisons between countries can be made.
## B: PERFORMANCE AND CONCLUSIONS

Outcome performance:

The EBA’s objective is to become a key policy tool for policymakers, leading to indicator-informed regulatory reform. Due to the positive progress made during the pilot phase, funding for the project has been extended for another three years and therefore the EBA will continue to make progress against the outcomes sought in the logframe.
The Outcomes depend upon understanding and uptake of indicators across participating countries. As yet, the indicators are still being rolled out through multiple country and regional dissemination events. As a result it is too early in the programme cycle for these outcomes to have yet been achieved.

Outcome	Outcome Indicator 1
Strengthen national policy institutions to implement evidence-based policy reforms	Reduction of transaction costs of dealing with government regulations for agribusiness firms and smallholders	Too early to track this outcome
	Outcome Indicator 2
	Improved perception of regulatory reforms being implemented according to how they are written in national legislation.	Too early to track this outcome

Outputs performance:

Output	Indicators	Output score	Impact weighting
Output1: Comprehensive and inclusive data collection in a reflective range of countries where agriculture is an important sector	Number of countries covered; and number of EBA indicators developed / Effective CSO engagement and partnership / Targeted research on effectiveness and impact of EBA indicators	A	33%
Output 2: Technically robust indicator development	2.1 Development of gender indicators / 2.2 Development of the efficiency index / 2.3 Updates and revision to the EBA indicators based on ongoing consultation	A	33%
Output 3: Dissemination and uptake of the EBA	3.1 Events organised and attended where the EBA is effectively presented to relevant participants / 3.2 Effective use of social media and website to disseminate information on and about the EBA	A	33%

EBA has consistently performed according to expectations across all outputs, and as such has been rated A, met expectations as an overall review rating.

Has the logframe been updated since the last review?

Yes. The logframe has been significantly amended in the last year following previous Annual Review recommendations:

Previous Output	Previous Indicators	New Output	New Indicators
Output 1: Development and roll-out of Doing Business in Agriculture methodology	Number of DBA indicators developed / Number of countries in which DBA is rolled out / Number of DBA reports produced. / Number of workshops, seminars, conferences organised or co-organised	Output1: Comprehensive and inclusive data collection in a reflective range of countries where agriculture is an important sector	Number of countries covered; and number of EBA indicators developed / Effective CSO engagement and partnership / Targeted research on effectiveness and impact of EBA indicators
Output 2: Development of Deep Dive multi-country studies	2.1 Number of DD indicators developed / 2.2 Number of DD reports produced	Output 2: Technically robust indicator development	2.1 Development of gender indicators / 2.2 Development of the efficiency index / 2.3 Updates and revision to the EBA indicators based on ongoing consultation
		Output 3: Dissemination and uptake of the EBA	3.1 Events organised and attended where the EBA is effectively presented to relevant participants / 3.2 Effective use of social media and website to disseminate information on and about the EBA

## C: DETAILED OUTPUT SCORING

Output Title	Comprehensive and inclusive data collection in a reflective range of countries where agriculture is an important sector
Output number per LF		1	Output Score	A
Risk:		Moderate	Impact weighting (%):	34%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones	Progress
1.1 Number of countries covered; and number of EBA indicators developed	n.a (EBA data collection will not take place in year 2017)	None in 2017
1.2 Effective CSO engagement and partnership	1. EBA-CSO Working Group (WG) created; / 2. First round of virtual technical consultation on EBA methodology refinement with the WG finalised. / 3. 1 major CSO conference joined; / 4. 1 in-country CSO event organised / 5. CSO participation in 1 EBA dissemination event	1. Established in 2017 / 2. Technical consultations commenced via the WG / 3. CSPF policy forum April 2017 / 4. In country events in Uganda and Tanzania in March 2017 / 5. CSO participation in dissemination events in Zambia and Zimbabwe
1.3 Targeted research on effectiveness and impact of EBA indicators	3 research outputs covering the impact of regulation in agricultural development	4 research outputs completed

Key Points

  1. The EBA will now produce biannual reports, the next one due in 2019. Given that, there was no data collection in 2017 and the next round of data collection will be in 2018.

EBA measures legal barriers for businesses operating in 62 economies and 12 topic areas. The country range includes low, medium and higher income countries and is not directly related to DFID priority countries. EBA provides quantitative indicators on regulation for seed, fertiliser, machinery, access to finance, markets, transport, water and information and communications technology (ICT). Two overarching themes, gender and environmental sustainability are included in report analysis to ensure that messages being delivered by EBA encourage inclusive and sustainable practices. Scoring was piloted for the land topic area in 28 countries and it is expected that the data for the remaining 24 countries will be collected during the next programme year. Data collection on the livestock topic focused on veterinary medicinal products.

The majority of the data are collected remotely. However every other year the EBA team travels to the countries where it is most difficult to collect data remotely. Data collected are then reviewed and validated by World Bank focal points in each country. The data are then aggregated into the indicators allowing for further analysis and comparisons and then are in a state to contribute to the annual report. The report undergoes rigorous internal and external peer review before being passed as ready for publication.

1.2 The EBA CSO working group (WG) was established in 2017 and technical consultations via this group commenced. The group will produce a forward workplan by the end of November 2017. The WG will review the EBA indicators and provide feedback to EBA by December 31st.

In April 2017 EBA presented the project and participated in a panel discussion at the World Bank’s annual Civil Society Policy Forum (CSPF). The CSPF is held twice per year alongside the International Monetary Fund (IMF) and World Bank Group (WBG) Spring and Annual Meetings, and provides an open space for Civil Society Organizations (CSOs) to dialogue and exchange views with WBG and IMF staff, their peers, government delegations, and other stakeholders on a wide range of topics. CSOs participating included the World Farmers Association, Practical Action and the Alliance for a Green Revolution in Africa/Africa Green Revolution Forum (AGRA/AGRF).

The World Bank also organised a conference on Land and Poverty in March 2017 at which EBA presented and EBA also participated in the CAADP meeting in Kampala in June 2017 at which there was strong CSO representation.

1.3 EBA has produced Policy notes and policy briefs based on Research Outputs as follows (which are all publically available for download via the EBA website http://eba.worldbank.org/):

- The regulation of agriculture in developing East Asia – EBA policy note – downloaded 32 times
- Measurement and patterns of world agribusiness trade – Research Policy Brief - downloaded 8 times
- Structural transformation of the agricultural sector: A Primer – Research Policy brief – downloaded 6 times
- Regulatory constraints to Agricultural productivity – World Bank working paper – downloaded 368 times

Three more research briefs are currently under preparation, and awaiting peer review and feedback from academic reviewers.

Summary of responses to issues raised in previous annual reviews (where relevant)

The programme should move to a biannual publication cycle following the publication of the 2017 report. This gives time for the team to focus on uptake of the report’s content to create more opportunity for impact, e.g. for reforms to take place.

The programme has moved to a biannual cycle with next data collection in 2018 and next report due in 2019.

Recommendations

None further for this output

This output has been rated A. Meets expectations

Output Title	Technically robust indicator development
Output number per LF		2	Output Score	A
Risk:		Moderate	Impact weighting (%):	33%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones	Progress
2.1 Development of gender indicators	1. EBA Gender background note finalised; / 2. Methodology refined for data collection in 4 countries / 3. Joint Analysis with the Women Business and the Law team completed.	1.Gender background note finalised and under internal review / 2.Methodology refined and ready for data collection in a least 4 countries in 2018 / 3. Joint analysis with WBL team still to be completed (by November 2017)
2.2 Development of the efficiency index	1. Preliminary EBA 2017 Efficiency Index for 62 countries published; / 2. Background paper (analysis and research) for the efficiency index finalised; / 3. Methodology to capture regulatory efficiency developed.	1. Efficiency index for 62 countries published as integral to Annual Report. / 2. Background papers completed in summer 2017 / 3. The description of methodology included as an Annex to the Annual Report
2.3 Updates and revision to the EBA indicators based on ongoing consultation	1. Technical consultation on EBA 2017 indicators; / 2. Assessment of EBA indicators and scoring methodology refinement. 3. 4,500 contributors consulted	1. Technical consultation integral to all dissemination events. / 2. Steering committees and working groups have been established to assess EBA indicators. / 3. 4,000 up to 2016 and 500 in 2017

Key Points

2.1 EBA completed a Chapter in the 2017 Annual Report on gender. EBA collected data on availability of gender-disaggregated data, restrictions on women’s employment and activities, women’s participation and leadership in collective groups, and non-discriminatory legal proceedings. The chapter concludes that EBA indicators cover a range of regulatory and procedural aspects that have a direct impact on women working as producers and in agricultural value chains. New data were collected this year that highlighted where regulations can have a more direct impact on women’s productivity and opportunity. Progress in these areas can improve women’s prospects as producers and in value chains am improve equity with men.

However this analysis is seen as preliminary by EBA and this is being developed further through the gender background note (which is currently written but being held as an internal document), next round of data collection (in 2018) and the joint work with the Women Business and Law Team. EBA notes the complexity of gender data across thematic areas and there is no ‘one size fits all’ approach appropriate.

2.2 The efficiency index is described in some detail in the 2017 Annual Report. Efficiency indicators reflect the time and cost imposed by the regulatory system, for example the number of procedures and the time and cost associated with such a process as certifying seed. So far the focus has been largely on the time and cost of undertaking transactions, for example how long it takes to regulate fertiliser, how much this process costs. EBA is still to look in more detail at the legal requirements of these processes.

2.3 EBA is developing a more effective feedback loop so that recommendations coming back via feedback (after review and analysis) can have a potential operational impact. This feedback loop is an important mechanism, demonstrating the validity of the EBA but also ensuring that is refined by potential users, to suit their needs and particular context.

Summary of responses to issues raised in previous annual reviews (where relevant)

The EBA team should strengthen and deepen indicators and analysis on gender and environmental sustainability across topics. Data should be presented in two standalone chapters on gender and environmental sustainability in the 2017 report

The EBA team has made substantial progress in developing analysis on gender as an overarching theme. The team has made less progress on developing analysis on environmental sustainability.
These were presented as two standalone chapters in the 2017 report.

The gender indicators measure aspects of the business environment that matter for all participants along agricultural value chains regardless of gender. Women can benefit from an improved business environment as measured by EBA indicators through streamlined operational and business requirements for businesses, member-based rural institutions, innovation for financial inclusion and land use and ownership.

The EBA team should develop an implementation efficiency index for data collection in 2018, to improve understanding of policy practice and implementation of laws and regulations which are needed to create an enabling environment for agribusiness.

The EBA team has made progress in developing an efficiency index. In the first instance this index is based on cost and time. Further work is in progress to develop this index further for the legal barriers.

The EBA team has also been working on development of the environmental sustainability indicators throughout the year focusing on Conservation of Plant Genetic Resources, Access and Sustainable use of plant genetic resources, Water Quality management and Soil Health management. EBA has noted the complexity of establishing this thematic cross-cutting indicator, in terms of having to address a multiplicity of stakeholders, across seed supply, soil and water management, use of pesticides etc. Collecting data in this area has proved very challenging and EBA is still working on improving their data collection methodology. It is hoped that this will be refined in time for the 2018 round of data collection.

Recommendations

The environmental sustainability indicators measure the legal and regulatory framework applicable to the management and sustainable use of natural resources vital for agricultural production. This covers:
- The conservation of plant genetic resources
- Access and sustainable use of plant genetic resources
- Water quality management
- Soil health management

EBA to continue to keep donors apprised in terms of the development of the methodology to assess environmental sustainability indicators and potentially engage with donors on discussions relating to methodology options and approaches.

Review and release Gender background note for external access.

EBA and DFID to engage closely in using these indicators for the development of the new CASA (Commercial Agriculture for Smallholders) Programme, in terms of establishing effective monitoring and embedded in programme design.

This output has been rated A. Meets expectations

Output Title	Dissemination and uptake of the EBA
Output number per LF		3	Output Score	A
Risk:		Moderate	Impact weighting (%):	33%
Risk revised since last AR?		n/a (new output)	Impact weighting % revised since last AR?	n/a (new output)

Indicator(s)	Milestones	Progress
3.1 Events organised and attended where the EBA is effectively presented to relevant participants	1. Dissemination of EBA17 indicators to target audiences through multiple channels (print report, website update, communication materials such as press release, FAQs, presentations, handouts). For specific audiences dissemination will take the following form: / Policy makers: -methodology workshops on how to improve on EBA indicators through smart regulatory reform (at least one global event, 1 regional event and 2 country dissemination events) / Private sector: webinars on specific topics (at least 4) / - Industry events (at least 2) / Civil society: as part of overall engagement, present findings at global events with CSO participants (at least 1 global event) / Multilateral organisations: partner with multilateral organizations to use EBA indicators in analysis (FAO, IFPRI, AfDB, and others) / Academia: present EBA report and other analytical research at academic conferences to entice more academic research that uses EBA data (at least 3 conferences).	The Annual Report was produced as a downloadable pdf document on the EBA website / 9 national events held in 2017 in Africa and Latin America (Tanzania, Uganda, Rwanda, Malawi, Zambia, Zimbabwe, Sudan, Nicaragua and Honduras) / Other key events; / WB Civil Society Policy Forum presentation. / World Bank Conference on Land and Poverty / (See Annex 2 for full list)
3.2 Effective use of social media and website to disseminate information on and about the EBA	1. New data posted for 12 topics and 62 countries; / 2. 62 country profiles developed and posted; / 3. 2 quarterly newsletters published; / 4. 3 bi-monthly data highlights published; / 5. 10% average monthly increase in page views; / 6. 30,000 page views; / 7. 5,000 unique visitors.	1. Completed in Feb 2017 / 2. Completed in Feb 2017 / 3. First quarterly newsletter published in July 2017. Second due end of October 2017 / 4. Two sets of highlights published (via Website) in April 17 and Sept 17 / 5. 15% average monthly increase in page views / 6. From Jan-Oct 17, 53,638 page views / 7. From Jan-Oct 17, 16,0693 unique visitors

  1. The EBA Annual Report was published in January 2017 (slightly delayed from December 2016) as World Bank 2017, Enabling the Business of Agriculture 2017. Washington DC. World Bank. http://eba.worldbank.org/~/media/WBG/AgriBusiness/Documents/Reports/2017/EBA2017-Report17.pdf

Throughout the year, EBA has been engaging with key stakeholders from government, the private sector, civil society, and academia to ensure effective dissemination of EBA data and analysis. Feedback on EBA indicators and methodology is welcome as part of these activities, and feeds into EBA's research agenda. EBA has held launch events in 2017 in Tanzania, Uganda, Rwanda and Malawi (March 2017), Nicaragua and Honduras (April 2017), Zambia, Zimbabwe and Sudan (May 2017). These have ben attended by representatives from governments, the private sector, farmers groups and associations, farmer’s unions, civil society, international development agencies and organisations.

In April 2017 EBA presented the project and participated in a panel discussion at the World Bank’s annual Civil Society Policy Forum (CSPF). The CSPF is held twice per year alongside the International Monetary Fund (IMF) and World Bank Group (WBG) Spring and Annual Meetings, and provides an open space for Civil Society Organizations (CSOs) to dialogue and exchange views with WBG and IMF staff, their peers, government delegations, and other stakeholders on a wide range of topics.

EBA presented to the 18th Annual World Bank Conference on Land and Poverty (Washington DC on March 20-24, 2017), with a view to explaining its coverage of issues related to rural land productivity and the functioning of land markets.

Annex 2 provides a comprehensive list of all events at which EBA indicators were introduced or presented at in 2017.

A next step should be building on the dissemination process, tracking the uptake of the EBA indicators in-country and assessing on an on-going basis how these are influencing the legal and regulatory environment. EBA and the Gates Foundation (BMGF) have started work together on this, and this initiative should be supported and developed further (with DFID support?) as a clear measure of potential and real impact of the EBA indicators. Progress to date on developing this is shown in Annex 3 World Bank EBA reform status tracker (Sept 2017) which shows that to date three processes in Vietnam related toTractor import, Tractor operations and Tractor testing/standards have been completed in that the issues raised by EBA have been addressed in a policy reform, as reflected in EBA indicators scores. Sixteen other regulatory reforms are in process in Vietnam, Sudan, Rwanda and Ethiopia following on from EBA dissemination.

3.2 The EBA website (http://eba.worldbank.org/) provides an overview of the EBA under the following headings:
- About EBA
- Rankings and scoring
- Data by country
- Data by indicator
- Methodology
- Stakeholders
- Reports
- Law library
- News
The website has translations into French, Russian and Spanish.
The EBA is not linked to its own dedicated social media pages but rather via World Bank social media. There is therefore as yet no ‘effective use of social media’ per se in relation to EBA, but very effective use of the EBA dedicated website within the World Bank website. EBA will continue to look into use of social media over the next year including Facebook, Twitter and Linkedin.

Recommendations from 2016 Annual Review
New output. No prior recommendations

Recommendations

EBA to develop the evidence links between indicator dissemination and legal and regulatory reform. DFID to support this process and analysis.

Improve use of social media for dissemination of methodology and results of EBA work

This output has been rated A. Meets expectations
## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance

The business case identified two cost drivers (i) the design and development of indicators (economic efficiency) and (ii) the take up and impact of the findings and deep dive indicators in the decision making of policymakers in developing countries (economic effectiveness). Now that the EBA project has moved to a bi-annual publication, total costs are higher during the year preceding the report publication. Staff costs are ultimately the largest cost driver given the data collection and report dissemination activities rely heavily on high quality personnel and networks. Dissemination activities come with their own set of cost drivers, including travel, accommodation and event organisation (although most of the EBA events are linked into other pre-existing events). Currency exchange fluctuations have been a source of some cost variation however, this variation appears to be fairly modest.
It is recommended that in future years EBA disaggregates financial reporting on different stages of programme activities to show the specific comparative costs of data collection, report preparation and dissemination. (Recommendation 6)

VfM performance compared to the original VfM proposition in the business case

The UK disbursed £3m to Phase 1 of the EBA pilot, equalling £1m per year against a total project budget of $17.6m. The total funding for the three year extension of the project as a whole is $11.99m. The addendum for £1.9m over three years represents a relative reduction in our funding compared to the first three years. Currently no new funders have been secured, beyond USAID and the Bill and Melinda Gates Foundation. The Danish Ministry of Foreign affairs and Netherlands Ministry of Foreign Affairs have ceased funding. In the past reporting year (July 2016 to June 2017), DFID disbursed £475,000, which leaves DFID’s burden share at 48% for the period July 2016 to June 2017. This is a substantial increase on 28% burden share over the first three years of funding (2013 to 2016), however does not take into account USAID funding (which is routed through a separate Trust Fund). Taking into account USAID funding DFID’s burden share falls to 19% for the period June 2016 to July 2017.

Expense Categories	Total FY17 TF Disbursement ($)	DFID's FY17 Disbursement ($)
Staff Costs	817,854	390,504
Consultant Fees	262,037	125,116
Associated Overhead Costs	37,098	17,713
Travel expenses	51,128	24,412
Equipment Costs	-	-
Media Workshop	20,073	9,584
Contractual Services	35,313	16,861
Total	1,223,503	584,190

Table 1: DFID support against total EBA disbursement by component (July 2016 - June 2017)

Assessment of whether the programme continues to represent value for money

The EBA team collect a large amount of data and produce a high quality report with fairly modest resources. The team effectively leverages the expertise of the Agriculture Global Practice and Global Indicators Group and works with hundreds of local partners, drawing on consultants only when necessary e.g. when particular expertise is required and during periods of especially high workload.

The majority of DFID funding goes to finance value-adding operations such as data collection, analysis and dissemination, ensuring that DFID’s funding is delivering impact. Overhead costs account for 3% of total funding which compares favorable against similar projects. Coverage has been successfully expanded to 62 countries across 10 thematic areas whilst costs have remained roughly unchanged. On this basis the EBA project is considered to represent good value for money.

That said, the EBA team could still do more to demonstrate the effectiveness of the report and engagement activities to ensure that the research continues to inform strategies, policies and operations. (Recommendation 8) This process has commenced informally but can be made a higher priority activity (see Recommendation 4). Furthermore, DFID is keen to see the EBA project move to a more sustainable funding model, where by some countries fund their inclusion in the EBA report, for example. It appears however, that little progress has been made to broaden the donor base with no new proposals currently being considered. Although there is an intension to secure core Bank funding there is no concrete plan to move to a more sustainable funding model. That said, experience shows that it takes more than the few years that the EBA has existed for governments to start adopting a model for which they have understood the added value by also budgeting for it in their own processes.

Quality of financial management

The EBA Multi-Donor Trust Fund (MDTF) is managed in accordance with standard World Bank procedures for Trust Funds, including fees and staff salaries. DFID’s £475,000 contribution for this financial year was disbursed in August 2017 and as further £475,000 is due to be disbursed in December 2017.. The World Bank provided an unaudited trust funds financial report and a budget breakdown prior to the request for disbursement. Although the Trust Fund is not subject to independent audit, it is part of the single audit that the World Bank undertakes for all of its core Trust Fund Operations. As of the 30 of June 2017 the EBA (MDTF) and Parallel Trust Fund had a combined balance of 2,405,935.5USD available for allocation.

Date of last narrative financial report	n/a
Date of last audited annual statement	n/a

E: RISK

Note, the DFID risk Framework introduced in 2015-16 against which DFID supported projects are now assessed.

Overall risk rating: Moderate

The Business Case identified two types of risk: (i) the purpose and methodology of EBA is not well understood; and (ii) the programme cannot achieve buy-in among policymakers and key users. The risks, mitigation strategies and updates on any progress made and changes in context are provided in the table below.

Overview of programme risk

Risk identified in business case	Risk rating	How will risk be managed?	Annual Review Update
Methodology
Confusion over or misinterpretation of what the indicators do and don’t measure.	Moderate	EBA to continually communicate the range and limits of the data.	The EBA team has communicated the range and limits of the data through the 2015, 2016 and 2017 EBA reports, the EBA website and a large number of engagement/dissemination meetings (Annex 2).
The programme narrowly focuses on indicators that measure the status of laws and regulations in the books and does not reflect the experience of businesses in reality.	Moderate	EBA is expanding its indicator set to capture the practice and efficiency of processes to comply with laws and regulations.	The EBA 2017 Report presented indicators that capture practice-related dimensions for 5 EBA topic areas - seed, fertilizer, agricultural machinery, markets and transport – and to overlay them across legal indicators. These indicators will be used to further expand this area in upcoming iterations of EBA.
Significant variations between the regulatory frameworks for different agricultural commodities limit the comparability of EBA indicators.	Minor	Indicators will use a standardised case study to allow comparison across different countries.	A standardised case assumption methodology has been developed and applied during the last 4 years.
Indicators produced are not considered to be relevant and/or rigorous.	Moderate	A broad group of experts and stakeholders (including researchers and target users) have been consulted and their advice is informing indicator selection and subsequent refinements.	Data points used to build indicators are backed up by documented laws and regulations, and verified by target country governments and World Bank country offices. A growing circle of technical and operational experts are being consulted to ensure the relevance of the indicators and to vet them, and a Technical Advisory Committee formed in 2015 has provided guidance on the approach for strengthening them. Engagement has been held and continues to be planned with stakeholders, such as government representatives, policy sector players, CSOs and the research community, to collect and incorporate relevant feedback.
Countries selected are not aligned to programme objectives.	Minor	The World Bank will consult donors on the country selection process. A geographically diverse set of countries at different stages of agricultural growth will be selected to allow for sub-comparisons.	Countries were selected in consultation with donors and World Bank agricultural operations experts. Geographical, income level and agricultural transformation diversity, as well as relevance to programme objectives, was considered and ensured for country selection. It is noted however that these are not yet aligned with DFID priority countries.
Insufficient attention given to gender and environmental sustainability	Minor	Integration across relevant topic areas such as land, financial access and water	Gender and environmental sustainability were integrated into the 2016 report, and were further expanded in the 2017 report.
Take-up and Buy-In
Lack of government buy-in	Moderate	Governments of countries covered by the EBA are being targeted for dissemination and consultation. Proper interpretation and understanding of the evidence provided by EBA indicators will be fostered through dissemination events and technical workshops.	The EBA team has worked with World Bank country office specialists to present the report and hold discussions with governments and other stakeholders in a number of countries, which has included in the last year Tanzania, Uganda, Rwanda, Malawi, Zambia, Zimbabwe, Sudan, Nicaragua and Honduras. Engagement has generated substantial interest in using EBA data for policy planning. The EBA team is planning to expand and reinforce outreach in order to engage governments further in the use of EBA indicators.
Programme activities do not lead to regulatory changes.	Moderate	EBA team will work closely with operational colleagues in the World Bank, and in other institutions, to translate findings into policy dialogue and actions that trigger changes in the regulatory environment related to the project’s interventions.	A dissemination and operationalization strategy are being developed to follow up the third year report, and to build on 2016 developments in this area. This includes meetings/workshops in at least 3 regions and presenting the EBA at several key conferences.
Pressure over regulatory indicators and country rankings lead to a pushback on the EBA.	Moderate	EBA should carefully consider pros and cons before proceeding with country rankings.	In EBA’s communication and engagement efforts, it has been clarified that for the time being rankings are not being considered as a mechanism. However in the 2017 report countries were ranked against the key thematic areas although not against each other.
Unintended consequences	Moderate	The programme will devise a way to model the expected policy responses from the indicators to ensure against negative outcomes.	Research on the regulatory environment and links to agriculture transformation should help inform the sequencing and impacts of these types of indicators.
Governments narrowly target their reform efforts to trigger EBA indicators only.	Moderate	Besides broadening EBA indicators to measure practice-related elements of the regulatory framework, the team will work with other World Bank units to support their programs providing technical assistance to client governments that go beyond what is measured by the indicators. The team will also devise a way to model the expected policy responses from the indicators to ensure against this risks of narrow reforms. Finally, the team will continue to clarify and emphasize that business regulation reforms are one element of a strategy aimed at improving competitiveness and establishing a solid foundation for sustainable economic growth in the context of dissemination as well as of interactions with governments, other institutions, partners and stakeholders in general.	Increased engagement and integration with the Bank’s policy operations will encourage a broad reform discussion as opposed to narrow indicator focused reforms.
The process of agreeing to policy changes is not sufficiently inclusive and consultative at country level.	Moderate	The programme is paying attention to not only encouraging policy reforms, but how they have been achieved, particularly in terms of including key stakeholders in the discussions that EBA indicators generate.	The EBA team is doing more to engage the private sector, civil society and academia in country and have participated or hosted in a number of national and regional events.
Programme is not sufficiently proactive to engage stakeholders.	Minor	Specific actions including a strategic outreach plan should be a central component of the programme.	A stakeholder engagement plan continues to me used, which includes dialogue via meetings and conferences with a range of stakeholders. A new CSO working group has been established and technical consultations commenced. (further details in Annex 2)
The programme is not financially sustainable over the long term	Major	The EBA team needs to fundraise money from sources other than donors. This should include country governments financing data collection for the indicator in their own country. It is appreciated that this takes time but needs to be part of their strategy from early on. Further, the team should explore if there is interest in the private sector or with CSOs to finance the EBA, possibly through a ‘black box’ fund.	The EBA team is currently liaising with a number of country governments regarding financing the EBA. Countries, which so far have not been included but would like to be featured in the EBA are asked to finance 2/3 of the costs for data collection, with 1/3 coming from the multi-donor trust fund. Further, there are ongoing talks with the AfDB how they can contribute, as they are considering a roll-out of the EBA across all African countries.

Outstanding actions from risk assessment
The majority of risks to the project’s ability to deliver results remain relevant, as the project goes into Phase II. However, a number of risks have had their risk rating downgraded to minor. “The programme is not financially sustainable over the long-term” has been added to risks, which is seen as major and will need to be closely monitored during Phase II.

Regarding main risks that were raised in last year’s annual review, i.e. the level of uptake of EBA indicators and their ability to bring about reform, the EBA team mitigated the risk with their outreach and dissemination activities in the past year, the direct and continuous engagement with government, as well as improving collaboration with World Bank colleagues, mainstreaming the EBA findings in other World Bank activities.
Therefore, while these risks still remain, their risk level might reduce in the future due to ongoing and successful mitigation activities.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe
The EBA team have delivered against their milestones. These are slightly out of sync with the original business case owing to a delay in starting operations in the first year. The new project cycle means reports will be finalised by the end of the calendar year, rather than in the summer. The third report was therefore only slightly delayed and became publicly available in January 2017. In Phase II, reports will only be published biannually, reducing the pressure on the team to meet publication deadlines whilst also trying to disseminate the previous report. This should allow increased emphasis on uptake and therefore a better contribution to the outcomes of the project.

Performance of partnership (s)
The EBA team have remained responsive to the donors in the multi-donor trust fund. They have kept donors up to date on progress and informed the group on proposed changes as well as the process to make decisions. The multi-donor trust fund met face-to-face once in year 3 in June 2016 in Rome. Other MDTF meetings have been via teleconferences. There has also been regular email correspondence allowing for more real time communication between the EBA team and the donor group and the EBA team presented to DFID staff during the spring of 2016.
Consultation with the Bill and Melinda Gates Foundation (BMGF), another key donor to EBA in Phase 2, as part of this Annual Review, showed a strong working partnership and communications between DFID and BMGF over an extended period of time in support of the EBA.

Asset monitoring and control

Not applicable
G: CONDITIONALITY

Update on partnership principles (if relevant)

Not applicable, as the programme is not funding governments.
It was therefore not deemed relevant to use the partnership principles for management and monitoring when the programme was approved

H: MONITORING & EVALUATION

Evidence and evaluation

The cost extension for Phase II has earmarked £ 100,000 to finance an independent mid-term evaluation of the EBA. This will take place in November 2017 with the final report expected to be available in February 2018.

Monitoring progress throughout the review period

The EBA monitoring and evaluation follows World Bank standards and requirements for project implementation. Two key steps highlight this process:

Concept note approval – at the beginning of each year of project implementation, a concept note and work programme for the year is developed, reviewed and approved to determine deliverables and ensure alignment to project goals.

Decision making – review and approval of the project deliverables, in this case the yearly report, ensuring that the proposed goals are met.

For this annual review, views were gathered from the EBA team and additional World Bank colleagues, and other EBA donors. It was noted that other donors look up to DFID in terms of the rigour and quality of the monitoring and reviews of the EBA programme which establish notably high standards.

Annex 1: Acronyms and Abbreviations

AfDB	African Development Bank
AGRA	Alliance for a Green Revolution in Africa
AGRF	Africa Green Revolution Forum
BBA	Benchmarking the Business of Agriculture
BMGF	Bill and Melinda Gates Foundation
CAADP	Comprehensive African Agricultural Development Programme
CSO	Civil Society Organisation
CSPF	Civil Society Policy Forum
DANIDA	Danish International Development Agency
DBA	Doing Business in Agriculture
EBA	Enabling the Business of Agriculture
FAQ	Frequently Asked Questions
IFPRI	International Food Policy Research Institute
IMF	International Monetary Fund
MDTF	Multi-Donor Trust Fund
MM	Market Metrics
SRO	(DFID) Senior Responsible Owner
VfM	Value for Money
WBG	World Bank Group
WG	Working Group

Annex 2-Outreach and dissemination events in 2017

Enabling the business of Agriculture (EBA) events 2017
Month	Title of Event	Where	Audience
Jan-17	UK Veterinary Medicines Directorate: Presentation to staff members of the UK VMD on EBA's livestock topic	Surrey, UK	Public

Feb-17	Global Donor Platform for Rural Development: EBA presentation in a panel session on “What is new in Support of Rural Transformation”	Brussels	Public, development agencies
	Argus FMB Africa Fertilizer Conference	Capetown	Regional, private, public, academia
Mar-17	18th Annual World Bank Conference on Land and Poverty: EBA presentation	Washington, DC	Global, public, private, CSOs, academia
	The recent launch of the EBA 2017 Report marks the beginning of our engagement with the Government of Tanzania on EBA. Given the characteristics and timing of policy processes in Tanzania, last year we spent time and effort understanding how to effectively present EBA findings and tailor our messages to elicit a positive response from Government counterparts. We held discussions with a number of CSOs, private sector representatives and international development agencies, and consulted carefully with our Country Office in Dar. Last week we engaged for the first time directly with the Government on EBA, in a successful event we jointly held at the Agricultural Policy Conference and a technical workshop. The outcome was very positive in terms of gaining the Ministry of Agriculture’s interest and intention to begin a dialogue around EBA indicators and their use for policy planning. We had a very successful launch of the EBA 2017 Report at the Agricultural Policy Conference in Dar, where the report was a highlight and really captured the attention of an audience of approximately 250 participants. The launch was enhanced with the participation and remarks of the representative of the Minister of Agriculture and WB Program Leader Gayle Martin, along with comments from the Executive Secretary of ANSAF (Agricultural Non-State Actors Forum) and our Senior Agricultural Specialist Sarah Simons. There was a lot of excitement and interest stirred up around the report, which we all agreed will lead to interesting upcoming dialogue and opportunities. This was preceded by a workshop focused on the 2017 report findings for Tanzania, in which some 30 representatives from the public sector and different international and regional development agencies participated. We spent a whole morning looking at and discussing the data, which was very well received. The main recommendation put forward – in different shapes and forms – was the importance of bringing in other metrics, contextual information and country-specific considerations to enhance the value of our indicator set and its implications for the country. We also held a meeting with 4 CSOs – one of which was affiliated with the Oakland Institute’s campaign against EBA (Tanzanian Organic Agriculture Movement) – to discuss EBA’s work. TOAM was very set in its thinking and didn’t contribute to a constructive dialogue, although the technical weaknesses of the person present was apparent, and Sarah and Farbod were able to spend some extra time with him exchanging ideas and hopefully/apparently moderating his views. One of the CSOs present, the Aga Khan, seemed particularly interesting for ongoing engagement and work	Tanzania	Regional, country, public, private, CSOs, international and regional development agencies
	The African Seed Trade Association Annual Congress: EBA presentation in the session on Seed market in Africa: challenges and prospects	Senegal	Regional, private, public
	Annual Bank's Water Week (organized by Water GP): During the Water Week organized by the Water GP, EBA EBA Water team worked closely with the Water in Agriculture GSG and presented at the session named "Of Datasets and Water Tenure: Global Approaches to Supporting Water Management with Law"	Maryland, VA	WBG staff
	USAID Market Systems Global Learning and Evidence Exchange: USAID seminar for regional partners	Bangkok	Regional, international development agencies, private
	EBA Learning event during Ag Forum Learning Week: "Using EBA indicators for regulatory diagnostics and reform": Presentation to WBG operation staff and topic-specific break-out sessions to discuss EBA indicators in WBG operational work	Washington, DC	WBG staff
	Key meetings were held with the Minister of Agriculture, the Minister of State for Agriculture, and the Permanent Secretary of the Ministry of Agriculture, which included discussion on the inclusion of EBA measurements for regulatory planning. The objective of the discussion was to engage with senior officials within the Ministry of Agriculture and other relevant Ministries around the development of a policy vision and strategy which would inform the new National Agricultural Policy. The specific objectives were to understand and clarify expectations for World Bank support in the development of the new Agriculture Policy, to explore lessons learned generated by relevant National Agricultural Policy processes, and to agree on a road map and timetable for World Bank inputs over the next twelve months. Based on these discussions, the EBA team will be providing tailored documentation on key data and findings that can be used to inform reform opportunities and priorities in the country	Rwanda	Country, public
May-17	Farbod Youssefi joined the Agriculture Workshop organized by Turkey’s Ministry of Agriculture and Livestock, to present EBA to an audience of over 200 participants from several key Government agencies (Ministry of Development, Ministry of Commerce, Ministry of Finance, Central Bank, etc.) and numerous stakeholders in Turkey’s agribusiness sector. EBA was one of many pieces presented at the workshop, but called the attention of participants to key issues related to the legislative environment affecting producer organizations, agricultural trade and other marketing-related issues. Beyond the outcome of the broader engagement and focus of this workshop, the Ministry of Agriculture’s Director General expressed his interest in EBA findings in a debriefing meeting following the workshop, highlighting the accuracy and value of EBA results for key areas the Government is interested in improving. The EBA team will remain attentive to opportunities to support any prospective technical assistance work requested by the Government to be led by GFADR	Turkey	Country, public, private
	The EBA 2017 Report was launched in Lusaka on May 19, at a National Seminar organized by the Ag GP and the Zambia CMU. The event was chaired by Mr. Chance Kabaghe, President of Indaba Agricultural Policy Research Institute (IAPRI), with the participation of the Vice-President of the World Bank for Sub-Saharan Africa Makhtar Diop, Minister of Agriculture Dora Siliya, Minister of Finance Felix Mutati and Minister of Commerce, Trade and Industry Margaret Mhango Mwanakatwe. Farbod Youssefi and Alva Kretschmer presented the report and some of its findings. Along with the Permanent Secretary of Ministry of Commerce, Trade and Industry Kayula Siame, the President of the Zambia National Farmers Union Jervis Zimba, and the CEO of the incubator AgBIT Brian Mwanambo presented a series of insights, followed by comments and questions raised by members of the audience. Ms. Siame furthermore used the occasion to introduce the recently agreed Zambia Agribusiness and Trade Project to the audience. The event was attended by 120 participants from a range of stakeholder groups, including government officers, private sector, farmer organizations and trade associations, development agencies. The launch was preceded by a technical workshop held with a group of 30 key participants from both the public and the private sectors, in which the report was presented and several topic areas discussed. The session was opened with a series of remarks from Permanent Secretary Kayula Siame, who highlighted the value of the report for policy analyses and actions in the sector. Farbod Youssefi and Alva Kretschmer presented the report and led the group through a few of the topics it covered: seed, fertilizer, markets and finance. This led to a constructive discussion with participants, which included representatives from the Ministry of Agriculture, the Ministry of Commerce, Trade and Industry, the Ministry of Water Development, Sanitation and Environmental Protection, the Zambia Trade Revenue, the Zambia Seed Trade Association, Seed Co., Zambian Fertilizers Ltd., AFGRI Corporation, the First National Bank of Zambia, Zambia Business in Development, Kakanga Food Supplies and the Indaba Agricultural Policy Research Institute (IAPRI).	Zambia	Country, public, private
	The EBA 2017 Report was presented at a day-long workshop in Harare, which gathered around 80 key players from different stakeholder groups within Zimbabwe’s agribusiness sector. Beyond the broader findings of the report on the country’s regulatory environment for agriculture, sessions were held on fertilizer, water, finance, markets and land, with valuable contributions from national experts in each of the fields. The audience remained attentive and engaged throughout the event, and the discussion was participatory and productive. A Zimbabwe Country Report, based on EBA findings for the country, will be produced.	Zimbabwe	Country, public
	Africa Finance and Agribusiness Conference: EBA presented at the Pleminary session on the Enabling the business of agriculture	Egypt	Regional, country, public, international development agencies
	The EBA 2017 Report was launched along with another report that the Ag GP produced on Agriculture Expenditure for Sudan, organized by CMU. The Minister of Agriculture for Sudan, along with official representatives from the Arab Authority for Agricultural Investment & Development, the African Development Bank, the Food and Agriculture Organization (FAO) and the national private sector, offered remarks highlighting the value of EBA for Sudan’s National Agricultural Investment Plan. Besides the interest generated, EBA was highlighted as a tool to be used to inform policy planning as the Government aims to invigorate the agribusiness sector. Based on the discussions held, a synthesis report will be developed that will offer a readily usable document that can be used by CMU staff to advance policy discussions and operations. Additionally, the CMU will use EBA finance indicators to set goals and monitor progress in the Results Framework for the Sudan Multi-Partner Fund, focusing on a financial inclusion survey leading to a financial inclusion strategy, the development of regulations for agent banking and the development of regulations for warehouse receipts.	Sudan	Regional, private, international and regional development agencies, CSOs
Jun-17	EBA involved in preparation of Laos PDR Agriculture Commercialization Project (key inputs provided into the prpearation of the project appraisal document (PAD) on: Seed, Fertilizer, Machinery, Markets	Laos	WBG staff

	5th European Research Conference on Microfinance: EBA presentation of the research paper, titled “How can regulations promote financial inclusion?” The paper presented uses data from the Finance indicators of the EBA project, and finds strong and positive association between regulatory environment and financial inclusion. Countries that have adopted good regulatory practices in the areas measured by EBA Finance indicators are showing better financial inclusion scenario, indicated by higher probability of individuals to open an account and save at a formal financial institution.	Portsmouth, UK	Academia
	ICABR 2017 Conference: EBA presentation on Rethinking Agriculture Transformation through Business Regulation and on the Business Environment for the Bioeconomy in Africa	Berkeley, USA	Public, private, academia
	At the request from the Ministry of Foreign Affairs, the Netherlands, EBA delivered presentation and participated in the discussions on the findings of the Enabling the Business of Agriculture (EBA) 2017 Report. Specifically, two events were held. The first one - the general presentation of the EBA 2017 report followed by a more focused discussion on 3 countries: Ethiopia, Uganda and Vietnam. Representatives from the public sector, knowledge institutions, civil society and private sector participated in the event. The second event consisted of a technical meeting with policy officers from Ministries of Economic Affairs and Foreign Affairs and new Agricultural Counsellors.	Netherlands	Public, private, academia, CSOs
	EBA team met with the Secretary of State of the Ministry of Agriculture, H.E. Ty Sokhun, and his team for discussions on Cambodia’s agribusiness enabling environment, the following points were raised: • The Ministry of Agriculture, Forestry and Fisheries (MAFF) established on August 10, 2016, a “Taskforce for monitoring and addressing challenges associated with Agricultural Production & Access to Markets”, which will be given the mandate to use the EBA 2017 Report to analyze and propose areas of improvement within Cambodia’s enabling environment for agribusiness. The Secretary of State requested that EBA team reviews and provides input for the TOR of the Taskforce to reflect the work it will do in this area. In response to the Secretary of State’s request, the team will also meet and worke with the Taskforce to examine areas of emphasis based on EBA findings on Cambodia and other elements to be jointly analyzed. • The Secretary of State would like EBA and related agribusiness enabling environment issues to be included in the new agriculture project Concept Note currently being prepared. He has requested that the team reviews and helps integrate the EBA’s finding on Cambodia. • Dr. Sokhun also asked Mudita Chamroeun to present to Country Manager Inguna Dobraja his request that the work around EBA be included in the World Bank support projects as well as request Farbod to help support integration of EBA finding into the on-going preparation of the agriculture master development plan.	Cambodia	Country, public
	EBA team met with the Korea Rural Economic Institute (KREI) President, Dr. Chang-Gil Kim, and Dr. Dae Seob Lee, focusing primarily on EBA’s developments and findings during its first phase and plans for the next one. Farbod then traveled to Naju to present and discuss results of the EBA 2017 Report at a seminar organized at the Institute’s headquarters. The report was received with much interest and a degree of eagerness to participate in its development. Much of the discussion focused on the relevance of EBA findings for small-scale producers and traders. KREI has been mandated by the Ministry of Agriculture to become familiar with EBA findings and its plans for future development.	Korea	Country, public
	EBA team met with key CSOs in the country to present and discuss the work presented in the EBA 2017 Report. Feedback was collected on the relevance and use of EBA indicators nationally, and a few of the participating entities identified for ongoing engagement. EBA team worked with Country Office colleagues to prepare a presentation of Enabling the Business of Agriculture for an upcoming USAID Market Systems Workshop. Finally, EBA team heald meetings with two key private sector actors (from a local seed company and regional fertilizer supplier) to research issues in these areas, as they relate to EBA indicators, for the Closing the Potential-Performance Divide in Ugandan Agriculture project. Material on the engagement with CSOs will be published on the EBA website and used internally for the project’s ongoing work on refining its methodology. The EBA team will provide a write up for the Closing the Potential-Performance Divide in Ugandan Agriculture project, presenting key EBA findings and other relevant considerations for this analytical piece.	Uganda	Country, CSOs, private
	US-Africa Business Summit: EBA panel participation in the Agribusiness Panel: Dissecting the Enabling Environment for Agribusiness focusing on the role that business regulations play in helping or hindering business development on the continent. The focus of the presentation was specifically on seeds, fertilizers, water and the regulatory framework around those issues.	Washington, DC	Regional, public, private, international development agencies, academia

Jul-17	2017 EFITA WCCA Congress: EBA presentation on the role of ICT regulations in agribusiness and rural development	Montpellier, France	Academia, private, public
	Leibniz Institute of Agricultural Development in Transition Economies (IAMO) conference on "Eurasian Food Economy between Globalization and Geopolitics". The conference aims to provide a platform to discuss ongoing research and different strategies to ensure food security and intensify trade in the context of geopolitical tensions and divergent trade integration efforts.	Halle, Germany	Public, academia

Aug-17	EBA workshop to present EBA 2017 Report at an Agribusiness and Value-Chain Development Roundtable, with high officials and representatives from the Ministry of Agriculture, Food Industry and Melioration. EBA team presentated EBA indicators and findings for the country, and focused on the use of EBA as a tool that can inform policy making.	Kyrgyz Republic	Country, public, private, international development agencies
	EBA team held meetings with a number of key entities and Government representatives (Ministry of Agriculture and Rural Development, and Ministry of Planning and Investment) focused on policy analysis and development for Vietnam’s agribusiness sector. Given the keen interest in EBA findings, meetings raised a number of options and actions to utilize the evidence provided by EBA for policy work being done in the sector. The following agreements were made: • The Institute of Policy and Strategy for Agriculture and Rural Development (IPSARD), which shared information on the use of EBA for policy improvements to date, will be developing a policy brief based on the EBA findings, which will be brought to the attention of senior management of the Ministry of Agriculture and Rural Development (MARD). They will focus on describing changes since 2013, the start of the MARD’s Agricultural Restructuring Plan. IPSARD will also be included as a contributor for EBA’s data collection and will offer its support for data verification. • The Central Institute for Economic Management (CIEM) will aim to incorporate EBA findings into the work being done in the next few months on a number of decrees and resolutions that focus on improving the business environment in Vietnam. It will develop a proposal on the work it can do using EBA indicators to provide an analysis of the agribusiness enabling environment and input for targeted resolutions. The proposal will include areas which could be developed with the availability of additional resources. • Complementarity and synergy between the Provincial Competitiveness Index and Enabling the Business of Agriculture was discussed with the Legal Department of the Vietnam Chamber of Commerce and Industry (VCCI). Contingent on the necessary funding, a mini-report would be produced to jointly present the results of both initiatives to describe and analyze Vietnam’s agribusiness environment. Plans would also be made to hold joint workshops in 2-3 key agricultural provinces, to hold discussions on the provincial agribusiness environment and to generate awareness on areas that can be improved. Funds will need to be identified to cover these initiatives.	Vietnam	Country, public, academia
Sep-17	IWA-ASPIRE Asia Pacific Water Conference: EBA presentation on the Role of Law in Water Security: Conflicting Evidence from The Asia Pacific Region	Malaysia	Public, academia
Oct-17	EBA regional presentation at the Annual Food Security Conference to deliver EBA findings for Central Asia and highlight their relevance for private sector agribusiness investment in the region. The Conference – which gathers public and private sector leaders and policymakers, representatives of academia and civil society – aims to identify priorities for the agri-food sector in the region and produce actionable, evidence-based recommendations for the Eurasian Food Security Program.	Tajikistan	Regional, public, private, academia, international developmnet agencies
	Meeting with IFC colleagues at the Country Office there, on the use of EBA for sector analysis and planning.	Kazakhstan	IFC staff
	ICID Congress: EBA team gave a presentation entitled “Water law’s untapped potential for supporting water security in developing countries,” during a dedicated session on water security for growth and development. This presentation introduced the EBA Water dataset to a broader audience of potential end users, and explored several examples of how the EBA Water dataset can be used to create new models for cross-learning between countries. The presentation aimed to spread recognition among technical audiences of the importance of the legal framework for supporting the spread and implementation of the new water management practices and techniques being discussed at the Congress.	Mexico	Public, private, academia
	EBA team presented at an agribusiness development workshop organized around the EBA Report, with key stakeholders from Kenya’s agricultural sector, including government representatives, private sector players, civil society and the development community.	Kenya	Country, public, private, SCOs, development agencies
	EBA team met with Ethiopia’s Private Sector Development Task Force and with the Ethiopian Investment Commission, to present and discuss EBA 2017 Report findings	Ethiopia	Country, private
	IPPC Seminar on Plant Health and Trade Facilitation: EBA presentation on the background of the project, its country coverage, thematic coverage, and the methodology used	Rome	International development agencies
	EBA team be presented at an event organized by AGRA with Ministry of Agriculture, Livestock and Fisheries representatives, a handful of private sector organizations and development partners. Discussions were also be held with the Ministry of Industry, Trade and Investment	Tanzania	Country, public, private, development agencies

Appendix 3:

World Bank EBA reform status tracker (Sept 2017)

Country	Target indicator	Status
Vietnam	Variety registration	In process
Vietnam	Seed quality control	In process
Vietnam	Fertilizer quality control	To be confirmed
Vietnam	Fertilizer import/distribution	To be confirmed
Vietnam	Tractor import	Completed
Vietnam	Tractor operations	Completed
Vietnam	Tractor testing/standards	Completed
Vietnam	Warehouse receipt system	To be confirmed
Vietnam	Agent banking	To be confirmed
Vietnam	Agricultural trade	To be confirmed
Sudan	Variety registration	In process
Sudan	Seed quality control	In process
Sudan	Fertilizer registration	In process
Sudan	Fertilizer quality control	In process
Sudan	Fertilizer import/distribution	In process
Sudan	Warehouse receipt system	In process
Sudan	Agent banking	In process
Sudan	E-money	In process
Burundi	Variety registration	To be started
Burundi	Fertilizer import requirements	To be started
Burundi	Water resources management	To be started
Burundi	Plant protection framework	To be started
Burundi	Warehouse receipt system	To be started
Laos	Plant breeding	To be confirmed
Laos	Variety registration	To be confirmed
Laos	Seed quality control	To be confirmed
Laos	Fertilizer registration	To be confirmed
Laos	Fertilizer quality control	To be confirmed
Laos	Fertilizer import/distribution	To be confirmed
Laos	Tractor import	To be confirmed
Laos	Tractor operations	To be confirmed
Laos	Tractor testing/standards	To be confirmed
Laos	Plant protection framework	To be confirmed
Laos	Agricultural trade	To be confirmed
Laos	Efficiency export documents	To be confirmed
Cambodia	Variety registration	To be confirmed
Cambodia	Fertilizer registration	To be confirmed
Cambodia	Fertilizer quality control	To be confirmed
Cambodia	Fertilizer import/distribution	To be confirmed
Cambodia	Tractor operations	To be confirmed
Cambodia	Tractor testing/standards	To be confirmed
Cambodia	Plant protection framework	To be confirmed
Cambodia	Agricultural trade	To be confirmed
Cambodia	Cooperative farming	To be confirmed
Cambodia	Non-bank lending institutions	To be confirmed
Cambodia	Warehouse receipt system	To be confirmed
Cambodia	E-money	To be confirmed
Uganda	Seed quality control	To be confirmed
Uganda	Fertilizer import/distribution	To be confirmed
Uganda	Plant protection framework	To be confirmed
Uganda	Producer organizations	To be confirmed
Uganda	Branchless banking	To be confirmed
Rwanda	Variety registration	In process
Rwanda	Seed quality control	In process
Rwanda	pending	Potential
Malawi	Plant breeding	To be started
Malawi	Variety registration	To be started
Malawi	Efficiency variety registration	To be started
Malawi	Seed quality control	To be started
Malawi	Fertilizer registration	To be started
Malawi	Efficiency fertilizer registration	To be started
Malawi	Fertilizer quality control	To be started
Malawi	Fertilizer import/distribution	To be started
Malawi	Agricultural trade	To be started
Ethiopia	Plant breeding	In process
Ethiopia	Variety registration	In process
Ethiopia	Efficiency variety registration	In process
Ethiopia	Seed quality control	In process
Turkey	Agricultural trade	Pending agreement
Zambia	Agricultural trade	Pending agreement
Bangladesh	Individual water use for irrigation	Pending agreement
Zimbabwe	pending	Potential
Cote d’Ivoire	pending	Potential

Potential area of interest	Pending agreement	To be confirmed	To be started	In process	Completed

Potential area of interest
Interest has been expressed by the Government in acting on issues raised by EBA.
Pending agreement
There is an intention expressed and an opportunity identified for acting on issues raised by EBA, but the mechanism is not yet established or agreed on.
To be confirmed
There is a specific project or initiative in which the issues raised by EBA will be addressed/improved through policy reforms, but the specific indicator and/or goal is still to be confirmed.
To be started
There is a specific project or initiative to improve issues/reforms raised by EBA, and the specific indicators that will reflect the reform have been confirmed, but implementation of the project has not yet begun.
In process
The project/initiative that will be addressing/improving issues raised by EBA is in course.
Completed
The issues raised by EBA have been addressed in a policy reform, as reflected in EBA indicators scores.