#### ADDENDUM TO BUSINESS CASE INCLUDING FOR BRIDGE FUNDING AND SCALE-UP COST EXTENSIONS
SUMMARY INFORMATION
Project Name	Customs Development and Trade Facilitation
Country or region targeted	South Sudan
Type of cost extension (if applicable)	Bridge Funding
Original project budget	£7,700,000
Original project start and end dates	August 2012 to April 2016
Cost extension value (if applicable)	£2,000,000
New project end date (if applicable)	December 2016
Business Case Quest Document No.	3769118

INFORMATION
What is the project’s purpose?
The programme’s purpose is effective and transparent customs institutions to facilitate trade through increased ease of trading across borders, reduced transport time and increased volumes.
What is the objective of the cost extension or other changes?
The Customs Development and Trade Facilitation programme (CDTF) was designed to support customs reform (including fast tracking the movement of humanitarian goods); rationalisation of non-tariff barriers; capacity building of the Bureau of Standards; scoping effective customs and trade policy through private and civil society organisations and support to the East African Community (EAC) accession process. Given the looming economic crisis and worsening humanitarian situation, and the need for efficient humanitarian aid delivery and increased non-oil revenue, we judge it important to maintain critical investment in trade and customs. / The extension of support to the CTDF programme through additional funding of £2 million will help maintain and consolidate gains on raising non-oil revenues, reducing non-tariff barriers, and efficient clearance of humanitarian cargo. We propose to extend those project activities that can achieve this by: a) enhancing capacity of the Customs Department to reduce non-tariff barriers and other barriers to trade and investment; b) maintaining gains made on the efficient clearance of cargo; c) training, support on legislation, and procurement of equipment to help with the identification of sub-standard goods. The extension will also allow the UK to protect key institutional relationships with the Customs Department, Bureau of Standards and the Ministry of Finance and Economic Planning. While we no longer propose to directly support South Sudan’s EAC accession process, extending the project gives Trade Mark East Africa (TMEA) scope to draw on regional resources instead. This will keep open a channel of influence on reforms and anti-corruption measures. / These efforts are imperative for South Sudan as the country is struggling to cope with a complex humanitarian and economic crisis that continues to be heightened by the ongoing conflict. Low volumes of trade, little non-oil revenue collection, high costs of imports and exports could exacerbate the economic crisis and increase humanitarian need.
What is the additional and total support the UK will provide?
DFID South Sudan’s current contribution to the CDTF programme is £7.7 million (from August 2012 to mid-April 2016). The additional funding of £2 million will bring the total costs to £9.7 million.
What are the expected results?
DFID’s continued support will help to: further strengthen the customs service and associated trade related institutions; deepen business processes and procedures of the Customs Department to increase its capability to generate non-oil revenues and fast-track the movement of humanitarian goods; increase the number of cross border traders, including women, and the volume of trade; reduce incidences of harmful food and non-food imports and enhance the ease of doing business and trade. / Project outputs for the cost extension (as derived from the draft TMEA SS Results Framework) are detailed below. These outputs are still tentative and will be revisited to test realism and ambition once this addendum has been approved. The approval will provide the go-ahead for DFID to work with TMEA to revise the 2016/17 milestone targets for the continuation phase. This revision will be finalised in early April 2016 in close consultation with the Statistics Adviser. / Outputs Indicator Current status (as at December 2015) Draft 2016/17 target / Increased ease of trading across borders Changes in ranking on Trading Across Borders (Doing Business IFC) / % of customs revenue collected at the point of entry 187 / $4.4m 175 / US$252.4[1] / Effective trade systems, agencies and procedures Reduction in average import/export customs clearance (including inspections) time. / Reduced time to clear humanitarian cargo (in at least one direction) at Nimule border 2 / 1.5 1 day / 1 day / Establishment of an effective regional and national framework for managing trading standards across EAC No. of High Priority NTBs eliminated (disaggregated by country) against the total number of NTBs still reported as outstanding. 29 NTBS identified through mapping exercise 33% (10NTBs) / Effective regional and national framework for managing trading standards across the EAC Number of additional tests performed by National Bureaux of Standards (Disaggregated by country ) / Reduction in the average time to test and issue relevant certificates for selected goods for intra-regional export by country / Upgraded new laboratories operational / Number of Bureau of Standard staff trained across SQMT spectrum (Standards development, Quality assurance, Metrology and Testing) and to conduct testing using the new equipment (Disaggregated by country) No data available in 2015 / 9 / 1 one-stop testing facility established at Nimule border to house testing equipment / No staff trained 220 / 3 / 3 upgraded labs, and new equipment in place / 30 trained
What is the approach to implementation?
The Customs Development and Trade Facilitation programme is implemented by TMEA. A National Oversight Committee provides strategic oversight. It is well attended by all programme beneficiary institutions and is chaired by the Under Secretary, Ministry of Finance and Economic Planning. TMEA works through a number of downstream partners, such as technical assistance providers Crown Agents/Adam Smith International, private sector and civil society organisations. DFID oversight is managed through a Senior Responsible Owner with support from the Senior Programme Manager.
Describe any key changes to the original business case?
TMEA are revising their own results framework by the end of March 2016. Much of the content is already agreed between DFID and TMEA, and DFID will use this to populate a project-specific logframe by early April 2016. This is also a recommendation from the annual review carried out in October 2015. The programme risk log will also be reviewed to reflect the high risks posed to programme delivery and impact of the worsening economic context. Mitigating actions for the ongoing risks of corruption and lack of political will to embed customs reform, tackle corruption and build capacity will be strengthened. / Compliance with the Gender Equality Act: This programme can have a significant positive effect on gender equality, specifically by improving the economic choices of women in cross border trade. Transparent rules and regulations, especially in relation to tax (which can be low or zero for low volume goods) can encourage women to use official border crossings and abandon back routes where they can be subject to exploitation, violence, sexual harassment and unofficial taxation. The project extension, though technical assistance to customs, will maintain progress the project has already made on reducing the amount of time to clear humanitarian aid into South Sudan, with obvious benefits to the most vulnerable populations, including women and children. The impact on gender issues will be monitored through reviews and field visits.
[1] This is an example of a target that will likely be revised downwards in light of the current economic crisis.