Project Completion Review
Title: Land Tenure Support Programme
Final Programme: £4.74m DFID contribution.	Review Date:	August 2019
Programme Code: 201843	Start Date: October 2014	Final End Date: 30th June 2019

Summary of Programme Performance

Year	2014/5	2015/6	2016/7	2017/8	2018/9
Programme Score	C	C	B	A	B
Risk Rating	Medium	Medium	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-202843/documents
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-202843/documents

A. Summary and Overview (1-2 pages)

Description of programme and what it has achieved

The Land Tenure Support Programme (LTSP) was designed to strengthen the land administration system to support agriculture and other land-related investments. The programme supports the Government Tanzania to test different approaches to land titling in order to decrease the cost per title, and then roll out good practice across the country. This is the first step necessary to achieve the Government of Tanzania’s goal of more transparent and accountable land governance, together with cost effective rural land administration. The Government of Tanzania’s draft Review of National Land Policy (2017) indicates only 15% of Tanzanian land is titled, a major constraint to investment, cause of land conflict, and contributor to the high cost of doing business in Tanzania. The LTSP is a four year $15.2m programme supported by the Governments of the UK, Sweden, and Denmark. The programme operates in the Southern Agricultural Corridor, a fertile area of particularly high agricultural potential, where a number of DFID’s agri-business investments are concentrated.

The original programme design anticipated that LTSP would run for three years from October 2014 to October 2017. The implementation phase suffered some unexpected challenges including delays in procurement of the technical asssitance company, severe rainfall in the project area, and delays in fund disbursement both from development partners to bank of Tanzania and from Bank of Tanzania to project account . Subsequently, the programme was granted a no cost extension of one year. Despite these delays, the programme has achieved its overall objective: to develop the necessary tools, techniques, and processes for achieving systematic land registration of village land and complete the associated activities at low cost and with a highly participatory approach. Notable achievements include the following[1]:
[1] Data is up to date as of June 2019
- Adoption of the Mobile Application to Secure Tenure (MAST) technology which allows registration of CCRO claims through the use of hand-held tablets linked to Global Positioning System (GPS). Over the last three years, MAST has been consistently improved to allow data capture and support field operations for issuing Certificates of Customary Rights of Occupancy (CCROs). Another application, Transaction Utility for Secure Tenure (TRUST), has been developed to manage subsequent transactions.
- A significant reduction in the cost of each CCRO from $24 in 2016 to $10 in June 2019. The cost reduction is attributed to capacity building of local staff, use of para-surveyors[2], and application of MAST technology in mapping and data management.
  [2] These are trained members of the community who assist qualified land surveyors in surveying and demarcating farmlands, so as to reduce costs and make CCROs affordable.
- A total of 6,715 land holders in the programme area used the CCROs as collateral to secure a total of $609,000 in loans, mainly from NMB and CRDB banks. Some landholders are also using CCROs for bailing people from court and as collateral for informal financial transactions.
- The percentage of women accessing individual land title has significantly increased from 9% in baseline to 32%. In addition, 21% of women have accessed co-ownership.
- The number of women accessing individual land title has significantly increased above expectations, which can be attributed to effective public awareness campaigns.
- Adoption of Land Tenure Regularization (LTR) Manual which provides procedures on how to carry out village systematic adjudication and land registration for the issuance of CCROs.
- Government ownership of the programme continues to be high. Processes and procedures developed by LTSP are being adopted by the Ministry of Land, Housing, and Human Settlement Development (MLHHSD), including:
  - Amendment of laws to allow the use and application of digital technology for mapping and data collection;
  - Upgrading of MAST for use in urban planning;
  - Rolling out MAST in some villages in Morogoro using Ministry of Land budget
  - Use of electronic signatures for land registration, which reduced the total number of signatures required from the District Land Officer and Village Officer from ten to one, without any loss of integrity.
- A Dispute Resolution Manual for Village Councillors and Ward tribunal members has been prepared and the programme has delivered training to 473 ward tribunal members and 3,850 Village Land Council members.
- A total of 297,305 land parcel were adjudicated compare to original target of 310,000 parcels. This is the first time in Tanzania that the Ministry of Land has demarcated an entire district.

Key lessons from the lifetime of the programmes

Strong leadership, commitment and a political champion are essential for success. The programme was designed to be implemented through the MLHHSD, and this produced significant Government of Tanzania (GoT) buy-in. As a result, the GoT has expressed its willingness to roll it out nationwide.

Capacity building and institution strengthening is often slow, but perseverance is rewarded. Maintaining a close relationship with the Ministry means that there is openness to adopting improved practices very rapidly once their value is demonstrated.

Land title registration by itself is not enough. The land administration system must be in place to manage registration data and support post-registration transactions and the emergence of formal land markets. Additional support for access to finance, valuation, market, and transaction support for responsible investment, leasing mechanisms etc., are needed. There needs to be a clear regulatory structure in place, and strong, consistent public engagement on the incentives and added value for formal transactions, or informal transactions are likely to continue.

Consider appropriate use of fit-for purpose new technologies. New technologies, such as tablets, low-cost GPS, and drones, backed up by customised software like MAST and TRUST can reduce the costs of mapping and documenting land rights and promote greater transparency. However, there needs to be technical and financial capacity; an appropriate legal and policy framework for selection, operation, and access; capacity building for storing and processing the data generated; and awareness raising to overcome resistance from surveyors and others with vested interests who may feel threatened by their introduction. As the MLHHSD is currently understaffed by an estimated 74%, job losses due to the introduction of new digital technologies should not be a prominent issue.

Land administration is a politicised process, and purely technical interventions are insufficient. It is vital to ensure that appropriate people, skill sets, regulatory frameworks, institutions, and systems are in place to support the design and implementation of land administration programmes, and deal with any disputes that arise. Political economy analyses and appropriately informed responses from national to village level need to be embedded at the heart of programming.

Participation is crucial for effective land use planning, but behaviour does not change overnight. Public awareness campaigns can achieve change, for example in the perceptions of the ability and right of women and people with disabilities to hold land title. However, adequate time and resources need to be allocated to these activities. Engaging local civil society organisations (CSOs) with appropriate expertise and local knowledge can be highly effective.

The demand side also needs kickstarting. The programme needs to work with other stakeholders, including the private sector, to develop appropriate financial products and professional services (rental agreement, leasing, valuation, estate agency), which both build private sector capacity and deliver services needed to support formalised land mobility.

Table 1: Financial contribution
Founder	Budget ($)	Spend ($)	Balance
DFID	6,967,800	6,967,800	0.00
SIDA	5,898,631	4,321,574	1,577,057
DANIDA	3,112,090	2,314,747	797,343
GoT	896,860	318,382	578,478
TOTAL	15,260,424	13,535,148	2,374,399

The LTSP was implemented by Ministry of Land through a Programme Implementation Unit (PIU). The PIU was staffed by a combination of four people seconded from MLHSSD including a Programme Coordinator (PC), and four advisers from a Programme Management Company – Land Equity International. The land programme was estimated to cost $15.2m which include $6.9m (£4.72 m) from DFID, $5.8m from SIDA and $3.1m from DANIDA. In May 2019, due to delays submission of exit plan and budget by LTSP, DANIDA withhold part of their committed fund at the same time SIDA also released only USD 0.95m out of remaining funds amounting to USD 2.4 m. This decision has affected the completion of some indicators for this PCR and its likely to affect the overall sustainability of the programme achievements. Ministry of Land is in bilateral discussion with SIDA and DANIDA for possible release of the remaining fund at the same time the Ministry in the process of relocating their internal fund to complete some of the remaining activities.

Action going forward

- Formal recording of decisions regarding the asset disposal- Action PM.
- Inform the Ministry of Land/Finance on closure of the programme- Action DFID SRO to consult other Funders
DFID office wide lesson learn session-Action SRO.

## B: DETAILED OUTPUT SCORING (suggest 1 page per output)

Output Title	Improved land administration institutions at the district and village level
Output number per LF		1	Output Score	A
Impact weighting (%)?		40%	Impact weighting % revised since last AR?	N

*Indicators affected by suspended funding.
Indicator(s)	Milestones	Progress
1.1. Number of district land offices constructed	3	*Work in progress, completion of all 3 expected in September
1.2. Number of renovated and equipped village registers	160	130*.
1.3. Number of demarcated and surveyed village boundaries	121	127. The increase in number was due to emergence of unexpected subdivision of some villages and border disputes between villages and the wetland area that required resurveying.
1.4. Number of villages issued with Certificate of Village Land (CVL)	128	128
1.5 Number of Village Land Use Plan (VLUP) prepared for gazettement	127	120*
1.6. Average cost for preparing VLUP per village	$ 4,800	$ 3,500
1.7. % of community member participating in the awareness and education meeting for VLUP	Men: 52%	60%
	Women:34%	43%
1.8. % total of pastoralists residing in a village participating in awareness and education meetings for VLUP.	60%	41%

The overall scoring for this indicator is “A - outputs met expectations”. Although some milestones were not met, some achievements from 2018 have been sustained, and the milestones for women’s participation in VLUP meetings and costs of preparing VLUPs have been exceeded. The programme continues to have strong buy in from the MLHHSD at both National and District levels, which bodes well for the sustainability of the programme activities.

Key accomplishments
- The cost reduction for preparing VLUP (Output 1.6) that was achieved in 2018 was maintained this year, suggesting the sustainability of this cost reduction using the method developed by LTSP. Cost reductions were achieved through building the capacity of local Participatory Land Use Management (PLUM) teams to conduct VLUP rather than engaging expertise through the central National Land Use Planning Commission.
- LTSP has successfully changed the precedent in the MLHHSD from top-down planning to participatory planning. Participatory boundary surveying and land use planning has helped improve ownership of the plans within the villages and has built local capacity for effective planning.
- The milestone for % of women participating in VLUP awareness meetings (Output 1.7) has been exceeded. This can be attributed to the effective public awareness efforts by LTSP, and particularly the work of local CSOs engaged by the programme. LTSP successfully implemented its Gender Strategy and now disaggregates all routine data.
- An additional benefit has been improved participation of people with disabilities (PWD) in VLUP discussions. The programme engaged CSOs like the Tanzania League of the Blind, who were able to directly reach out to PWD in the project area. Once the CSOs had engaged in public awareness with the communities it was reported that more PWD participated in programme meetings and had an understanding of their legal rights and the importance of registering their land. This is key as PWD are often vulnerable to tenure insecurity on inherited land.

Milestones not met
- Funding delays have meant that the target of constructing three District Land Offices (DLOs) (Output 1.1) has not been met. The physical structures for the DLOs in all three districts have been completed, but much work still remains before staff can move in. It is expected that this will be completed by the end of September. Currently, staff are working in cramped conditions with insufficient capacity to hold the registries.
- Lack of funds has also prevented Output 1.2 on the number of renovated and equipped village land registries from being achieved. As well as often inadequate physical structures, there is a problem of poor-quality facilities to store the paper registries. The programme team budgeted to supply one metal cabinet per village to store the registry, but this is insufficient. It is expected that this work will be completed with local government funds. The intention was for villagers to provide the labour to construct or renovate the offices, but low commitment and pace of work have been identified as issues in some villages.
- The number of VLUP prepared for gazettement (Output 1.5) has not yet met the milestone, but activities are ongoing to achieve this. Border disputes slowed the issuing of CVLs, which had a knock-on effect on the number of VLUPs prepared in the programme timeframe.
- The target for % of pastoralists residing in the village participating in awareness and education meetings for VLUP (Output 1.8) has not been met. The programme team expressed that the 60% of the total number residing in the village was an ambitious target for a variety of reasons. Pastoralists were often fearful of identifying themselves in case of repercussions, for example having to pay financial contributions to the village or face criminal proceedings for grazing on farmland. It was found to be common for a pastoralist family to send one representative, which meant that attendance did not represent the full extent of pastoralists reached by LTSP. As their livelihoods are nomadic, often pastoralists were not in the village at the time of the meetings or were difficult to reach. Despite these explanations, the low participation of pastoralists is a concern. A continuing theme throughout the PCR field work was disputes between pastoralists and farmers, due to pastoralists moving across village boundaries or increasing herd sizes so the area of land set aside in the VLUP was no longer sufficient. There are questions as to whether drawing rigid land use boundaries can accommodate the nomadic nature of pastoral livelihoods.

Lessons identified this year linked to this output and recommendations for future programmes
Inter-village dialogue should be embedded into the VLUP process to ensure that sufficient land is set aside to accommodate pastoralists and other land uses that often cross boundaries, for example burial sites. It is unclear how mapping rigid village boundaries can accommodate those whose livelihoods involve regularly crossing village boundaries and unpredictably increasing and decreasing herd sizes. At national level, Government of Tanzania through a National Land Use Planning Commission is planning for National Land Use Plan to demarcate and assign appropriate use of land including agriculture and pastoralist.
More time is needed for public awareness activities. Programme and Ministry staff, villagers, and CSOs commented that the time taken for awareness activities was often rushed, meaning that plans and certificates were issued before they had been fully agreed. Public awareness also needs to include the importance of formal processes for post-registration transaction.

Output Title	CCRO issued in a participatory and cost-efficient manner in project districts.
Output number per LF		2	Output Score	B
Impact weighting (%)?		40%	Impact weighting % revised since last AR?	N

*Indicators affected by suspended funding
Indicator(s)	Milestones	Progress
2.1. Number of demarcated and adjudicated land parcel	310,000	297,302*
2.2. Number of CCROs registered and issued to Village Executive Officer (VEO)	218,125	165,204*
2.3. % of CCROs collected by landholders	80%	78%
2.4. Average cost of issuing CCROs in programme area	$9	$10
2.5. % CCRO
Women as an individual	26%	32%
Men as individual	41%	46%
Co-ownership with women	33%	21%

The overall scoring of this indicator is “B – outputs moderately did not meet expectations”. The progress for these indicators is mixed, but there have been continued improvements in some key areas.

Key accomplishments
- The average cost of issuing CCROs (Output 2.4) has been maintained at $10, down from the original figure of $24 at the start of the programme. Although this is $1 above the milestone, LTSP confirmed that any further cost reductions would jeopardise quality based on existing technologies and legal requirements. Cost reductions have been achieved by the use of MAST digital technology for surveying and registering CCROs and use of local para-surveyors. This has cut the number of technical staffs needed in the field and the time taken for surveying, while simultaneously increasing accuracy. The MLHHSD is now looking at adapting MAST for urban land titling.
- The milestone for the number of women accessing an individual CCRO (Output 2.5) has been exceeded. This can be attributed to the awareness raising efforts of the programme staff and the local CSOs, as discussed under Output 1. LTSP supported widows to access CCROs as they often face tenure insecurity after the death of the husband. The % of co-titled CCROs has not met the milestone, but this may be linked to the increase in women accessing sole land title.

Milestones not met
- Border disputes meant that some parcels could not be demarcated (Output 2.1). These border disputes were both between farmers and reserved wetland areas, and between farmers and farmers. Many of the conflicts have now been resolved, but the process for how those parcels will be demarcated is unclear now that the programme is ending.
- The % of CCROs collected by landholders (Output 2.3) is slightly below the milestone. A variety of explanations were given for this, including some people not living in the village where they owned land or temporarily staying at far way farms meaning that they were not aware that the CCRO had been issued, or were unable to collect it. The programme team used bulk SMSs to titleholders and their neighbours to increase collection rates.

Lessons identified this year linked to this output and recommendations for future programmes
- More research is needed on the impacts of issuing CCROs. Key questions include the impacts of CCROs on economic development; gendered land ownership; frequency of land transactions and the extent to which they are being formalised; patterns of land inheritance; changes to frequency and typology of land disputes.
- Future programming should manage expectations regarding the role of CCROs in unlocking access to finance. The expectation of using CCROs as collateral to access bank loans was repeatedly cited as one of the benefits of the programme, but further investigation revealed that there were no reports of people being able to access bank loans with just a CCRO.[3] For banks like NMB, the CCRO is a necessary document to demonstrate legal ownership to be used for collateral, but by itself the CCRO is insufficient. Applicants also need to prove that they have sufficient reliable income from their economic activities to be able to repay the loan. In the project area, the farmers who had successfully secured a loan were mainly contracted sugarcane out growers for Illovo Sugar, and this provided evidence of their guaranteed income. The loans that were issued were also using settlement land title as collateral, not farmland parcels, demonstrating the continued emphasis placed by banks on the role of physical structures to increase land value. The need to demonstrate reliable income to secure loans is potentially preferable as it may prevent people from taking out inappropriate loan packages and then lacking the financial capacity to repay. Future programmes could look to Ethiopia, where specific financial products linked to land title have been developed.
  [3] CCROs had, however, been used as collateral for informal loans and for providing bail at court.
- Handover planning should be embedded into programme activities from the start to ensure sustainability and a smooth transition of activities from the programme to MLHHSD. A large number of temporary staffs employed by the programme risk being let go when the programme ends. Clearer plans are needed for how the MLHHSD can retain temporary staff or streamline activities to enable continuation with fewer staff. For example, staff in the printing division could also compile the CCRO documents into the folders - currently there are separate teams conducting these roles.
- LTR programmes need to also consider how to manage formal land transaction processes. This was not adequately addressed from the start in LTSP. In the past year, LTSP began trialling the TRUST digital system for post-registration transactions, but it is not yet the accepted process for the DLOs or the MLHHSD. No formal transactions were registered in Malinyi or Ulanga Districts, although the continuation of informal transactions was highlighted at village level. The continuity of informal transactions increases the risk of land disputes in the short term and in the long term has potential to render existing CCROs out of date and obsolete, threatening the long-term impacts and relevance of LTSP. It is unclear whether the major factor encouraging informal land transactions is lack of awareness of the formal process, or unwillingness to pay associated transaction fees. While there are set costs for certain parts of the transaction process, it emerged that some villages were charging an additional 10% for transactions; there is a lack of transparency and clarity over official transaction fees.
- When various digital systems are introduced emphasis should be placed on their integration. The adoption of various digital tools and systems has been a major success of this programme with positive impacts on cost-effectiveness and accuracy. However, more attention on how the systems can be integrated is needed. Currently MAST and TRUST can be integrated, but TRUST and the World Bank’s Integrated Land Management Information System (ILMIS) are not yet integrated. The systems for registering urban and rural land title are also not yet integrated. Furth more, continued capacity building is importance to retain institutional knowledge of how to effectively use the tools.

Output Title	Policy and institutional framework strengthening
Output number per LF		3	Output Score	B
Impact weighting (%)?		20%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
3.1. Number of position paper for review of 5 land laws and policy brief with 25 areas for review of laws prepared.	3 policy briefs with 25 areas for review prepared	Prepared and submitted
3.2. Number of village council trained on land disputes mediation	160	129
3.3. Number of ward tribunals trained on land disputes mediation	66	66
3.4. District land and housing tribunals refurbished	1	1
3.5. Climate change issues incorporated into NLUP PLUM guidelines and piloted	Climate change in land use planning incorporated into PLUM guideline	PLUM guideline incorporated in the project area especially allocation of dedicated area for forests.
3.6. Guidelines on the roles and responsibilities of the investors, Government, and village prepared and approved	Guidelines informing all land investment in Tanzania	Study on Benefit Sharing Models under development, from which the guidelines will be developed.

Over the course of the programme this output has continually displayed weaker performance. This year results have improved in some areas while others are still progressing slowly. With this in mind, the output score is “B – outputs moderately did not meet expectations”.

Key accomplishments
- The multi-stakeholder group (MSG) has continued to advocate for legal and policy reform on issues raised during the implementation of the programme. Both the DPS and the National Commissioner for Lands reflected on the importance of the MSG for highlighting issues that might otherwise not have been considered, for example gender. The independence of the MSG was also cited as a major benefit, in comparison to the new National Land Advisory Committee (NLAC) which is a Presidential Commission.
- LTSP has completed the final draft of a Discussion Paper for the Review of the Legal Framework on Land Administration (Output 3.1). Three policy briefs will be extracted from this paper and will be used as input in the forthcoming review of land laws following approval of the revised National Land Policy.
- Climate change considerations in the form of identifying land to be preserved for forests is now part of the PLUM process (Output 3.5). This is encouraging villagers to think about environmental issues in land use planning, especially how to preserve forested areas alongside complimentary economic activities like honey production. These are recent changes and it is too early to make robust conclusions on impacts for forest preservation.
- Milestones for training of ward tribunal staff and refurbishment of district tribunals have been met (Output 3.4). LTSP played a major role in the inauguration of a new District Tribunal in Ulanga.

Milestones not met
- The number of village councils trained on land dispute mediation (Output 3.3) is significantly below the milestone. This is due to lack of funds, and there are plans to complete the remaining training with local government funds. Low capacity for dispute resolution at village level is of major concern for the sustainability of the programme impacts after closure. Poor dispute mediation at village level may place additional pressure on ward and district tribunals, may lead villagers to lose trust in CCROs, and may increase the volume of informal post-registration land transactions.
- Due to procurement delays, the guidelines on roles, responsibilities of investors, government and villagers (Output 3.6) has not yet been completed. LTSP has now procured a consultant who is in the process of preparing a study on Benefit Sharing Models from which the guidelines will be developed. It is unclear how this model will be used and by whom.

Lessons identified this year linked to this output and recommendations for future programmes
- Future programmes should consider addressing the coordination between ministries. Land issues often involve the MLHHSD as well as the Ministries of Natural Resources, Water, Energy, Forestry, Livestock, and PO-RALG. Major delays to this programme were caused by boundary disputes where villages bordered protected wetlands, which are under the authority of the Ministry of Natural Resources and Ministry of Water.
- Handover plans should be considered when setting up new institutions such as the MSG. The future of the MSG is currently unclear. While the benefits of having an independent advisory body are widely agreed, it is an expensive institution to maintain, and it is unclear whether its role will be taken over by the NLAC, or if it has added value to be maintained as a separate institution.
- Future programmes should ensure political economy analyses and institutional strengthening are embedded in programme activities from the start. LTSP was established to find technical solutions to speed up cost-effective land use planning and titling. Consequently, consideration of policy issues and institutional strengthening was an under-resourced and lower priority add-on. During the programme, socio-political and policy issues from local up to national level have been the most challenging and deepest threats to the successful and sustainable implementation of the programme. These include issues relating to pastoralist-farmer conflicts, ministry coordination, institutional strengthening, low capacity at village and district level, and insufficient processes for post-registration transactions. Embedding policy concerns, political economy analysis, and institutional strengthening at the heart of programming on land issues is a key lesson moving forwards.

## C: THEORY OF CHANGE AND PROGRESS AGAINST OUTCOMES (1-2 pages)

Overall assessment of whether the expected outcomes and contribution to target impact(s) were achieved

The overall impact is stated as “greater security of land tenure to land holders and users” which results from the outcome “more transparent and accountable land governance and effective land administration systems in Tanzania. Based on the existing indicators, the project achieved a “B” rating (outputs moderately did not meet expectation). Progress against many output indicators has been good, however some of the targets were directly affected by the decision of the funding partners to withhold some to the funds and the prolonged Government procurement system especially in the recruitment of consultants for scaling up plan. The outcome indicators are listed below

Outcome Indicator	Milestones	Progress
Disposal rate of backlog of cases filed in the DLHT’s before 2016/7 in project districts	70% target	60% (733 cases resolved)
National scale programme designed for implementation after the pilot programme	Scale Up Plan agreed, and funding secured	Scale Up Plan has been developed and approved by GoT though funding has not been secured
% of stakeholders in the land sector agreeing that Multi-Stakeholder Group (MSG) effectively promotes greater transparency and improved land governance	75%	82%

Progress at Outcome level

Clearance of backlog in Kilombero; The target was not fully achieved due to the prolonged procedure for appointing assessors for District Land and House Tribunal (DLHT) which led to late commencement tribunal activity. Land disputes resolution usually starts at the village level with mediation by the Village Land Council. Most cases that find their way to the DLHT originate from the Ward Tribunal, and prior to LTSP it could take up to 2 years to conclude due to low staff capacity. In 2016/17, 1040 cases were reported pending at Kilombero District Tribunal. In 2018/19, with programme support, Kilombero District Tribunal cleared 723 cases out of 1208 pending cases. During PCR field work, there was consensus that the adjudications and public awareness on land related issues has led to fewer cases being reported to ward and District tribunal.

Development of National Land Tenure scaling up plan: Ministry of Land through has successfully developed and approved the framework and methodology for scale up land tenure regularization in Tanzania. The Scale Up Plan is expected to run for a period of 10-15 years at a total cost $380m USD and the Ministry of Land is expected to raise the mentioned amount through a blended finance approach of Development Partners Contribution, GoT, a revolving fund and Private Sector Investment. On separate note, MLHHSD has submitted a $150m funding proposal to the World Bank for land sector support. Although the negotiation was at early stages, there is clear commitment that the Ministry of Land will use the loan to fund the scale up plan.

Transition of MSG role to NLAC: The MSG was established as a temporary stakeholder forum to drive land issues and act as an advocate for legal and policy issues raised by the programme ahead of the formation of the National Land Advisory Council[4] (NLAC). MSG was made up of five members, two from GoT, two from CSOs and the private sector, and one from an academic institution. The MSG was initially meant to operate at national level, but during implementation the suggestion was made to form local MSGs at district level with similar composition to track district-level policy issues and cascade them to national level. Although the role of the MSG has been largely taken overtaken by NLAC, the interviews with some stakeholders suggest the need to continue with the MSG structure as it was perceived to provide independent oversight.
[4] cross-sector body responsible for advising the Government (and the President directly) on all land matters

Summarise the programme’s theory of change and major changes to it in the past year (1/2 page)
The original LTSP theory of change[5] (Figure 1 below) provides an overall logic model of the intervention, depicting the linkages between resources (inputs), intervention activities (processes), intervention results (outputs or deliverables), intended outcomes (intervention objectives), overall impacts, and their relationships in terms of relevance, efficiency, effectiveness, and impact.
[5] https://devtracker.dfid.gov.uk/projects/GB-1-202843/documents/

Figure 1: Theory of change

The original theory of change required the programme to publish data on large farms. At the start of the programme in 2016, the GoT rolled out new laws which required all such data to be collected, verified, and published by the National Bureau of Statistics. On this basis, it was decided to remove the publication requirement and shift the emphasis to providing the right preconditions to foster further responsible investments.

Over the course of the programme it has become clear that some of the initial assumptions in the Theory of Change have not materialised as expected, or had unforeseen consequences:
- Disputes between pastoralists and farmers do not seem to have been solved by improved transparency and awareness of village land use planning, and in some cases conflicts have escalated.
- Farmers have not been able to access loans to invest in their land just by using CCRO as collateral – other documents to demonstrate ability to repay are also needed.
- Greater security of tenure through CCROs is not sustainable without effective post-registration transaction administration processes.

Explain major changes to the logframe in the past year (1/2 page)

No changes

## D: VALUE FOR MONEY (1-2 pages)

Assess VfM compared to the proposition in the Business Case, based on the past year and during the lifetime of the programme (1 page)

The overall VfM proposition for LTSP is to improve efficiency in the MLHHSD by reducing operating costs across their services that will lead to cost reductions of participatory land use planning and titling in line with international benchmarks. LTSP developed its VfM metrics during the inception phase and has implemented them through a number of measures.

Economy
LTSP localised the implementation systems at district level by moving the entire field team from Dar es Salaam to the field and this has automatically cut down the transportation and field living expenses.
- LTSP had a robust procurement system which uses a competitive tendering process.
- MLHHSD contribution to the programme. This involves 5 vehicles, paying salaries for three fulltime field managers, and paying for a programme field office in Malinyi.

## Efficiency
LTSP became the first LTR project in Tanzania to introduce adjudication of land parcel by using handheld GPS, satellite imagery, and finally by using MAST. From February 2018, LTSP adopted MAST technology; this has significantly improved output per day from 100 to 500 CCRO per day per team of three people. At the same time, there has been continued and substantial improvement in cost efficiency from a $25 baseline to $15 in Year 1 and currently it is $10. In Sub Saharan Africa- Rwanda has achieved the lowest cost per parcel in recent years, at less than $7 per parcel in rural areas and less than $6 per parcel in urban areas. This suggests that there is potential for Tanzania to lower costs further.
LTSP is scaling up the use of locally trained personnel as para-surveyors and recorders. These have replaced the significant number of qualified land officers that would have been recruited by the programme at much higher cost.
PIU contracted the National Land Use Planning Commission to train respective district teams on how to conduct VLUP. District teams are now working independently and LTSP estimates that the cost of doing a VLUP has decreased from Tsh 13m to Tsh 7.5m[6].
[6] The annual review team could not verify this figure.
## Effectiveness
- The programme has adjudicated 297,305 land parcels and issuance of titles to land holders is in progress. The original target ws 300,000 parcels.
- Based on LTSP achievements, the Ministry of land is negotiating $150 million from WB to fund a scale up of land tenure regularisation to address both urban and rural land administration.
- A total of $609,045 was advanced as a loan from financial institutions mainly NMB and CRDB banks to 6,715 land holders in programme area by use of CCRO as collateral.

## Equity
- Involvement of disadvantaged groups: LTSP has a community outreach strategy which is used to conduct public awareness to women and disadvantaged groups, including pastoralists, youth, elderly and people with disabilities. The strategy includes mapping of stakeholders and their socio-economic and cultural context to understand who, when, and how to influence the beneficiaries for change in terms of land access and ownership. This has led the community to consider land access and ownership by different community groups.
- The number of women accessing an individual CCRO in programme areas has gone from 9% in baseline to 32%. In addition, 21% of women have accessed co-ownership.

LTSP engaged CSOs like the Tanzania League of the Blind, who were aware of PWD in the project areas a result more PWD participated in programme meetings and understood their legal rights and the importance of registering their land. This is key as PWD are often vulnerable to tenure insecurity on inherited land.
E: RISK (½ page)
Overview of programme risk (noting the rating from page 1) during the past year and over the life of the programme

The overall programme risk is moderate. This was largely associated with the capacity of the implementation team to deliver, rather than political economy of the land sector and or resistance from Government to implement the programme. The LTSP original risk matrix has 19 risks. The risk register was updated on quarterly basis and approved by during the Quarterly Management meetings which included the programme senior team, 5 permanent secretaries from land related ministries and a representative from Development Partners.

 In 2018, the programme recorded three additional risks:
- Delays in gaining the agreement on the village boundaries adjoining game control area;
- Backlog of the pre-MAST villages;
- Possibility of securing follow on funding for scaling up.

The programme is still presenting the following risks:
Risk	Mitigations
Funds for scale up not secured	MLHHSD has developed a national Scale Up Plan / MLHHSD has submitted a $150m funding proposal to the World Bank to implement a national programme. The proposal is still under negotiation and is expected to start implementation 2020.
PIU may fail to complete and sustain the programme deliverables due to lack of enough funds following partial disbursement from DANIDA and SIDA.	MLHHSD has requested additional funding from treasury to wind up key activities that is essential for sustainability of programme including the completion of District land office and titling a few remaining villages

Update on partnership principles (1/2 page)

The Partnership Principles Assessment for Tanzania was most recently updated in August 2019.  It found that the government continues to demonstrate a long-term commitment across the Partnership Principles but commitment is stronger to some aspects than to others, with particular concerns about domestic accountability, and social, civil and political rights under pillar 2. .

In the context of this programme, particular attention was paid to the respect of the legal, economic, social, and cultural rights of poor landowners, women and pastoralist. Based on this review, there was no deterioration in the partnership principles.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE (1-2 pages)

Performance of partners and DFID, notably on commercial, and financial issues (1-2 pages
The main stakeholders in the LTSP programme were DFID, SIDA, DANIDA, MLHHSD, and Land Equity International (Project Management Company).

Performance of partners in programme management and delivery

Relations between DFID and MLHSSD, was good. MLHSSD provided strong programme leadership, planning, monitoring oversight, and problem-solving capacity. The quarterly progress meetings and good communication that were maintained throughout the programme have been instrumental to the success of LTSP. The DFID SRO and Programme Manager were actively engaged in supporting the programme to adhere to Smart Rules through regular contact with LTSP, attending management and multi-stakeholder meetings, and retaining regular connections with partners and stakeholders.

PIU and Project Management Company: The Project Management Company (LEI) was appointed to provide the international technical support to LTSP. LEI was expected to bring in four international advisers for LTR, Land Policy, M&E and the Team Leader. Unfortunately, LEI recruited only one international staff member, undoubtedly that has limited the LTSP opportunity to draw on regional international experience.

Programme Delivery, Financial Oversight and Reporting
The LTSP programme is organised as Financial Aid through MLHSSD and is responsible to the Permanent Secretary (PS) in all matters including financial approvals. Funding is provided by the development partners DANIDA, SIDA, and DFID, and is approved on a quarterly basis against requests and actual expenditure. The LTSP programme and work plan is effectively integrated into the MLHHSD budget and annual work plan, with Ministry Departments and Units participating in the implementation of LTSP using a pool of human resources and equipment available in the Ministry. Separately, the PIU maintains its own internal accounts.

The PIU report directly to the PS through the LTSP Coordinator on all matters and works closely with the Directorates and units in MLHSD. The PIU is essentially the delivery unit accessing the development partner funds and then implementing the LTSP programme, according to the overall objectives and the approved annual work plan. Work planning and management is reviewed and approved through quarterly progress reports at the quarterly management meetings chaired by the PS and including the development partners, LTSP management, and Ministry Directorate Heads. The Policy and Land Administration components are managed from the LTSP main office.

Table 2: bud
Component	Budget ($)	Spend ($)	% of budget
CCROs issuance (Including VLUP)	7,452,623	6,524,028	43%
Policy and Institutional Development	1,306,910	1,053,842	7%
Transparency and benefits of large land deals	1,512,618	1,027,037	7%
Administration Management activities (PIU)	2,385,400	2,666,905	15%
Programme Management Unit (PMU) LE	2,542,449	2,542,449	17%
Total million	15,200,000	13,414,261	88%

Financial forecasting and management:
The total budget of the programme is USD 15.2 million, of which the total spend to date is USD 13.4 million, 88% of total commitment. The difference is due to decision taken by DANIDA and SIDA to withhold part of their already committed funds due to delays in LTSP submitting the programme exit plan.

The financial aid mechanism used was that funds were delivered to the Ministry of Finance and then transferred to a programme account (LTSP) in a holding account. According to the Audit Reports of 2017 and 2018 all accounts were prepared in line with best practices underlying public accounts and in compliance with International Public Sector Accounting standards (IPSAS).

Quality and timeliness of narrative reporting and audited financial statements
The LTSP programme was integrated in the national reporting system for physical work implementation and financial reconciliation. Reports are collected on a quarterly basis and quality assured by the Programme Implemented Unit (PIU), with reports generated and submitted to DPs.

Annual independent financial and technical audits were also performed to ensure value for money aspects are assessed. The findings from these reports were discussed in the quarterly meetings and recommendations were taken forward by PIU. Findings from the latest (FY 2017/18) technical audit report were presented to DFID in June 2019 and have been quoted in this PCR.

Since its inception, PIU has reported to DPs quarterly updates on finances, narrative, risk register, asset register, and annual audited financial statements. These have formed the basis of quarterly meetings between PIU and DFID. A delivery chain map was submitted to DFID during the past year.

Date of last narrative financial report for Jan– March 2019	https://ec.vault.dfid.gov.uk/otcs/cs.exe?func=ll&objId=38078906&objAction=viewheader
Date of last audited annual statement (Audit report for 2018 received June 2019)	https://ec.vault.dfid.gov.uk/otcs/cs.exe?func=ll&objId=3832634&objAction=browse&viewType=1#1_1__50_

Asset monitoring and control
Assets are procured as per the annual procurement plan and government procurement regulations. Asset management is covered in the Programme Operations Manual and calls for a fixed asset register to be maintained and updated. The programme register was last updated in July 2019.

DFID evaluated assets identified by DFID Finance Analysis in August 2019, confirming their presence and asset controls in all 4 programme offices the Dar es Salaam, Kilombero, Ulanga, and Malanyi. All assets were verified, some fixed assets were found to have different codes to those in the Asset Register. PIU is now revising the register to ensure all asset contains all relevant information and is updated regularly to capture changes on fixed assets before the submission of asset transfer request to DP for approval. In the exit strategy PIU requested DPs to retain the assets in the project area and others to HQ MLHHSD, as the programme activities will be ongoing.

Proactive dialogue on risks and monitoring of assets.

Proactive dialogue has been maintained throughout the LTSP programme by means of the quarterly monitoring visits and progress meetings. Progress meetings were chaired by PIU and attended by DFID, SIDA and DANIDA. Progress meetings provided a platform for open dialogue on progress of LTSP activities, status on follow up of previous recommendations and constraints encountered during implementation.

Could DFID have been a more effective partner to help deliver the programme?

Throughout implementation of LTSP, DFID has been actively involved in supporting delivery of the programme. This was done through quarterly meetings where PIU and DFID met and discussed various issues to improve programme implementation. Activities included reviewing work plans and budgets; scrutinising financial and narrative reports; and strategizing procurement of goods, services, and works. DFID has supported acceleration of programme implementation through direct procurement of some working tools and equipment such as satellite imagery and vehicles.

However, DFID could have done more to help improve delivery of the programme in the following ways:
- Undertaking quarterly field supervision missions instead of only undertaking Annual Review field trips. Through quarterly reviews it will be possible to identified challenges in the field in a timely manner and agree on measures to address those challenges, instead of waiting for recommendations for improving programme implementation once a year.
- Disbursements for implementation of the programme should at least be on a 6-month horizon instead of a 3-month horizon. Experiences from implementing LTSP shows that there are lengthy processes from the time funds have been disbursed from DFID to the time funds are received into the programme account. This has brought a lot of challenges for timely implementation of planned activities, and sometimes it has led to outstanding liabilities from suppliers and contractors. However, financial and narrative reporting can continue to be on a 3-month horizon.
- Efforts to deliver on a timely manner face challenges in synchronising with lengthy government procurement procedures. In future, the procurement component should be monitored by technical assistance or by DPs. The components were not assigned adequate resources and prioritisation at the design stage was underestimated.

G: MONITORING, EVIDENCE & LEARNING (1-2 pages)

Monitoring (1/2 page)

LTSP has a full time M&E adviser and has produced a detailed M&E Framework that sets out how the M&E system should work, together with a comprehensive risk register and detailed instructions for reporting structures. The LTSP monitoring process includes:

Logframe and M&E frameworks: During the inception phase LTSP prepared an M&E Framework and Logframe which were then reviewed annually to incorporate needs raised in the Annual Reviews and routine monitoring of the Programme.

Baseline study: The PIU through the National Bureau of Statistics (NBS) undertook a baseline survey for 123 villages in Kilombero, Ulanga, Malinyi, and 20 control villages in Kilosa District. The surveys provided baseline data that was used as benchmarks in the programme Logframe.

Annual Reviews: A total of 4 Annual Reviews on the implementation of the programme enabled the PIU to improve implementation of the LTSP to achieve the set indicator targets.

Development of M&E database: the PIU prepared an M&E database. The database is web-based and simplifies data collection; processing and analysis; and reporting and storage. The database has taken into account the Programme M&E Framework and Logframe. The Ministry staff were trained on application and administration of the M&E database and on the mobile application for collecting data on android devices. M&E data on major LTSP interventions has been collected in July 2019 and tested in the M&E database.

Additional oversight: The programme was closely supported by the Management Committee that met quarterly to review work plans, cash flow forecasts, and the progress of programme implementation against log-frame indicators, quarterly plans, and budgets. The Permanent Secretary of the MLHHSD chairs the Management Committee and it comprises representatives of the Programme Implementation Team, District Land Officers from to pilot districts of Kilombero and Ulanga, Commissioner for Lands, Director for Surveys and Mapping, Director for Rural and Town Planning, Director for Policy and Planning and representatives of the DPs (DFID, SIDA, and DANIDA).

Evidence (1/2 page)

Important changes in the land sector as a result of LTSP intervention include:
- Adoption of digital mapping which was initially challenged due to data protection perception.
- Evidence that the CCRO itself is not enough to access bank finance.
- Growing interest of the MLHHSD to engage local CSOs in the public awareness throughout the process of land adjudication due to demonstration of effectiveness.
- Producing and disseminating CCROs is costly. More evidence is needed on willingness to pay and cost-sharing models.
- While technical assistance is highly necessary, the arrangement should not restrict the career growth of public servants.
- If adequate post-registration land transaction systems and associated public awareness campaigns are not in place, informal land transactions will continue.

Learning (1/2 page)

- LTSP is the first programme to introduce digital mapping in Tanzania and it was quickly adopted by MLHHSD.
- Programme developed a Land Tenure Regularisation Manual, standardising and capturing all steps in the LTR process. The Manual is under review by the MLHHSD and will then be adopted by the Ministry as a standard document for land tenure regularisation.
- Programme developed a comprehensive Dispute Resolution and Training Manual for training at village and ward level.
- Programme has successfully transferred skills and knowledge from MLHSSD teams in Dar as Salaam to the districts especially on Participatory Land Use Management and the revised processes for detailed settlement plans.
- LTSP has successfully adopted and extended the MAST data capture tool across the land sector and has piloted the use of TRUST to capture CCRO transaction.
- Programme organised a sector wide dissemination workshop together with two other land related programme, Land Tenure Assistance (USAID) and Integrated Land Management Information System (WB).

Progress on recommendations from annual reviews for this programme

2018 Recommendations	Action Taken
LTSP to plan for the DLO to take over the LTSP work.	Not completed. DLO construction has not yet been completed, and completion relies on accessing local government funds. It is uncertain whether the DLOs will be able to retain all the current staff with government funds, and there is a lack of clarity over how to maintain activities with fewer staff.
LTSP to urgently develop a system to manage transactions at district level.	In progress. LTSP is trialling the use of TRUST digital system for post-registration land transactions.
LTSP to complete the scale up plan	Completed. The scale up plan has been completed and submitted to DFID for review. It details how lessons learnt from LTSP can be scaled up into a national programme.
LTSP to conduct an assessment of the remaining workload and plan of what can be achieved with available time and current resources.	Completed. Programme Implementation Unit prepare LTR Work Plan indicating activities start and end dates based on available resources and timeline.
LTSP to rebalance the LTR teams and office processing team to deal with the backlog of CCROs to be processed.	Completed. 3 teams reallocated in Kilombero and Ulanga to clear the backlog in 25 villages. Clearance of backlog is now completed. Number of printing staff has also been increased.
LTSP to develop a strategy to clear the pre-MAST backlog.	Completed. Clearance of backlog has been completed for 25 villages in Kilombero and Ulanga.
LTSP to actively manage the VEO issue of CCROs and track every CCRO collection.	PUI prepared a strategy for accelerating signing and collection of CCROs e.g. using bulk SMS messages to inform landholders. The bulk SMS was helpful especially for people who owns a land in multiple villages
LTSP and MLHHSD to update the LTR Manual to include detail on the methodology currently in use. The Manual should then become the official MLHHSD manual.	Completed. LTR Manual has been finalised and approved by the Ministry.
LTSP and MLHHSD to urgently complete and document the CCRO ‘business rules and data model’.	Completed. The Ministry has prepared guidelines on CCRO business rules, including on the use of MAST and TRUST.
LTSP to strengthen sensitisation, outreach and involvement of CSOs.	Completed. CSOs reported their involvement at all stages of the process from village boundary survey, through VLUP, to issuing CCROs.
LTSP should complete outstanding policy studies	Completed. Position paper completed and submitted to DFID for review.
LTSP to ensure the Policy component is connected to the main programme and escalate important issues through MSG to MLHHSD and NLAC to inform national land policy.	Completed. Temporary lawyers and community development experts recruited to the programme have been fully integrated into LTR processes to identify and escalate legal and policy issues. Through quarterly meetings, the MSG has contributed to several discussions on land policy as well as the position paper that will be used to inform the review of national land laws. The duties and responsibilities of MSG will be handed over to the National Land Advisory Committee.
LTSP to develop a clear policy and guidelines on how to treat pastoralists and agro-pastoralists.	Not completed. Conflict between pastoralists and farmers continues to be a major issue in the programme area as discussed under Output 1. Grazing areas allocated are often inadequate, and the process has not taken into account that pastoralists regularly move across village boundaries with chaging herd sizes. It is unclear how VLUPs will be able to accommodate pastoral livelihoods.
New financial and other support products for CCRO holders required.	Not completed.
LTSP to ensure that the Responsible Investments sub activity explores existing and potential leasing of village land to investors, rather than alienation and derivative rights.	In progress. Preparation of Benefit Sharing Model on Large Scale Investment in Land is ongoing. The models will be accompanied with four propositions, one of which is leasing.

## Smart Guide
## The Project Completion Review is the opportunity to reflect on the entire programme, its performance, achievements, lessons and how learning will be shared to inform future programming.
The Project Completion Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Teams should refer to the considerations below when completing this template. Suggested section lengths are indicative. Some reviews may need to be longer and others can be shorter (e.g. first year of a programme which has largely focused on mobilisation activities) – it is for the SRO and Head of Department to decide. All text needs to be suitable for publication. Bullets rather than full narrative may make sense for some sections.

A: Summary and Overview
Programme Code is the AMP I.D. number (same on Devtracker) / Enter risk rating (Minor, Moderate, Major or Severe) at the time of the review, taken from AMP / Describe the programme in 1-2 paras including what it aimed to achieve. You might want to include headline points on changes in the operating context, partner performance, DFID management of the programme or other points relevant to the 10 Delivery Questions in the Smart Rules. You should assume that readers may not go beyond this summary. / Describe –without repeating detail from Section B- progress in the past year and why the programme has scored as it has against the output indicators. There needs to be a record of any follow up actions that may be required after completion of this review (e.g. related to final payments, audited statements etc – see the extension and closure section in the Smart Rules). These may sit best in the Delivery Plan – but you should agree them with the person signing off the PCR and include them in this (publicly available) report or the Delivery Plan.
B: Detailed Output Scoring
Output Title, Number, Weighting, Indicators and milestones / Use the wording exactly as is from the current logframe. This will need to be entered on AMP as part of loading the PCR for approval. Indicate (Yes or No) if the impact weighting has been revised since last Annual Review (Business Case approval if the programme is under 15 months and hasn’t had an AR) and if Yes in which direction (up or down). Input progress against the milestone for this review
Output Score / Enter the rating (using the scale A++ to C) exactly as generated on the programme scoring calculation sheet
Provide a brief description of the output (unless obvious from the information in the box above) and supporting narrative for the score
Lessons and recommendations linked to this output. Some of these may inform or need to be included in Section A. For anything that can’t be published please use the Delivery Plan
Repeat above for each Output in the logframe and add new sub-sections for additional outputs.
C: Theory of change and progress against outcomes
Overall assessment of whether the expected outcomes and contribution to target impact(s) were achieved? Review this in view of the overall programme score; but it is possible that outputs were delivered but the envisaged outcomes or impact were not – or vice versa – and consider reasons for this. It is not unusual for programmes to be off track against at least some of the expected outcomes or impact. You should refer to the indicators in the logframe. Did any unexpected outcomes emerge? Were there any significant changes in the planned timetable for delivery of the programme? Were there any changes to expected outcomes or impact on gender equality compared to what was described in the approved Business Case?
Theory of Change (ToC). You might want to use a diagram to summarise it. You should flag any major changes in the past year. You should consider if the steps to achieving outcome and impact were valid e.g. did the ToC logic, supporting evidence and assumptions hold up against implementation experience? Is there any new evidence which challenges the programme design or rationale? If relevant you might also want to flag any major changes since the programme started rather than just over the year in question.
Logframe. Describe major changes in the past year –including when they were made and why- and what their implications were for the programme. Ideally changes should not have be made to any targets or indicators less than six months before they are being reviewed unless agreed with the Head of Department. All changes should be recorded as part of the programme’s documentation (there is a ‘change frame’ tab on the logframe template). If relevant you might also want to flag any major changes since the programme started.
D: Value for Money
Assess VfM compared to the proposition in the Business Case, based on the past year and during the lifetime of the programme You should refer to VfM measures and metrics from the Business Case and/or ARs. Changes in cost drivers (e.g. costs of major inputs) and the theory of change may be relevant. The assessment should encompass the 4 E’s of DFID’s value for money framework – economy, efficiency, effectiveness and equity, including gender equality (referring back to the relevant text in the approved Business Case’s Strategic Case may be relevant), disability and leaving no one behind. You should note any formal extensions or amendments to the programme giving brief details about cost, duration and the reasons why. Significant changes to logframe indicators or targets may also be relevant.

E: Risk

Provide an overview of the programme’s risk (noting the rating from page 1) during the past year and over the life of the programme / Note the overall risk rating now as captured in AMP and on p1. Flag any changes to the overall risk environment/ context in the past year and how they impacted on the programme and were mitigated. Use DFID’s standard risk terminology where possible e.g. categories of risk and risk appetite. Remember to take account of any relevant recommendations from Due Diligence Assessments on implementing partners. Some relevant information may not be suitable for publication but ensure the risk register on AMP and Delivery Plan are updated as necessary following this review (remember that projects remain open until they are archived, even after the PCR is complete). / Update on Partnership Principles. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four PPs over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences?
F: Delivery, Commercial and Financial Performance
Issues to consider for both the implementing partner(s) and DFID include: quality and timeliness of narrative reporting and audited financial statements; proactive dialogue on risks and updating of delivery chain maps; quality of financial management e.g. accuracy of forecasting; monitoring of assets. Consider also how DFID could have been a more effective partner to help deliver the programme (key points could be included in Section G too). / If there is a contract involved, set out: / Delivery against contract KPIs (and Terms and Conditions) / Compliance with the Supply Partner Code, where applicable, drawing on advice from PCD. / Compliance with the new cost and transparency requirements, where applicable (i.e. highlighting any profit variance and challenge and use of Open Book Accounting) / Performance of Partners. Where applicable, an annual summary of the new SRM scorecard assessment for each delivery partner involved in delivering this programme.
G: Monitoring, Evidence and Learning
Monitoring. / Summarise monitoring activities throughout the review period (field visits, reviews, engagement with stakeholders including beneficiary feedback) and how these have informed programming decisions. Where there is an external M&E supplier, how they engaged with the programme implementer(s) and DFID. Briefly describe the PCR process itself including any inputs from outside the programme team (within or beyond DFID). / Evidence / Describe any changes in evidence and implications for the programme. Include any relevant comments on the quality/breadth of the evidence. / Monitoring data, evidence and learning should consider the ‘Leave no one Behind’ agenda and as far as possible disaggregate information by age, sex, disability, geography (update geocoding information on AMP as needed) and other relevant variables. / Where an evaluation is planned or has taken place set out what progress has been made. / Learning / What learning processes have been used over the past year to capture and share lessons, new evidence and know-how? / What are the key lessons identified over the past year for (i) this programme (ii) wider DFID and development work? / Any specific implications or follow-up actions of that learning for this programme may be best captured in Section A / Progress on recommendations from previous review(s) / It is important to keep track of this. Some may not be publishable and feature in the Delivery Plan. But a brief update on progress against any recommendations from ARs (especially the last one) should be provided.